{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","남부발전"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":14,"n_cols":16,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 5월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #3 M.Tr A-1","2016년 구리전력지사 362kV GIS 정밀점검공사","신가평S/S #3M.Tr 2차 7771, 7700 Bay GIS 정밀점검","2016-05-23 09:00","2016-05-27 18:00","2016-05-23 09:00","2016-05-27 18:00","연속",null,null,null,201603180150]
[2,"경기북부","구리","신가평S/S #4 M.Tr A-1","2016년 구리전력지사 362kV GIS 정밀점검공사","신가평S/S #4M.Tr 2차 7871, 7800 Bay GIS 정밀점검","2016-05-30 09:00","2016-06-03 18:00","2016-05-30 09:00","2016-06-03 18:00","연속",null,null,null,201603180152]
[3,"경기북부","구리","신가평S/S #2 M.Tr A-1","2016년 구리전력지사 362kV GIS 정밀점검공사","신가평S/S #2M.Tr 2차 7571, 7500 Bay GIS 정밀점검","2016-05-09 09:00","2016-05-13 18:00","2016-05-09 09:00","2016-05-13 18:00","연속",null,null,null,201603180136]
[4,"경기","성남","신안성S/S #2 M.Tr 1차 CB","신안성S/S 765kV CB보통점검","신안성S/S 765kV 8572 CB보통점검","2016-05-18 09:30","2016-05-19 18:00","2016-05-18 09:30","2016-05-19 18:00","연속",null,null,null,201603140489]
[5,"경기","성남","신안성S/S 신안성-신가평 T/L CB","신안성S/S 765kV CB보통점검","신안성S/S 765kV 8671 CB보통점검","2016-05-23 09:30","2016-05-24 18:00","2016-05-23 09:30","2016-05-24 18:00","연속",null,null,null,201603140492]
[6,"경기","성남","신안성S/S TIE-#3 M.Tr 1차 CB","신안성S/S 765kV CB보통점검","신안성S/S 765kV 8600 CB보통점검","2016-05-25 09:30","2016-05-26 18:00","2016-05-25 09:30","2016-05-26 18:00","연속",null,null,null,201603140493]
[7,"경기","성남","신안성S/S #3 M.Tr 1차 CB","신안성S/S 765kV CB보통점검","신안성S/S 765kV 8672 CB보통점검","2016-05-30 09:30","2016-05-31 18:00","2016-05-30 09:30","2016-05-31 18:00","연속",null,null,null,201603140494]
[8,"경기","성남","신안성S/S TIE-#2 M.Tr 1차 CB","신안성S/S 765kV CB보통점검","신안성S/S 765kV 8500 CB보통점검","2016-05-16 09:30","2016-05-17 18:00","2016-05-16 09:30","2016-05-17 18:00","연속",null,null,null,201603140479]
[9,"경남","함안","북경남신고리NP#2 T/L","765kV 북경남-신고리NPT/L 초기점검","765kV 북경남-신고리NP#2T/L 초기점검","2016-05-29 09:00","2016-06-07 18:00","2016-05-30 09:00","2016-06-08 18:00","연속",null,null,null,201603080079]
[10,"경남","함안","북경남신고리NP#1 T/L","765kV 북경남-신고리NPT/L 초기점검","765kV 북경남-신고리NP#1T/L 초기점검","2016-05-19 09:00","2016-05-28 18:00","취소","취소","연속",null,null,null,201603080077]

{"sheet":"345송부","index":1,"n_rows":170,"n_cols":16,"rows_kept":170,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 5월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr A","16년 성동 변전협력회사 총액공사 (성동S/S 345kV #2M.Tr)","170kV GIS 보통점검 (성동S/S 345kV #2M.Tr 2차)","2016-05-11 10:00","2016-05-11 17:00","2016-05-11 10:00","2016-05-11 17:00","당일",null,null,null,201603070105]
[2,"서울","성동","성동S/S #1 M.Tr A","16년 성동 변전협력회사 총액공사 (성동S/S 345kV #1M.Tr)","170kV GIS 보통점검 (성동S/S 345kV #1M.Tr 2차)","2016-05-10 10:00","2016-05-10 17:00","2016-05-10 10:00","2016-05-10 17:00","당일",null,null,null,201603070103]
[3,"서울","중부","양주중부#2 T/L","향동 C/H부지 차폐벽 설치공사","차폐벽 설치 : H:6~7m x L:85m","2016-05-14 09:00","2016-05-14 18:00","2016-05-14 09:00","2016-05-14 18:00","당일",null,null,null,201603090138]
[4,"서울","중부","양주중부#2 T/L","향동 C/H부지 차폐벽 설치공사","차폐벽 설치 : H:6~7m x L:85m","2016-05-07 09:00","2016-05-07 18:00","2016-05-07 09:00","2016-05-07 18:00","당일",null,null,null,201603090137]
[5,"서울","중부","양주중부#1 T/L","향동 C/H부지 차폐벽 설치공사","향동 C/H부지 차폐벽 설치 : H:6~7m x L:85m","2016-05-06 09:00","2016-05-07 18:00","2016-05-06 09:00","2016-05-07 18:00","연속",null,null,null,201603090132]
[6,"서울","중부","양주중부#1 T/L","향동 C/H부지 차폐벽 설치공사","차폐벽 설치 : H:6~7m x L:85m","2016-05-27 09:00","2016-05-28 18:00","2016-05-27 09:00","2016-05-28 18:00","연속",null,null,null,201603090134]
[7,"서울","중부","양주중부#2 T/L","향동 C/H부지 차폐벽 설치공사","차폐벽 설치 : H:6~7m x L:85m","2016-05-28 09:00","2016-05-28 18:00","2016-05-28 09:00","2016-05-28 18:00","당일",null,null,null,201603090139]
[8,"서울","중부","양주중부#1 T/L","향동 C/H부지 차폐벽 설치공사","차폐벽 설치 : H:6~7m x L:85m","2016-05-13 09:00","2016-05-14 18:00","2016-05-13 09:00","2016-05-14 18:00","연속",null,null,null,201603090133]
[9,"남서울","동서울","동서울S/S 345kV #1 Sh.R","동서울S/S #1Sh.R 7A71,7A00 보통점검","동서울S/S #1Sh.R 7A71,7A00 보통점검","2016-05-02 09:00","2016-05-03 18:00","2016-05-02 09:00","2016-05-03 18:00","연속",null,null,null,201603150231]
[10,"인천","김포","신가좌가정#1 T/L","축소형고장기록장치 설치","신속, 정확한 고장점표정을 위한 축소형 고장기록장치 설치, 양단 변전소 보호배전반 PNL 안에 취부","2016-05-06 09:00","2016-05-06 17:00","2016-05-06 09:00","2016-05-06 17:00","당일",null,null,null,201603160152]
[11,"인천","김포","신김포S/S 345kV #1 Sh.R","신김포S/S #1 Sh.R 제작사 점검","신김포S/S 345kV #1 Sh.R 방압안전장치 설치","2016-05-02 10:00","2016-05-02 18:00","2016-05-02 10:00","2016-05-02 18:00","당일",null,null,null,201603040016]
[12,"인천","김포","신김포S/S 345kV #2 Sh.R","신김포S/S #2 Sh.R 제작사 점검","신김포S/S 345kV #2 Sh.R 송유펌프(유류지시 불량) 교체","2016-05-03 10:00","2016-05-05 18:00","2016-05-03 10:00","2016-05-05 18:00","연속",null,null,null,201603040017]
[13,"인천","시흥","신시흥#1S/S #3 M.Tr A","신시흥#1S/S #3 M.Tr 정밀점검공사","신시흥#1S/S #3 M.Tr 정밀점검공사","2016-05-19 09:30","2016-05-28 18:00","2016-05-19 09:30","2016-05-28 18:00","연속",null,null,null,201603020175]
[14,"인천","시흥","신시흥#1S/S #1 M.Tr A","신시흥#1S/S #1 M.Tr 정밀점검공사","신시흥#1S/S #1 M.Tr 정밀점검공사","2016-05-09 09:30","2016-05-18 18:00","2016-05-09 09:30","2016-05-18 18:00","연속",null,null,null,201603020176]
[15,"인천","인천","서인천C/C 신경서서인천CCT/L CB (7271)","서인천C/C 신경서서인천CCT/L GIS(7271) 초기점검","서인천C/C 신경서서인천CCT/L GIS(7271) 초기점검","2016-05-23 09:00","2016-05-23 18:00","2016-05-23 09:00","2016-05-23 18:00","당일",null,null,null,201603150083]
[16,"인천","인천","서인천C/C 신경서서인천CCT/L-#2 M.Tr 1차 CB (7200)","서인천C/C 2 M.Tr 1차 GIS(7200) 초기점검","서인천C/C 2 M.Tr 1차 GIS(7200) 초기점검","2016-05-24 09:00","2016-05-24 18:00","2016-05-24 09:00","2016-05-24 18:00","당일",null,null,null,201603150084]
[17,"인천","인천","서인천C/C #2 M.Tr 1차 CB (7272)","서인천C/C 2 M.Tr 1차 GIS(7272) 초기점검","서인천C/C 2 M.Tr 1차 GIS(7272) 초기점검","2016-05-25 09:00","2016-05-25 18:00","2016-05-25 09:00","2016-05-25 18:00","당일",null,null,null,201603150085]
[18,"인천","인천","서인천C/C 345kV #2 Sh.R","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #2Sh.R용 CB(7479) 대체","2016-05-06 09:30","2016-05-20 17:30","2016-05-06 09:30","2016-05-20 17:30","연속",null,null,null,201603150013]
[19,"인천","인천","서인천C/C #3 M.Tr 1차 CB (7372)","서인천C/C #3M.Tr 1차 GIS(7372) 초기점검","서인천C/C #3M.Tr 1차 GIS(7372) 초기점검","2016-05-30 09:00","2016-05-30 18:00","2016-05-30 09:00","2016-05-30 18:00","당일",null,null,null,201603150090]
[20,"경기북부","구리","미금S/S 345kV #1 Sh.R","미금S/S 345kV #1 Sh.R","345kV 분로리액터 1대 하자점검","2016-05-03 09:00","2016-05-04 18:00","2016-05-03 09:00","2016-05-04 18:00","연속",null,null,null,201602120739]
[21,"경기북부","구리","신가평S/S 345kV #2 Sh.R","신가평S/S 345kV #2 Sh.R 보통점검","345kV 분로리액터 1대 보통점검","2016-05-23 09:00","2016-05-24 18:00","2016-05-23 09:00","2016-05-24 18:00","연속",null,null,null,201602120744]
[22,"경기북부","구리","신가평S/S 345kV #4 Sh.R","2016년 구리전력지사 362kV GIS 정밀점검공사","신가평S/S #4Sh.R 7600, 7679 Bay GIS 정밀점검","2016-05-16 09:00","2016-05-20 18:00","2016-05-16 09:00","2016-05-20 18:00","연속",null,null,null,201603180146]
[23,"경기북부","구리","신포천S/S 345kV #1 Sh.R","신포천S/S 345kV #1 Sh.R 보통점검","345kV 분로리액터 1대 보통점검","2016-05-11 09:00","2016-05-12 18:00","2016-05-11 09:00","2016-05-12 18:00","연속",null,null,null,201602120747]
[24,"경기북부","직할","신의정부S/S 345kV #1 Sh.R","신의정부S/S #1 Sh.R","2016년 직할 변전협력회사 총액공사 - 본체보통","2016-05-09 10:00","2016-05-09 18:00","2016-05-09 10:00","2016-05-09 18:00","당일",null,null,null,201603180009]
[25,"경기북부","직할","신의정부S/S 345kV #3 Sh.R","신의정부S/S #3 Sh.R","2016년 직할 변전협력회사 총액공사 - 본체보통","2016-05-10 10:00","2016-05-10 18:00","2016-05-10 10:00","2016-05-10 18:00","당일",null,null,null,201603180010]
[26,"경기북부","파주","신덕은S/S #4 M.Tr A","2016년 신덕은S/S 362kV #4M.Tr 1차 GIS 정밀점검공사","2016년 신덕은S/S 362kV #4M.Tr 1차 GIS 정밀점검공사","2016-05-09 09:00","2016-05-13 18:00","2016-05-09 09:00","2016-05-13 18:00","연속",null,null,null,201603180148]
[27,"경기북부","파주","신덕은S/S 345kV #2 BUS","2016년 신덕은S/S 362kV #4M.Tr 1차 GIS 정밀점검공사","2016년 신덕은S/S 362kV #4M.Tr 1차 7452DS 정밀점검","2016-05-09 09:00","2016-05-10 18:00","2016-05-09 09:00","2016-05-10 18:00","연속",null,null,null,201603180149]
[28,"경기북부","파주","신김포신파주#2 T/L","345kV 신김포-신파주TL 접속함 교체공사","대상선로 : 345kV 신김포-신파주#1TL 교체대상 : J/B1 등 48상 접속함 내용 : PMJ Type 교체","2016-05-07 09:00","2016-06-15 18:00","2016-05-07 09:00","2016-06-15 18:00","연속",null,null,"신뢰도개선",201603170144]
[29,"경기","군포","신안산S/S #4 M.Tr A","345kV 신안산SS 모자익 대체 공사","345kV 신안산SS 모자익 대체 공사","2016-05-23 09:00","2016-05-27 18:00","2016-05-09 09:00","2016-05-13 18:00","연속",null,null,null,201603140404]
[30,"경기","군포","신시흥신안산 T/L","345kV 신시흥신안산T/L 송전선로용 피뢰기 설치공사","- 송전선로용 피뢰기 설치 1기(신안산분기)","2016-05-29 13:00","2016-05-29 19:00","2016-05-29 13:00","2016-05-29 19:00","당일",null,null,null,201603140061]
[31,"경기","군포","화성신안산 T/L","345kV 화성신안산T/L 송전선로용 피뢰기 설치공사","- 송전선로 피뢰기 설치 1기(신안산분기)","2016-05-29 07:00","2016-05-29 13:00","2016-05-29 07:00","2016-05-29 13:00","당일",null,null,null,201603140060]
[32,"경기","동부","곤지암S/S 345kV #1Sh.R","16년 동부 변전협력회사 총액공사","곤지암S/S 345kV #1Sh.R 하자점검","2016-05-30 09:30","2016-05-30 18:00","2016-05-30 09:30","2016-05-30 18:00","당일",null,null,null,201603140210]
[33,"경기","성남","서안성S/S #1 M.Tr A","서안성S/S #1 M.Tr","서안성S/S #1 M.Tr,7100,7172,6144 보통점검","2016-05-28 09:30","2016-05-29 18:00","2016-05-28 09:30","2016-05-29 18:00","연속",null,null,null,201603110200]
[34,"경기","성남","신안성신성남#2 T/L","345kV 신성남-동서울#2T/L 정밀점검 관련 안전이격거리 확보차","345kV 신성남-동서울#2T/L 정밀점검 관련 안전이격거리 확보차","2016-05-28 13:00","2016-05-28 18:00","2016-05-28 13:00","2016-05-28 18:00","연속",null,null,null,201603150158]
[35,"경기","성남","신성남동서울#2 T/L","345kV 신성남-동서울#2T/L 유사고장예방 케이블 교체공사","345kV 신성남-동서울#2T/L 유사고장예방 케이블 교체 케이블 846m, 접속함 3개 교체시행, 정밀점검(23-93호) 병행","2016-05-27 09:00","2016-06-13 18:00","2016-05-27 09:00","2016-06-13 18:00","연속",null,null,null,201603090212]
[36,"경기","성남","신안성신성남#1 T/L","345kV 신성남-동서울#1T/L 정밀점검 관련 안전이격거리 확보차","345kV 신성남-동서울#1T/L 정밀점검 관련 안전이격거리 확보차","2016-05-22 13:00","2016-05-22 18:00","2016-05-22 13:00","2016-05-22 18:00","연속",null,null,null,201603150157]
[37,"경기","성남","신시흥신성남#1 T/L","345kV 신성남-동서울#1T/L 정밀점검 관련 안전이격거리 확보차","345kV 신성남-동서울#1T/L 정밀점검 관련 안전이격거리 확보차","2016-05-22 08:00","2016-05-22 13:00","2016-05-22 08:00","2016-05-22 13:00","연속",null,null,null,201603150163]
[38,"경기","성남","신성남신양재#2 T/L","345kV 신성남-신양재#2T/L 정밀점검(구간 No.1~22)","345kV 신성남-신양재#2T/L 정밀점검(22기)","2016-05-11 09:00","2016-05-12 18:00","2016-05-11 09:00","2016-05-12 18:00","연속",null,null,null,201603150075]
[39,"경기","성남","신성남신양재#1 T/L","345kV 신성남-신양재#1T/L 정밀점검(구간 No.1~22)","345kV 신성남-신양재#1T/L 정밀점검(22기)","2016-05-09 09:00","2016-05-10 18:00","2016-05-09 09:00","2016-05-10 18:00","연속",null,null,null,201603150073]
[40,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L 유사고장예방 케이블 교체공사","345kV 신성남-동서울#1T/L 유사고장예방 케이블 교체 케이블 846m, 접속함 3개 교체시행, 정밀점검(23-93호) 병행","2016-05-09 09:00","2016-05-26 18:00","2016-05-09 09:00","2016-05-26 18:00","연속",null,null,null,201603090201]
[41,"경기","성남","신시흥신성남#2 T/L","345kV 신성남-동서울#2T/L 정밀점검 관련 안전이격거리 확보차","345kV 신성남-동서울#2T/L 정밀점검 관련 안전이격거리 확보차","2016-05-28 08:00","2016-05-28 13:00","2016-05-28 08:00","2016-05-28 13:00","연속",null,null,null,201603150161]
[42,"경기","성남","신안성신용인#2 T/L","345kV 신안성-신용인#2T/L 스페이서댐퍼 정비공사","345kV 신안성-신용인#2T/L 스페이서댐퍼 정비(증설) 스페이서댐퍼수량 일반지역에서 특수지역 조건으로 변경설치 No.38~56(10경간)","2016-05-02 08:00","2016-05-05 18:00","2016-05-02 08:00","2016-05-05 18:00","매일",null,null,null,201603100250]
[43,"경기","성남","신용인삼성 T/L","345kV 신용인S/S 용량부족 GIS 대체공사","345kV 신용인-삼성T/L 인출변경 345kV GIS (63kA 6300A)설치 * 2CB 용량대체","2016-05-20 09:00","2016-05-24 18:00","2016-05-20 09:00","2016-05-24 18:00","연속",null,null,null,201601140109]
[44,"경기","직할","아산화성#1 T/L","345kV 아산화성#1T/L 안전이격거리확보","- 154kV 화성-장덕T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보","2016-05-07 07:00","2016-05-07 13:00","2016-05-07 07:00","2016-05-07 13:00","당일",null,null,null,201603140049]
[45,"경기","직할","화성평택TP#2 T/L","345kV 화성평택T/P#2T/L 송전전로용 피뢰기 설치공사","-70기(2~70호) 송전선로용 피뢰기 설치","2016-05-30 07:00","2016-06-06 19:00","2016-05-30 07:00","2016-06-06 19:00","연속",null,null,null,201603140046]
[46,"경기","직할","화성평택TP#1 T/L","345kV화성평택TP#1T/L 안전이격거리확보","- 154kV 화성-장덕T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보","2016-05-08 07:00","2016-05-08 13:00","2016-05-08 07:00","2016-05-08 13:00","당일",null,null,null,201603140052]
[47,"강원","강릉","신양양S/S #2 M.Tr A","2016-17년 강릉PO 변전협력회사 총액공사","- #2M.Tr 보통점검 - #2M.Tr 1, 2차 GIS 보통점검 - #2M.Tr 기타기기(LA, PT) 점검","2016-05-16 10:00","2016-05-19 18:00","2016-05-16 10:00","2016-05-19 18:00","매일",null,null,null,201603040123]
[48,"강원","강릉","신양양S/S #1 M.Tr A","2016-17년 강릉PO 변전협력회사 총액공사","- #1M.Tr 보통점검 - #1M.Tr 1, 2차 GIS 보통점검 - #1M.Tr 기타기기(LA, PT) 점검","2016-05-09 10:00","2016-05-12 18:00","2016-05-09 10:00","2016-05-12 18:00","매일",null,null,null,201603040119]
[49,"강원","강릉","동해신양양 T/L","2016년 가공송전 순시점검 위탁공사","○ 345kV 양양양수T/L No.3~76호 스페이서 점검","2016-05-23 09:00","2016-05-27 18:00","2016-05-23 09:00","2016-05-27 18:00","매일",null,null,null,201603060007]
[50,"강원","강릉","신양양_양양PP T/L","2016년 가공송전 순시점검 위탁공사","○ 345kV 양양양수T/L No.1~2호 스페이서 및 정밀점검 ○ 345kV 신양양분기T/L No.1~5호 스페이서 및 정밀점검","2016-05-28 09:00","2016-05-28 18:00","2016-05-28 09:00","2016-05-28 18:00","당일",null,null,null,201603070020]
[51,"강원","동해","삼척GP한울NP1#2 T/L","345kV 삼척GP-한울NP1T/L 전선접속개소 전선교체공사","1. No.12~20 전선접속개소 전선교체","2016-05-25 057:00","2016-06-01 18:00","2016-05-25 07:00","2016-06-01 18:00","연속",null,null,null,201603040167]
[52,"충북","직할","신제천신충주#1 T/L","2016년 직할 가공송전선로 순시점검 위탁공사","정밀점검 (124~186호)","2016-05-23 08:00","2016-05-27 18:00","2016-05-23 08:00","2016-05-27 18:00","매일",null,null,null,201603220156]
[53,"충북","직할","신제천신충주#2 T/L","2016년 직할 가공송전선로 순시점검 위탁공사","정밀점검 (124~186호)","2016-05-16 08:00","2016-05-20 18:00","2016-05-16 08:00","2016-05-20 18:00","매일",null,null,null,201603220155]
[54,"충북","직할","신제천S/S #3 M.Tr A","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 조립(안전거리 확보)","2016-05-01 08:00","2016-05-01 18:00","2016-05-01 08:00","2016-05-01 18:00","당일",null,null,null,201603040153]
[55,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 모선 조립(안전거리 확보)","2016-05-09 08:00","2016-05-14 18:00","2016-05-09 08:00","2016-05-14 18:00","매일",null,null,null,201603040152]
[56,"충북","직할","곤지암신충주#1 T/L","장기사용 보호배전반 대체","장기사용 보호배전반 대체","2016-05-16 09:00","2016-05-20 18:00","2016-05-16 09:00","2016-05-20 18:00","연속",null,null,null,201601130101]
[57,"충북","직할","곤지암신충주#2 T/L","장기사용 보호배전반 대체","장기사용 보호배전반 대체","2016-05-23 09:00","2016-05-27 18:00","2016-05-23 09:00","2016-05-27 18:00","연속",null,null,null,201601130102]
[58,"충북","청주","신옥천무주양수 T/L","345kV 무주분기T/L 송전선로 피뢰기설치공사","345kV 무주분기T/L 1-57호 -송전용 피뢰기설치 : 57기 171set","2016-05-23 08:00","2016-05-31 18:00","2016-05-23 08:00","2016-05-31 18:00","당일",null,null,null,201603140266]
[59,"충북","청주","신옥천S/S 신옥천-신남원#2T/L CB (7272)","16년 청주 변전협력회사 총액공사","신옥천S/S 345kV 72Bay 7252DS 과열보수","2016-05-03 09:00","2016-05-03 18:00","2016-05-03 09:00","2016-05-03 18:00","당일",null,null,null,201603230094]
[60,"충북","청주","신옥천S/S 345kV #2 BUS","16년 청주 변전협력회사 총액공사","신옥천S/S 345kV 72Bay 7252DS 과열보수","2016-05-03 09:00","2016-05-03 18:00","2016-05-03 09:00","2016-05-03 18:00","당일",null,null,null,201603230092]
[61,"충북","청주","신옥천S/S 345kV #2 BUS","16년 청주 변전협력회사 총액공사","신옥천S/S 345kV 75Bay 분기모선 보강시행","2016-05-27 08:00","2016-05-27 20:00","2016-05-27 08:00","2016-05-27 20:00","당일",null,null,null,201603250024]
[62,"충북","청주","청원S/S #1 M.Tr","16년 청주 변전협력회사 총액공사","청원S/S #1 M.Tr B상 및 예비변압기 원복운전","2016-05-09 09:00","2016-05-10 18:00","취소","취소","당일",null,null,null,201603150061]
[63,"충북","청주","청원S/S #1 예비 M.Tr <CB>","16년 청주 변전협력회사 총액공사","청원S/S #1 M.Tr B상 및 예비변압기 원복운전","2016-05-09 09:00","2016-05-10 18:00","취소","취소","당일",null,null,null,201603150063]
[64,"충북","청주","청원S/S #2 M.Tr A","16년 청주 변전협력회사 총액공사","청원S/S #2 M.Tr B상 부싱 절연열화 측정","2016-05-06 09:00","2016-05-06 18:00","2016-05-06 09:00","2016-05-06 18:00","당일",null,null,null,201603150058]
[65,"충북","충주","서안성신진천#2 T/L","2016년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(신진천S/T~35호)","2016-05-09 09:00","2016-05-13 18:00","2016-05-09 09:00","2016-05-13 18:00","매일",null,null,null,201602150812]
[66,"충북","충주","서안성신진천#1 T/L","2016년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(신진천S/T~35호)","2016-05-02 09:00","2016-05-06 18:00","2016-05-02 09:00","2016-05-06 18:00","매일",null,null,null,201602150811]
[67,"대전충남","대전","신계룡청양 T/L","○ 345kV 신계룡S/S 부분방전센서 설치","○ 345kV 신계룡S/S 부분방전센서 설치","2016-05-30 09:00","2016-06-01 18:00","2016-05-30 09:00","2016-06-01 18:00","연속",null,null,null,201603140538]
[68,"대전충남","대전","신계룡S/S #2 M.Tr A","○ 345kV 신계룡S/S 부분방전센서 설치","○ 345kV 신계룡S/S 부분방전센서 설치","2016-05-26 09:00","2016-05-28 18:00","2016-05-26 09:00","2016-05-28 18:00","연속",null,null,null,201603140549]
[69,"대전충남","대전","신계룡S/S 345kV #2 BUS","○ 345kV 신계룡S/S #2 BUS 부분방전센서 설치","○ 345kV 신계룡S/S #2 BUS 부분방전센서 설치","2016-05-23 09:00","2016-05-25 18:00","2016-05-23 09:00","2016-05-25 18:00","연속",null,null,null,201603140547]
[70,"대전충남","대전","신계룡S/S 345kV #1 BUS","○ 345kV 신계룡S/S #1 BUS 부분방전센서 설치","○ 345kV 신계룡S/S #1 BUS 부분방전센서 설치","2016-05-19 09:00","2016-05-21 18:00","2016-05-19 09:00","2016-05-21 18:00","연속",null,null,null,201603140546]
[71,"대전충남","대전","신계룡S/S #1 M.Tr A","○ 345kV 신계룡S/S 7200 GIS 정밀점검, 부분방전센서 설치","○ 345kV 신계룡S/S 7200 GIS 정밀점검 및 부분방전센서 설치","2016-05-16 09:00","2016-05-18 18:00","2016-05-16 09:00","2016-05-18 18:00","연속",null,null,null,201603140544]
[72,"대전충남","대전","신옥천신계룡 T/L","○ 345kV 신계룡S/S 7200 GIS 정밀점검, 부분방전센서 설치","○ 345kV 신계룡S/S 7200 GIS 정밀점검 및 부분방전센서 설치","2016-05-12 09:00","2016-05-14 18:00","2016-05-12 09:00","2016-05-14 18:00","연속",null,null,null,201603140543]
[73,"대전충남","서산","신당진현대제철 T/L","345KV 현대제철 등 2개T/L 피뢰기 설치공사","[송전]신당진-현대제철T/L No.0.1~71(219set) -아킹혼 철거 -피뢰기 설치","2016-05-23 09:00","2016-06-03 18:00","2016-05-23 09:00","2016-06-03 18:00","매일",null,null,null,201603150008]
[74,"대전충남","서산","신당진S/S #1 M.Tr A","신당진S/S #1M.Tr 차단기 부동작 시험 및 LA 교체","○ 154kV 신당진S/S #1M.Tr 차단기 부동작 시험 및 LA 교체","2016-05-03 09:00","2016-05-03 18:00","2016-05-03 09:00","2016-05-03 18:00","당일",null,null,null,201603140616]
[75,"대전충남","서산","신당진S/S #2 M.Tr A","신당진S/S #2M.Tr 차단기 부동작 시험 및 B상 ,LA 보통점검","○ 154kV 신당진S/S #2M.Tr 차단기 부동작 시험 및 B상 LA 보통점검","2016-05-04 09:00","2016-05-04 18:00","2016-05-04 09:00","2016-05-04 18:00","당일",null,null,null,201603140640]
[76,"대전충남","서산","신서산S/S 345kV #4 Sh.R CB 7779 (7779)","2016년 서산P/O 765/345kV GIS 점검공사","○345kV GIS 정밀점검","2016-05-02 09:00","2016-05-04 18:00","2016-05-02 09:00","2016-05-04 18:00","연속",null,null,null,201602140095]
[77,"대전충남","서산","신서산S/S 345kV #5 Sh.R CB 7979 (7979)","2016년 서산P/O 765/345kV GIS 점검공사","○345kV GIS 정밀점검(7979)","2016-05-16 09:00","2016-05-18 18:00","2016-05-16 09:00","2016-05-18 18:00","연속",null,null,null,201602140096]
[78,"대전충남","아산","신온양신탕정#1 T/L","[송전] 345kV 아산-화성 등 15개T/L 피뢰기 설치공사","1. 공 사 명 : 345kV 아산-화성 등 15개T/L 피뢰기 설치공사 2. 공사구간 및 개요 : 444기(1,332 set) 설치 ○ 345kV 신서산-아산 등 4개T/L 202기(내장 128기, 현수 74기), 606set ○ 154kV 둔포-석곡 등 11개T/L 242기(내장 158기, 현수 84기)","2016-05-27 07:00","2016-05-31 18:00","2016-05-27 07:00","2016-05-31 18:00","매일",null,null,null,201603040087]
[79,"대전충남","아산","신서산아산#2 T/L","[송전] 345kV 신서산-아산#2T/L 정밀점검","345kV 신서산-아산 #2T/L 정밀점검 시행","2016-05-21 07:00","2016-05-26 18:00","2016-05-21 07:00","2016-05-26 18:00","매일",null,null,"신뢰도개선",201603140239]
[80,"대전충남","아산","신서산아산#1 T/L","[송전] 345kV 신서산-아산#1T/L 정밀점검","345kV 신서산-아산 #1T/L 정밀점검 시행","2016-05-09 07:00","2016-05-14 18:00","2016-05-09 07:00","2016-05-14 18:00","매일",null,null,"신뢰도개선",201603140238]
[81,"대전충남","청양","보령T/P #3 M.Tr 1차 CB (7371)","보령화력 362kV GIS 보통점검","○ 345kV 7371 GIS 보통점검","2016-05-03 09:00","2016-05-04 18:00","2016-05-03 09:00","2016-05-04 18:00","연속",null,null,null,201603140164]
[82,"대전충남","청양","보령T/P 아산-보령화력#2T/L-#5M.Tr1차 CB (7500)","보령화력 362kV GIS 보통점검","○ 345kV 7500 GIS 보통점검","2016-05-17 09:00","2016-05-18 18:00","2016-05-17 09:00","2016-05-18 18:00","연속",null,null,null,201603140166]
[83,"대전충남","청양","보령T/P #3 M.Tr 1차-#3,4 SU Tr 1차 CB (7300)","보령화력 362kV GIS 보통점검","○ 345kV 7300 GIS 보통점검","2016-05-03 09:00","2016-05-04 18:00","2016-05-03 09:00","2016-05-04 18:00","연속",null,null,null,201603140163]
[84,"대전충남","청양","보령T/P #5 M.Tr 1차 CB (7572)","보령화력 362kV GIS 보통점검","○ 345kV 7572 GIS 보통점검","2016-05-17 09:00","2016-05-18 18:00","2016-05-17 09:00","2016-05-18 18:00","연속",null,null,null,201603140167]
[85,"대전충남","청양","청양S/S 70-71-0 SEC CB (70-71-0)","청양S/S 345kV SEC Bay B/F반 교체","○ B/F반 교체","2016-05-09 09:30","2016-05-11 18:00","2016-05-09 09:30","2016-05-11 18:00","연속",null,null,null,201603140469]
[86,"대전충남","청양","청양S/S 75-76-0 SEC CB (75-76-0)","청양S/S 345kV SEC Bay B/F반 교체","○ B/F반 교체","2016-05-09 09:30","2016-05-11 18:00","2016-05-09 09:30","2016-05-11 18:00","연속",null,null,null,201603140473]
[87,"전북","군산","군산신김제#1 T/L","345kV 군산S/S 군산-신김제#1T/L","군산P/O 345kV 차단기 정밀점검공사 군산-신김제#1T/L(7271), 군산-신김제#1T/L-#1M.Tr 1차(7200) CB 차단기 정밀점검","2016-05-09 09:00","2016-05-27 18:00","2016-05-09 09:00","2016-05-27 18:00","연속",null,null,null,201602120049]
[88,"전북","군산","군산S/S #1 M.Tr A","345kV 군산S/S #1M.Tr A","군산P/O 345kV 차단기 정밀점검공사 #1M.Tr 1차(7272) CB 차단기 정밀점검","2016-05-09 09:00","2016-05-27 18:00","2016-05-09 09:00","2016-05-27 18:00","연속",null,null,null,201602120043]
[89,"전북","직할","신남원의령#1 T/L","345kV 신남원-의령 #1T/L 안전이격거리 확보공사","1. 철탑교체 (No.163~164) 2. 전력선교체 (No.160~164, 164~170)","2016-05-23 08:00","2016-06-02 18:00","2016-05-23 08:00","2016-06-02 18:00","연속",null,null,null,201603140340,"○"]
[90,"전북","직할","신남원의령#2 T/L","345kV 신남원-의령 #2T/L 안전이격거리 확보공사","1.철탑교체 (No.163~164) 2.전력선교체(No.160~164, 164~179)","2016-05-16 08:00","2016-05-22 18:00","2016-05-16 08:00","2016-05-22 18:00","연속",null,null,null,201603140333]
[91,"광주전남","강진","신강진S/S TIE-#3 M.Tr 1차 CB (7700)","345kV 신강진S/S 7700 CB(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 11 : 신강진S/S #3M.Tr 1차 TIE CB(7700)","2016-05-11 09:00","2016-05-11 18:00","2016-05-11 09:00","2016-05-11 18:00","당일",null,null,null,201603140673]
[92,"광주전남","강진","신강진S/S TIE-#2 M.Tr 1차 CB (7600)","345kV 신강진S/S 7600 CB(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 10 : 신강진S/S #2M.Tr 1차 TIE CB(7600)","2016-05-10 09:00","2016-05-10 18:00","2016-05-10 09:00","2016-05-10 18:00","당일",null,null,null,201603140672]
[93,"광주전남","강진","신강진S/S #1 M.Tr A","345kV 신강진S/S #1M.Tr(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 9 : 신강진S/S #1M.Tr 2차 CB(6144)","2016-05-09 09:00","2016-05-09 18:00","2016-05-09 09:00","2016-05-09 18:00","당일",null,null,null,201603140670]
[94,"광주전남","강진","신강진S/S TIE - 신강진-광양#2T/L CB (7400)","345kV 7400 TIE CB(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 6 : 신강진S/S 신강진-광양#2T/L TIE CB(7400)","2016-05-06 09:00","2016-05-06 18:00","2016-05-06 09:00","2016-05-06 18:00","당일",null,null,null,201603140669]
[95,"광주전남","강진","신강진S/S 신강진-광양 #2T/L CB (7471)","345kV 신강진-광양#2T/L(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 4 : 신강진S/S 신강진-광양#2T/L CB(7471)","2016-05-04 09:00","2016-05-04 18:00","2016-05-04 09:00","2016-05-04 18:00","당일",null,null,null,201603140668]
[96,"광주전남","강진","신강진S/S 신강진-광양#1T/L CB (7372)","345kV 신강진-광양#1T/L(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 3 : 신강진S/S 신강진-광양#1T/L CB(7372)","2016-05-03 09:00","2016-05-03 18:00","2016-05-03 09:00","2016-05-03 18:00","당일",null,null,null,201603140667]
[97,"광주전남","강진","신강진S/S신화순신강진#2-신강진광양#1 CB (7300)","345kV 7300 TIE CB(변전협력회사 총액공사)","문서번호 광전본(변전)-1947(2016. 3. 3)관련으로 공기압 조작방식 옥외 차단기 특별점검 - 5. 2 : 신강진S/S 신화순신강진#2-신강진광양#1T/L TIE CB(7300)","2016-05-02 09:00","2016-05-02 18:00","2016-05-02 09:00","2016-05-02 18:00","당일",null,null,null,201603140666]
[98,"광주전남","광주","신광주S/S 신광주-신화순#2T/L CB(신) (7571)","신광주S/S 신광주-신화순#2T/L CB(변전협력회사공사)","7571 GIS 초기점검","2016-05-17 09:00","2016-05-17 18:00","2016-05-17 09:00","2016-05-17 18:00","당일",null,null,null,201603100083]
[99,"광주전남","광주","신광주S/S 신광주-신화순#2T/L-TIE CB(신) (7500)","신광주S/S 신광주-신화순#2T/L-TIE CB(변전협력회사공사)","7500 GIS 초기점검","2016-05-16 09:00","2016-05-16 18:00","2016-05-16 09:00","2016-05-16 18:00","당일",null,null,null,201603100082]
[100,"광주전남","광주","신광주신화순#2 T/L","345kV신광주-신화순T/L 전선접속개소해소공사(협력총액)","전선교체","2016-05-31 07:00","2016-06-04 18:00","2016-05-31 07:00","2016-06-04 18:00","연속",null,null,null,201603090217]
[101,"광주전남","광주","신광주S/S 신광주-신화순#1T/L CB(15년) (7671(신))","신광주S/S 신광주-신화순#1T/L CB(변전협력회사공사)","7671 GIS 초기점검","2016-05-09 09:00","2016-05-09 18:00","2016-05-09 09:00","2016-05-09 18:00","당일",null,null,null,201603100081]
[102,"광주전남","광주","신광주신화순#1 T/L","345kV신광주-신화순T/L 전선접속개소해소공사(협력총액)","전선교체","2016-05-26 07:00","2016-05-30 18:00","2016-05-26 07:00","2016-05-30 18:00","연속",null,null,null,201603090216]
[103,"광주전남","순천","여수T/P #2 Tie-Tr","여수T/P 345kV #2M.Tr(변압기 및 OLTC 정밀점검공사)","2016년 상반기 주변압기 및 OLTC 정밀점검공사 - #2M.Tr 주변압기 및 OLTC 정밀점검","2016-05-23 10:00","2016-05-31 18:00","2016-05-23 10:00","2016-05-31 18:00","연속",null,null,null,201603140615]
[104,"광주전남","순천","여수T/P #1Tie-Tr","여수T/P 345kV #1M.Tr(변압기 및 OLTC 정밀점검공사)","2016년 상반기 주변압기 및 OLTC 정밀점검공사 - #1M.Tr 주변압기 및 OLTC 정밀점검","2016-05-09 10:00","2016-05-17 18:00","2016-05-09 10:00","2016-05-17 18:00","연속",null,null,null,201603140614]
[105,"광주전남","목포","한빛1NP-한빛2NP #1 T/L","16년 변전협력회사 총액공사","한빛1개폐소 한빛연락#1T/L GIS 점검","2016-05-23 09:00","2016-06-04 18:00","2016-05-23 09:00","2016-06-04 18:00","연속",null,null,null,201603240057]
[106,"대구경북","경산","울주신경산#2 T/L","신경산S/S 362kV 울주-신경산#2T/L 관련설비 보통점검","7300, 7371 CB 보통점검, LA 하자점검, Line PT 보통점검","2016-05-30 09:00","2016-05-31 18:00","2016-05-30 09:00","2016-05-31 18:00","연속",null,null,null,201603140360]
[107,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ 가공지선 철거 및 POST(#3) 철거 ○ 송전선로 및 가공지선 신규 설치","2016-05-23 08:00","2016-05-27 18:00","2016-05-23 08:00","2016-05-27 18:00","연속",null,null,null,201603090103]
[108,"대구경북","영주","신영주S/S #3M.Tr A","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거\"","2016-05-21 08:00","2016-05-31 18:00","2016-05-21 08:00","2016-05-31 18:00","연속",null,null,null,201603090100]
[109,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","○ #1BUS 연장 → 모선 GIB 연계 ○ #1B/P PNL 신규설치(86T 병렬 구성)","2016-05-18 13:00","2016-05-20 18:00","2016-05-18 13:00","2016-05-20 18:00","연속",null,null,null,201603090097]
[110,"대구경북","영주","신제천신영주#2 T/L","신영주S/S 362kV GIS화 공사","\"○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거\"","2016-05-21 08:00","2016-05-31 18:00","2016-05-21 08:00","2016-05-31 18:00","연속",null,null,null,201603090099]
[111,"대구경북","영주","신영주S/S #3M.Tr A","신영주S/S 362kV GIS화 공사","○ GIS용 LA, CVT 설치를 위한 안전이격 확보","2016-05-01 08:00","2016-05-02 18:00","2016-05-01 08:00","2016-05-02 18:00","연속",null,null,null,201603090093]
[112,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV GIS화 공사","○ GIS용 LA, CVT 설치를 위한 안전이격 확보","2016-05-03 08:00","2016-05-04 18:00","2016-05-03 08:00","2016-05-04 18:00","연속",null,null,null,201603090094]
[113,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","○ GIS용 LA, CVT 설치를 위한 안전이격 확보","2016-05-06 08:00","2016-05-07 18:00","2016-05-06 08:00","2016-05-07 18:00","연속",null,null,null,201603090095]
[114,"대구경북","영주","신제천신영주#1 T/L","신영주S/S 362kV GIS화 공사","○ #1,2BUS 모선연계 ○ GIS 무부하 가압(GIS CB,DS 수동 투입 / 개방)","2016-05-14 08:00","2016-05-20 18:00","2016-05-14 08:00","2016-05-20 18:00","연속",null,null,null,201603090098]
[115,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ #2BUS 연장 → GIS 78Bay(향후 신제천-신영주#1T/L) 연계 ○ #2B/P PNL 신규설치(86T 병렬 구성) ○ GIS 78Bay(7800,7801,7802 DS) 투입조건 모선가압 → 무부하가압 48h","2016-05-14 08:00","2016-05-18 13:00","2016-05-14 08:00","2016-05-18 13:00","연속",null,null,null,201603090096]
[116,"대구경북","영주","신태백한울NP2#3 T/L","한울N/P 345kV 송전선로 인출정비공사","인출 송전선로 게통변경(기설 2발 → 3발)","2016-05-16 08:00","2016-05-23 18:00","2016-05-16 08:00","2016-05-23 18:00","연속",null,null,null,201603090253]
[117,"대구경북","영주","한울1NP-한울2NP #1 T/L","한울N/P 345kV 송전선로 인출정비공사","송전선로 계통변경(신태백-한울NP3+신태백-한울NP2#3+한울연락#5 → 한울연락#4)","2016-05-16 08:00","2016-05-26 18:00","2016-05-16 08:00","2016-05-26 18:00","연속",null,null,null,201603090255]
[118,"대구경북","영주","한울3N/P 345kV #2 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-05-25 09:00","2016-05-27 18:00","2016-05-25 09:00","2016-05-27 18:00","연속",null,null,null,201602110008]
[119,"대구경북","영주","신영주한울NP3#1 T/L","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-05-25 09:00","2016-07-06 18:00","2016-05-25 09:00","2016-07-06 18:00","연속",null,null,null,201602110009]
[120,"대구경북","영주","신태백한울NP3 T/L","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-05-17 09:00","2016-05-24 18:00","2016-05-17 09:00","2016-05-24 18:00","연속",null,null,null,201602110005]
[121,"대구경북","영주","한울3N/P 345kV #1 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-05-22 09:00","2016-05-24 18:00","2016-05-22 09:00","2016-05-24 18:00","연속",null,null,null,201602110007]
[122,"대구경북","영주","신영주한울NP3#2 T/L","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-05-11 09:00","2016-05-24 18:00","2016-05-09 17:00","2016-05-24 18:00","연속",null,null,null,201602110004]
[123,"대구경북","칠곡","신포항북대구 T/L","GIS 정밀점검","GIS 정밀점검","2016-05-09 09:30","2016-05-14 18:00","2016-05-09 09:30","2016-05-14 18:00","연속",null,null,null,201603080011]
[124,"대구경북","칠곡","북대구S/S 345kV #1 BUS","GIS 정밀점검, UHF 센서설치","GIS 정밀점검, UHF 센서설치","2016-05-26 09:30","2016-05-27 18:00","2016-05-10 09:30","2016-05-11 18:00","연속",null,null,null,201603080012]
[125,"대구경북","칠곡","북대구S/S 345kV #2 BUS","GIS 정밀점검, UHF 센서설치","GIS 정밀점검, UHF 센서설치","2016-05-30 09:30","2016-05-31 18:00","2016-05-13 09:30","2016-05-14 18:00","연속",null,null,null,201603080013]
[126,"대구경북","칠곡","서대구S/S #3 M.Tr A","M.Tr 하자보수","M.Tr 하자보수","2016-05-23 09:30","2016-05-24 18:00","2016-05-23 09:30","2016-05-24 18:00","연속",null,null,null,201603070234]
[127,"대구경북","포항","신영일안동CC T/L","345kV 영포T/L 전선접속개소 제거공사","영포T/L No.210~253, 259~267 전선교체 : ACSR 480㎟(R) × 4B × 2C, 38.35C-km 가공지선교체 : ACSR120㎟ × S ×1C, 19.2C-km","2016-05-29 08:00","2016-06-11 18:00","취소","취소","연속",null,null,null,201603100002]
[128,"대구경북","포항","신포항청송PP T/L","345kV 영포T/L 전선접속개소 제거공사","영포T/L No.210~253, 259~267 전선교체 : ACSR 480㎟(R) × 4B × 2C, 38.35C-km 가공지선교체 : ACSR120㎟ × S ×1C, 19.2C-km","2016-05-15 08:00","2016-05-28 18:00","2016-05-15 08:00","2016-05-28 18:00","연속",null,null,null,201603100001]
[129,"부산울산","동부산","울주고리NP#1 T/L","345kV 울주-고리NP #1T/L 전선접속개소 전선교체공사","전선접소개소 해소, 30~68호, ACSR480 * 9.406km, 48가닥","2016-05-16 08:00","2016-05-30 18:00","2016-05-15 08:00","2016-05-29 18:00","연속",null,null,null,201603110045]
[130,"부산울산","동부산","울주고리NP#2 T/L","345kV 울주-고리NP #2T/L 전선접속개소 전선교체공사","전선접소개소 해소, 30~68호, ACSR480 * 9.406km, 48가닥","2016-05-31 08:00","2016-06-14 18:00","취소","취소","연속",null,null,null,201603110046]
[131,"부산울산","동부산","신양산고리NP#1 T/L","345kV 신양산-고리NP #1T/L 전선접속개소 전선교체공사","전선접소개소 해소, 11 ~ 32호, ACSR480 * 1.714km, 25가닥","2016-05-06 08:00","2016-05-14 18:00","2016-05-06 08:00","2016-05-14 18:00","연속",null,null,null,201603110042]
[132,"부산울산","동부산","신양산고리NP#2 T/L","345kV 신양산-고리NP #2T/L 전선접속개소 전선교체공사","전선접소개소 해소, 11 ~ 32호, ACSR480 * 1.714km, 25가닥","2016-05-02 08:00","2016-05-05 18:00","2016-05-02 08:00","2016-05-05 18:00","연속",null,null,null,201603110043]
[133,"부산울산","북부산","북부산울산TP T/L","345kV 북부산-울산TP 등 2개T/L 피뢰기 설치공사","345kV 북부산-울산TP 등 2개T/L 피뢰기 설치공사 (No.29~148, 123기)","2016-05-06 08:00","2016-05-25 18:00","2016-05-06 08:00","2016-05-15 18:00","연속",null,null,null,201603080148]
[134,"부산울산","북부산","신김해북부산#2 T/L","16년 가공송전 협력업체 정비공사","신김해북부산#2T/L 21,25호 애자교체,35호 금구류교체","2016-05-16 07:30","2016-05-18 18:00","2016-05-16 07:30","2016-05-18 18:00","연속",null,null,null,201601060092]
[135,"부산울산","북부산","북부산신온산 T/L","345kV 북부산-울산TP 등 2개T/L 전선접속개소 전선교체","345kV 북부산-신온산 T/L 전선접속개소 전선교체 (No.90~117, 7.263km)","2016-05-26 08:00","2016-06-14 18:00","2016-05-26 08:00","2016-06-14 18:00","연속",null,null,null,201603080151]
[136,"부산울산","북부산","북부산S/S 북신양#2T/L-#3M.Tr 1차 CB (7700)","2016년 북부산변전협력회사 총액공사","7700 GIS 하자점검","2016-05-02 09:30","2016-05-02 18:00","2016-05-02 09:30","2016-05-02 18:00","당일",null,null,null,201603130056]
[137,"부산울산","북부산","북부산S/S 신양산-북부산#2T/L CB (7771)","2016년 북부산변전협력회사 총액공사","7771GIS 하자점검","2016-05-03 09:30","2016-05-03 18:00","2016-05-03 09:30","2016-05-03 18:00","당일",null,null,null,201603130055]
[138,"부산울산","서부산","서부산S/S #3 M.Tr A","서부산S/S #3M.Tr 및 OLTC 정밀점검","서부산S/S #3M.Tr 및 OLTC 정밀점검","2016-05-30 10:00","2016-06-10 18:00","2016-05-30 10:00","2016-06-10 18:00","연속",null,null,null,201603140304]
[139,"부산울산","서부산","신녹산S/S #3 M.Tr A","신녹산S/S #3M.Tr 초기점검","신녹산S/S #3M.Tr 초기점검 [병행]#3M.Tr 1,2차 GIS 초기점검, #3S.Tr GIS 초기점검","2016-05-16 10:00","2016-05-20 18:00","2016-05-16 10:00","2016-05-20 18:00","연속",null,null,null,201603140298]
[140,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산 T/L 지장이설공사 No.60~65","철탑신설 5기(일반기초 1기,파일기초 4기), 철거 4기, 가철탑 2기, 기설철탑보강 2기","2016-05-11 08:00","2016-05-16 18:00","2016-05-11 08:00","2016-05-16 18:00","연속",null,null,null,201603090111]
[141,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산T/L NO.60~65 지장이설공사","철탑신설 5기(일반기초 1기, 파일기초 4기), 철거 4기, 가철탑 2기, 기설철탑보강 2기","2016-05-17 08:00","2016-05-26 18:00","2016-05-17 08:00","2016-05-26 18:00","연속",null,null,null,201603090114,"○"]
[142,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산 T/L 지장이설공사 No.60~65","철탑신설 5기(일반기초 1기,파일기초 4기), 철거 4기, 가철탑 2기, 기설철탑보강 2기","2016-05-27 08:00","2016-05-31 18:00","2016-05-27 08:00","2016-05-31 18:00","연속",null,null,null,201603090112]
[143,"부산울산","울산","신울산S/S #5 M.Tr A","SA 시범설비 개선공사","SA 시범설비 철거 및 보호배전반 설치, 제어케이블 설치 등","2016-05-09 09:00","2016-05-28 18:00","2016-05-09 09:00","2016-05-28 18:00","연속",null,null,null,201603110146]
[144,"부산울산","울산","울산C/C #2,3 S/T-#3,4 G/T CB (7700)","2016-17년 울산전력지사 변전협력회사 총액공사","7700 GIS 하자점검","2016-05-12 09:00","2016-05-12 18:00","2016-05-12 09:00","2016-05-12 18:00","당일",null,null,null,201603110133]
[145,"부산울산","울산","울산C/C #3 M.Tr A","공사명:345kV #3M.Tr GE제 보호계전기 성능개선","345kV #3M.Tr GE제 보호계전기 Power Mpdule 및 DSP 교체","2016-05-30 10:00","2016-05-30 18:00","2016-05-23 10:00","2016-05-23 18:00","당일",null,null,null,201603080067]
[146,"부산울산","울산","울산C/C #3,4 G/T 1차 CB (7772)","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 7772 GIS 하자점검","2016-05-16 09:00","2016-05-16 18:00","2016-05-16 09:00","2016-05-16 18:00","당일",null,null,null,201603110134]
[147,"부산울산","울산","울산C/C #2,3 S/T CB (7771)","2016-17년 울산전력지사 변전협력회사 총액공사","7771 GIS 하자점검","2016-05-11 09:00","2016-05-11 18:00","2016-05-11 09:00","2016-05-11 18:00","당일",null,null,null,201603110132]
[148,"부산울산","울산","울산C/C #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 M.Tr 보통점검, 7800,7871,6244,4284 GIS 보통점검","2016-05-26 09:00","2016-05-27 18:00","2016-05-24 09:00","2016-05-25 18:00","연속",null,null,null,201603110127]
[149,"부산울산","울산","울산C/C #3M.Tr 1차 CB (7271)","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 7271 GIS 하자점검","2016-05-17 09:00","2016-05-17 18:00","2016-05-17 09:00","2016-05-17 18:00","당일",null,null,null,201603110128]
[150,"부산울산","울산","울산C/C 4복합 #7,8G/T 1차-TIE CB (7100)","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 7100 GIS 하자점검","2016-05-18 09:00","2016-05-18 18:00","2016-05-18 09:00","2016-05-18 18:00","당일",null,null,null,201603110129]
[151,"부산울산","울산","울산C/C #1 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 M.Tr 보통점검, 7400,7471,6144,4184 GIS 보통점검","2016-05-03 09:00","2016-05-04 18:00","2016-05-03 09:00","2016-05-04 18:00","연속",null,null,null,201603110126]
[152,"부산울산","울산","울산C/C 4복합 #7,8G/T 1차 CB (7172)","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 7172 GIS 하자점검","2016-05-20 09:00","2016-05-20 18:00","2016-05-20 09:00","2016-05-20 18:00","당일",null,null,null,201603110135]
[153,"경남","직할","신김해삼천포화력#1 T/L","신김해-삼천포화력#1T/L 전력선 교체공사","전력선 교체공사(105~108, 159~160, 181~183, 201~202, 207~208)","2016-05-02 08:00","2016-05-15 18:00","2016-05-02 08:00","2016-05-15 18:00","연속",null,null,"신뢰도개선",201603100131]
[154,"경남","진주","의령S/S 의령-산청양수#1T/L-TIE CB (7400)","7400 차단기 정밀점검","7400 차단기 정밀점검 (시송전차단기)","2016-05-09 09:00","2016-05-11 18:00","2016-05-09 09:00","2016-05-11 18:00","연속",null,null,null,201603100130,"○"]
[155,"경남","진주","의령S/S #2 M.Tr A","#2M.Tr 변압기보호반PNL 대체공사","#2M.Tr 변압기보호반PNL 대체공사","2016-05-24 09:00","2016-05-26 18:00","2016-05-24 09:00","2016-05-26 18:00","연속",null,null,null,201603100180]
[156,"경남","진주","의령S/S 고령-의령#2T/L CB (7571)","7571 GIS CB 정밀점검","7571 GIS CB 정밀점검","2016-05-17 09:30","2016-05-19 18:30","2016-05-17 09:30","2016-05-19 18:30","연속",null,null,null,201603100158]
[157,"경남","진주","의령S/S #1 M.Tr A","#1M.Tr 3차 CB(4179) 부동작예방점검","#1M.Tr 3차 CB(4179) 부동작예방점검","2016-05-13 09:30","2016-05-13 18:30","2016-05-13 09:30","2016-05-13 18:30","당일",null,null,null,201603100161]
[158,"경남","통영","삼천포T/P 신고성#1T/L-TIE CB (7A00)","삼천포T/P 신고성#1T/L-TIE CB(7A00) 보통점검","삼천포T/P 신고성#1T/L-TIE CB(7571) 보통점검","2016-05-17 09:30","2016-05-17 18:30","2016-05-17 09:30","2016-05-17 18:30","당일",null,null,null,201603090281]
[159,"경남","통영","삼천포T/P 신고성-삼천포화력#2T/L CB (7B71)","삼천포T/P 신고성-삼천포화력#2T/L CB 보통점검","삼천포T/P 신고성-삼천포화력#2T/L CB(7B71) 보통점검","2016-05-23 09:30","2016-05-23 18:30","2016-05-23 09:30","2016-05-23 18:30","당일",null,null,null,201603090265]
[160,"경남","통영","삼천포T/P 신고성#2T/L-TIE CB (7B00)","삼천포T/P 신고성#2T/L-TIE CB(7B00) 보통점검","삼천포T/P 신고성#2T/L-TIE CB(7B00) 보통점검","2016-05-24 09:30","2016-05-24 18:30","2016-05-24 09:30","2016-05-24 18:30","당일",null,null,null,201603090298]
[161,"경남","통영","삼천포T/P 신김해-삼천포화력#2T/L CB (7672)","신고성S/S 345kV 신김해-삼천포화력#2T/L CB 보통점검","신고성S/S 345kV 신김해-삼천포화력#2T/L CB(7672) 보통점검","2016-05-19 09:30","2016-05-19 18:30","2016-05-19 09:30","2016-05-19 18:30","당일",null,null,null,201603090258]
[162,"경남","통영","삼천포T/P 신고성-삼천포화력#1T/L CB (7A71)","삼천포T/P 신고성-삼천포화력#1T/L CB(7A71) 보통점검","삼천포T/P 신고성-삼천포화력#1T/L CB(7A71) 보통점검","2016-05-18 09:30","2016-05-18 18:30","2016-05-18 09:30","2016-05-18 18:30","당일",null,null,null,201603090285]
[163,"경남","통영","신고성S/S #3 M.Tr A","신고성변전소 345kV #3M.Tr 1,2차 GIS 정밀점검공사","신고성변전소 345kV #3M.Tr 1,2차 GIS 정밀점검공사 1차 GIS(7F71,7F62,7F22) 정밀점검 2차 GIS(6244,6242,6241) 정밀점검 실리콘러버히터설치, 3차 모선지지애자 청소, 1,2,3차 LA 및 PT 보통점검","2016-05-09 09:30","2016-05-11 18:30","2016-05-09 09:30","2016-05-11 18:30","당일",null,null,null,201603090243]
[164,"경남","통영","신고성S/S #3 M.Tr 1차-TIE CB (7F00)","신고성S/S #3M.Tr 1차 TIE GIS 정밀점검","신고성S/S #3M.Tr 1차 TIE GIS 정밀점검 -7F00 CB 단독휴전","2016-05-12 09:30","2016-05-14 18:30","2016-05-12 09:30","2016-05-14 18:30","연속",null,null,null,201603090245]
[165,"경남","함안","신마산삼천포화력#2 T/L","345kV 신마산-삼천포화력 #2T/L 전력선 교체공사","345kV 신마산-삼천포화력 #2T/L 전력선 교체공사 (61~64호, 165~173호)","2016-05-29 08:30","2016-06-10 18:00","2016-05-29 08:30","2016-06-10 18:00","연속",null,null,"신뢰도개선",201603160222]
[166,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산-삼천포화력 #1T/L 전력선 교체공사","345kV 신마산-삼천포화력 #1T/L 전력선 교체공사 (61~64호, 165~173호)","2016-05-16 08:30","2016-05-28 18:00","2016-05-16 08:30","2016-05-28 18:00","연속",null,null,"신뢰도개선",201603160220]

{"sheet":"154송부","index":2,"n_rows":333,"n_cols":16,"rows_kept":333,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 5월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","녹번옥인 T/L","녹번S/S 인출T/L 교체공사","1. 사 업 명 : 154kV 녹번S/S 인출T/L 선종 교체공사 2. 사업목적 : 녹번변전소(지하복합) 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 154kV 녹번S/S ∼ 녹번분기전력구 ○ 사업내용 - 철거 : 154kV OF 2000㎟ 2C, 총길이1.8㎞ - 신설 : 154kV XLPE 2000㎟ 2C, 총길이1.8㎞","2016-05-02 09:00","2016-06-24 18:00","2016-05-02 09:00","2016-06-24 18:00","연속",null,null,null,201603210012]
[2,"서울","직할","아현서소문 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (#2M.Tr 1차, 아현서소문T/L GIS)","2016-05-23 10:00","2016-06-13 18:00","2016-05-23 10:00","2016-06-13 18:00","연속",null,null,null,201603180261]
[3,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (순화서소문#2T/L, 종로서소문T/L GIS)","2016-05-13 10:00","2016-05-23 10:00","2016-05-13 10:00","2016-05-23 10:00","연속",null,null,null,201602150731]
[4,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (#2M.Tr 1차 GIS, 아현서소문T/L GIS)","2016-05-23 10:00","2016-05-25 10:00","2016-05-23 10:00","2016-05-25 10:00","연속",null,null,null,201603180237]
[5,"서울","직할","서소문S/S 154kV #1 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (#2M.Tr 1차 GIS, 아현서소문T/L GIS)","2016-05-25 10:00","2016-06-02 10:00","2016-05-25 10:00","2016-06-02 10:00","연속",null,null,null,201603180238]
[6,"서울","직할","운니원남#1 T/L","2016년 직할 170kV GIS 정밀점검","운니S/S 170kV GIS 운니원남#1T/L 정밀점검","2016-05-16 09:30","2016-05-18 18:00","2016-05-16 09:30","2016-05-18 18:00","연속",null,null,null,201603180247]
[7,"서울","직할","운니원남#2 T/L","2016년 직할 170kV GIS 정밀점검","운니S/S 170kV GIS 운니원남#2T/L 정밀점검","2016-05-19 09:30","2016-05-21 18:00","2016-05-19 09:30","2016-05-21 18:00","연속",null,null,null,201603180249]
[8,"남서울","강남","신사S/S 154kV #2 BUS","170kV GIS 정밀점검 (신사S/S #2M.Tr)","170kV GIS 정밀점검 (신사S/S #2M.Tr, 신사-논현#2T/L)","2016-05-30 09:00","2016-05-31 13:00","2016-05-30 09:00","2016-05-31 13:00","연속",null,null,null,201603250111]
[9,"남서울","강남","신사S/S 154kV #1 BUS","170kV GIS 정밀점검 (신사S/S #1M.Tr)","170kV GIS 정밀점검 (신사S/S #1M.Tr, 신사-논현#2T/L)","2016-05-24 13:00","2016-05-27 18:00","2016-05-24 13:00","2016-05-27 18:00","연속",null,null,null,201603250108]
[10,"남서울","강남","신사S/S 154kV #1 BUS","170kV GIS 정밀점검 (신사S/S #2M.Tr)","170kV GIS 정밀점검 (신사S/S #2M.Tr, 신양재-신사#2T/L)","2016-05-31 13:00","2016-06-03 18:00","2016-05-31 13:00","2016-06-03 18:00","연속",null,null,null,201603250110]
[11,"남서울","강남","신사S/S 154kV #2 BUS","170kV GIS 정밀점검 (신사S/S #1M.Tr)","170kV GIS 정밀점검 (신사S/S #1M.Tr, 신사-논현#2T/L)","2016-05-23 09:00","2016-05-24 13:00","2016-05-23 09:00","2016-05-24 13:00","연속",null,null,null,201603250106]
[12,"남서울","강남","신사논현#2 T/L","신사S/S 신사-논현#2T/L 170kV GIS 정밀점검","신사S/S 신사-논현#2T/L 170kV GIS 정밀점검","2016-05-23 09:00","2016-05-27 18:00","2016-05-23 09:00","2016-05-27 18:00","연속",null,null,null,201603150294]
[13,"남서울","강남","신양재S/S 154kV #65 BUS","신양재S/S 65-66 SEC 170kV GIS 정밀점검공사","신양재S/S 65-66 SEC 170kV GIS 정밀점검공사","2016-05-08 08:00","2016-05-09 08:00","2016-05-08 08:00","2016-05-09 08:00","연속",null,null,null,201603150291]
[14,"남서울","강남","신양재신사#1 T/L","신양재-신사#1T/L 구형 절연통보호장치 교체공사","신양재-신사#1T/L 구형 절연통보호장치 교체공사","2016-05-02 11:00","2016-05-06 10:00","2016-05-02 11:00","2016-05-06 10:00","연속",null,null,null,201603130014]
[15,"남서울","강남","신양재S/S 154kV #60 BUS","신양재S/S 60-61 SEC 170kV GIS 정밀점검공사","신양재S/S 60-61 SEC 170kV GIS 정밀점검공사","2016-05-01 08:00","2016-05-02 08:00","2016-05-01 08:00","2016-05-02 08:00","연속",null,null,null,201603150289]
[16,"남서울","강남","신양재신사#2 T/L","신양재-신사#2T/L 노후배전반 대체 공사 -변전협력회사","신양재-신사#2T/L 노후배전반 대체 공사 -변전협력회사","2016-05-30 10:00","2016-06-03 18:00","2016-05-30 10:00","2016-06-03 18:00","연속",null,null,null,201603150284]
[17,"남서울","영서","화곡가양#1 T/L","154kV 마곡분기 지중T/L 건설공사","ㅇ 선종/긍장 : 154kV XLPE 2000㎟ , 2C-0.6km ㅇ 공사구간 : 신설 154kV 마곡S/S ~ 기설 M/H#3[화곡-가양 지중T/L] ㅇ 관련공사 : 마곡S/S 및 전력구 건설공사, 화곡-가양 지중T/L 이설공사","2016-05-02 09:00","2016-05-30 18:00","2016-05-02 09:00","2016-05-30 18:00","연속",null,null,"신뢰도개선",201601180024]
[18,"남서울","영서","광명구공#1 T/L","영서P/O 170kV GIS 정밀점검( 광명-구공#1 및 구철T/L)","- 광명-구공#1T/L GIS 정밀점검 - 구철T/L GIS 정밀점검","2016-05-02 09:00","2016-05-04 18:00","2016-05-02 09:00","2016-05-04 18:00","연속",null,null,"신뢰도개선",201602110390]
[19,"남서울","영서","영서시흥#1 T/L","송전선로 정밀점검","지지물 : 20기 긍 장 : 4.624km","2016-05-21 09:00","2016-05-22 18:00","2016-05-21 09:00","2016-05-22 18:00","연속",null,null,null,201603170184]
[20,"남서울","영서","영서시흥#2 T/L","송전선로 정밀점검","지지물 : 20기 긍 장 : 4.624km","2016-05-28 09:00","2016-05-29 18:00","2016-05-28 09:00","2016-05-29 18:00","연속",null,null,null,201603170186]
[21,"남서울","영서","천왕구로#1 T/L","2016년 영서P/O 변전협력회사 총액공사(주기점검)","천왕S/S 170kV GIS 보통점검(천왕-구로#1T/L)","2016-05-09 10:00","2016-05-09 18:00","2016-05-09 10:00","2016-05-09 18:00","당일",null,null,null,201603100254]
[22,"남서울","영서","천왕구로#2 T/L","2016년 영서P/O 변전협력회사 총액공사(주기점검)","천왕S/S 170kV GIS 보통점검(천왕-구로#2T/L)","2016-05-10 10:00","2016-05-10 18:00","2016-05-10 10:00","2016-05-10 18:00","당일",null,null,null,201603100259]
[23,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(화곡-가양#1T/L)","- 화곡-가양#1T/L GIS 정밀점검","2016-05-26 10:03","2016-05-27 18:00","2016-05-26 10:03","2016-05-27 18:00","연속",null,null,null,201603110076]
[24,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(화곡-가양#1T/L)","- 화곡-가양#1T/L GIS 정밀점검","2016-05-25 09:00","2016-05-26 13:00","2016-05-25 09:00","2016-05-26 13:00","연속",null,null,null,201603110074]
[25,"남서울","직할","교대이수#1 T/L","154kV 교대-이수T/L 지중선로 이설공사(방배로 1구간)","배경: 서초구청 시행 하수암거 설치에 따른 지중선로 이설 개요: 154KV 교대-이수T/L J/B#7~8, #9~10 (2구간, 0.66KM) XLPE1200 * 2회선","2016-05-02 09:00","2016-06-17 18:00","2016-05-02 09:00","2016-06-17 18:00","연속",null,null,null,201603210134]
[26,"인천","김포","경서S/S 154kV #2 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT","2016-05-06 08:00","2016-05-20 18:00","2016-05-06 08:00","2016-05-20 18:00","연속",null,null,null,201602110343]
[27,"인천","김포","신경서경서#1 T/L","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT - 신경서경서#1T/L 휴전 : BUS-TIE 작업에 따른 모선절체용","2016-05-12 11:00","2016-05-13 11:00","2016-05-12 11:00","2016-05-13 11:00","연속",null,null,null,201602120544]
[28,"인천","김포","신경서경서#1 T/L","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT - 신경서경서#1T/L 휴전 : BUS-TIE 작업에 따른 모선절체용","2016-05-04 18:00","2016-05-04 21:00","2016-05-04 18:00","2016-05-04 21:00","당일",null,null,null,201602110409]
[29,"인천","김포","신경서경서#1 T/L","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT - 신경서경서#1T/L 휴전 : BUS-TIE 작업에 따른 모선절체용","2016-05-06 08:00","2016-05-06 11:00","2016-05-06 08:00","2016-05-06 11:00","당일",null,null,null,201602120399]
[30,"인천","시흥","서시화S/S 154kV #1 BUS","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","2016-05-26 09:30","2016-05-27 14:00","2016-05-26 09:30","2016-05-27 14:00","연속",null,null,null,201603020222]
[31,"인천","시흥","북시화서시화#1 T/L","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","2016-05-26 09:30","2016-05-28 18:00","2016-05-26 09:30","2016-05-28 18:00","연속",null,null,"신뢰도개선",201603020219]
[32,"인천","시흥","서시화S/S 154kV #2 BUS","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","2016-05-27 14:00","2016-05-28 18:00","2016-05-27 14:00","2016-05-28 18:00","연속",null,null,null,201603020230]
[33,"인천","시흥","북시화서시화#2 T/L","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","2016-05-30 09:30","2016-06-01 18:00","2016-05-30 09:30","2016-06-01 18:00","연속",null,null,null,201603020220]
[34,"인천","시흥","서시화S/S 154kV #1 BUS","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","2016-05-30 09:30","2016-05-31 14:00","2016-05-30 09:30","2016-05-31 14:00","연속",null,null,null,201603020223]
[35,"인천","시흥","서시화S/S 154kV #2 BUS","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","2016-05-31 14:00","2016-06-01 18:00","2016-05-31 14:00","2016-06-01 18:00","연속",null,null,null,201603020224]
[36,"인천","시흥","소래S/S 154kV #1 BUS","소래S/S #2 M.Tr 1차 GIS 정밀점검공사","소래S/S #2 M.Tr 1차 GIS 정밀점검공사","2016-05-16 09:30","2016-05-17 14:00","2016-05-16 09:30","2016-05-17 14:00","연속",null,null,null,201603020208]
[37,"인천","시흥","소래S/S 154kV #1 BUS","소래S/S #1 M.Tr 1차 GIS 정밀점검공사","소래S/S #1 M.Tr 1차 GIS 정밀점검공사","2016-05-12 09:30","2016-05-13 14:00","2016-05-12 09:30","2016-05-13 14:00","연속",null,null,null,201603020206]
[38,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #1 M.Tr 1차 GIS 정밀점검공사","소래S/S #1 M.Tr 1차 GIS 정밀점검공사","2016-05-13 14:00","2016-05-14 18:00","2016-05-13 14:00","2016-05-14 18:00","연속",null,null,null,201603020211]
[39,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #2 M.Tr 1차 GIS 정밀점검공사","소래S/S #2 M.Tr 1차 GIS 정밀점검공사","2016-05-17 14:00","2016-05-18 18:00","2016-05-17 14:00","2016-05-18 18:00","연속",null,null,null,201603020210]
[40,"인천","시흥","소래S/S 154kV #1 BUS","소래S/S 154kV #1 BUS TIE GIS 정밀점검공사","소래S/S 154kV #1 BUS TIE GIS 정밀점검공사","2016-05-19 09:30","2016-05-20 14:00","2016-05-19 09:30","2016-05-20 14:00","연속",null,null,null,201603030071]
[41,"인천","시흥","소래S/S 154kV #1 BUS TIE GIS","소래S/S 154kV #1 BUS TIE GIS 정밀점검공사","소래S/S 154kV #1 BUS TIE GIS 정밀점검공사","2016-05-19 09:30","2016-05-21 18:00","2016-05-19 09:30","2016-05-21 18:00","연속",null,null,null,201603030070]
[42,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S 154kV #1 BUS TIE GIS 정밀점검공사","소래S/S 154kV #1 BUS TIE GIS 정밀점검공사","2016-05-20 14:00","2016-05-21 18:00","2016-05-20 14:00","2016-05-21 18:00","연속",null,null,null,201603030072]
[43,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #63 Sh.C GIS 정밀점검공사","신시흥#1S/S 154kV #63 Sh.C GIS 정밀점검공사","2016-05-03 14:00","2016-05-04 18:00","2016-05-03 14:00","2016-05-04 18:00","연속",null,null,null,201603170068]
[44,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","2016-05-06 14:00","2016-05-07 18:00","2016-05-06 14:00","2016-05-07 18:00","연속",null,null,null,201603170072]
[45,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥#1S/S 154kV #63 Sh.C GIS 정밀점검공사","신시흥#1S/S 154kV #63 Sh.C GIS 정밀점검공사","2016-05-02 09:30","2016-05-03 14:00","2016-05-02 09:30","2016-05-03 14:00","연속",null,null,null,201603170067]
[46,"인천","시흥","신시흥#1S/S 154kV #2 BUS TIE GIS","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","2016-05-05 09:30","2016-05-07 18:00","2016-05-05 09:30","2016-05-07 18:00","연속",null,null,null,201603020213]
[47,"인천","시흥","신시흥#1S/S 154kV #63 Sh.C","신시흥#1S/S 154kV #63 Sh.C GIS 정밀점검공사","신시흥#1S/S 154kV #63 Sh.C GIS 정밀점검공사","2016-05-02 09:30","2016-05-04 18:00","2016-05-02 09:30","2016-05-04 18:00","연속",null,null,null,201603020212]
[48,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","2016-05-05 09:30","2016-05-06 14:00","2016-05-05 09:30","2016-05-06 14:00","연속",null,null,null,201603170070]
[49,"인천","시흥","남동연수#2 T/L","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체","2016-05-16 08:00","2016-05-30 18:00","2016-05-16 08:00","2016-05-30 18:00","연속",null,null,null,201602120308]
[50,"인천","인천","서인천C/C 154kV #61 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","서인천C/C #6G.Tr GIS 정밀점검 공사","2016-05-25 09:00","2016-05-26 10:00","취소","취소","연속",null,null,null,201603100268]
[51,"인천","인천","서인천C/C 154kV #66 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","서인천C/C #6G.Tr GIS 정밀점검 공사","2016-05-26 10:00","2016-05-27 18:00","2016-05-01 14:00","2016-05-01 22:00","연속",null,null,null,201603100270]
[52,"인천","인천","서인천C/C #6 G.Tr 1차 GIS","2016년 인천전력지사 170kV GIS 정밀점검 공사","서인천C/C #6G.Tr GIS 정밀점검 공사","2016-05-25 09:00","2016-05-27 18:00","취소","취소","연속",null,null,null,201603100265]
[53,"인천","인천","신경서S/S 154kV #61 BUS","154kV 신경서-영종S/S SW증설공사","- 신경서S/S 154kV GIS 1CCT 설치 - 보호배전반 1면 설치 - 기타 부대 작업 1식","2016-05-23 10:00","2016-05-30 10:00","2016-05-23 10:00","2016-05-30 10:00","연속",null,null,null,201603150183]
[54,"인천","인천","신경서S/S 154kV #66 BUS","154kV 신경서-영종S/S SW증설공사","- 신경서S/S 154kV GIS 1CCT 설치 - 보호배전반 1면 설치 - 기타 부대 작업 1식","2016-05-30 10:00","2016-06-03 18:00","2016-05-30 10:00","2016-06-03 18:00","연속",null,null,null,201603150185]
[55,"인천","직할","고강S/S 154kV #1 BUS","154kV 신부평-고강 #1T/L M/H#9~#10 지장이설공사","154kV 신부평-고강 #1T/L M/H#9~#10 지장이설공사 준공시험","2016-05-09 09:00","2016-05-09 18:00","2016-05-09 09:00","2016-05-09 18:00","당일",null,null,null,201603150146]
[56,"인천","직할","신가좌부개#2 T/L","신가좌-부개#2T/L 보호반 대체공사","신가좌-부개#2T/L 보호반 대체공사","2016-05-17 09:30","2016-05-21 18:00","2016-05-17 09:30","2016-05-21 18:00","연속",null,null,null,201603150233]
[57,"인천","직할","신부평S/S 60-61 SEC GIS","신부평S/S 60-65 모선보호반 대체공사","신부평S/S 60-65 모선보호반 대체공사","2016-05-23 09:30","2016-05-27 18:00","2016-05-23 09:30","2016-05-27 18:00","연속",null,null,null,201603150205]
[58,"인천","직할","신부평S/S 154kV #1 BUS TIE GIS","신부평S/S 60-65 모선보호반 대체공사","신부평S/S 60-65 모선보호반 대체공사","2016-05-23 09:00","2016-05-27 18:00","2016-05-23 09:00","2016-05-27 18:00","연속",null,null,null,201603150204]
[59,"인천","직할","신부평S/S 154kV #2 BUS TIE GIS","신부평S/S 61-66 모선보호반 대체공사","신부평S/S 61-66 모선보호반 대체공사","2016-05-30 09:30","2016-06-03 18:00","2016-05-30 09:30","2016-06-03 18:00","연속",null,null,null,201603150207]
[60,"인천","직할","신부평S/S 60-61 SEC GIS","신부평S/S 61-66 모선보호반 대체공사","신부평S/S 61-66 모선보호반 대체공사","2016-05-30 09:30","2016-06-03 18:00","2016-05-30 09:30","2016-06-03 18:00","연속",null,null,null,201603150208]
[61,"인천","직할","신부평S/S 65-66 SEC GIS","신부평S/S 61-66 모선보호반 대체공사","신부평S/S 61-66 모선보호반 대체공사","2016-05-30 09:30","2016-06-03 18:00","2016-05-30 09:30","2016-06-03 18:00","연속",null,null,null,201603150209]
[62,"인천","직할","신부평부천#2 T/L","154kV 신부평-부천#2T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신부평-부천#1,2T/L(J/B#3,6,9,13,16)","2016-05-06 09:00","2016-05-09 18:00","2016-05-06 09:00","2016-05-09 18:00","연속",null,null,null,201602290074]
[63,"인천","직할","신부평부천#1 T/L","154kV 신부평-부천#1T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신부평-부천#1,2T/L(J/B#3,6,9,13,16)","2016-05-01 09:00","2016-05-04 18:00","2016-05-01 09:00","2016-05-04 18:00","연속",null,null,null,201602290073]
[64,"인천","직할","신부평S/S 65-66 SEC GIS","신부평S/S 60-65 모선보호반 대체공사","신부평S/S 60-65 모선보호반 대체공사","2016-05-23 09:30","2016-05-27 18:00","2016-05-23 09:30","2016-05-27 18:00","연속",null,null,null,201603150206]
[65,"인천","직할","중동화곡#2 T/L","154kV 중동화곡#2T/L 피뢰기 설치공사","154kV 중동화곡#2T/L 피뢰기 설치공사(No.1~21)","2016-05-30 08:00","2016-05-31 18:00","2016-05-30 08:00","2016-05-31 18:00","매일",null,null,null,201603160109]
[66,"경기북부","구리","덕소마석#2 T/L","송전선로보호반 교체","- 덕소-마석#2T/L 보호반 교체(덕소, 마석S/S 양단) - 젤파워제(오동작실적 과다 계전기) 대체","2016-05-16 09:00","2016-05-20 18:00","2016-05-16 09:00","2016-05-20 18:00","연속",null,null,null,201603180077,"○"]
[67,"경기북부","구리","덕소마석#1 T/L","송전선로보호반 교체","- 덕소-마석#1T/L 보호반 교체(덕소, 마석S/S 양단) - 젤파워제(오동작실적 과다 계전기) 대체","2016-05-09 09:00","2016-05-13 18:00","2016-05-09 09:00","2016-05-13 18:00","연속",null,null,null,201603180076,"○"]
[68,"경기북부","구리","미금화양 T/L","154kV 미금-화양T/L 지장송전선로 이설공사","154kV 미금-화양T/L 지장송전선로 이설공사 ㅇ 가공분야 - 신설 : No.15(CH), No.16 설치 - 철거 : No.3 ~ 16호간 철거 ㅇ 지중 - No.15(CH) ~ 미금S/S","2016-05-08 09:00","2016-05-27 18:00","2016-05-08 09:00","2016-05-27 18:00","연속",null,null,null,201603210039]
[69,"경기북부","직할","신의정부송우#2 T/L","신의정부송우#2 T/L","2016년 직할 변전협력회사 총액공사 - GIS 보통","2016-05-19 10:00","2016-05-19 18:00","2016-05-19 10:00","2016-05-19 18:00","당일",null,null,null,201603180020]
[70,"경기북부","직할","신의정부송우#1 T/L","신의정부송우#1 T/L","2016년 직할 변전협력회사 총액공사 - GIS 보통","2016-05-18 10:00","2016-05-18 18:00","2016-05-18 10:00","2016-05-18 18:00","당일",null,null,null,201603180019]
[71,"경기북부","직할","양주녹양#1 T/L","양주녹양#1 T/L","2016년 직할 변전협력회사 총액공사 - GCB 보통","2016-05-16 10:00","2016-05-16 18:00","2016-05-16 10:00","2016-05-16 18:00","당일",null,null,null,201603180013]
[72,"경기북부","직할","양주쌍문#2 T/L","양주쌍문#2 T/L","2016년 직할 변전협력회사 총액공사 - GCB 보통","2016-05-30 10:00","2016-05-30 18:00","2016-05-30 10:00","2016-05-30 18:00","당일",null,null,null,201603180018,"○"]
[73,"경기북부","직할","양주녹양#2 T/L","양주녹양#2 T/L","2016년 직할 변전협력회사 총액공사 - GCB 보통","2016-05-17 10:00","2016-05-17 18:00","2016-05-17 10:00","2016-05-17 18:00","당일",null,null,null,201603180014]
[74,"경기북부","직할","양주고양#2 T/L","양주고양#2 T/L","2016년 직할 변전협력회사 총액공사 - GCB 보통","2016-05-24 10:00","2016-05-24 18:00","2016-05-24 10:00","2016-05-24 18:00","당일",null,null,null,201603180016,"○"]
[75,"경기북부","직할","양주고양#1 T/L","양주고양#1 T/L","2016년 직할 변전협력회사 총액공사 - GCB 보통","2016-05-23 10:00","2016-05-23 18:00","2016-05-23 10:00","2016-05-23 18:00","당일",null,null,null,201603180015,"○"]
[76,"경기북부","파주","신파주송포#1 T/L","신파주S/S 신파주-송포#1T/L GIS 정밀점검공사","신파주S/S 신파주-송포#1T/L GIS 정밀점검","2016-05-23 09:30","2016-05-27 18:00","2016-05-23 09:30","2016-05-27 18:00","연속",null,null,null,201603180189]
[77,"경기북부","파주","신파주송포#2 T/L","신파주S/S 신파주-송포#2T/L GIS 정밀점검공사","신파주S/S 신파주-송포#2T/L GIS 정밀점검","2016-05-30 09:30","2016-06-01 18:00","2016-05-30 09:30","2016-06-01 18:00","연속",null,null,null,201603180190]
[78,"경기북부","파주","일산지도#2 T/L","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-05-16 08:00","2016-06-04 18:00","2016-05-16 08:00","2016-06-04 18:00","연속",null,null,null,201603170151]
[79,"경기북부","파주","일산S/S 154kV #65 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-05-29 08:00","2016-06-04 18:00","2016-05-29 08:00","2016-06-04 18:00","연속",null,null,"신뢰도개선",201603170150]
[80,"경기북부","파주","일산S/S 154kV #60 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-05-19 08:00","2016-05-28 18:00","2016-05-19 08:00","2016-05-28 18:00","연속",null,null,"신뢰도개선",201603170153]
[81,"경기북부","파주","일산S/S 154kV #65 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-05-16 08:00","2016-05-18 18:00","2016-05-16 08:00","2016-05-18 18:00","연속",null,null,"신뢰도개선",201603180088]
[82,"경기북부","파주","일산호수#1 T/L","호수S/S 일산-호수#1T/L GIS 정밀점검공사","호수S/S 일산-호수#1T/L GIS 정밀점검","2016-05-09 08:00","2016-05-11 18:00","2016-05-09 08:00","2016-05-11 18:00","연속",null,null,null,201603180172]
[83,"경기북부","파주","일산호수#2 T/L","호수S/S 일산-호수#2T/L GIS 정밀점검공사","호수S/S 일산-호수#2T/L GIS 정밀점검","2016-05-12 08:00","2016-05-14 18:00","2016-05-12 08:00","2016-05-14 18:00","연속",null,null,null,201603180173]
[84,"경기","군포","서서울S/S 61-62-0 SEC CB","서서울S/S 154kV 61-62-0 SEC GCB 정밀점검공사","서서울S/S 154kV 61-62-0 SEC GCB 정밀점검공사","2016-05-10 09:00","2016-05-11 18:00","2016-05-10 09:00","2016-05-11 18:00","연속",null,null,null,201603140576]
[85,"경기","군포","서서울S/S 66-67-0 SEC CB","서서울S/S 154kV 66-67-0 SEC GCB 정밀점검공사","서서울S/S 154kV 66-67-0 SEC GCB 정밀점검공사","2016-05-12 09:00","2016-05-13 18:00","2016-05-12 09:00","2016-05-13 18:00","연속",null,null,null,201603140577]
[86,"경기","군포","신안산남안산#1 T/L","345kV 신안산SS 모자익 대체 공사","345kV 신안산SS 모자익 대체 공사","2016-05-16 09:00","2016-05-18 18:00","2016-05-16 09:00","2016-05-18 18:00","연속",null,null,null,201603140563]
[87,"경기","군포","서서울일동#1 T/L","154kV 서서울일동#1T/L 송전선로용 피뢰기 설치공사","- 24기(1~24호) 송전선로용 피뢰기 설치","2016-05-27 07:00","2016-05-28 19:00","2016-05-27 07:00","2016-05-28 19:00","연속",null,null,null,201603140058]
[88,"경기","군포","화성조암#1 T/L","조암S/S 154kV 화성조암#1T/L GIS 정밀점검공사","조암S/S 154kV 화성조암#1T/L GIS 정밀점검공사","2016-05-13 09:00","2016-05-15 18:00","2016-05-13 09:00","2016-05-15 18:00","연속",null,null,null,201603140573]
[89,"경기","동부","오포모현#1 T/L","16년 동부 변전협력회사 총액공사","오포S/S 오포-모현#1T/L GIS 보통점검","2016-05-01 09:30","2016-05-01 18:00","2016-05-01 09:30","2016-05-01 18:00","연속",null,null,null,201603140197]
[90,"경기","동부","분당오포#2 T/L","16년 동부 변전협력회사 총액공사","분당-오포#2T/L GIS 보통점검(분당,오포S/S)","2016-05-08 09:30","2016-05-08 18:00","2016-05-08 09:30","2016-05-08 18:00","당일",null,null,null,201603140200]
[91,"경기","성남","신성남정자#2 T/L","신성남S/S 신성남-정자#2 T/L 비상트립장치시공","신성남S/S 신성남-정자#2 T/L 비상트립장치시공","2016-05-21 10:00","2016-05-21 13:00","2016-05-21 10:00","2016-05-21 13:00","당일",null,null,null,201603110165]
[92,"경기","성남","신성남서판교#1 T/L","신성남S/S 154kV 신성남-서판교#1T/L 비상트립장치시공","신성남S/S 154kV 신성남-서판교#1T/L 비상트립장치시공","2016-05-21 13:00","2016-05-21 18:00","2016-05-21 13:00","2016-05-21 18:00","당일",null,null,"신뢰도개선",201603110225]
[93,"경기","성남","용인남사#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-05-09 09:00","2016-05-15 18:00","2016-05-09 09:00","2016-05-15 18:00","연속",null,null,null,201603150128]
[94,"경기","성남","모현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-05-16 09:00","2016-06-09 18:00","2016-05-16 09:00","2016-06-09 18:00","연속",null,null,null,201603150129]
[95,"경기","직할","율전의왕#1 T/L","율전의왕#1 T/L","의왕S/S 율전의왕#1T/L GIS 정밀점검","2016-05-20 09:00","2016-05-22 18:00","2016-05-20 09:00","2016-05-22 18:00","연속",null,null,"신뢰도개선",201603140401]
[96,"경기","직할","의왕동안양#2 T/L","154kV 의왕동안양#2T/L 애자교체공사(구간 No.11)","16년 가공송전선로 순시점검 위탁공사 154kV 의왕동안양#2T/L 애자교체(구간 No.11)_하단(율전의왕#1T/L 휴전필요)","2016-05-22 09:00","2016-05-22 18:00","2016-05-22 09:00","2016-05-22 18:00","당일",null,null,null,201603150141]
[97,"경기","직할","화성조암#2 T/L","345kV 화성조암#2T/L 안전이격거리확보","- 154kV 화성-장덕T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보","2016-05-07 07:00","2016-05-07 13:00","2016-05-07 07:00","2016-05-07 13:00","당일",null,null,null,201603140050]
[98,"경기","평택","안성S/S 서안성-안성#1T/L GIS","안성S/S 서안성-안성#1T/L 보호반대체","안성S/S 서안성-안성#1T/L 보호반대체","2016-05-23 10:00","2016-05-25 18:00","2016-05-23 10:00","2016-05-25 18:00","연속",null,null,null,201603140279]
[99,"강원","동해","동해정선 T/L","345kV 신제천-동해T/L 등 7개T/L 송전선로용 피뢰기 설치공사","1. No.1~25 송전선로용 피뢰기설치 2. No.1~25 송전선로 정밀점검","2016-05-09 08:00","2016-05-13 18:00","2016-05-09 08:00","2016-05-13 18:00","매일",null,null,null,201603040162]
[100,"강원","원주","횡성홍천#2 T/L","154kV 홍천T/L 안전이격확보공사","안전이격확보공사 시행(철거 4기, 신설 3기)","2016-05-12 09:00","2016-05-18 18:00","2016-05-12 09:00","2016-05-18 18:00","연속",null,null,null,201603070219]
[101,"강원","원주","횡성홍천#1 T/L","154kV 홍천T/L 안전이격확보공사","안전이격확보공사 시행(철거 4기, 신설 3기)","2016-05-12 09:00","2016-05-18 18:00","2016-05-12 09:00","2016-05-18 18:00","연속",null,null,null,201603070218]
[102,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-05-08 07:30","2016-05-09 18:00","2016-05-08 07:30","2016-05-09 18:00","연속",null,null,null,201603070075]
[103,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-05-19 07:30","2016-05-24 18:00","2016-05-19 07:30","2016-05-24 18:00","연속",null,null,null,201603230017]
[104,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-05-29 07:30","2016-06-01 18:00","2016-05-29 07:30","2016-06-01 18:00","연속",null,null,null,201603230019]
[105,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-05-10 07:30","2016-05-11 18:00","2016-05-10 07:30","2016-05-11 18:00","연속",null,null,null,201603070073]
[106,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-05-25 07:30","2016-05-28 18:00","2016-05-25 07:30","2016-05-28 18:00","연속",null,null,null,201603070074]
[107,"강원","직할","상남인제#2 T/L","2016년 관내변전소 154kV GCB ,GIS 정밀점검공사 시행","154kV 상남인제 #2T/L CB, #1,2DS, LDS 등 내부점검 조작메카니즘 부 점검","2016-05-23 08:00","2016-05-25 18:00","2016-05-23 08:00","2016-05-25 18:00","연속",null,null,null,201603050010]
[108,"강원","직할","가평춘천HP T/L","2016년 상반기 장기 미동작 차단기 조작시험","2016년 상반기 장기 미동작 차단기 조작시험 시행","2016-05-03 10:00","2016-05-03 18:00","2016-05-03 10:00","2016-05-03 18:00","당일",null,null,null,201603020030]
[109,"강원","태백","동해동영월 T/L","154kV 태백-영월 등 3개T/L 피뢰기 설치공사","154kV 동영월분기T/L 피뢰기설치 No.1~6(동해-동영월T/L 측)","2016-05-27 08:30","2016-06-03 18:00","2016-05-27 08:30","2016-06-03 18:00","매일",null,null,null,201603070138]
[110,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC#2T/L GIS(#2BUS DS) 정밀점검","2016-05-10 10:00","2016-05-11 18:00","2016-05-10 10:00","2016-05-11 18:00","연속",null,null,null,201603180389]
[111,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC#2T/L GIS(#1BUS DS) 정밀점검","2016-05-09 08:00","2016-05-10 10:00","2016-05-09 08:00","2016-05-10 10:00","연속",null,null,null,201603180388]
[112,"강원","태백","단양영월CC#2 T/L","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC#2T/L GIS 정밀점검","2016-05-09 08:00","2016-05-11 18:00","2016-05-09 08:00","2016-05-11 18:00","연속",null,null,null,201603180386]
[113,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC #1 T/L GIS(#2BUS DS) 정밀점검","2016-05-03 10:00","2016-05-04 18:00","2016-05-03 10:00","2016-05-04 18:00","연속",null,null,null,201603070164]
[114,"강원","태백","단양영월CC#1 T/L","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC #1 T/L GIS 정밀점검","2016-05-02 08:00","2016-05-04 18:00","2016-05-02 08:00","2016-05-04 18:00","연속",null,null,null,201603070142]
[115,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC #1 T/L GIS(#1BUS DS) 정밀점검","2016-05-02 08:00","2016-05-03 10:00","2016-05-02 08:00","2016-05-03 10:00","연속",null,null,null,201603070143]
[116,"강원","태백","고한영월 T/L","154kV 태백-영월 등 3개T/L 피뢰기 설치공사","154kV 고한분기T/L 피뢰기설치 No.1~33(고한-영월T/L 측)","2016-05-09 08:30","2016-05-18 18:00","2016-05-09 08:30","2016-05-18 18:00","매일",null,null,null,201603070110]
[117,"강원","태백","영월S/S 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월 GT #1 GIS(#1BUS DS) 정밀점검","2016-05-16 08:00","2016-05-17 10:00","2016-05-16 08:00","2016-05-17 10:00","연속",null,null,null,201603070149]
[118,"강원","태백","영월S/S 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월 GT#1 GIS(#2BUS DS) 정밀점검","2016-05-17 10:00","2016-05-18 10:00","2016-05-17 10:00","2016-05-18 10:00","연속",null,null,null,201603070155]
[119,"강원","태백","태백고한 T/L","16~17년 태백전력지사 송전정비 협력회사 총액공사","154kV 태백-고한T/L No.103~107 접속개소해소 전선교체공사","2016-05-19 08:30","2016-05-25 18:00","2016-05-19 08:30","2016-05-25 18:00","연속",null,null,null,201603070123]
[120,"충북","직할","문경단양 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","154kV 문경-단양T/L 전력선 교체 (7~47호)","2016-05-09 07:30","2016-05-22 18:00","2016-05-27 07:30","2016-06-09 18:00","당일",null,null,null,201603150001]
[121,"충북","직할","점촌단양 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","154kV 점촌-단양T/L 전력선 교체 (9~47호), 피뢰기 설치 (1~47호)","2016-05-23 07:30","2016-06-09 18:00","2016-05-09 07:30","2016-05-26 18:00","연속",null,null,null,201603150005]
[122,"충북","직할","신제천영월CC#2 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 내압시험","2016-05-10 09:00","2016-05-10 18:00","2016-05-10 09:00","2016-05-10 18:00","당일",null,null,null,201603040159]
[123,"충북","직할","신제천남원주#1 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 조립(안전거리 확보)","2016-05-02 08:00","2016-05-02 13:00","2016-05-02 08:00","2016-05-02 13:00","당일",null,null,null,201603040157]
[124,"충북","직할","신제천주진#2 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 조립(안전거리 확보)","2016-05-01 08:00","2016-05-01 18:00","2016-05-01 08:00","2016-05-01 18:00","당일",null,null,null,201603040155]
[125,"충북","직할","신제천남원주#1 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 조립(안전거리 확보)","2016-05-02 13:00","2016-05-02 18:00","2016-05-02 13:00","2016-05-02 18:00","당일",null,null,null,201603040158]
[126,"충북","직할","음성금왕#2 T/L","2016~2017년 충주 송전정비 협력회사 총액공사 (피뢰기 설치)","피뢰기 설치 (No.1~65)","2016-05-16 08:00","2016-05-22 18:00","2016-05-16 08:00","2016-05-22 18:00","매일",null,null,null,201602290052,"○"]
[127,"충북","청주","신옥천서대전#1 T/L","16년 청주 154kV 개폐장치 정밀점검","신옥천S/S 신옥천-서대전 #1T/L GCB 정밀점검","2016-05-23 09:00","2016-05-25 18:00","2016-05-23 09:00","2016-05-25 18:00","연속",null,null,null,201603150056]
[128,"충북","청주","청원죽림#2 T/L","16년 청주 154kV 개폐장치 정밀점검","죽림S/S 청원-죽림#2T/L GIS (657CB, 651,652DS) 정밀점검","2016-05-13 09:00","2016-05-15 18:00","2016-05-13 09:00","2016-05-15 18:00","연속",null,null,null,201603150052]
[129,"충북","청주","청원부강#2 T/L","154kV 신진천오창 등 8개T/L 송전용피뢰기 설치공사","청원부강T/L 송전용피뢰기 설치(No.5-28, 24기)","2016-05-12 08:00","2016-05-13 19:00","2016-05-12 08:00","2016-05-13 19:00","매일",null,null,null,201603190001,"○"]
[130,"충북","청주","청주대청HP T/L","16-17년 송전정비협력회사 총액공사","전력선교체(18~57, 58~88) 23개소","2016-05-06 08:00","2016-05-30 19:00","2016-05-06 08:00","2016-05-30 19:00","연속",null,null,null,201603150239,"○"]
[131,"충북","청주","청원청주#2 T/L","16-17년 송전정비협력회사 총액공사","전력선교체(18~57, 58~88) 23개소","2016-05-06 08:00","2016-05-30 19:00","2016-05-06 08:00","2016-05-30 19:00","연속",null,null,null,201603150237]
[132,"충북","충주","금왕남음성#1 T/L","2016년 충주 송전정비 협력회사 총액공사","154kV 음성-금왕#2T/L 피뢰기 설치 (안전확보 병행휴전)","2016-05-20 09:00","2016-05-22 18:00","2016-05-20 09:00","2016-05-22 18:00","매일",null,null,null,201603180319,"○"]
[133,"충북","충주","금왕남음성#2 T/L","154kV GIS 초기점검","주기도래 전력설비 초기점검","2016-05-09 10:00","2016-05-09 18:00","2016-05-09 10:00","2016-05-09 18:00","당일",null,null,null,201602140060,"○"]
[134,"충북","충주","남음성덕산#2 T/L","154kV GIS 하자점검","주기도래에 따른 해당 차단기 하자점검","2016-05-18 10:00","2016-05-19 18:00","2016-05-18 10:00","2016-05-19 18:00","매일",null,null,null,201602120905]
[135,"충북","충주","충주충주HP#1 T/L","2016~2017년 충주 송전정비 협력회사 총액공사 (금구류 교체)","금구류 교체 (No.22)","2016-05-11 08:00","2016-05-11 18:00","2016-05-11 08:00","2016-05-11 18:00","당일",null,null,null,201603080080,"○"]
[136,"충북","충주","충주충주HP#2 T/L","2016~2017년 충주 송전정비 협력회사 총액공사 (전선교체)","전선교체 (S/T ~ 1호)","2016-05-09 08:00","2016-05-10 18:00","2016-05-09 08:00","2016-05-10 18:00","연속",null,null,null,201603080076,"○"]
[137,"충북","충주","풍동음성#1 T/L","2016년 충주 송전정비 협력회사 총액공사","154kV 풍동T/L(풍동-장연측) 피뢰기 설치 (안전확보 병행휴전)","2016-05-30 09:00","2016-05-31 18:00","2016-05-30 09:00","2016-05-31 18:00","매일",null,null,null,201603180320,"○"]
[138,"대전충남","서산","아산송악#1 T/L","154kV 아산-송악#1T/L 정밀점검","[송전] 154kV 아산송악#1T/L 정밀점검 - No.103~149","2016-05-30 09:00","2016-06-02 18:00","2016-05-30 09:00","2016-06-02 18:00","매일",null,null,null,201603110168]
[139,"대전충남","서산","신당진당진#2 T/L","154kV 서산-대산#3,4 등 2개T/L 피뢰기 설치공사","[송전]신당진-당진#2T/L No.1~43(129set) -아킹혼 철거 -피뢰기 설치","2016-05-16 09:00","2016-05-20 18:00","2016-05-16 09:00","2016-05-20 18:00","매일",null,null,null,201603150011]
[140,"대전충남","서산","태안T/P 154kV #1 BUS","태안T/P 154kV GIS 정밀점검","○ 154kV GIS 정밀점검","2016-05-02 09:00","2016-05-03 15:00","2016-05-02 09:00","2016-05-03 15:00","연속",null,null,null,201603140459]
[141,"대전충남","서산","태안T/P 154kV #2 BUS","태안T/P 154kV GIS 정밀점검","○ 154kV GIS 정밀점검","2016-05-03 15:00","2016-05-04 18:00","2016-05-03 15:00","2016-05-04 18:00","연속",null,null,null,201603140460]
[142,"대전충남","아산","불당서천안#1 T/L","[송전]154kV불당-서천안 등 2개T/L SVL교체공사","불당-서천안 등 2개T/L 구형SVL 교체 84set","2016-05-07 09:00","2016-05-10 18:00","2016-05-07 09:00","2016-05-10 18:00","매일",null,null,null,201603140353]
[143,"대전충남","아산","불당서천안#2 T/L","[송전]154kV불당-서천안 등 2개T/L SVL교체공사","불당-서천안 등 2개T/L 구형SVL 교체 84set","2016-05-18 09:00","2016-05-21 18:00","2016-05-18 09:00","2016-05-21 18:00","매일",null,null,null,201603140356]
[144,"대전충남","아산","아산S/S 154kV #1 BUS TIE CB","아산S/S 154kV 새롬프로텍 모선보호반 성능개선 공사","○ 154kV 새롬프로텍 모선보호반 성능개선 공사","2016-05-12 09:00","2016-05-12 12:00","2016-05-12 09:00","2016-05-12 12:00","당일",null,null,null,201603180032]
[145,"대전충남","아산","아산S/S 154kV #2 BUS TIE CB","아산S/S 154kV 새롬프로텍 모선보호반 성능개선 공사","○ 154kV 새롬프로텍 모선보호반 성능개선 공사","2016-05-12 13:00","2016-05-12 18:00","2016-05-12 13:00","2016-05-12 18:00","당일",null,null,null,201603180033]
[146,"대전충남","아산","인주S/S 154kV #1 BUS TIE CB","인주S/S 154kV 영인제 모선보호반 제작사 성능개선 공사","○ 154kV 영인제 모선보호반 제작사 성능개선 공사","2016-05-10 09:00","2016-05-10 18:00","2016-05-10 09:00","2016-05-10 18:00","당일",null,null,null,201603180031]
[147,"대전충남","아산","아산인주#1 T/L","[송전] 154kV 아산-인주#1T/L 정밀점검","154kV 아산-인주#1T/L 정밀점검","2016-05-28 07:00","2016-05-29 18:00","2016-05-28 07:00","2016-05-29 18:00","매일",null,null,"신뢰도개선",201603140247]
[148,"대전충남","아산","장재S/S 주공#1T/L CB","장재S/S 154kV 주공#1T/L 장기미동작 차단기 조작시험","○154kV 주공#1T/L 장기미동작 차단기 조작시험","2016-05-12 10:00","2016-05-12 11:00","2016-05-12 10:00","2016-05-12 11:00","당일",null,null,null,201603140310]
[149,"대전충남","아산","장재S/S 주공#2T/L CB","장재S/S 154kV 주공#2T/L 장기미동작 차단기 조작시험","○154kV 주공#2T/L 장기미동작 차단기 조작시험","2016-05-12 11:00","2016-05-12 12:00","2016-05-12 11:00","2016-05-12 12:00","당일",null,null,null,201603140313]
[150,"대전충남","아산","풍세장재#1 T/L","풍세S/S 154kV 풍세-장재#1T/L GIS 하자점검","○154kV 풍세-장재#1T/L GIS 하자점검","2016-05-10 09:00","2016-05-10 18:00","2016-05-10 09:00","2016-05-10 18:00","당일",null,null,null,201603140294]
[151,"대전충남","아산","풍세장재#2 T/L","풍세S/S 154kV 풍세-장재#2T/L GIS 하자점검","○154kV 풍세-장재#2T/L GIS 하자점검","2016-05-11 09:00","2016-05-11 18:00","2016-05-11 09:00","2016-05-11 18:00","당일",null,null,null,201603140302]
[152,"대전충남","청양","보령C/C 154kV #1 BUS","2016년 청양P/O 170kV GIS 정밀점검공사","○ 154kV GIS 정밀점검","2016-05-09 08:00","2016-05-10 15:00","2016-05-09 08:00","2016-05-10 15:00","당일",null,null,null,201603140088]
[153,"대전충남","청양","보령C/C 154kV #2 BUS","2016년 청양P/O 170kV GIS 정밀점검공사","○ 154kV GIS 정밀점검","2016-05-10 15:00","2016-05-12 15:00","2016-05-10 15:00","2016-05-12 15:00","당일",null,null,null,201603140089]
[154,"대전충남","청양","보령C/C 154kV #1 BUS","2016년 청양P/O 170kV GIS 정밀점검공사","○ 154kV GIS 정밀점검","2016-05-12 15:00","2016-05-14 15:00","2016-05-12 15:00","2016-05-14 15:00","당일",null,null,null,201603140090]
[155,"대전충남","청양","보령C/C 154kV #2 BUS","2016년 청양P/O 170kV GIS 정밀점검공사","○ 154kV GIS 정밀점검","2016-05-14 15:00","2016-05-15 18:00","2016-05-14 15:00","2016-05-15 18:00","당일",null,null,null,201603140093]
[156,"대전충남","청양","관창보령복합 T/L","2016년 청양P/O 170kV GIS 정밀점검공사","○ 154kV GIS 정밀점검","2016-05-09 08:00","2016-05-13 18:00","2016-05-09 08:00","2016-05-13 18:00","연속",null,null,null,201603140101]
[157,"대전충남","청양","신풍공주#2 T/L","신풍공주#2T/L 보호배전반 교체","○ 154kV 보호배전반 교체 ○ 제어케이블 교체","2016-05-02 09:30","2016-05-04 18:00","2016-05-02 09:30","2016-05-04 18:00","연속",null,null,null,201603140465]
[158,"전북","군산","내초SE열병합#1 T/L","내초SE열병합#1 T/L","차단기 초기점검공사","2016-05-16 10:00","2016-05-16 18:00","2016-05-16 10:00","2016-05-16 18:00","당일",null,null,null,201603090264]
[159,"전북","군산","내초SE열병합#2 T/L","내초SE열병합#2T/L","차단기 초기점검공사","2016-05-17 10:00","2016-05-17 18:00","2016-05-17 10:00","2016-05-17 18:00","당일",null,null,null,201603090273]
[160,"전북","군산","동군산군산CC#1 T/L","동군산군산CC#1 T/L","1년 미동작 차단기 특별점검","2016-05-11 10:00","2016-05-11 18:00","2016-05-11 10:00","2016-05-11 18:00","당일",null,null,null,201603100080]
[161,"전북","군산","군공군산CC#1 T/L","154kV군공-군산복합T/L 지중선로 이설공사","154kV 군공-군산복합T/L M/H#10~12번 구간 군장대고 건설관련 지장이설 신청으로 선로 이설","2016-05-06 09:00","2016-05-23 18:00","취소","취소","연속",null,null,"신뢰도개선",201603100210]
[162,"전북","군산","군공군산CC#2 T/L","154kV군공-군산복합T/L 지중선로 이설공사","154kV 군공-군산복합T/L M/H#10~12번 구간 군장대고 건설관련 지장이설 신청으로 선로 이설","2016-05-24 09:00","2016-06-10 18:00","취소","취소","연속",null,null,"신뢰도개선",201603100223]
[163,"전북","군산","군산영등#2 T/L","154kV 군산-영등#2T/L 피뢰기 설치공사","1. 피뢰기 설치 : No.1~56","2016-05-02 07:00","2016-05-05 18:00","2016-05-02 07:00","2016-05-05 18:00","매일",null,null,null,201603110191]
[164,"전북","군산","동군산장항#2 T/L","154kV 동군산-장항#2T/L 피뢰기 설치공사","1. 피뢰기 설치 : No.18~38","2016-05-18 07:00","2016-05-19 18:00","2016-05-18 07:00","2016-05-19 18:00","매일",null,null,null,201603110231]
[165,"전북","군산","동군산장항#1 T/L","동군산장항#1 T/L","차단기 보통점검공사","2016-05-10 09:00","2016-05-10 18:00","2016-05-10 09:00","2016-05-10 18:00","당일",null,null,null,201603090304]
[166,"전북","군산","서군산소룡#2 T/L","서군산소룡#2 T/L","차단기 보통점검공사","2016-05-03 09:00","2016-05-04 18:00","2016-05-03 09:00","2016-05-04 18:00","매일",null,null,null,201603090296]
[167,"전북","군산","서군산소룡#1 T/L","154kV 서군산-소룡#1T/L 피뢰기 설치공사","1. 피뢰기 설치 : No.1~16","2016-05-06 07:00","2016-05-07 18:00","2016-05-06 07:00","2016-05-07 18:00","매일",null,null,null,201603110201]
[168,"전북","군산","팔봉영등#2 T/L","154kV 팔봉-영등#2T/L 피뢰기 설치공사","1. 피뢰기 설치 : No.1~14","2016-05-16 07:00","2016-05-17 18:00","2016-05-16 07:00","2016-05-17 18:00","매일",null,null,null,201603110232]
[169,"전북","군산","이리S/S 154kV #2 BUS","이리S/S 154kV #2 BUS","모선CVT점검","2016-05-12 09:00","2016-05-12 18:00","2016-05-12 09:00","2016-05-12 18:00","당일",null,null,null,201603100062]
[170,"전북","군산","팔봉영등#1 T/L","154kV 팔봉-영등#1T/L 정밀점검","No.1~14 구간 송전선로 정밀점검","2016-05-20 09:00","2016-05-20 18:00","2016-05-20 09:00","2016-05-20 18:00","당일",null,null,null,201602110250]
[171,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 피뢰기 설치공사","공사명 : 정주-고창#2T/L 피뢰기 설치공사 대상 : 1~95호 내용 : 송전선로용 피뢰기 설치","2016-05-09 08:00","2016-05-15 18:00","2016-05-09 08:00","2016-05-15 18:00","매일",null,null,null,201603100325]
[172,"전북","김제","김제섬진강HP T/L","김제-섬진강 T/L","차단기 정밀점검","2016-05-11 09:00","2016-05-13 18:00","2016-05-11 09:00","2016-05-13 18:00","연속",null,null,null,201603090263]
[173,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공#2T/L 피뢰기 설치공사","공사명 : 신김제-정공#2T/L 피뢰기 설치공사 대상 : 1~88호 내용 : 송전선로용 피뢰기 설치공사 안전거리확보","2016-05-16 08:00","2016-05-22 18:00","2016-05-16 08:00","2016-05-22 18:00","매일",null,null,null,201603100327]
[174,"전북","김제","신김제동전주#2 T/L","154kV 신김제-정공#2T/L 피뢰기 설치공사 (병가구간 안전거리확보)","공사명 : 신김제-동전주#2T/L 피뢰기 설치공사 대상 : 1~11호 내용 : 송전선로용 피뢰기 설치공사 안전거리확보","2016-05-16 08:00","2016-05-18 18:00","2016-05-16 08:00","2016-05-18 18:00","연속",null,null,null,201603100328]
[175,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 피뢰기 설치공사","공사명 : 154kV 정공-정주#1T/L 피뢰기 설치공사 대상 : No.1~31 내영 : 송전선로용 피뢰기 설치","2016-05-30 09:00","2016-06-01 18:00","2016-05-29 09:00","2016-05-31 18:00","매일",null,null,null,201602180197]
[176,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강T/L 피뢰기 설치공사","공사명 : 154kV 정공-섬진강T/L 피뢰기 설치공사 대상 : No.1~4 내영 : 송전선로용 피뢰기 설치","2016-05-29 09:00","2016-05-30 18:00","2016-05-28 09:00","2016-05-29 18:00","매일",null,null,null,201602180196,"○"]
[177,"전북","김제","정주고창#1 T/L","154kV 정주-부안#1T/L 피뢰기 설치공사(안전거리확보)","공사명 : 154kV 정주-부안#1T/L 피뢰기 설치공사 대상 : No.1~75 내영 : 송전선로용 피뢰기 설치 (병가구간 안전거리확보)","2016-05-02 09:00","2016-05-08 18:00","2016-05-02 09:00","2016-05-08 18:00","매일",null,null,null,201602180199]
[178,"전북","직할","북전주봉동#1 T/L","154kV 북전주-봉동 #1T/L 정밀점검","No.1~9호 정밀점검","2016-05-02 09:00","2016-05-03 18:00","취소","취소","매일",null,null,"신뢰도개선",201603140375]
[179,"전북","직할","북전주용담수력 T/L","북전주용담수력 T/L","2016년 전북직할 170kV 차단기 정밀점검공사 - 170kV GIS 정밀점검","2016-05-23 09:00","2016-05-25 18:00","2016-05-23 09:00","2016-05-25 18:00","연속",null,null,null,201603150253]
[180,"전북","직할","북전주봉동#2 T/L","154kV 북전주-봉동 #2T/L 정밀점검","No.1~9호 정밀점검","2016-05-04 09:00","2016-05-06 18:00","취소","취소","매일",null,null,"신뢰도개선",201603140409]
[181,"광주전남","광주","신광주계림#1 T/L","154kV 신광주-계림T/L 지장철탑 이설공사","154kV 신광주-계림T/L No.21∼27 아파트 신축 지장철탑 이설공사","2016-05-19 09:00","2016-05-22 18:00","2016-05-19 09:00","2016-05-22 18:00","연속",null,null,null,201603250028]
[182,"광주전남","광주","신광주계림#2 T/L","154kV 신광주-계림T/L 지장철탑 이설공사","154kV 신광주-계림T/L No.21∼27 아파트 신축 지장철탑 이설공사","2016-05-23 09:00","2016-05-26 18:00","2016-05-23 09:00","2016-05-26 18:00","연속",null,null,null,201603250029]
[183,"광주전남","광주","신광주곡성#1 T/L","154kV 곡성-남원T/L 전력선 교체공사 관련 안전 확보","154kV 곡성-남원T/L 전력선 교체공사(전북본부) 관련 4회선 병가구간 작업을 위한 안전 확보차 휴전 시행","2016-05-05 07:30","2016-05-07 18:00","2016-05-05 07:30","2016-05-07 18:00","연속",null,null,null,201603160146]
[184,"광주전남","광주","신광주곡성#2 T/L","154kV 곡성-남원T/L 전력선 교체공사 관련 안전 확보","154kV 곡성-남원T/L 전력선 교체공사(전북본부) 관련 4회선 병가구간 작업을 위한 안전 확보차 휴전 시행","2016-05-02 07:30","2016-05-04 18:00","2016-05-02 07:30","2016-05-04 18:00","연속",null,null,null,201603160145]
[185,"광주전남","광주","담양S/S 154kV #2 BUS","광주전력지사 170kV GIS 정밀점검(#2BUS 휴전)","광주전력지사 170kV GIS 정밀점검(#2BUS 휴전)","2016-05-24 14:00","2016-05-25 18:00","2016-05-24 14:00","2016-05-25 18:00","연속",null,null,null,201603150133]
[186,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 전선접속개소해소공사","전선교체 No.7-11","2016-05-30 07:00","2016-06-04 18:00","2016-05-30 07:00","2016-06-04 18:00","연속",null,null,null,201603090230]
[187,"광주전남","광주","정공담양 T/L","154kV 정공-담양T/L 전선접속개소해소공사","전선교체 No.176-180","2016-05-23 07:00","2016-05-28 18:00","취소","취소","연속",null,null,null,201603090234]
[188,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 전선접속개소해소공사","전선교체 No.7-11","2016-05-23 07:00","2016-05-28 18:00","취소","취소","연속",null,null,null,201603090229]
[189,"광주전남","광주","담양S/S 154kV #1 BUS","광주전력지사 170kV GIS 정밀점검(#1BUS 휴전)","광주전력지사 170kV GIS 정밀점검(#1BUS 휴전)","2016-05-23 09:00","2016-05-24 14:00","2016-05-23 09:00","2016-05-24 14:00","연속",null,null,null,201603150132]
[190,"광주전남","광주","담양김제 T/L","154kV 김제-담양T/L 전선접속개소해소공사","전선교체 No.176-180","2016-05-30 07:00","2016-06-04 18:00","2016-05-30 07:00","2016-06-04 18:00","연속",null,null,null,201603090231]
[191,"광주전남","광주","북광주계림#2 T/L","지중송전설비 위탁정비공사","지중송전설비 케이블 및 접속함 점검","2016-05-02 09:00","2016-05-04 18:00","2016-05-02 09:00","2016-05-04 18:00","연속",null,null,null,201603030082]
[192,"광주전남","광주","북광주계림#1 T/L","지중송전설비 위탁정비공사","지중송전설비 케이블 및 접속함 점검","2016-05-02 09:00","2016-05-04 18:00","2016-05-02 09:00","2016-05-04 18:00","연속",null,null,null,201603030081]
[193,"광주전남","광주","신광주일곡#1 T/L","154kV신광주-일곡#1T/L 아킹혼철거공사","아킹혼철거 15기","2016-05-17 07:00","2016-05-17 18:00","2016-05-01 07:00","2016-05-05 18:00","매일",null,null,"신뢰도개선",201603140379]
[194,"광주전남","광주","신광주장성#2 T/L","154kV신광주-장성#2T/L 아킹혼철거공사","아킹혼철거 47기","2016-05-18 07:00","2016-05-20 18:00","2016-05-18 07:00","2016-05-20 18:00","매일",null,null,null,201603140378]
[195,"광주전남","광주","화순승주#1 T/L","154kV화순-승주#1T/L","전선접속개소해소공사(154kV화순-승주T/L)","2016-05-09 08:00","2016-05-25 18:00","2016-05-09 08:00","2016-05-25 18:00","연속",null,null,null,201603090015]
[196,"광주전남","광주","화순승주#2 T/L","154kV화순-승주#2T/L","전선접속개소해소공사(154kV화순-승주T/L)","2016-05-26 08:00","2016-06-11 18:00","2016-05-26 08:00","2016-06-11 18:00","연속",null,null,null,201603090021]
[197,"광주전남","순천","서순천주암HP T/L","154kV 서순천-주암HP T/L(전선접속개소 해소공사)","345kV 광양-여수TP 등 6개 T/L 전선접속개소 해소공사 - 전력선 교체 : 16~21호","2016-05-30 07:00","2016-06-01 18:00","2016-05-12 07:00","2016-05-14 18:00","연속",null,null,null,201603140430]
[198,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주#1T/L(송전선로 배전반 교체)","2016년 변전협력회사 총액공사 - 순천-승주#1T/L 송전선로 배전반 교체","2016-05-02 10:00","2016-05-04 18:00","2016-05-02 10:00","2016-05-04 18:00","연속",null,null,null,201603140512]
[199,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L(전선접속개소 해소공사)","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사 - 전력선 교체 : 16~21호 등 7경간","2016-05-07 07:00","2016-05-19 18:00","2016-05-15 07:00","2016-05-25 18:00","연속",null,null,null,201603140414]
[200,"광주전남","순천","승주주암HP T/L","154kV 승주-주암HP T/L(전선접속개소 해소공사)","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사 - 전력선 교체 : 34~36호 등 6경간","2016-05-20 07:00","2016-05-29 18:00","2016-05-26 07:00","2016-06-03 18:00","연속",null,null,null,201603140415]
[201,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성#1TL(송전선로 보호반 성능개선)","-영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419) -16-17 순천전력지사 변전총액공사 내용 : 154kV GIS 보통점검","2016-05-31 10:00","2016-05-31 18:00","2016-05-31 10:00","2016-05-31 18:00","당일",null,null,null,201603110064]
[202,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천#1T/L(상반기 GIS 정밀점검공사)","2016년 상반기 순천전력지사 GIS 정밀점검공사 - 154kV 여수TP-여천#1T/L GIS 정밀점검(CB,#1DS,#2DS,상부BUS) 2016년 순천전력지사 변전협력회사 총액공사 - 여수TP, 여천S/S 송전선로 보호반 교체","2016-05-16 09:00","2016-05-18 18:00","2016-05-16 09:00","2016-05-18 18:00","연속",null,null,null,201602150358]
[203,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천#2T/L(상반기 GIS 정밀점검공사)","2016년 상반기 순천전력지사 GIS 정밀점검공사 - 여천S/S 154kV 여수TP-여천#2T/L GIS 정밀점검(CB,#1DS,#2DS,상부BUS) 2016년 순천전력지사 변전협력회사 총액공사 - 여수TP, 여천S/S 송전선로 보호반 교체","2016-05-24 09:00","2016-05-26 18:00","2016-05-24 09:00","2016-05-26 18:00","연속",null,null,null,201602150363]
[204,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수#1T/L(상반기 GIS 정밀점검공사)","2016년 상반기 순천전력지사 GIS 정밀점검공사 - 여천S/S 여천-여수#1T/L GIS 정밀점검(CB,#1DS,#2DS,상부BUS)","2016-05-02 09:00","2016-05-04 18:00","2016-05-02 09:00","2016-05-04 18:00","연속",null,null,null,201602150344]
[205,"광주전남","순천","여천여수#2 T/L","154kV 여천-여수#2T/L(GIS 차단기 동작시험)","2016년 순천전력지사 변전협력회사 총액공사 - GIS 차단기 동작시험","2016-05-06 10:00","2016-05-06 18:00","2016-05-06 10:00","2016-05-06 18:00","당일",null,null,null,201603290061]
[206,"광주전남","순천","여수산단여천#1 T/L","154kV 여수산단-여천#1T/L(송전선로 보호반 성능개선)","영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419)","2016-05-30 09:00","2016-05-30 14:00","2016-05-30 09:00","2016-05-30 14:00","당일",null,null,null,201603110055]
[207,"광주전남","순천","여수산단여천#2 T/L","154kV 여수산단-여천#2T/L(송전선로 보호반 성능개선)","영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419)","2016-05-30 14:00","2016-05-30 18:00","2016-05-30 14:00","2016-05-30 18:00","당일",null,null,null,201603110059]
[208,"광주전남","순천","율촌민자#2 T/L","154kV 율촌민자#2T/L(송전선로 피뢰기 설치공사)","345kV 신남원-광양 등 16개 T/L 피뢰기 설치공사 - 피뢰기 설치 : 1~9호, 9기","2016-05-15 07:00","2016-05-15 18:00","2016-05-15 07:00","2016-05-15 18:00","당일",null,null,null,201603140477]
[209,"광주전남","직할","나주S/S 신화순-나주#2T/L CB","154kV 나주변전소 옥내화 부지 확보 철거공사","○ 154kV #2BUS 모선길이 변경 - 신화순-나주#1T/L ∼ 나주-평동#2T/L 구간 철거 ○ 154kV #1·2PT 위치 변경 ○ 나주S/S 170kV 50kA 2000A GCB × 3CCT 철거, #2BUS측 DS 포함","2016-05-16 08:00","2016-05-20 18:00","2016-05-16 08:00","2016-05-20 18:00","연속",null,null,null,201603210132]
[210,"광주전남","직할","나주S/S 신화순-나주#2T/L CB","154kV 나주변전소 옥내화 부지 확보 철거공사","○ 154kV #1BUS 모선길이 변경 - 신화순-나주#1T/L ∼ 나주-평동#2T/L 구간 철거 ○ 154kV #1·2PT 위치 변경 ○ 나주S/S 170kV 50kA 2000A GCB × 3CCT 철거, #1BUS측 DS 포함","2016-05-09 08:00","2016-05-13 18:00","2016-05-09 08:00","2016-05-13 18:00","연속",null,null,null,201603210129]
[211,"광주전남","직할","나주S/S 나주-평동#2T/L CB","154kV 나주변전소 옥내화 부지 확보 철거공사","- 154kV 나주변전소 옥내화 공사","2016-05-06 08:00","2017-12-31 18:00","-","-","연속",null,null,null,201603210128]
[212,"광주전남","직할","나주S/S 신화순-나주#1T/L CB","154kV 나주변전소 옥내화 부지 확보 철거공사","- 변전분야 : 154kV 송전선로 보호배전반 × 1SET 이설 - 송전분야 : 신화순-나주#1T/L - 나주-평동#1T/L 송전선로 직결","2016-05-02 08:00","2016-05-04 18:00","2016-05-02 08:00","2016-05-04 18:00","연속",null,null,null,201603210125]
[213,"광주전남","직할","나주S/S 나주-평동#1T/L CB","154kV 나주변전소 옥내화 부지 확보 철거공사","- 변전분야 : 154kV 송전선로 보호배전반 × 1SET 이설 - 송전분야 : 신화순-나주#1T/L - 나주-평동#1T/L 송전선로 직결","2016-05-02 08:00","2016-05-04 18:00","2016-05-02 08:00","2016-05-04 18:00","연속",null,null,null,201603210133]
[214,"광주전남","직할","수완흑석#2 T/L","154kV 수완S/S 수완-흑석#2T/L(직할 변전 총액공사)","수완S/S 수완-흑석#2T/L GIS 보통점검","2016-05-11 09:00","2016-05-11 18:00","2016-05-11 09:00","2016-05-11 18:00","당일",null,null,null,201603140586]
[215,"광주전남","직할","수완흑석#1 T/L","154kV 수완S/S 수완-흑석#1T/L(직할 변전 총액공사)","수완S/S 수완-흑석#1T/L GIS 보통점검","2016-05-10 09:00","2016-05-10 18:00","2016-05-10 09:00","2016-05-10 18:00","당일",null,null,null,201603140585]
[216,"대구경북","경산","진량노변 T/L","2016년 경산전력지사 총액공사","철찹피뢰기설치[진량분기 No.1~3,신경산-노변 No.21~47]","2016-05-23 08:00","2016-05-26 18:00","2016-05-23 08:00","2016-05-26 18:00","연속",null,null,null,201603080203]
[217,"대구경북","구미","구미고아#1 T/L","154kV 구미-고아T/L 지장송전선로 이설공사","철탑 : 5기 신설(No.10,11,17,18,19), 5기 철거 전력선교체 : 2.194km(HSTACIR/AW 330mm2 X S X 2C)","2016-05-09 08:00","2016-05-17 18:00","2016-05-09 08:00","2016-05-17 18:00","연속",null,null,null,201602150013]
[218,"대구경북","구미","구미고아#2 T/L","154kV 구미-고아T/L 지장송전선로 이설공사","철탑 : 5기 신설(No.10,11,17,18,19), 5기 철거 전력선교체 : 2.194km(HSTACIR/AW 330mm2 X S X 2C)","2016-05-03 08:00","2016-05-12 18:00","2016-05-03 08:00","2016-05-12 18:00","연속",null,null,null,201602150012]
[219,"대구경북","구미","남인동인동#2 T/L","남인동S/S 남인동-인동 #2T/L 휴전","154kV CVT 교체","2016-05-19 09:00","2016-05-19 18:00","2016-05-19 09:00","2016-05-19 18:00","당일",null,null,null,201603090158]
[220,"대구경북","구미","남인동인동#1 T/L","남인동S/S 남인동-인동 #1T/L 휴전","154kV CVT 교체","2016-05-18 09:00","2016-05-19 18:00","2016-05-18 09:00","2016-05-19 18:00","연속",null,null,null,201603090156]
[221,"대구경북","달성","강창성서#2 T/L","정밀점검","정밀점검 No.1~14","2016-05-08 09:00","2016-05-08 18:00","2016-05-08 09:00","2016-05-08 18:00","당일",null,null,null,201603070060]
[222,"대구경북","달성","강창성서#1 T/L","정밀점검","정밀점검 No.1~14","2016-05-08 09:00","2016-05-08 18:00","2016-05-07 09:00","2016-05-07 18:00","당일",null,null,null,201603070055]
[223,"대구경북","달성","논공달성#1 T/L","EBA 자기애관 교체공사","EBA 폴리머 애관 제작관련 현장 실측","2016-05-07 09:00","2016-05-07 18:00","2016-05-05 09:00","2016-05-05 13:00","당일",null,null,null,201603090082]
[224,"대구경북","달성","다산강창#1 T/L","안전확보 휴전","강창-성서#1 정밀점검(No.1~4) 시 상단 다산-강창#1(No.52~49) 안전확보 휴전","2016-05-05 09:00","2016-05-05 13:00","2016-05-07 09:00","2016-05-07 14:00","당일",null,null,null,201603070059]
[225,"대구경북","달성","다산강창#2 T/L","안전확보 휴전","강창-성서#2 정밀점검(No.1~4) 시 상단 다산-강창#2(No.52~49) 안전확보 휴전","2016-05-07 09:00","2016-05-07 14:00","2016-05-08 09:00","2016-05-08 14:00","당일",null,null,null,201603070064]
[226,"대구경북","달성","달성상인#1 T/L","6100 GIS 정밀점검 테스트선로","6100 GIS 정밀점검 테스트선로","2016-05-08 09:00","2016-05-08 14:00","2016-05-17 12:00","2016-05-18 18:00","매일",null,null,null,201603100040]
[227,"대구경북","달성","내당두류#2 T/L","627 GIS 정밀점검","627 GIS 정밀점검","2016-05-12 09:00","2016-05-14 18:00","2016-05-12 09:00","2016-05-14 18:00","연속",null,null,null,201603100022]
[228,"대구경북","달성","두류봉덕#2 T/L","두류,봉덕 판넬대체공사","보호반 판넬교체","2016-05-16 09:30","2016-05-17 18:00","2016-05-16 09:30","2016-05-17 18:00","연속",null,null,null,201603080063]
[229,"대구경북","달성","내당두류#1 T/L","617 GIS 정밀점검","617 GIS 정밀점검","2016-05-02 09:00","2016-05-04 18:00","2016-05-02 09:00","2016-05-04 18:00","연속",null,null,null,201603100020]
[230,"대구경북","달성","두류봉덕#1 T/L","6100정밀점검 테스트선로","6100정밀점검 테스트선로","2016-05-10 13:00","2016-05-11 18:00","2016-05-10 13:00","2016-05-11 18:00","매일",null,null,null,201603140075]
[231,"대구경북","달성","성서달성#2 T/L","안전확보 휴전","강창-성서#1 정밀점검(No.13) 시 하단 성서-달성#2(No.1) 안전확보 휴전","2016-05-07 14:00","2016-05-07 18:00","2016-05-07 14:00","2016-05-07 18:00","당일",null,null,null,201603070062]
[232,"대구경북","달성","성서달성#1 T/L","안전확보 휴전","강창-성서#2 정밀점검(No.13) 시 하단 성서-달성#1(No.1) 안전확보 휴전","2016-05-08 14:00","2016-05-08 18:00","2016-05-08 14:00","2016-05-08 18:00","당일",null,null,null,201603070058]
[233,"대구경북","영주","문경단양 T/L","문경S/S 154kV 6100 GIS 정밀점검-테스트 T/L(즉시가압)","문경S/S 154kV #1BUS TIE 6100 GIS 정밀점검 - 테스트 T/L","2016-05-31 15:00","2016-06-02 18:00","취소","취소","매일",null,null,null,201603140690]
[234,"대구경북","영주","점촌문경 T/L","문경S/S 617 GIS 정밀점검, 617 GIS 누유개소 보수(제작사)","문경S/S 617 GIS 정밀점검, 617 GIS 누유개소 보수(제작사)","2016-05-28 09:00","2016-05-30 18:00","취소","취소","연속",null,null,null,201603090373]
[235,"대구경북","영주","신영주안동#1 T/L","345kV 신영주-한울NP3T/L 전선접속개소 교체공사","공사구간 : 231~236호간 전선교체관련 하단선로 양회선 동시휴전 필요","2016-05-17 09:00","2016-05-18 18:00","2016-05-14 09:00","2016-05-15 18:00","연속",null,null,null,201603140063]
[236,"대구경북","영주","신영주안동#2 T/L","345kV 신영주-한울NP3T/L 전선접속개소 교체공사","공사구간 : 231~236호간 전선교체관련 하단선로 양회선 동시휴전 필요","2016-05-17 09:00","2016-05-18 18:00","2016-05-14 09:00","2016-05-15 18:00","연속",null,null,null,201603140064]
[237,"대구경북","직할","범물남대구#1 T/L","16년 직할 가공송전정비 위탁공사","154kV 범물-남대구#1T/L 정밀점검(No.1~14)","2016-05-18 08:00","2016-05-19 13:00","2016-05-18 08:00","2016-05-19 13:00","매일",null,null,null,201603100012]
[238,"대구경북","직할","범물남대구#2 T/L","16년 직할 가공송전정비 위탁공사","154kV 범물-남대구#2T/L 정밀점검(No.1~14)","2016-05-19 13:00","2016-05-20 18:00","2016-05-19 13:00","2016-05-20 18:00","매일",null,null,null,201603100013]
[239,"대구경북","직할","노변효목#1 T/L","16년 직할 가공송전정비 위탁공사","154kV 범물-남대구#1T/L No.13~14 정밀점검 안전이격확보","2016-05-19 08:00","2016-05-19 13:00","2016-05-19 08:00","2016-05-19 13:00","당일",null,null,null,201603100053]
[240,"대구경북","직할","노변효목#2 T/L","16년 직할 가공송전정비 위탁공사","154kV 범물-남대구#2T/L No.13~14 정밀점검 안전이격확보","2016-05-19 13:00","2016-05-19 18:00","2016-05-19 13:00","2016-05-19 18:00","당일",null,null,null,201603100056]
[241,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 6432DS 정밀점검관련 시험가압(웅촌-서창#1T/L)","2016-05-27 16:00","2016-05-27 17:00","2016-05-27 16:00","2016-05-27 17:00","당일",null,null,null,201603140176]
[242,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 647 GIS 정밀점검(웅촌-서창#1T/L)","2016-05-15 09:00","2016-05-17 17:00","2016-05-15 09:00","2016-05-17 17:00","연속",null,null,null,201603140168]
[243,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 6100 CB+1DS 정밀점검관련 시험가압(웅촌-서창#1T/L)","2016-05-31 16:00","2016-05-31 17:00","2016-05-31 16:00","2016-05-31 17:00","당일",null,null,null,201603140179]
[244,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 6433 CB+1DS 정밀점검관련 시험가압(웅촌-서창#1T/L)","2016-05-26 16:00","2016-05-26 17:00","2016-05-26 16:00","2016-05-26 17:00","당일",null,null,null,201603140175]
[245,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 6333 CB+1DS 정밀점검관련 시험가압(웅촌-서창#1T/L)","2016-05-23 16:00","2016-05-23 17:00","2016-05-23 16:00","2016-05-23 17:00","당일",null,null,null,201603140171]
[246,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 6332DS 정밀점검관련 시험가압(웅촌-서창#1T/L)","2016-05-24 16:00","2016-05-24 17:00","2016-05-24 16:00","2016-05-24 17:00","당일",null,null,null,201603140173]
[247,"부산울산","동부산","신양산S/S 61-62-0 SEC CB","ABB제 154kV #61-66 모선보호반 성능개선","1. 제목 : ABB제 154kV 모선보호반 성능개선 2. 개요 - 154kV 모선보호반 BFI 입력부 로직개선","2016-05-18 09:00","2016-05-18 18:00","2016-05-18 09:00","2016-05-18 18:00","당일",null,null,null,201603210066]
[248,"부산울산","동부산","수영정보 T/L","154kV 수영-정보T/L 선로 분리공사","시험가압","2016-05-27 18:00","2016-05-27 19:00","2016-05-27 18:00","2016-05-27 19:00","당일",null,null,null,201603230022]
[249,"부산울산","북부산","북부산삼랑진PP#2 T/L","154kV 북부산삼랑진양수T/L 전선접속개소 전선교체","호포-물금T/L No.25~45 전선접속개소 전선교체에 따른 작업자 안전거리 확보","2016-05-10 08:00","2016-05-18 18:00","2016-05-10 08:00","2016-05-18 18:00","매일",null,null,null,201603080094]
[250,"부산울산","북부산","북부산삼랑진PP#2 T/L","154kV 북부산삼랑진양수T/L 전선접속개소 전선교체","북부산-삼랑진#2T/L No.25~45 전선접속개소 전선교체","2016-05-19 08:00","2016-05-29 18:00","2016-05-19 08:00","2016-05-29 18:00","연속",null,null,null,201603080095]
[251,"부산울산","북부산","서창산막#2 T/L","154kV 서창산막 등 5개T/L 전선접속개소 전선교체","서창산막#2T/L No.14~36 전선접속개소 전선교체","2016-05-28 08:00","2016-06-06 18:00","2016-05-28 08:00","2016-06-06 18:00","연속",null,null,null,201603080100]
[252,"부산울산","북부산","서창산막#1 T/L","154kV 서창산막 등 5개T/L 전선접속개소 전선교체","서창산막#1T/L No.14~36 전선접속개소 전선교체","2016-05-18 08:00","2016-05-27 18:00","2016-05-18 08:00","2016-05-27 18:00","연속",null,null,null,201603080099]
[253,"부산울산","북부산","학장S/S 154kV #1 BUS","학장S/S 170kV 장기사용 GIS 대체","학장-개금#2T/L(667) GIS 및 #3M.Tr 1차 GIS 대체: #1DS, CB 철거 및 설치","2016-05-19 20:00","2016-05-30 18:00","2016-05-19 20:00","2016-05-30 18:00","연속",null,null,null,201603170220]
[254,"부산울산","북부산","학장S/S 154kV #2 BUS","학장S/S 170kV 장기사용 GIS 대체공사","#4M.Tr 1차 GIS 및 PT & ES GIS 대체: #2DS 설치","2016-05-02 09:00","2016-05-12 18:00","2016-05-02 09:00","2016-05-12 18:00","연속",null,null,null,201603140380]
[255,"부산울산","북부산","학장S/S 154kV #2 BUS","학장S/S 170kV 장기사용 GIS 대체","학장-개금#2T/L(667) GIS 및 #3M.Tr 1차 GIS 대체: #2DS 설치","2016-05-30 18:00","2016-06-10 18:00","2016-05-30 18:00","2016-06-10 18:00","연속",null,null,null,201603170221]
[256,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체","학장-개금#2T/L(667) GIS 및 #3M.Tr 1차 GIS 대체: 시험가압(#1DS, CB, #1BUS)","2016-05-28 10:00","2016-05-30 10:00","2016-05-28 10:00","2016-05-30 10:00","연속",null,null,null,201603120029]
[257,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체","학장-개금#2T/L(667) GIS 및 #3M.Tr 1차 GIS 대체: 시험가압(2BUS 고깔설치부)","2016-05-19 18:00","2016-05-19 20:00","2016-05-19 18:00","2016-05-19 20:00","당일",null,null,null,201603120028]
[258,"부산울산","북부산","학장개금#2 T/L","학장S/S 170kV 장기사용 GIS 대체","학장-개금#2T/L(667) GIS 및 #3M.Tr 1차 GIS 대체","2016-05-16 09:00","2016-06-10 18:00","2016-05-16 09:00","2016-06-10 18:00","연속",null,null,null,201603120027]
[259,"부산울산","북부산","학장개금#1 T/L","154kV 학장-개금#1T/L 유사고장방지 동박스 특별점검","154kV 학장-개금#1T/L 유사고장방지 동박스 특별점검 - 방식층제거 및 동관부, 연공부 점검","2016-05-14 09:00","2016-05-15 18:00","2016-05-14 09:00","2016-05-15 18:00","연속",null,null,null,201603090236]
[260,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체","#4M.Tr 1차 GIS 및 PT & ES GIS 대체: 시험가압(#2DS, #2BUS)","2016-05-10 10:00","2016-05-12 10:00","2016-05-10 10:00","2016-05-12 10:00","연속",null,null,null,201602160018]
[261,"부산울산","북부산","호포물금 T/L","154kV 북부산삼랑진양수T/L 전선접속개소 전선교체","북부산-삼랑진#2T/L No.25~45 전선접속개소 전선교체에 따른 작업자 안전거리 확보","2016-05-19 08:00","2016-05-29 18:00","2016-05-19 08:00","2016-05-29 18:00","매일",null,null,null,201603080096]
[262,"부산울산","북부산","호포물금 T/L","154kV 북부산삼랑진양수T/L 전선접속개소 전선교체","호포-물금T/L No.25~45 전선접속개소 전선교체","2016-05-10 08:00","2016-05-18 18:00","2016-05-10 08:00","2016-05-18 18:00","연속",null,null,null,201603080093]
[263,"부산울산","서부산","신녹산용원#1 T/L","용원S/S 신녹산-용원#1T/L GIS 하자점검","용원S/S 신녹산-용원#1T/L GIS 하자점검","2016-05-22 10:00","2016-05-22 18:00","2016-05-22 10:00","2016-05-22 18:00","당일",null,null,null,201603140291]
[264,"부산울산","서부산","신녹산용원#2 T/L","용원S/S 신녹산-용원#2T/L GIS 하자점검","용원S/S 신녹산-용원#2T/L GIS 하자점검","2016-05-29 10:00","2016-05-29 18:00","2016-05-29 10:00","2016-05-29 18:00","당일",null,null,null,201603140292]
[265,"부산울산","서부산","용원녹공#2 T/L","용원S/S 용원-녹공#2T/L GIS 하자점검","용원S/S 용원-녹공#2T/L GIS 하자점검","2016-05-15 10:00","2016-05-15 18:00","2016-05-15 10:00","2016-05-15 18:00","당일",null,null,null,201603140286]
[266,"부산울산","서부산","용원녹공#1 T/L","용원S/S 용원-녹공#1T/L GIS 하자점검","용원S/S 용원-녹공#1T/L GIS 하자점검","2016-05-08 10:00","2016-05-08 18:00","2016-05-08 10:00","2016-05-08 18:00","당일",null,null,null,201603140281]
[267,"부산울산","울산","동울산방어진 T/L","2016년도 가공송전 순시점검 위탁공사","154kV 동울산-방어진 T/L 송전선로 초기점검 : 10기","2016-05-14 09:00","2016-05-14 18:00","2016-05-14 09:00","2016-05-14 18:00","당일",null,null,null,201603210026]
[268,"부산울산","울산","동울산효문#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","동울산측 GIS 하자점검","2016-05-30 09:00","2016-05-30 18:00","2016-05-30 09:00","2016-05-30 18:00","당일",null,null,null,201603110144]
[269,"부산울산","울산","동울산효문#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","동울산측 GIS 하자점검","2016-05-31 09:00","2016-05-31 18:00","2016-05-31 09:00","2016-05-31 18:00","당일",null,null,null,201603110145]
[270,"부산울산","울산","동울산방어진 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","154kV 동울산-방어진 T/L 송전선로 초기점검 : 21기","2016-05-07 09:00","2016-05-08 18:00","2016-05-07 09:00","2016-05-08 18:00","연속",null,null,null,201603100123]
[271,"부산울산","울산","동울산효문#3 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","154kV 동울산-효문#3 T/L 송전선로 초기점검 : 31기","2016-05-09 09:00","2016-05-11 18:00","2016-05-09 09:00","2016-05-11 18:00","연속",null,null,null,201603100125]
[272,"부산울산","울산","신온산온산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신온산측 657 GIS 보통점검","2016-05-06 09:00","2016-05-06 18:00","2016-05-06 09:00","2016-05-06 18:00","당일",null,null,null,201603110138]
[273,"부산울산","울산","신온산온산#2 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 6100,6101 시험가압","2016-05-13 09:00","2016-05-13 10:00","2016-05-13 09:00","2016-05-13 10:00","당일",null,null,null,201603110147]
[274,"부산울산","울산","신온산온산#2 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 6102 시험가압","2016-05-13 17:00","2016-05-13 18:00","2016-05-13 17:00","2016-05-13 18:00","당일",null,null,null,201603110148]
[275,"부산울산","울산","신온산온산#1 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 6200,6201 시험가압","2016-05-19 09:00","2016-05-19 10:00","2016-05-19 09:00","2016-05-19 10:00","당일",null,null,null,201603110151]
[276,"부산울산","울산","신온산온산#1 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 60-61-2 시험가압","2016-05-17 17:00","2016-05-17 18:00","2016-05-17 17:00","2016-05-17 18:00","당일",null,null,null,201603110149]
[277,"부산울산","울산","신온산온산#1 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 60-61-1, 60-61-0 시험가압","2016-05-17 09:00","2016-05-17 10:00","2016-05-17 09:00","2016-05-17 10:00","당일",null,null,null,201603110150]
[278,"부산울산","울산","신온산온산#1 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 6202 시험가압","2016-05-19 17:00","2016-05-19 18:00","2016-05-19 17:00","2016-05-19 18:00","당일",null,null,null,201603110152]
[279,"부산울산","울산","신온산온산#1 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 65-66-1, 65-66-0 시험가압","2016-05-24 09:00","2016-05-24 10:00","2016-05-24 09:00","2016-05-24 10:00","당일",null,null,null,201603110154]
[280,"부산울산","울산","신온산온산#1 T/L","2016년 170kV 개폐장치 정밀점검공사","신온산측 65-66-2 시험가압","2016-05-24 17:00","2016-05-24 18:00","2016-05-24 17:00","2016-05-24 18:00","당일",null,null,null,201603110153]
[281,"부산울산","울산","신울산S/S 62-63-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산 GIS 보통점검","2016-05-12 09:00","2016-05-12 18:00","2016-05-12 09:00","2016-05-12 18:00","당일",null,null,null,201603110140]
[282,"부산울산","울산","신울산S/S 67-68-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산 GIS 보통점검","2016-05-13 09:00","2016-05-13 18:00","2016-05-13 09:00","2016-05-13 18:00","당일",null,null,null,201603110141]
[283,"부산울산","울산","신울산명례#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신울산측 ILC PNL 대체","2016-05-16 09:00","2016-05-18 18:00","2016-05-16 09:00","2016-05-18 18:00","연속",null,null,null,201603110142]
[284,"부산울산","울산","신울산명례#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신울산측 ILC PNL 대체","2016-05-23 09:00","2016-05-25 18:00","2016-05-23 09:00","2016-05-25 18:00","연속",null,null,null,201603110143]
[285,"부산울산","울산","신온산온산#3 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","온산측 637 GIS 보통점검","2016-05-04 09:00","2016-05-04 18:00","2016-05-04 09:00","2016-05-04 18:00","당일",null,null,null,201603110137]
[286,"부산울산","직할","서부산부민#1 T/L","부민S/S 서부산-부민 #1T/L(617) GIS 초기 점검","부민S/S 서부산-부민 #1T/L(617) GIS 초기 점검","2016-05-20 10:00","2016-05-20 18:00","2016-05-20 10:00","2016-05-20 18:00","당일",null,null,null,201603140041]
[287,"부산울산","직할","부민부산 T/L","16년 직할 상반기 170kV GIS 정밀점검","부산S/S 부민-부산T/L GIS 정밀점검","2016-05-02 08:00","2016-05-04 18:00","2016-05-02 08:00","2016-05-04 18:00","연속",null,null,null,201603020027]
[288,"부산울산","직할","범일서면#1 T/L","서면,범일S/S 범일-서면#1T/L(617,637) 보호반 대체","서면,범일S/S 범일-서면#1T/L(서면-617,범일- 637) 보호반 대체","2016-05-17 10:00","2016-05-19 18:00","2016-05-17 10:00","2016-05-19 18:00","연속",null,null,null,201603140043]
[289,"부산울산","직할","범일서면#2 T/L","서면,범일S/S 범일-서면#2T/L(627,647) 보호반 대체","서면,범일S/S 범일-서면#2T/L(서면-627,범일- 647) 보호반 대체","2016-05-24 10:00","2016-05-26 18:00","2016-05-24 10:00","2016-05-26 18:00","연속",null,null,null,201603140044]
[290,"경남","직할","마천진해#1 T/L","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사(모선절체 : #1BUS → #2BUS)","2016-05-20 10:00","2016-05-20 10:10","2016-05-20 10:00","2016-05-20 10:10","당일",null,null,null,201603080159]
[291,"경남","직할","마천진해#2 T/L","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사(모선절체 : #1BUS → #2BUS)","2016-05-20 10:10","2016-05-20 10:20","2016-05-20 10:10","2016-05-20 10:20","당일",null,null,null,201603080161]
[292,"경남","직할","마천진해#1 T/L","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사(모선절체 : #2BUS → #1BUS)","2016-05-27 10:00","2016-05-27 10:10","2016-05-27 10:00","2016-05-27 10:10","당일",null,null,null,201603080176]
[293,"경남","직할","마천진해#2 T/L","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사(모선절체 : #2BUS → #1BUS)","2016-05-27 10:10","2016-05-27 10:20","2016-05-27 10:10","2016-05-27 10:20","당일",null,null,null,201603080178]
[294,"경남","직할","마천S/S 154kV #1 BUS TIE CB","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사","마천S/S 170kV GIS BUS-TIE, PT&ES반 교체공사","2016-05-18 09:30","2016-06-03 17:30","2016-05-18 09:30","2016-06-03 17:30","연속",null,null,null,201603080145]
[295,"경남","직할","차룡창공#1 T/L","창공S/S 154kV 옥외철구설비 GIS화 공사","창공S/S 차룡-창공#1T/L 이설(옥외철구 GIS 이설)","2016-05-09 08:30","2016-05-24 08:30","2016-05-09 08:30","2016-05-24 08:30","연속",null,null,null,201603110032]
[296,"경남","직할","차룡창공#2 T/L","창공S/S 154kV 옥외철구설비 GIS화 공사","창공S/S 차룡-창공#2T/L 이설(옥외철구 GIS 이설)","2016-05-24 08:30","2016-06-06 08:30","2016-05-24 08:30","2016-06-06 08:30","연속",null,null,null,201603110040]
[297,"경남","진주","하동개양#2 T/L","154㎸ 하동-개양T/L 철거 및 임시가공선로 설치공사","신진주역세권 지중화공사 관련 154㎸ 하동-개양#1,2T/L 철거 및 임시가공선로 설치(철탑조립 2,3,4,5호 및 연긴선 1-1,2,3,4,5,6호)","2016-05-03 08:30","2016-05-08 17:30","2016-05-03 08:30","2016-05-08 17:30","연속",null,null,null,201603110027]
[298,"경남","진주","하동개양#1 T/L","154㎸ 하동-개양T/L 철거 및 임시가공선로 설치공사","신진주역세권 지중화공사 관련 154㎸ 하동-개양#1,2T/L 철거 및 임시가공선로 설치(철탑조립 2,3,4,5호 및 연긴선 1-1,2,3,4,5,6호)","2016-05-03 08:30","2016-05-08 17:30","2016-05-03 08:30","2016-05-08 17:30","연속",null,null,null,201603110024]
[299,"경남","진주","개양S/S 154KV #2 BUS","무림페이퍼T/L GIS 차단기 정밀점검","무림페이퍼T/L GIS 차단기 정밀점검","2016-05-24 10:00","2016-05-25 10:00","2016-05-24 10:00","2016-05-25 10:00","연속",null,null,null,201603100174]
[300,"경남","진주","개양S/S 154KV #1 BUS","무림페이퍼T/L GIS 차단기 정밀점검","무림페이퍼T/L GIS 차단기 정밀점검","2016-05-25 10:00","2016-05-26 09:00","2016-05-25 10:00","2016-05-26 09:00","연속",null,null,null,201603100176]
[301,"경남","진주","동진주진주#2 T/L","송전선로 보호반 IED 성능개선공사","보호반 IED 하드웨어, 소프트웨어 업그레이드","2016-05-22 14:00","2016-05-22 20:00","2016-05-22 14:00","2016-05-22 20:00","당일",null,null,null,201603100354]
[302,"경남","진주","동진주진주#1 T/L","송전선로 보호반 IED 성능개선공사","보호반 IED 하드웨어, 소프트웨어 업그레이드","2016-05-22 08:00","2016-05-22 14:00","2016-05-22 08:00","2016-05-22 14:00","당일",null,null,null,201603100353]
[303,"경남","진주","의령동진주#2 T/L","송전선로 보호반 IED 성능개선공사","보호반 IED 하드웨어, 소프트웨어 업그레이드","2016-05-21 14:00","2016-05-21 20:00","2016-05-21 14:00","2016-05-21 20:00","당일",null,null,null,201603100356]
[304,"경남","진주","의령동진주#1 T/L","송전선로 보호반 IED 성능개선공사","보호반 IED 하드웨어, 소프트웨어 업그레이드","2016-05-21 08:00","2016-05-21 14:00","2016-05-21 08:00","2016-05-21 14:00","당일",null,null,null,201603100355]
[305,"경남","진주","의령산청 T/L","154kV 의령-이현 등 8개T/L 피뢰기설치 및 전선교체공사","154kV 의령-산청T/L 산청분기T/L 1~17호 피뢰기설치 : 17기 / 51Set","2016-05-07 06:00","2016-05-08 20:00","2016-05-07 06:00","2016-05-08 20:00","당일",null,null,null,201603090077]
[306,"경남","진주","의령함양 T/L","의령-함양T/L PNL 대체공사","의령-함양T/L PNL 대체공사","2016-05-01 09:30","2016-05-03 18:30","2016-05-01 09:30","2016-05-03 18:30","연속",null,null,null,201603100128]
[307,"경남","진주","하동하동화력#2 T/L","154kV 의령-이현 등 8개T/L 피뢰기설치 및 전선교체공사","154kV 하동-남해#2T/L 하동S/S~남해S/S 피뢰기설치 안전이격거리확보","2016-05-09 06:00","2016-05-13 20:00","2016-05-09 06:00","2016-05-13 20:00","당일",null,null,null,201603090069]
[308,"경남","진주","함양거창#1 T/L","함양-거창#1T/L GCB 보통점검","함양-거창#1T/L GCB 보통점검","2016-05-12 09:30","2016-05-12 18:30","2016-05-12 09:30","2016-05-12 18:30","당일",null,null,null,201603100168]
[309,"경남","진주","산청함양 T/L","산청-함양T/L PNL 대체","산청-함양T/L PNL 대체","2016-05-09 09:30","2016-05-11 18:30","2016-05-09 09:30","2016-05-11 18:30","연속",null,null,null,201603100159]
[310,"경남","진주","함양거창#2 T/L","함양-거창#2T/L GCB 보통점검","함양-거창#2T/L GCB 보통점검","2016-05-04 09:30","2016-05-04 18:30","2016-05-04 09:30","2016-05-04 18:30","당일",null,null,null,201603100169]
[311,"경남","진주","쌍림합천#2 T/L","거창-합천#1T/L GIS 정밀점검","거창-합천#1T/L GIS #2DS 시험가압","2016-05-31 12:00","2016-05-31 13:00","2016-05-31 12:00","2016-05-31 13:00","당일",null,null,null,201603100186]
[312,"경남","진주","쌍림합천#1 T/L","쌍림-합천#1T/L GIS 정밀점검","쌍림-합천#1T/L GIS CB 정밀점검","2016-05-16 09:00","2016-05-18 18:00","2016-05-16 09:00","2016-05-18 18:00","연속",null,null,null,201603100151]
[313,"경남","진주","쌍림합천#2 T/L","쌍림-합천#2T/L GIS 정밀점검","쌍림-합천#2T/L GIS 정밀점검","2016-05-19 09:00","2016-05-21 18:00","2016-05-19 09:00","2016-05-21 18:00","연속",null,null,null,201603100163]
[314,"경남","진주","거창합천#1 T/L","쌍림-합천#1T/L GIS 정밀점검","쌍림-합천#1T/L GIS #1DS 시험가압","2016-05-18 16:00","2016-05-18 17:00","2016-05-18 16:00","2016-05-18 17:00","당일",null,null,null,201603100156]
[315,"경남","진주","거창합천#1 T/L","거창-합천#1T/L GIS 정밀점검","거창-합천#1T/L GIS 정밀점검","2016-05-30 09:00","2016-06-01 18:00","2016-05-30 09:00","2016-06-01 18:00","연속",null,null,null,201603100182]
[316,"경남","진주","거창합천#2 T/L","쌍림-합천#1T/L GIS 정밀점검","쌍림-합천#1T/L GIS #2DS 시험가압","2016-05-17 12:00","2016-05-17 13:00","2016-05-17 12:00","2016-05-17 13:00","당일",null,null,null,201603100155]
[317,"경남","진주","거창합천#2 T/L","#1BUS-TIE(6100)정밀점검","#1BUS-TIE(6100)정밀점검 #BUS 시험가압","2016-05-13 12:00","2016-05-13 13:00","2016-05-13 12:00","2016-05-13 13:00","당일",null,null,null,201603100137]
[318,"경남","진주","거창합천#1 T/L","#1BUS-TIE(6100) 정밀점검","#1BUS-TIE(6100) 정밀점검 시험가압","2016-05-14 16:00","2016-05-14 17:00","2016-05-14 16:00","2016-05-14 17:00","당일",null,null,null,201603100138]
[319,"경남","통영","고성안정#1 T/L","고성S/S 170kV GIS 대체공사관련 시험가압","고성S/S 170kV GIS 대체공사관련 시험가압 - 시험가압대상 : 고성-통영T/L","2016-05-07 09:30","2016-05-08 18:30","2016-05-07 09:30","2016-05-08 18:30","연속",null,null,null,201603090316]
[320,"경남","통영","신고성고성 T/L","154kV 신고성-고성T/L GIS 대체공사","154kV 신고성-고성T/L GIS 대체공사","2016-05-09 09:30","2016-05-29 18:30","2016-05-09 09:30","2016-05-29 18:30","연속",null,null,null,201603100014]
[321,"경남","통영","삼천포사천#2 T/L","송전용 피뢰기 설치 안전이격(154kV 삼천포-사천#2T/L)","송전용 피뢰기 설치 안전이격(154kV 삼천포-사천#2T/L)","2016-05-09 08:30","2016-05-12 17:30","2016-05-09 08:30","2016-05-12 17:30","매일",null,null,null,201603070024]
[322,"경남","통영","삼천포사천#1 T/L","삼천포S/S #3M.Tr 1차 GIS 정밀점검","삼천포S/S #3M.Tr 1차 GIS 정밀점검","2016-05-19 17:30","2016-05-19 18:30","2016-05-19 17:30","2016-05-19 18:30","당일",null,null,null,201603090235]
[323,"경남","통영","삼천포사천#1 T/L","삼천포S/S #3M.Tr 1차 GIS 정밀점검","삼천포S/S #3M.Tr 1차 GIS 정밀점검","2016-05-17 17:30","2016-05-17 18:30","2016-05-17 17:30","2016-05-17 18:30","당일",null,null,null,201603090232]
[324,"경남","통영","삼천포사천#1 T/L","SB Damper 설치 (154kV 삼천포-사천#1T/L)","SB Damper 설치 (154kV 삼천포-사천#1T/L)","2016-05-13 08:30","2016-05-16 17:30","2016-05-13 08:30","2016-05-16 17:30","당일",null,null,null,201603070030]
[325,"경남","통영","신고성삼천포#1 T/L","SB Damper 설치 안전이격(154kV 신고성-삼천포#1T/L)","SB Damper 설치(154kV 신고성-삼천포#1T/L)","2016-05-13 08:30","2016-05-16 17:30","2016-05-13 08:30","2016-05-16 17:30","당일",null,null,null,201603070029]
[326,"경남","통영","신고성삼천포#2 T/L","송전용 피뢰기 설치(154kV 신고성-삼천포#2T/L)","송전용 피뢰기 설치(154kV 신고성-삼천포#2T/L)","2016-05-09 08:30","2016-05-12 17:30","2016-05-09 08:30","2016-05-12 17:30","당일",null,null,null,201603070022]
[327,"경남","함안","마산수출#2 T/L","154kV 마산-수출#2T/L 송전선로 보호반대체공사","마산,수출S/S 154kV 마산-수출#2T/L 송전선로 보호교체","2016-05-07 09:00","2016-05-08 18:00","2016-05-07 09:00","2016-05-08 18:00","연속",null,null,null,201603140242]
[328,"경남","함안","초동밀양#1 T/L","2016년 밀양S/S 장기사용 GIS 대체공사","초동-밀양#1T/L GIS 대체","2016-05-05 08:00","2016-05-29 17:30","2016-05-05 08:00","2016-05-29 17:30","연속",null,null,null,201603090194]
["추가1","대구경북","달성","고령쌍림#2T/L","6279 GIS 고장복구 무부하 가압용","6279 GIS 고장복구 무부하 가압용","2016-05-13 14:00","2016-05-13 18:00","2016-05-13 14:00","2016-05-13 18:00","당일"]

{"sheet":"한수원","index":3,"n_rows":20,"n_cols":20,"rows_kept":20,"cut":false,"hidden":false,"merged":[[10,19,11,19],[10,13,11,13],[10,14,11,14],[10,15,11,15],[10,16,11,16],[10,17,11,17],[10,18,11,18],[3,18,4,18],[10,5,11,5],[10,6,10,7],[10,8,10,9],[10,10,11,10],[10,11,11,11],[3,19,4,19],[10,0,11,0],[10,1,11,1],[10,2,11,2],[10,3,11,3],[10,4,11,4],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,14,4,14],[10,12,11,12],[3,15,4,15],[3,16,4,16],[3,17,4,17],[0,0,0,7],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7]]}
["2016년도 5월 휴전계획표(한국수력원자력)"]
[]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리2발","#3 주변압기","3호기 간이정비\n* 조작차단기 : PCB 8200, 8272","○ 주변압기 내부점검 ","2016-05-24 10:00","2016-06-16 18:00","2016-05-24 10:00","2016-06-16 18:00","연속"]
[]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","1발전소","2호기\n주변압기","한빛2호기\n제22차 계획예방정비","한빛2호기 계획예방정비관련\n주변압기 및 보조변압기 점검\n* 조작차단기 : PCB 7400, 7471","2016-05-02\n10:00","2016-06-29\n12:00","2016-05-02\n10:00","2016-06-29\n12:00","연속","Y",null,null," "]
[2,"한빛본부","1발전소","2호기\n기동변압기\n(MC-X01)","한빛2호기\n제22차 계획예방정비","한빛2호기 계획예방정비관련\n기동변압기(MC-X01) 송수전선로 개선 및 점검 \n* 조작차단기 : PCB 7300, 7371","2016-05-04\n20:00","2016-06-06\n09:00","2016-05-04\n20:00","2016-06-06\n09:00","연속","Y",null,null," "]
[3,"한울본부","1발전소","#2 주변압기","20차 계획예방정비","한울2호기 계획예방정비관련\n주/소내보조변압기 점검\n* 조작차단기 : PCB 7400, 7472","2016-05-12 10:00","2016-06-01 12:00","2016-05-12 10:00","2016-06-01 12:00","연속","N",null,null,null,"N","N","N","N","Y"]
[4,"한울본부","1발전소","#2대기보조변압기","20차 계획예방정비","한울2호기 계획예방정비관련\n대기보조변압기 점검\n* 조작차단기 : PCB 7200, 7272","2016-06-02T10:00:00","2016-06-08T12:00:00","2016-06-02T10:00:00","2016-06-08T12:00:00","연속","N",null,null,null,"N","N","N","N","Y"]
[5,"한울본부","2발전소","#3 대기보조변압기 02M","한울3호기 대기보조변압기 02M 접속 변경\n(기존→신설 SWYD)","○ 한울3호기 신설 SWYD 대체 관련 대기보조변압기 02M 접속 변경\n* 조작차단기 : 신설 SWYD PCB 7500,7572\n※ 가압절차 : 차단기 투입","2016-05-22 17:00",null,"2016-05-22 17:00",null,"연속","Y"]
[6,"한울본부","2발전소","#3 대기보조변압기 02N","한울3호기 대기보조변압기 02N 접속 변경\n(기존→신설 SWYD)","○ 한울3호기 신설 SWYD 대체 관련 대기보조변압기 02N 접속 변경\n* 조작차단기 : 신설 SWYD PCB 7600,7672\n※ 가압절차 : 차단기 투입","2016-05-22 17:00",null,"2016-05-22 17:00",null,"연속","Y"]
[7,"한울본부","2발전소","#3 주변압기","한울3호기 제13차 계획예방정비 소내전원절체시험","한울3호기 계획예방정비 관련 소내전원 절체시험\n - 절체시험 후 개방차단기 재투입\n* 개방차단기 : 신설 SWYD PCB 7900,7972","2016-05-22 14:00","2016-06-03 18:00","2016-05-22 14:00","2016-06-03 18:00","당일","Y"]
[8,"한울본부","한울3발","#5 대기보조변압기","5호기 9차 계획예방정비\n- 조작차단기 : PCB 7E00,7E72","○ 스위치야드 E Bay 교체공사\n○ 대기보조변압기 일반점검\n○ 갑종보호반 설비개선(SAT)","2016-05-26T09:00:00","2016-07-10T10:00:00","2016-05-26T09:00:00","2016-07-10T10:00:00","연속","Y",null,null,null,"N","N","N","N","Y"]

{"sheet":"남부발전","index":4,"n_rows":12,"n_cols":16,"rows_kept":12,"cut":false,"hidden":false,"merged":[[9,10,10,10],[9,11,10,11],[9,12,10,12],[9,13,10,13],[9,14,10,14],[9,15,10,15],[2,14,3,14],[2,15,3,15],[9,0,10,0],[9,1,10,1],[9,2,10,2],[9,3,10,3],[9,4,10,4],[9,5,10,5],[9,6,9,7],[9,8,9,9],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5]]}
["남부발전"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산복합","부산복합","4MTG004 주변압기(#7,8GT 용)","변압기 일반점검 및 정기검사 수검","조작차단기(PCB 7500, 7572)","2016-05-22 10:00","2016-07-01 18:00","2016-05-22 10:00","2016-07-01 18:00","당일",null,null,null,201603070105]
[]
[]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산복합","부산복합","4MTS401 주변압기(#4ST 용)","변압기 일반점검 및 정기검사 수검","조작차단기(PCB 6M7)","2016-05-22 10:00","2016-07-01 18:00","2016-05-22 10:00","2016-07-01 18:00","당일",null,null,null,201603070105]