{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #3 M.Tr A-1","345kV 장경간 GIB 구조개선 공사","#3M.Tr 2차 345kV 장경간 GIB 지지애자 점검 및 스페이서 설치","2017-04-03 09:00","2017-05-13 18:00","2017-04-03 09:00","2017-05-13 18:00","연속",null,null,null,201608120283]
[2,"경기","성남","신안성신가평 T/L","765kV 신안성-신가평T/L 정밀점검(구간 No.1~117)","765kV 신안성-신가평T/L 정밀점검(117기)","2017-04-03 09:00","2017-04-12 18:00","2017-04-10 09:00","2017-04-18 18:00","연속",null,null,null,201702100216]
[3,"강원","태백","신태백신한울#1 T/L","OPGW특별점검 및 위해개소 정비","OPGW특별점검 및 위해개소 정비","2017-04-27 10:00","2017-04-27 18:00","2017-04-27 10:00","2017-04-27 18:00","당일",null,null,null,201702210018]
[4,"부산울산","동부산","신고리S/S #2 M.Tr A-1","신고리 #2M.Tr 부싱압력계 센서 교체","1. 신고리 #2M.Tr 부싱압력계 센서 교체 2. 고리NP S/Y 362kV 7F71, 7F00 GIS 보통점검(#2M.Tr 휴전필요)","2017-04-03 09:30","2017-04-04 17:00","2017-04-03 09:30","2017-04-04 17:00","연속",null,null,null,201702100501]
[5,"부산울산","동부산","신고리S/S #3 M.Tr A-1","345kV 유호제 T/L보호반 내부통신회로 개선","345kV 유호제 T/L보호반 내부통신회로 개선(신고리-고리NP#3T/L = 신고리 #3M.Tr 휴전 필요)","2017-04-05 09:30","2017-04-05 17:00","2017-04-05 09:30","2017-04-05 17:00","당일",null,null,null,201702100503]

{"sheet":"345송부","index":1,"n_rows":206,"n_cols":16,"rows_kept":206,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #3 M.Tr A","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #3M.Tr 2차)","2017-04-03 09:30","2017-04-04 18:00","2017-04-03 09:30","2017-04-04 18:00","연속",null,null,null,201702160394,"-"]
[2,"서울","성동","성동S/S #4 M.Tr A","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #4M.Tr 2차)","2017-04-05 09:30","2017-04-06 18:00","2017-04-05 09:30","2017-04-06 18:00","연속",null,null,null,201702160395,"-"]
[3,"남서울","동서울","신성남동서울#2 T/L","345kV 신성남-동서울T/L 전선접속개소 전선교체공사","345kV 신성남-동서울#2T/L 전선교체공사 내용 : #2T/L No.3-9, 13-15, 17-22 상중하단 전선접속개소 전선교체","2017-04-01 08:00","2017-04-14 18:00","2017-04-01 08:00","2017-04-14 18:00","연속",null,null,null,201702070192,"-"]
[4,"남서울","영등포","영서S/S #1 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-04-24 08:00","2017-04-24 18:00","2017-04-24 08:00","2017-04-24 18:00","당일",null,null,null,201702160109,"-"]
[5,"남서울","영등포","신시흥영서#1 T/L","17년 가공송전협력회사공사(송전선로 스페이셔 댐퍼 교체)","신시흥-영서#1T/L 송전선로 스페이셔 댐퍼 교체(S/T~No.9)","2017-04-24 08:00","2017-04-24 18:00","2017-04-24 08:00","2017-04-24 18:00","당일",null,null,null,201702170051,"-"]
[6,"남서울","영등포","신시흥영서#2 T/L","17년 가공송전협력회사공사(송전선로 스페이셔 댐퍼 교체)","신시흥-영서#2T/L 송전선로 스페이셔 댐퍼 교체(S/T~No.9)","2017-04-25 08:00","2017-04-25 18:00","2017-04-25 08:00","2017-04-25 18:00","당일",null,null,null,201702170052,"-"]
[7,"인천","김포","신김포S/S 345KV 신김포-신인천T/L TIE CB","신김포S/S 345KV 신김포-신인천T/L 7400 CB 기기점검","신김포S/S 345KV 신김포-신인천T/L 7400 CB 기기점검","2017-04-05 10:00","2017-04-05 18:00","2017-04-05 10:00","2017-04-05 18:00","당일",null,null,null,201702060028,"-"]
[8,"인천","김포","신김포S/S #1 M.Tr","345kV신김포S/S 1차측 CB 기기점검","345kV신김포S/S #1 M.Tr 7300,7372CB 기기점검","2017-04-10 10:00","2017-04-10 18:00","취소","취소","당일",null,null,null,201702070012,"-"]
[9,"인천","김포","신김포S/S #2 M.Tr","345kV신김포S/S #2 M.Tr 1차측 CB 기기점검","345kV신김포S/S #2 M.Tr 7400,7472 CB 기기점검","2017-04-11 10:00","2017-04-11 18:00","취소","취소","당일",null,null,null,201702070025,"-"]
[10,"인천","김포","345KV 신김포S/S #1Sh.R 1차 CB","345KV 신김포S/S 7171CB 개폐제어기 설치공사"," 7171CB 노즐(Main/Inner), Main 주 접촉자 교체, 투입저항기 설치, 7171CB용 개폐제어기 설치 ","2017-04-21 09:00","2017-04-30 18:00","2017-04-21 09:00","2017-04-30 18:00","당일",null,null,null,201702240033,"-"]
[11,"인천","시흥","신시흥#2S/S #4 M.Tr A","신시흥#2S/S #4M.Tr 정밀점검","신시흥#2S/S #4M.Tr 정밀점검","2017-04-10 08:00","2017-04-21 18:00","2017-04-10 08:00","2017-04-21 18:00","연속",null,null,null,201701110048,"-"]
[12,"인천","시흥","영흥T/P #1 TIE Tr 1차-#2 TIE-Tr 1차 CB (7300)","영흥S/Y 7300 CB 보통점검","영흥S/Y 7300 CB 보통점검","2017-04-07 10:00","2017-04-07 18:00","2017-04-07 10:00","2017-04-07 18:00","연속",null,null,null,201702130273,"-"]
[13,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 345kV 서인천C/C #70BUS 모선개조 및 관련 DS 대체","2017-04-12 10:00","2017-05-16 17:00","2017-04-12 10:00","2017-05-16 17:00","연속",null,null,null,201702140412,"-"]
[14,"인천","인천","신가좌신시흥#2 T/L","애자금구류 교체 및 피뢰기 설치공사","애자금구류 교체 및 피뢰기 설치공사","2017-04-24 08:00","2017-04-25 18:00","2017-04-24 08:00","2017-04-25 18:00","당일",null,null,null,201702140446,"-"]
[15,"인천","인천","인천CC S/Y #1Tie-Tr A","인천CC #1Tie-Tr 2차 GIS (6244) 보통점검 공사","인천CC #1Tie-Tr 2차 GIS (6244) 보통점검 공사","2017-04-19 09:00","2017-04-19 18:00","취소","취소","당일",null,null,null,201702130420,"-"]
[16,"인천","인천","포스코S/Y 포스코#1Step-Up-Tr T/L CB (7172)","2017년 362kV GIS 정밀점검 공사(7172CB)","2017년 362kV GIS 정밀점검 공사(7172 CB) - 362kV GIS 정밀점검 공사","2017-04-24 09:00","2017-04-26 18:00","취소","취소","연속",null,null,null,201702130430,"-"]
[17,"인천","인천","포스코SY인천CC#1T/L-#1GEN STEPUP TIE CB (7100)","2017년 362kV GIS 정밀점검 공사(7100 CB)","2017년 362kV GIS 정밀점검 공사(7100 CB) - 362kV GIS 정밀점검 공사","2017-04-20 09:00","2017-04-22 18:00","취소","취소","연속",null,null,null,201702130426,"-"]
[18,"인천","인천","포스코파워S/Y 포스코SY-인천CC#1T/L CB (7171)","2017년 362kV GIS 정밀점검 공사(7171CB)","2017년 362kV GIS 정밀점검 공사(7171 CB) - 362kV GIS 정밀점검 공사","2017-04-17 09:00","2017-04-19 18:00","취소","취소","연속",null,null,null,201702130425,"-"]
[19,"경기북부","구리","미금S/S STATCOM CB","미금S/S STATCOM 에어컨 설치공사","미금S/S STATCOM 에어컨 설치공사","2017-04-03 09:00","2017-04-06 18:00","2017-04-03 09:00","2017-04-06 18:00","당일",null,null,null,201702080184,"-"]
[20,"경기북부","구리","미금S/S 345kV #3 Sh.R CB","미금S/S 345kV #3 Sh.R GIS 7379 CB 하자점검","미금S/S 345kV #3 Sh.R GIS 7379 CB 하자점검","2017-04-04 10:00","2017-04-04 18:00","2017-04-04 10:00","2017-04-04 18:00","당일",null,null,null,201702070093,"-"]
[21,"경기북부","구리","미금S/S 345kV #1 Sh.R CB","미금S/S 345kV #1 Sh.R GIS 7179 CB 보통점검","미금S/S 345kV #1 Sh.R GIS 7179 CB 보통점검","2017-04-06 10:00","2017-04-06 18:00","2017-04-06 10:00","2017-04-06 18:00","당일",null,null,null,201702070133,"-"]
[22,"경기북부","구리","미금S/S 345kV #4 Sh.R CB","미금S/S 345kV #4 Sh.R GIS 7479 CB 하자점검","미금S/S 345kV #4 Sh.R GIS 7479 CB 하자점검","2017-04-05 10:00","2017-04-05 18:00","2017-04-05 10:00","2017-04-05 18:00","당일",null,null,null,201702070103,"-"]
[23,"경기북부","구리","신가평S/S 345kV #4 Sh.R CB","765kV신가평S/S 소음저감대책 공사","345kV #2, #3, #4Sh.R 방음벽 및 흡음재 설치 - 관련 기초공사 및 방음벽 조립 - 방호벽면 흡음재 설치","2017-04-10 09:00","2017-04-14 18:00","2017-04-10 09:00","2017-04-14 18:00","매일",null,null,null,201702220036,"-"]
[24,"경기북부","구리","신가평S/S 345kV #2 Sh.R CB","765kV신가평S/S 소음저감대책 공사","345kV #2, #3, #4Sh.R 방음벽 및 흡음재 설치 - 관련 기초공사 및 방음벽 조립 - 방호벽면 흡음재 설치","2017-04-17 09:00","2017-04-21 18:00","2017-04-17 09:00","2017-04-21 18:00","매일",null,null,null,201702220037,"-"]
[25,"경기북부","구리","신가평S/S 345kV #3 Sh.R CB","765kV신가평S/S 소음저감대책 공사","345kV #2, #3, #4Sh.R 방음벽 및 흡음재 설치 - 관련 기초공사 및 방음벽 조립 - 방호벽면 흡음재 설치","2017-04-24 09:00","2017-04-28 18:00","2017-04-24 09:00","2017-04-28 18:00","매일",null,null,null,201702220039,"-"]
[26,"경기북부","구리","신포천S/S #4 M.Tr A","신포천S/S #4 M.Tr 하자보수","○신포천S/S #4 M.Tr 하자보수 - OFU 누유부위, M.Tr 누유부위 점검","2017-04-10 09:00","2017-04-10 18:00","2017-04-10 09:00","2017-04-10 18:00","연속",null,null,null,201702140223,"-"]
[27,"경기북부","파주","신파주S/S #3 M.Tr A","파주전력지사 362kV GIS 정밀점검공사","신파주 #3M.TR 1차 7472 GIS 정밀점검","2017-04-10 08:00","2017-04-15 18:00","2017-04-10 08:00","2017-04-15 18:00","연속",null,null,null,201702210039,"-"]
[28,"경기북부","파주","신파주S/S #1SVC Tr B CB","신파주S/S SVC 콘덴서용 차단기 설치공사","- FC5, FC7 용 GCB 설치 - #1,2TCR용 열교환기 청소","2017-04-24 09:00","2017-04-28 18:00","2017-04-24 09:00","2017-04-28 18:00","연속",null,null,null,201702010002,"-"]
[29,"경기","군포","화성서서울#1 T/L","345kV 서서울S/S 구내전력구 공사","- 구내전력구 파일항타 작업 간섭휴전","2017-04-05 07:00","2017-04-05 18:00","2017-04-05 07:00","2017-04-05 18:00","당일",null,null,null,201702100418,"-"]
[30,"경기","군포","신온양서서울#2 T/L","345kV 신온양-서서울T/L 전력선교체 등 3개공사","○ 전력선교체 : No.91~95, ○ 항공표시구정비 및 정밀점검(전체)","2017-04-06 07:00","2017-04-11 18:00","2017-04-06 07:00","2017-04-11 18:00","연속",null,null,null,201702080024,"-"]
[31,"경기","군포","신온양서서울#1 T/L","345kV 신온양-서서울T/L 전력선교체 등 3개공사","○ 전력선교체 : No.91~95, ○ 피뢰기설치 : 79기, ○ 항공표시구정비 및 정밀점검(전체)","2017-04-12 07:00","2017-04-17 18:00","2017-04-12 07:00","2017-04-17 18:00","연속",null,null,null,201702080023,"-"]
[32,"경기","군포","서서울영서#1 T/L","345kV 신군포S/S 건설공사","- 신성남- 신시흥 #2T/L 분기인입시 근접거리 간섭휴전","2017-04-17 07:00","2017-04-21 18:00","2017-04-17 07:00","2017-04-21 18:00","연속",null,null,null,201702160321,"-"]
[33,"경기","군포","신안산S/S #1 M.Tr A","신안산S/S 345kV #1M.Tr 보호배전반 대체공사","- 신안산S/S 345kV #1M.Tr 보호배전반 대체 (선도제 보호계전기 불량)","2017-04-17 09:00","2017-04-21 18:00","2017-04-17 09:00","2017-04-21 18:00","연속",null,null,null,201702210213,"-"]
[34,"경기","군포","신안산S/S #4 M.Tr A","신안산S/S 345kV #4M.Tr 보호배전반 대체공사","- 신안산S/S 345kV #4M.Tr 보호배전반 대체 (선도제 보호계전기 불량)","2017-04-24 09:00","2017-04-28 18:00","2017-04-24 09:00","2017-04-28 18:00","연속",null,null,null,201702210214,"-"]
[35,"경기","성남","신시흥신성남#2 T/L","군포송정지구 345kV신시흥-신성남T/L 지장이설공사","○ 사업유형 : 가공송전 ○ 전압 : 345kV ○ 사업목적 : 군포송정지구 택지 개발사업과 관련으로 345kV신시흥-신성남T/L 지장구간에 대하여 지중으로 건설하고자 가공구간의 임시선로 및 본선로 건설 ○ 사업구간 : 기설 345kV 신시흥-신성남T/L No.48 ~ No.53 ○ 규모 : 철탑 8기, A480B, 2.357km","2017-04-17 07:00","2017-05-02 18:00","2017-04-17 07:00","2017-05-02 18:00","연속",null,null,null,201702160296,"-"]
[36,"경기","성남","신성남동서울#2 T/L","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","2017-04-17 07:00","2017-04-18 18:00","2017-04-17 07:00","2017-04-18 18:00","연속",null,null,null,201702170053,"-"]
[37,"경기","성남","신성남신양재#1 T/L","345kV 신성남-신양재T/L 송전선로용 피뢰기 설치공사(5개소)","345kV 신성남-신양재T/L 송전선로용 피뢰기 설치공사 (5개소 : No.4,13,18,19,21)","2017-04-06 09:00","2017-04-07 18:00","2017-04-06 09:00","2017-04-07 18:00","연속",null,null,null,201702160189,"-"]
[38,"경기","성남","신성남신양재#2 T/L","17년 성남변전협력회사 총액공사","7700, 7771 GIS 보통점검 CVT, LA 대체","2017-04-04 10:00","2017-04-05 18:00","2017-04-04 10:00","2017-04-05 18:00","연속",null,null,null,201702100143,"-"]
[39,"경기","성남","신성남동서울#2 T/L","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","2017-03-27 07:00","2017-03-28 18:00","2017-03-27 07:00","2017-03-28 18:00","연속",null,null,null,201701060101,"-"]
[40,"경기","성남","신수원S/S #3 M.Tr A","17년 성남변전협력회사 총액공사","7592 ES C상 단자대 교체 7522 A상 투입 결상 보수","2017-04-12 10:00","2017-04-12 18:00","2017-04-12 10:00","2017-04-12 18:00","당일",null,null,null,201702100112,"-"]
[41,"경기","성남","신안성신수원#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.11 OPGW 증설(1기)","2017-04-24 07:00","2017-04-27 18:00","2017-04-24 07:00","2017-04-27 18:00","연속",null,null,null,201702090082,"-"]
[42,"경기","성남","신안성서안성#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.11 ~ No.13 OPGW 증설(3기)","2017-04-24 07:00","2017-04-27 18:00","2017-04-24 07:00","2017-04-27 18:00","연속",null,null,null,201702090077,"-"]
[43,"경기","직할","화성신안산 T/L","345kV 화성-신안산T/L 애자련 보강공사","애자련 보강공사","2017-04-22 09:00","2017-04-23 18:00","2017-04-22 09:00","2017-04-23 18:00","연속",null,null,null,201702100452,"-"]
[44,"경기","직할","화성신시흥 T/L","345kV 화성-신시흥T/L 애자련 보강공사","35,36호 애자련 보강공사","2017-04-15 09:00","2017-04-16 18:00","2017-04-15 09:00","2017-04-16 18:00","연속",null,null,null,201702100427,"-"]
[45,"강원","강릉","신양양S/S #3 M.Tr A","2017년 변전협력회사 총액공사","1. 주변압기 하자점검 2. 1차 2차 GIS 하자점검","2017-04-24 09:00","2017-04-26 18:00","2017-04-24 09:00","2017-04-26 18:00","매일",null,null,null,201702150050,"-"]
[46,"강원","태백","신태백S/S 7372GROUP CB (7372)","신태백S/S 362kV CB 보통점검","7371CB 보통점검","2017-04-03 10:00","2017-04-03 18:00","2017-04-03 10:00","2017-04-03 18:00","당일",null,null,null,201702140252,"-"]
[47,"강원","태백","신태백S/S 345kV #2 Sh.R CB (7471)","신태백S/S 362kV CB 보통점검","7471CB 보통점검","2017-04-06 10:00","2017-04-06 18:00","2017-04-06 10:00","2017-04-06 18:00","당일",null,null,null,201702140260,"-"]
[48,"강원","태백","신태백S/S 345kV #2 Sh.R","신태백S/S 362kV #2Sh.R 7479CB 보통점검","7479CB 보통점검","2017-04-05 10:00","2017-04-05 18:00","2017-04-05 10:00","2017-04-05 18:00","당일",null,null,null,201702210007,"-"]
[49,"강원","태백","신태백한울NP2#1 T/L","신태백S/S 362kV CB 보통점검","7572CB 보통점검","2017-04-04 10:00","2017-04-04 18:00","2017-04-04 10:00","2017-04-04 18:00","당일",null,null,null,201702140255,"-"]
[50,"강원","태백","신태백S/S#2 Sh.R-신태백-한울NP3T/L CB (7400)","신태백S/S 362kV CB 보통점검","7400CB 보통점검","2017-04-07 10:00","2017-04-07 18:00","2017-04-07 10:00","2017-04-07 18:00","당일",null,null,null,201702140262,"-"]
[51,"강원","태백","신태백한울NP2#2 T/L","OPGW 특별점검 및 위해개소 조치","OPGW 특별점검 및 위해개소 조치","2017-04-24 10:00","2017-04-26 18:00","2017-04-24 10:00","2017-04-26 18:00","연속",null,null,null,201702210024,"-"]
[52,"충북","직할","신제천신영주#2 T/L","345kV 신제천-신영주T/L 전력선 교체공사","○ 전력선 교체 : 6.471km- 2c, ACSR 480㎟(R) X 4B ○ 가공지선 교체 : 4.863km-1조, ACSR 120㎟ ○ 스페이서댐퍼 교체 : 624개(전력선 교체구간)","2017-04-25 07:00","2017-05-10 18:00","2017-04-25 07:00","2017-05-10 18:00","연속",null,null,null,201702070353,"-"]
[53,"충북","직할","곤지암신충주#2 T/L","2017년도 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서점검, OPGW항공장애표시구 교체","2017-04-01 09:00","2017-04-05 09:00","2017-03-26 08:00","2017-03-31 18:00","매일",null,null,null,201702090193,"-"]
[54,"충북","직할","신제천신충주#1 T/L","2017년도 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서점검, OPGW항공장애표시구 교체","2017-04-01 09:00","2017-04-05 09:00","2017-03-26 08:00","2017-03-31 18:00","매일",null,null,null,201702090189,"-"]
[55,"충북","직할","신제천신충주#2 T/L","2017년도 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서점검","2017-03-26 09:00","2017-03-31 09:00","2017-04-01 08:00","2017-04-05 18:00","매일",null,null,null,201702090190,"-"]
[56,"충북","직할","곤지암신충주#1 T/L","2017년도 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서점검","2017-03-26 09:00","2017-03-31 09:00","2017-04-01 08:00","2017-04-05 18:00","매일",null,null,null,201702090192,"-"]
[57,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 72Bay #2BUS 철거작업","2017-04-10 13:00","2017-04-10 18:00","2017-04-10 13:00","2017-04-10 18:00","당일",null,null,null,201702080103,"-"]
[58,"충북","청주","신옥천신남원#2 T/L","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 75Bay #2BUS측으로 인출 변경 - 가선(인하선 연결) - 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-04-10 09:00","2017-04-20 18:00","2017-04-10 09:00","2017-04-20 18:00","연속",null,null,null,201702080104,"-"]
[59,"충북","청주","신옥천S/S 345kV #1 BUS","신옥천S/S 345 용량부족차단기 대체공사","기설 72Bay #1BUS 철거작업","2017-04-10 08:00","2017-04-10 12:00","2017-04-10 08:00","2017-04-10 12:00","당일",null,null,null,201702080102,"-"]
[60,"충북","청주","청원S/S #3 M.Tr A","17년 청주전력지사 362kV GIS 정밀점검공사","362kV GIS 정밀점검 및 M.Tr 1,2차 DS점검","2017-04-10 09:30","2017-04-14 18:00","2017-04-10 09:30","2017-04-14 18:00","연속",null,null,null,201702210081,"-"]
[61,"충북","청주","청원S/S #2 M.Tr A","17년 청주전력 변전정비 총액공사","기계적보호장치 Trip 회로변경(#2M.Tr 96D: Trip→경보)","2017-04-03 09:30","2017-04-03 18:00","2017-04-03 09:30","2017-04-03 18:00","당일",null,null,null,201702200008,"-"]
[62,"충북","청주","청원S/S #4 M.Tr A","17년 청주전력지사 345kV GIS 정밀점검공사","청원S/S #4 M.Tr 1차 GIS(7872), TIE-#4 M.Tr 1차 GIS(7800) 정밀점검","2017-04-17 09:00","2017-04-26 18:00","2017-04-17 09:00","2017-04-26 18:00","연속",null,null,null,201702210212,"-"]
[63,"충북","충주","청원신진천#1 T/L","345kV 신진천S/S 용량부족 GIS 대체공사","345kV 신진천S/S GIS 40kA 4000A → 63kA 6300A 12CB 대체 - #71BAY 2CB 철거 및 기초시공 - #71BAY 2CB 신규설치","2017-04-10 09:00","2017-07-31 18:00","2017-04-10 09:00","2017-07-31 18:00","연속",null,null,null,201702070073,"-"]
[64,"대전충남","서산","당진T/P #72 Tie-Tr A","당진화력 345kV #72Tie-Tr T60 D60 계전기 DSP모듈교체","당진화력 345kV #72Tie-Tr T60,D60 계전기 DSP모듈교체","2017-04-18 09:00","2017-04-18 18:00","2017-04-18 09:00","2017-04-18 18:00","당일",null,null,null,201702170180,"-"]
[65,"대전충남","서산","태안T/P 10호기 1차 CB (7A72)","태안T/P 10호기 1차 GIS(7A72) 하자점검","태안T/P 10호기 1차 GIS(7A72) 하자점검","2017-04-25 09:00","2017-04-25 18:00","2017-04-25 09:00","2017-04-25 18:00","당일",null,null,null,201702060273,"-"]
[66,"대전충남","서산","태안T/P 신서산-태안TP#2-10호기 1차 CB (7A00)","태안T/P 신서산-태안T/P#2-10호기 1차 GIS(7A00) 하자점검","태안T/P 신서산-태안T/P#2-10호기 1차 GIS(7A00) 하자점검","2017-04-26 09:00","2017-04-26 18:00","2017-04-26 09:00","2017-04-26 18:00","당일",null,null,null,201702060274,"-"]
[67,"대전충남","서산","신서산태안화력#1 T/L","2016-17년 변전협력회사 총액공사(B/F반 교체)","태안화력SWYD 76Bay B/F보호반 대체(노후장기 배전반)","2017-04-03 09:00","2017-04-07 18:00","2017-04-01 09:00","2017-04-02 18:00","연속",null,null,null,201702170043,"-"]
[68,"대전충남","아산","신온양신탕정#1 T/L","345kV 신온양-신탕정T/L 전선교체공사","※ 하단선 전선교체작업 안전이격확보 ○ 구간: 345kV 신온양-신탕정T/L No.3~신탕정S/T [하단선 교체] ○ 선로길이: 8.9km × 2C [지지물 23기]","2017-04-05 06:00","2017-04-25 18:30","2017-04-05 06:00","2017-04-25 18:30","연속",null,null,null,201612070184,"-"]
[69,"대전충남","아산","신탕정S/S 345kV #2 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","신탕정S/S 345kV 72Bay GIS 대체(50KA→63KA)","2017-04-15 10:00","2017-04-15 18:00","2017-04-15 10:00","2017-04-15 18:00","당일",null,null,null,201702080084,"-"]
[70,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","신탕정S/S 345kV 72Bay GIS 대체(50KA→63KA)","2017-04-16 10:00","2017-04-16 18:00","2017-04-16 10:00","2017-04-16 18:00","당일",null,null,null,201702080086,"-"]
[71,"대전충남","아산","아산화성#1 T/L","[송전]345kV 아산-화성T/L 전선교체공사","- 전력선 교체(ACSR 480㎟ × 4B) : 6.928c-km (교체사유 : 내장∼내장 구간 내 동일 소도체 2개 이상 접속개소) 1. No.2～5 : 6가닥 교체 2. No.8～10 : 2가닥 교체 3. No.10～15 : 4가닥 교체 4. No.35～36 : 2가닥 교체 5. No.36～39 : 4가닥 교체 6. No.50～5","2017-04-18 07:00","2017-04-27 18:00","2017-04-18 07:00","2017-04-27 18:00","매일",null,null,null,201702170140,"-"]
[72,"대전충남","아산","아산화성#2 T/L","[송전]345kV 아산-화성T/L 전선교체공사","- 전력선 교체(ACSR 480㎟ × 4B) : 6.928c-km (교체사유 : 내장∼내장 구간 내 동일 소도체 2개 이상 접속개소) 1. No.2～5 : 6가닥 교체 2. No.8～10 : 2가닥 교체 3. No.10～15 : 4가닥 교체 4. No.35～36 : 2가닥 교체 5. No.36～39 : 4가닥 교체 6. No.50～5","2017-04-28 07:00","2017-05-13 18:00","2017-04-28 07:00","2017-05-13 18:00","매일",null,null,null,201702170141,"-"]
[73,"대전충남","청양","청양보령TP#1 T/L","345kV 청양보령화력#1T/L 송전용피뢰기 설치공사","청양보령화력#1T/L No.1~86간 261set 송전용피뢰기 설치","2017-04-10 07:00","2017-04-15 18:00","2017-04-10 07:00","2017-04-15 18:00","매일",null,null,null,201702140434,"-"]
[74,"대전충남","청양","보령T/P 보령연락#1T/L-#2 M.Tr 1차 CB (7200)","보령화력 362kV GIS 보통점검","○ 345kV 7200 GIS 보통점검","2017-04-25 09:00","2017-04-26 18:00","2017-04-25 09:00","2017-04-26 18:00","연속",null,null,null,201702100274,"-"]
[75,"대전충남","청양","보령T/P #2 M.Tr 1차 CB (7272)","보령화력 362kV GIS 보통점검","○ 345kV 7272 GIS 보통점검","2017-04-25 09:00","2017-04-26 18:00","2017-04-25 09:00","2017-04-26 18:00","연속",null,null,null,201702100271,"-"]
[76,"대전충남","청양","아산보령화력#1 T/L","345kV 아산보령화력#1T/L 송전용피뢰기 설치공사","청양보령화력#1T/L No1-1 송전용피뢰기 설치 병가구간 안전거리 확보","2017-04-15 07:00","2017-04-15 18:00","2017-04-15 07:00","2017-04-15 18:00","당일",null,null,null,201702070188,"-"]
[77,"대전충남","청양","청양S/S 신옥천-청양T/L CB (7471)","청양S/S 362kV GIS 정밀점검","-7472, 7400, 7171, 7372. 7100, 7172, 7200, 7371, 7471, 7272 CB정밀점검","2017-04-24 08:00","2017-04-26 18:00","2017-04-24 08:00","2017-04-26 18:00","연속",null,null,null,201702010095,"-"]
[78,"대전충남","청양","청양S/S 청양-보령복합T/L CB (7272)","청양S/S 362kV GIS 정밀점검","-7472, 7400, 7171, 7372. 7100, 7172, 7200, 7371, 7471, 7272 CB정밀점검","2017-04-27 08:00","2017-04-29 18:00","2017-04-27 08:00","2017-04-29 18:00","연속",null,null,null,201702010096,"-"]
[79,"대전충남","청양","청양S/S 청양-신보령T/L-청양보령복합TL CB (7200)","청양S/S 362kV GIS 정밀점검","-7472, 7400, 7171, 7372. 7100, 7172, 7200, 7371, 7471, 7272 CB정밀점검","2017-04-03 08:00","2017-04-05 18:00","2017-04-03 08:00","2017-04-05 18:00","연속",null,null,null,201702010097,"-"]
[80,"대전충남","청양","청양S/S 신계룡-청양T/L CB (7171)","청양S/S 362kV GIS 정밀점검","-7472, 7400, 7171, 7372. 7100, 7172, 7200, 7371, 7471, 7272 CB정밀점검","2017-04-17 08:00","2017-04-19 18:00","2017-04-17 08:00","2017-04-19 18:00","연속",null,null,null,201702010093,"-"]
[81,"대전충남","청양","청양S/S 청양-신온양#1T/L CB (7371)","청양S/S 362kV GIS 정밀점검","-7472, 7400, 7171, 7372. 7100, 7172, 7200, 7371, 7471, 7272 CB정밀점검","2017-04-20 08:00","2017-04-22 18:00","2017-04-20 08:00","2017-04-22 18:00","연속",null,null,null,201702010094,"-"]
[82,"전북","군산","군산신김제#1 T/L","군산신김제#1T/L 전선접속개소 교체공사","○ 전선교체 - 구간 : No.24 ~ 30, No.34 ~ 36, 47 ~ 52, 135 ~ 138","2017-04-30 07:00","2017-05-14 18:00","2017-04-30 07:00","2017-05-14 18:00","연속",null,null,null,201702140558,"-"]
[83,"전북","군산","군산새만금#2 T/L","효성제 옥외차단기 특별점검","군산S/S 군산-새만금2T/L Tie CB","2017-04-19 10:00","2017-04-19 18:00","2017-04-19 10:00","2017-04-19 18:00","당일",null,null,null,201702150025,"-"]
[84,"전북","군산","청양군산#2 T/L","청양군산T/L 전선접속개소교체공사","전선교체(5~7,13~14,24~25,52~55)","2017-04-04 07:00","2017-04-18 18:00","2017-04-04 07:00","2017-04-18 18:00","연속",null,null,null,201701180075,"-"]
[85,"전북","군산","군산신김제#2 T/L","군산신김제#2T/L 전선접속개소 교체공사","○ 전선교체 - 구간 : No.24 ~ 30, 34 ~ 36, 135 ~ 138","2017-04-15 07:00","2017-04-29 18:00","2017-04-15 07:00","2017-04-29 18:00","연속",null,null,null,201702140550,"-"]
[86,"전북","김제","신김제S/S #4 M.Tr A","신김제S/S #4M.Tr 차단기 및 변압기 정밀점검","0 #4 M.Tr 1차 7800, 7872 차단기 정밀점검 0 #4 M.Tr 정밀점검","2017-04-10 09:00","2017-04-21 18:00","2017-04-10 09:00","2017-04-21 18:00","연속",null,null,null,201702160402,"-"]
[87,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","76Bay B/F 보호반 교체","2017-04-03 09:00","2017-04-07 18:00","2017-04-03 09:00","2017-04-07 18:00","연속",null,null,null,201611160101,"-"]
[88,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.58~83)","○ 전력선 교체 : 16.954C-km - 대상구간 : No.58~73, 75~83 ○ 가공지선 교체 : 4.224km - 대상구간 : No.68~71, 75~83 ○ 스페이서 댐퍼 설치/철거 : 780개/714개 ○ 아마롯드 설치 및 기타 부대공사","2017-04-04 07:00","2017-04-17 18:00","2017-04-04 07:00","2017-04-17 18:00","연속",null,null,"신뢰도 개선",201701310030,"-"]
[89,"전북","직할","신남원S/S 신옥천-신남원#2 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7171)","- 차단기 내부 균압콘덴서 도블측정","2017-04-18 10:00","2017-04-18 13:30","2017-04-18 10:00","2017-04-18 13:30","당일",null,null,null,201702150131,"-"]
[90,"전북","직할","신남원S/S 신남원-광양#2 - TIE GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7600)","- 차단기 내부 균압콘덴서 도블측정","2017-04-14 13:30","2017-04-14 17:00","2017-04-14 13:30","2017-04-14 17:00","당일",null,null,null,201702150129,"-"]
[91,"전북","직할","신남원S/S 신남원-광양#2 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7671)","- 차단기 내부 균압콘덴서 도블측정","2017-04-14 10:00","2017-04-14 13:30","2017-04-14 10:00","2017-04-14 13:30","당일",null,null,null,201702150128,"-"]
[92,"전북","직할","신남원S/S 신남원-광양#1 - TIE GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7500)","- 차단기 내부 균압콘덴서 도블측정","2017-04-13 13:30","2017-04-13 17:00","2017-04-13 13:30","2017-04-13 17:00","당일",null,null,null,201702150127,"-"]
[93,"전북","직할","신남원S/S 신남원-광양#1 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7571)","- 차단기 내부 균압콘덴서 도블측정","2017-04-13 10:00","2017-04-13 13:30","2017-04-13 10:00","2017-04-13 13:30","당일",null,null,null,201702150124,"-"]
[94,"전북","직할","신남원S/S 신남원-의 령#2 - TIE GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7400)","- 차단기 내부 균압콘덴서 도블측정","2017-04-12 13:30","2017-04-12 17:00","2017-04-12 13:30","2017-04-12 17:00","당일",null,null,null,201702150122,"-"]
[95,"전북","직할","신남원S/S 신남원-의 령#2 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7471)","- 차단기 내부 균압콘덴서 도블측정","2017-04-12 10:00","2017-04-12 13:30","2017-04-12 10:00","2017-04-12 13:30","당일",null,null,null,201702150120,"-"]
[96,"전북","직할","신남원S/S 신남원-의 령#1 - TIE GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7300)","- 차단기 내부 균압콘덴서 도블측정","2017-04-11 13:30","2017-04-11 17:00","2017-04-11 13:30","2017-04-11 17:00","당일",null,null,null,201702150119,"-"]
[97,"전북","직할","신남원S/S 신남원-의 령#1 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7371)","- 차단기 내부 균압콘덴서 도블측정","2017-04-11 10:00","2017-04-11 13:30","2017-04-11 10:00","2017-04-11 13:30","당일",null,null,null,201702150117,"-"]
[98,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.58~83)","○ 전력선 교체 : 16.954C-km - 대상구간 : No.58~73, 75~83 ○ 가공지선 교체 : 4.224km - 대상구간 : No.68~71, 75~83 ○ 스페이서 댐퍼 설치/철거 : 780개/714개 ○ 아마롯드 설치 및 기타 부대공사","2017-04-18 07:00","2017-05-01 18:00","2017-04-18 07:00","2017-05-01 18:00","연속",null,null,null,201701310032,"-"]
[99,"전북","직할","신남원S/S 신남원-신광주#1 - TIE CB (7700)","345kV 신남원S/S M.Tr 설치","362kV GIS CB(7772)×1대 증설, #1M.Tr 무부하가압","2017-04-04 09:00","2017-04-17 18:00","2017-04-04 09:00","2017-04-17 18:00","연속",null,null,null,201702100006,"-"]
[100,"전북","직할","신남원S/S 신옥천-신남원#1 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7271)","- 차단기 내부 균압콘덴서 도블측정","2017-04-19 13:30","2017-04-19 17:00","2017-04-19 13:30","2017-04-19 17:00","당일",null,null,null,201702150140,"-"]
[101,"전북","직할","신남원S/S 신남원-한빛NP#1 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7272)","- 차단기 내부 균압콘덴서 도블측정","2017-04-20 10:00","2017-04-20 13:30","2017-04-20 10:00","2017-04-20 13:30","당일",null,null,null,201702150142,"-"]
[102,"전북","직할","신옥천신남원#1-신남원한빛NP#1 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7200)","- 차단기 내부 균압콘덴서 도블측정","2017-04-20 13:30","2017-04-20 17:00","2017-04-20 13:30","2017-04-20 17:00","당일",null,null,null,201702150145,"-"]
[103,"전북","직할","신남원S/S 신남원-한빛NP#2 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7172)","- 차단기 내부 균압콘덴서 도블측정","2017-04-19 10:00","2017-04-19 13:30","2017-04-19 10:00","2017-04-19 13:30","당일",null,null,null,201702150139,"-"]
[104,"전북","직할","신옥천신남원#2-신남원한빛NP#2 T/L GIS","신남원S/S 345kV GIS 차단기 내부 균압콘덴서 도블측정(7100)","- 차단기 내부 균압콘덴서 도블측정","2017-04-18 13:30","2017-04-18 17:00","2017-04-18 13:30","2017-04-18 17:00","당일",null,null,null,201702150137,"-"]
[105,"광주전남","강진","신화순신강진#1 T/L","345kV 신화순-신강진TL 접속개소 해소공사","가. 구 간 : 345kV 신화순-신강진T/L No.132∼133 등 9구간 나. 전선교체 : ACSR 480㎟ × 4B × 2C, 16.666㎞ 다. 스페이서 댐퍼 설치 및 철거 라. 연가해소 : No.171, 신강진 S/T 인출변경","2017-04-17 09:00","2017-05-26 18:00","2017-04-17 09:00","2017-05-26 18:00","연속",null,null,null,201701110034,"-"]
[106,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S 345kV #3M.Tr(T-BUS 철거)","신강진S/S 154kV 옥외철구 GIS화 공사 2017. 4. 26 : 신강진S/S 345kV #3M.Tr","2017-04-28 09:00","2017-04-28 18:00","2017-04-28 09:00","2017-04-28 18:00","당일",null,null,null,201702170233,"-"]
[107,"광주전남","강진","신강진S/S #2 M.Tr A","신강진S/S 345kV #2M.Tr(T-BUS 철거)","신강진S/S 154kV 옥외철구 GIS화 공사 2017. 4. 26 : 신강진S/S 345kV #2M.Tr","2017-04-26 09:00","2017-04-26 18:00","2017-04-26 09:00","2017-04-26 18:00","당일",null,null,null,201702140400,"-"]
[108,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr(T-BUS 철거)","신강진S/S 154kV 옥외철구 GIS화 공사 2017. 4. 26 : 신강진S/S 345kV #1M.Tr","2017-04-20 09:00","2017-04-20 18:00","2017-04-20 09:00","2017-04-20 18:00","당일",null,null,null,201702170232,"-"]
[109,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3 M.Tr (인출변경및인출GIS연결)","- 인출GIS연결 - 제어케이불 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시첨","2017-04-01 07:00","2017-04-11 18:00","2017-04-21 07:00","2017-05-04 18:00","연속",null,null,null,201701250001,"-"]
[110,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1 M.Tr (인출변경 및 인출GIS연결)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-04-29 07:00","2017-05-08 18:00","2017-05-26 07:00","2017-06-03 18:00","연속",null,null,null,201701250013,"-"]
[111,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S #4 M.Tr (인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-04-16 07:00","2017-04-26 18:00","2017-05-14 07:00","2017-05-25 18:00","연속",null,null,null,201701250008,"-"]
[112,"광주전남","광주","신화순S/S #2 M.Tr 1차 CB (7772)","신화순S/S 345kV #2 M.Tr 1차 CB(7772) 정밀점검","신화순S/S 345kV #2 M.Tr 1차 CB(7772) 정밀점검","2017-04-10 09:00","2017-04-13 18:00","2017-04-10 09:00","2017-04-13 18:00","연속",null,null,null,201701090053,"-"]
[113,"대구경북","경산","신경산S/S #2 M.Tr A","신경산S/S 345kV #2M.Tr 휴전","6244 GIS 대체공사","2017-04-24 09:00","2017-05-15 09:00","취소","취소","연속",null,null,null,201702100007,"-"]
[114,"대구경북","경산","울주신경산#1 T/L","울주-신경산 등 3개T/L 전력선교체공사","울주신경산#1T/L No.106~118 전력선교체","2017-04-24 08:00","2017-05-02 18:00","2017-04-24 08:00","2017-05-02 18:00","연속",null,null,null,201702160222,"-"]
[115,"대구경북","경산","신경산대구#1 T/L","울주-신경산 등 3개T/L 전력선교체공사","경산자인#2T/L No.16~24 전력선교체 안전확보","2017-04-16 08:00","2017-04-23 18:00","취소","취소","연속",null,null,null,201702160210,"-"]
[116,"대구경북","경산","신경산대구#2 T/L","울주-신경산 등 3개T/L 전력선교체공사","경산자인#1T/L No.16~24 전력선교체 안전확보","2017-04-07 08:00","2017-04-15 18:00","취소","취소","연속",null,null,null,201702160209,"-"]
[117,"대구경북","구미","서대구선산#1 T/L","345kV 서대구-선산T/L 전선접속개소 전력선교체공사","o 구간 : 345kV 서대구-선산T/L No.2~27 o 전력선 : ACSR 480*4B o 긍장 : 5.043km o 예정시공사 : 태성산업(적격심사 준비중)","2017-04-24 08:00","2017-05-03 18:00","2017-04-24 08:00","2017-05-03 18:00","연속",null,null,null,201702130391,"-"]
[118,"대구경북","달성","고령S/S #4 M.Tr 1차 CB (7872)","고령 7872 유압실린더 블럭교체작업","유압실린더 블럭교체작업(7872CB)","2017-04-27 09:30","2017-04-28 18:00","2017-04-27 09:30","2017-04-28 18:00","연속",null,null,null,201702210020,"○"]
[119,"대구경북","달성","대구S/S #2 M.Tr A","2017년 달성전력 주변압기 정밀","주변압기 및 GIS정밀","2017-04-05 09:30","2017-04-12 18:00","2017-04-05 09:30","2017-04-12 18:00","연속",null,null,null,201702070041,"-"]
[120,"대구경북","달성","북경남대구#1 T/L","2017년 달성전력 GIS 정밀(7471CB)","GIS 정밀(7471CB)","2017-04-18 10:00","2017-04-18 18:00","2017-04-18 10:00","2017-04-18 18:00","당일",null,null,null,201702060050,"-"]
[121,"대구경북","달성","대구S/S 북경남-대구#1T/L CB (7471)","2017년 달성전력 GIS 정밀(7471CB)","GIS정밀(7471CB)","2017-04-17 09:30","2017-04-20 18:00","2017-04-17 09:30","2017-04-20 18:00","연속",null,null,null,201702140154,"-"]
[122,"대구경북","안동","신영일안동CC T/L","345kV 영포T/L 전선접속개소 전선교체공사","345kV 영포T/L 전선접속개소 전선교체공사 No.87-98 [직할]345kV 영포T/L 전선접속개소 전선교체공사","2017-04-13 07:00","2017-04-24 18:00","2017-04-13 07:00","2017-04-24 18:00","연속",null,null,null,201702130181,"-"]
[123,"대구경북","안동","신영주안동CC T/L","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS *3 CB 170kV GIS * 5CCT","2017-04-10 15:00","2017-04-12 15:00","취소","취소","연속",null,null,null,201702090226,"○"]
[124,"대구경북","안동","안동복합S/Y 345kV #1 BUS","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS * 3CB 170kV GIS * 5CCT.","2017-04-03 10:00","2017-04-12 18:00","취소","취소","연속",null,null,null,201702090202,"○"]
[125,"대구경북","안동","신영주청송PP T/L","345kV 영포T/L 전선접속개소 전선교체공사","345kV 영포T/L 전선접속개소 전선교체공사 No.87-98 [직할]345kV 영포T/L 전선접속개소 전선교체공사 [안동_송전]345kV 영포T/L 가공송전위탁 정밀점검 병행 [안동_변전]GIS정밀점검 병행","2017-04-01 07:00","2017-04-12 18:00","2017-04-01 07:00","2017-04-12 18:00","연속",null,null,null,201702130174,"-"]
[126,"대구경북","안동","청송P/P 신영주청송T/L-#1M.Tr 1차 CB (7100)","청송양수S/Y 7100 GIS 정밀점검공사","청송양수S/Y 7100 GIS 정밀점검공사","2017-04-06 09:00","2017-04-08 18:00","2017-04-06 09:00","2017-04-08 18:00","연속",null,null,null,201701060287,"-"]
[127,"대구경북","안동","청송P/P #1 M.Tr 1차 CB (7172)","청송양수S/Y 7172 GIS 정밀점검공사","청송양수S/Y 7172 GIS 정밀점검공사","2017-04-10 09:00","2017-04-12 18:00","2017-04-10 09:00","2017-04-12 18:00","연속",null,null,null,201701060289,"○"]
[128,"대구경북","안동","청송P/P 신포항청송T/L-#2M.Tr 1차 CB (7200)","청송양수S/Y 7200 GIS 정밀점검공사","청송양수S/Y 7200 GIS 정밀점검공사","2017-04-13 09:00","2017-04-15 18:00","2017-04-13 09:00","2017-04-15 18:00","연속",null,null,null,201701060290,"○"]
[129,"대구경북","안동","청송P/P #2 M.Tr 1차 CB (7272)","청송양수S/Y 7272 GIS 정밀점검공사","청송양수S/Y 7272 GIS 정밀점검공사","2017-04-17 09:00","2017-04-19 18:00","2017-04-17 09:00","2017-04-19 18:00","연속",null,null,null,201701060292,"○"]
[130,"대구경북","영주","신제천신영주#1 T/L","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-04-28 18:00","2017-04-29 18:00","2017-04-28 18:00","2017-04-29 18:00","연속",null,null,null,201702140051,"-"]
[131,"대구경북","영주","신영주S/S #1 예비 M.Tr CB","신영주S/S 345kV 예비M.Tr 하자점검","신영주S/S 345kV 예비M.Tr 하자점검","2017-04-03 09:00","2017-04-03 18:00","2017-04-03 09:00","2017-04-03 18:00","당일",null,null,null,201702010014,"-"]
[132,"대구경북","영주","신영주S/S #3M.Tr A","신영주S/S 345kV #3M.Tr 하자점검 등","#3M.Tr 하자점검, 7700, 7772 GIS 초기점검 6344 GCB 하자점검, 2차 LA 하자점검, 6341, 6342 DS 보통점검","2017-04-04 09:00","2017-04-06 18:00","2017-04-04 09:00","2017-04-06 18:00","매일",null,null,null,201702010015,"-"]
[133,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-04-17 10:00","2017-04-21 18:00","2017-04-17 10:00","2017-04-21 18:00","연속",null,null,null,201702140047,"○"]
[134,"대구경북","영주","신제천신영주#1 T/L","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-04-20 18:00","2017-04-21 18:00","2017-04-20 18:00","2017-04-21 18:00","연속",null,null,null,201702140050,"-"]
[135,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-04-25 10:00","2017-04-29 18:00","2017-04-25 10:00","2017-04-29 18:00","연속",null,null,null,201702140049,"-"]
[136,"대구경북","영주","신영주한울NP2#2 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","□ 공사구간 : 345kV 신영주-한울NP2T/L 43∼75호 □ 공사내용 : 전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-04-18 07:00","2017-05-02 18:00","취소","취소","연속",null,null,null,201702130354,"-"]
[137,"대구경북","영주","신영주한울NP2#1 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","□ 공사구간 : 345kV 신영주-한울NP2T/L 43∼75호 □ 공사내용 : 전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-04-03 07:00","2017-04-17 18:00","2017-04-17 07:00","2017-05-01 18:00","연속",null,null,null,201702130351,"-"]
[138,"대구경북","영주","한울3N/P 한울연락#4T/L CB (7C71)","한울 3발S/Y 345kV 7C Bay 초기점검","7C71, 7C00, 7C72 GIS 초기점검","2017-04-18 09:00","2017-04-19 18:00","2017-04-18 09:00","2017-04-19 18:00","연속",null,null,null,201702010011,"-"]
[139,"대구경북","영주","한울3N/P 한울연락#4T/L-#6M.Tr CB (7C00)","한울 3발S/Y 345kV 7C Bay 초기점검","7C71, 7C00, 7C72 GIS 초기점검","2017-04-18 09:00","2017-04-19 18:00","2017-04-18 09:00","2017-04-19 18:00","연속",null,null,null,201702010013,"-"]
[140,"대구경북","영주","한울3N/P #6M.Tr 1차 CB (7C72)","한울 3발S/Y 345kV 7C Bay 초기점검","7C71, 7C00, 7C72 GIS 초기점검","2017-04-18 09:00","2017-04-19 18:00","2017-04-18 09:00","2017-04-19 18:00","연속",null,null,null,201702010012,"-"]
[141,"대구경북","칠곡","북대구S/S 345kV #2 BUS","345kV 북대구S/S #3M.Tr 증설공사","345 #2BUS(기존 모선) 상 확인(접촉저항 측정)","2017-04-05 09:00","2017-04-06 18:00","2017-04-05 09:00","2017-04-06 18:00","연속",null,null,null,201701060307,"-"]
[142,"대구경북","칠곡","북대구S/S 345kV #1 BUS","345kV 북대구S/S #3M.Tr 증설공사","345 #1BUS(기존 모선) 상 확인(접촉저항 측정)","2017-04-03 09:00","2017-04-04 18:00","2017-04-03 09:00","2017-04-04 18:00","연속",null,null,null,201701060306,"-"]
[143,"대구경북","칠곡","북대구서대구#1 T/L","345kV 북대구S/S #3M.Tr 증설공사","345kV #1BUS 무부하가압 및 위상 Check","2017-04-20 09:00","2017-04-21 18:00","2017-04-20 09:00","2017-04-21 18:00","연속",null,null,null,201702010059,"-"]
[144,"대구경북","칠곡","북대구S/S 345kV #1 BUS","345kV 북대구S/S #3M.Tr 증설공사","345kV #1BUS 접속 및 무부하가압","2017-04-17 09:00","2017-04-21 18:00","2017-04-17 09:00","2017-04-21 18:00","연속",null,null,null,201702010054,"-"]
[145,"대구경북","칠곡","북대구선산 T/L","345kV 북대구S/S #3M.Tr 증설공사","345kV #2BUS 무부하가압 및 위상 Check","2017-04-24 09:00","2017-04-26 16:00","2017-04-24 09:00","2017-04-26 16:00","연속",null,null,null,201702010060,"-"]
[146,"대구경북","칠곡","북대구S/S 345kV #2 BUS","345kV 북대구S/S #3M.Tr 증설공사","345kV #2BUS 접속 및 무부하가압","2017-04-22 09:00","2017-04-26 18:00","2017-04-22 09:00","2017-04-26 18:00","연속",null,null,null,201702010055,"-"]
[147,"대구경북","칠곡","서대구S/S TIE-서대구-무주PPT/L-TIE CB (7300)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S 북경남-서대구#2T/L CB(7300) 정밀점검","2017-04-03 09:00","2017-04-05 18:00","취소","취소","연속",null,null,null,201702080292,"-"]
[148,"대구경북","칠곡","서대구S/S 345kV #2 BUS","서대구S/S 345kV #2 BUS 휴전","서대구S/S 345kV #2 BUS PT교체 (B상)","2017-04-13 09:30","2017-04-13 18:00","취소","취소","당일",null,null,null,201702130075,"-"]
[149,"대구경북","칠곡","서대구S/S 서대구-무주PPT/L CB (7372)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S 북경남-서대구#2T/L CB(7372) 정밀점검","2017-04-06 09:00","2017-04-08 18:00","취소","취소","연속",null,null,null,201702080294,"-"]
[150,"대구경북","포항","신포항신영일 T/L","신포항신영일 T/L 7771 GIS 보통점검","신포항신영일 T/L 7771 GIS 보통점검","2017-04-18 09:00","2017-04-18 18:00","2017-04-18 09:00","2017-04-18 18:00","당일",null,null,null,201702130102,"-"]
[151,"대구경북","포항","신포항S/S #1 M.Tr A","신포항S/S 옥외철구GIS화 공사","8DS 및 T-BUS 철거","2017-04-19 09:00","2017-04-20 18:00","취소","취소","연속",null,null,null,201702130290,"○"]
[152,"부산울산","동부산","신양산고리NP#2 T/L","신양산S/S 362kV GIS 보통점검","1. 신양산 362kV 7571, 7500 GIS 보통점검 2. 신양산 345 CVT 및 LA 보통점검 3. 345kV 유호제 T/L보호반 내부통신회로 개선","2017-04-12 09:30","2017-04-13 17:00","2017-04-12 09:30","2017-04-13 17:00","연속",null,null,null,201702100505,"-"]
[153,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 362kV GIS 보통점검","1. 신양산 362kV 7671, 7600 GIS 보통점검 2. 신양산 345 CVT 및 LA 보통점검 3. 345kV 유호제 T/L보호반 내부통신회로 개선","2017-04-10 09:30","2017-04-11 17:00","2017-04-10 09:30","2017-04-11 17:00","연속",null,null,null,201702100504,"○"]
[154,"부산울산","동부산","신양산신대연#2 T/L","17년 가공송전선로 순시점검위탁공사(정밀점검)","345kV 신양산-신대연T/L 정밀점검 구간 : 신양산S/T~신대연S/T(26기)","2017-04-06 09:00","2017-04-08 18:00","2017-04-06 09:00","2017-04-08 18:00","연속",null,null,null,201702070076,"-"]
[155,"부산울산","동부산","신양산신대연#1 T/L","17년 가공송전선로 순시점검위탁공사(정밀점검)","345kV 신양산-신대연T/L 정밀점검 구간 : 신양산S/T~신대연S/T(26기)","2017-04-03 09:00","2017-04-05 18:00","2017-04-03 09:00","2017-04-05 18:00","연속",null,null,null,201702070069,"-"]
[156,"부산울산","북부산","서부산북부산#3 T/L","345kV 북부산S/S 차단기용량대체공사","1. 서부산-북부산#3T/L GIS 대체 관련 GIS 구간분리","2017-04-24 09:00","2017-04-26 18:00","2017-04-24 09:00","2017-04-26 18:00","연속",null,null,null,201702080099,"-"]
[157,"부산울산","북부산","북부산S/S 서부산-북부산#2T/L Sh.R CB","345kV 북부산S/S 차단기용량대체공사","서부산-북부산#2T/L #2Sh.R용 GIS 대체작업, 기초보강 및 CB 대체","2017-04-24 09:00","2017-05-23 18:00","2017-04-24 09:00","2017-05-23 18:00","연속",null,null,null,201702080116,"-"]
[158,"부산울산","북부산","북부산S/S #4 M.Tr A","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S #4M.Tr 2차 6444 GIS 인출변경","2017-04-27 08:00","2017-05-04 18:00","2017-04-27 08:00","2017-05-04 18:00","연속",null,null,null,201702090380,"-"]
[159,"부산울산","서부산","서부산S/S #2 M.Tr A","서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사","-서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사 및 2차 GIS(6244) 정밀점검","2017-04-03 10:00","2017-04-12 18:00","2017-04-03 10:00","2017-04-12 18:00","연속",null,null,null,201702090067,"○"]
[160,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #1Sh.R 대체공사(시험가압)","서부산S/S 345kV #1Sh.R 대체공사(시험가압-24H)","2017-04-01 11:00","2017-04-02 11:00","2017-04-01 11:00","2017-04-02 11:00","연속",null,null,null,201702090062,"○"]
[161,"부산울산","서부산","서부산북부산#2 T/L","서부산S/S 345kV #72 B/F(차단실패)및 #1M.Tr PNL","-서부산S/S 345kV #72BAY B/F(차단실패) 및 #1M.TrPNL 교체 공사","2017-04-13 10:00","2017-04-20 18:00","2017-04-13 10:00","2017-04-20 18:00","연속",null,null,null,201702090072,"-"]
[162,"부산울산","서부산","서부산S/S #1 M.Tr A","서부산S/S 345kV #72 B/F(차단실패)및 #1M.Tr PNL","-서부산S/S 345kV #72BAY B/F(차단실패), #1M.TrPNL 교체 공사 및 #1M.Tr 2차 GIS(6144) 정밀점검","2017-04-13 10:00","2017-04-23 18:00","2017-04-13 10:00","2017-04-23 18:00","연속",null,null,null,201702090071,"-"]
[163,"부산울산","서부산","서부산S/S #5,6 G/T CB (7571)","서부산S/S #5,6G/T(7571) GIS 보통점검","서부산S/S #5,6G/T(7571) GIS 보통점검","2017-04-26 10:00","2017-04-26 18:00","취소","취소","당일",null,null,null,201702140157,"-"]
[164,"부산울산","서부산","서부산S/S #5,6 G/T-#7,8 G/T CB (7500)","서부산S/S #5,6 G/T-#7,8 G/T(7500) GIS 보통점검","서부산S/S #5,6 G/T-#7,8 G/T(7500) GIS 보통점검","2017-04-27 10:00","2017-04-27 18:00","취소","취소","당일",null,null,null,201702140161,"-"]
[165,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사","-서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사","2017-04-03 10:00","2017-04-09 18:00","2017-04-03 10:00","2017-04-09 18:00","연속",null,null,null,201702090066,"○"]
[166,"부산울산","울산","동울산S/S #3 M.Tr A","'16-17년 울산전력지사 변전협력회사 총액공사","동울산 #3M.Tr 하자점검","2017-04-12 09:00","2017-04-13 18:00","2017-04-12 09:00","2017-04-13 18:00","연속",null,null,null,201702100567,"-"]
[167,"부산울산","울산","동울산S/S #2 M.Tr A","'16-17년 울산전력지사 변전협력회사 총액공사","동울산S/S #2M.Tr 하자점검","2017-04-10 09:00","2017-04-11 18:00","2017-04-10 09:00","2017-04-11 18:00","연속",null,null,null,201702100566,"-"]
[168,"부산울산","울산","신울산신온산#2 T/L","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 71Bay B/F 계전기 추가설치 및 7172CB 예비가압","2017-04-28 09:00","2017-04-30 18:00","2017-04-28 09:00","2017-04-30 18:00","연속",null,null,null,201702060126,"-"]
[169,"부산울산","울산","북부산신온산 T/L","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 71Bay 신설 #2BUS (63kA) 예비가압","2017-04-20 09:00","2017-04-21 18:00","2017-04-20 09:00","2017-04-21 18:00","연속",null,null,null,201702060124,"-"]
[170,"부산울산","울산","신온산S/S 345kV #2 BUS","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 71Bay 신설 #2BUS (63kA) 및 7172CB 설치","2017-04-14 09:00","2017-04-21 18:00","2017-04-14 09:00","2017-04-21 18:00","연속",null,null,null,201702060116,"-"]
[171,"부산울산","울산","신온산S/S 신울산-신온산#2T/L 1차TIE CB (7100)","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5T/L(7172) 증설","2017-04-14 09:00","2017-05-09 18:00","2017-04-14 09:00","2017-05-09 18:00","연속",null,null,null,201702060121,"-"]
[172,"부산울산","울산","울산C/C #3 M.Tr A","울산복합화력 차단 고장파급방지시스템 회로구성","울산복합 345kV #3M.Tr 과부하 방지 차단회로 구성 M.Tr 및 1차 GIS 하자점검","2017-04-29 09:00","2017-04-30 18:00","2017-04-29 09:00","2017-04-30 18:00","연속",null,null,null,201702170096,"-"]
[173,"부산울산","울산","울산C/C #2 M.Tr A","'16-17년 울산전력지사 변전협력회사 총액공사","울산C/C #2M.Tr 및 울산화력 170kV GIS 보통점검","2017-04-08 09:00","2017-04-09 18:00","2017-04-08 09:00","2017-04-09 18:00","연속",null,null,null,201702100565,"-"]
[174,"부산울산","울산","울산C/C 345kV #1 BUS","2016~2017년 울산전력지사 변전협력 총액공사","시험가압(울산C/C 7801가스누기 조치작업관련)","2017-04-09 17:00","2017-04-09 18:00","취소","취소","당일",null,null,null,201702160116,"-"]
[175,"부산울산","울산","북부산울산TP T/L","2016~2017년 울산전력지사 변전협력 총액공사","시험가압(7801가스누기 조치작업관련)","2017-04-09 17:00","2017-04-09 18:00","취소","취소","당일",null,null,null,201702160114,"-"]
[176,"경남","직할","신김해S/S 신마산-신김해#1T/L CB (7271)","신김해S/S 신마산-신김해#1T/L CB(7271) 보통점검","신김해S/S 신마산-신김해#1T/L CB(7271),PT,LA 보통점검","2017-04-04 09:30","2017-04-04 17:30","2017-04-04 09:30","2017-04-04 17:30","당일",null,null,null,201702060068,"-"]
[177,"경남","직할","신김해S/S 신김해-북부산#1T/L CB (7371)","신김해S/S 신김해-북부산#1T/L CB(7371) 보통점검","신김해S/S 신김해-북부산#1T/L CB(7371),PT 보통점검, LA 교체","2017-04-06 09:30","2017-04-06 17:30","2017-04-06 09:30","2017-04-06 17:30","당일",null,null,null,201702060069,"-"]
[178,"경남","직할","신김해S/S 신마산-신김해#2T/L CB (7171)","신김해S/S 신마산-신김해#2T/L CB(7171) 보통점검","신김해S/S 신마산-신김해#2T/L CB(7171),PT,LA 보통점검","2017-04-03 09:30","2017-04-03 17:30","2017-04-03 09:30","2017-04-03 17:30","당일",null,null,null,201702060067,"-"]
[179,"경남","직할","신김해S/S 신김해-북부산#2T/L CB (7471)","신김해S/S 신김해-북부산#2T/L CB(7471) 보통점검","신김해S/S 신김해-북부산#2T/L CB(7471),PT,LA 보통점검","2017-04-07 09:30","2017-04-07 17:30","2017-04-07 09:30","2017-04-07 17:30","당일",null,null,null,201702060070,"-"]
[180,"경남","직할","신김해삼천포화력#1 T/L","신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체공사","345kV 신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체(214~228)","2017-04-15 07:00","2017-04-28 19:00","2017-04-15 07:00","2017-04-28 19:00","연속",null,null,null,201702070316,"-"]
[181,"경남","직할","신김해S/S 신녹산#1T/L-#3M.Tr 1차 CB (7700)","신김해S/S 신녹산#1T/L-#3M.Tr 1차 CB(7700) 보통점검","신김해S/S 신녹산#1T/L-#3M.Tr 1차 CB(7700) 보통점검","2017-04-20 09:30","2017-04-20 17:30","2017-04-20 09:30","2017-04-20 17:30","당일",null,null,null,201702060079,"-"]
[182,"경남","직할","신김해S/S #3 M.Tr 1차 CB (7772)","신김해S/S #3M.Tr 1차 CB(7772) 보통점검","신김해S/S #3M.Tr 1차 CB(7772) 보통점검","2017-04-21 09:30","2017-04-21 17:30","2017-04-21 09:30","2017-04-21 17:30","당일",null,null,null,201702060080,"-"]
[183,"경남","직할","신김해S/S #5M.Tr 1차 CB (7672)","신김해S/S #5M.Tr 1차 CB(7672) 보통점검","신김해S/S #5M.Tr 1차 CB(7672) 보통점검","2017-04-24 09:30","2017-04-24 17:30","2017-04-24 09:30","2017-04-24 17:30","당일",null,null,null,201702060081,"-"]
[184,"경남","직할","신김해S/S TIE-#5M.Tr 1차 CB (7600)","신김해S/S TIE-#5M.Tr 1차 CB(7600) 보통점검","신김해S/S TIE-#5M.Tr 1차 CB(7600) 보통점검","2017-04-25 09:30","2017-04-25 17:30","2017-04-25 09:30","2017-04-25 17:30","당일",null,null,null,201702060084,"-"]
[185,"경남","직할","신김해삼천포화력#2 T/L","신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체공사","345kV 신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체(214~228)","2017-04-29 07:00","2017-05-12 19:00","2017-04-29 07:00","2017-05-12 19:00","연속",null,null,null,201702070318,"-"]
[186,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","의령S/T~1호 인출변경, 43, 136호 연가해제","2017-04-24 07:00","2017-04-25 20:00","2017-04-24 07:00","2017-04-25 20:00","연속",null,null,null,201702070124,"-"]
[187,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","의령S/T~1호 인출변경, 43, 136호 연가해제, 임시136호 설치","2017-04-26 07:00","2017-04-30 20:00","2017-04-26 07:00","2017-04-30 20:00","연속",null,null,null,201702070125,"-"]
[188,"경남","진주","하동T/P #2 M.Tr 1차 CB (7272)","하동T/P #2 M.Tr 1차 CB 1차 CB(7272) 보통점검","하동T/P #2 M.Tr 1차 CB 1차 CB(7272) 보통점검","2017-04-28 09:30","2017-04-28 18:30","2017-04-28 09:30","2017-04-28 18:30","당일",null,null,null,201702030058,"-"]
[189,"경남","진주","하동T/P TIE-#2 M.Tr 1차 CB (7200)","하동T/P TIE-#2 M.Tr 1차 CB 1차 CB(7200) 보통점검","하동T/P TIE-#2 M.Tr 1차 CB 1차 CB(7200) 보통점검","2017-04-27 09:30","2017-04-27 18:30","2017-04-27 09:30","2017-04-27 18:30","당일",null,null,null,201702030057,"-"]
[190,"경남","진주","하동T/P #5 M.Tr 1차 CB (7572)","하동T/P #5 M.Tr 1차 CB 1차 CB(7572) 정밀점검","하동T/P #5 M.Tr 1차 CB 1차 CB(7572) 정밀점검","2017-04-20 09:30","2017-04-22 18:30","2017-04-20 09:30","2017-04-22 18:30","연속",null,null,null,201702030056,"-"]
[191,"경남","진주","하동T/P 의령-하동TP#2T/L-#5 M.Tr 1차 CB (7500)","의령-하동TP#2T/L-#5 M.Tr 1차 CB(7500) 정밀점검","의령-하동TP#2T/L-#5 M.Tr 1차 CB(7500) 정밀점검","2017-04-17 09:30","2017-04-19 18:30","2017-04-17 09:30","2017-04-19 18:30","연속",null,null,null,201702030055,"-"]
[192,"경남","통영","삼천포T/P 70-71-0 SEC CB (70-71-0)","삼천포T/P 345kV 70-71 BUS SEC CB 보통점검","삼천포T/P 345kV 70-71 BUS SEC CB 보통점검","2017-04-02 09:30","2017-04-02 18:30","2017-04-02 09:30","2017-04-02 18:30","당일",null,null,null,201702070085,"-"]
[193,"경남","통영","신마산삼천포화력#2 T/L","삼천포T/P 345kV 신마산-삼천포화력#2T/L CB 보통점검","삼천포T/P 345kV 신마산-삼천포화력#2T/L CB 보통점검 삼천포T/P 345kV 신마산-삼천포화력#2T/L LA,PT 보통점검","2017-04-04 09:30","2017-04-04 18:30","2017-04-04 09:30","2017-04-04 18:30","당일",null,null,null,201702120055,"-"]
[194,"경남","통영","삼천포T/P 75-76-0 SEC CB (75-76-0)","삼천포T/P 345kV 75-76 BUS SEC CB 보통점검","삼천포T/P 345kV 75-76 BUS SEC CB 보통점검","2017-04-09 09:30","2017-04-09 18:30","2017-04-09 09:30","2017-04-09 18:30","당일",null,null,null,201702070086,"-"]
[195,"경남","통영","신고성S/S #2 M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","3차 예비모선 배선관련 안전이격","2017-04-03 09:00","2017-04-04 18:00","2017-04-03 09:00","2017-04-04 18:00","연속",null,null,null,201701100021,"-"]
[196,"경남","통영","신고성S/S #4M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","23kV 30Mvar 3Bank 설치","2017-04-05 09:00","2017-04-17 18:00","2017-04-05 09:00","2017-04-17 18:00","연속",null,null,null,201701100026,"-"]
[197,"경남","함안","북경남서대구#2 T/L","345kV 북경남-서대구#2 T/L 초기점검","No.1-113 초기점검","2017-04-04 08:30","2017-04-15 18:00","2017-04-04 08:30","2017-04-15 18:00","연속",null,null,null,201702060017,"-"]
[198,"경남","함안","신옥천북경남 T/L","345kV 신옥천-북경남 T/L 초기점검","No.1-113 초기점검","2017-04-04 08:30","2017-04-15 18:00","2017-04-04 08:30","2017-04-15 18:00","연속",null,null,null,201702060015,"-"]
[199,"경남","함안","북경남서대구#1 T/L","345kV 북경남-서대구#1 T/L 초기점검","No.1-113 초기점검","2017-04-17 08:30","2017-04-28 18:00","2017-04-17 08:30","2017-04-28 18:00","연속",null,null,null,201702060023,"-"]
[200,"경남","함안","북경남무주양수 T/L","345kV 북경남-무주양수 T/L 초기점검","No.1-113 초기점검","2017-04-17 08:30","2017-04-28 18:00","2017-04-17 08:30","2017-04-28 18:00","연속",null,null,null,201702060024,"-"]
[201,"경남","함안","신마산S/S #2 M.Tr A","신마산S/S #2M.Tr 변압기 정밀점검","신마산S/S #2M.Tr 변압기 정밀점검 신마산S/S #2M.Tr OLTC 정밀점검","2017-04-24 08:00","2017-05-03 18:30","2017-04-24 08:00","2017-05-03 18:30","연속",null,null,null,201702070512,"-"]
[202,"경남","함안","신마산S/S #1 M.Tr A","신마산S/S #1M.Tr 하자점검","신마산S/S #1M.Tr 하자점검 2차 LA 보통점검 3차 LA 하자점검 4179,4184 VCB 보통점검","2017-04-19 09:30","2017-04-21 17:30","2017-04-19 09:30","2017-04-21 17:30","연속",null,null,null,201702070523,"-"]

{"sheet":"154송부","index":2,"n_rows":425,"n_cols":16,"rows_kept":425,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","화양광장 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (광장S/S 화양광장T/L)","2017-04-11 10:00","2017-04-11 17:00","2017-04-11T10:00:00","2017-04-11T17:00:00","당일",null,null,null,201702160390,"-"]
[2,"서울","성동","미금광장 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (광장S/S 미금광장T/L)","2017-04-07 10:00","2017-04-07 17:00","2017-04-07T10:00:00","2017-04-07T17:00:00","당일",null,null,null,201702160389,"-"]
[3,"서울","성동","성수뚝도#1 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (뚝도S/S 성수뚝도#1T/L)","2017-04-12 10:00","2017-04-12 17:00","2017-04-12T10:00:00","2017-04-12T17:00:00","당일",null,null,null,201702160393,"-"]
[4,"서울","성동","성수뚝도#2 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (뚝도S/S 성수뚝도#2T/L)","2017-04-13 10:00","2017-04-13 17:00","2017-04-13T10:00:00","2017-04-13T17:00:00","당일",null,null,null,201702160392,"-"]
[5,"서울","성동","성동마장#1 T/L","17년 마장S/S 성동마장#1T/L GIS 대체공사","17년 마장S/S 성동마장#1T/L GIS 대체공사","2017-04-12 09:30","2017-05-02 18:00","2017-04-12T09:30:00","2017-05-02T18:00:00","연속",null,null,null,201702160151,"-"]
[6,"서울","성동","성동S/S 154kV #65 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #3M.Tr 2차)","2017-04-03 18:00","2017-04-04 18:00","2017-04-03T18:00:00","2017-04-04T18:00:00","연속",null,null,null,201702160386,"-"]
[7,"서울","성동","성동S/S 154kV #60 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #3M.Tr 2차)","2017-04-03 09:00","2017-04-04 18:00","2017-04-03T09:00:00","2017-04-04T18:00:00","당일",null,null,null,201702160385,"-"]
[8,"서울","성동","성동S/S 154kV #61 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #4M.Tr 2차)","2017-04-05 09:30","2017-04-06 18:00","2017-04-05T09:30:00","2017-04-06T18:00:00","당일",null,null,null,201702160387,"-"]
[9,"서울","성동","성동S/S 154kV #66 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #4M.Tr 2차)","2017-04-05 18:00","2017-04-06 18:00","2017-04-05T18:00:00","2017-04-06T18:00:00","연속",null,null,null,201702160388,"-"]
[10,"서울","중부","중부당인리#2 T/L","2017년 중부PO 170kV GIS 정밀점검공사","당인리S/S 중부-당인리#2T/L GIS(647) 정밀점검","2017-04-06 10:00","2017-04-08 18:00","2017-04-27T10:00:00","2017-04-29T18:00:00","연속",null,null,null,201702160249,"-"]
[11,"서울","중부","당인리S/S 154kV #60 BUS","2017년 중부PO 170kV GIS 정밀점검공사","당인리S/S 중부-당인리#1T/L GIS 1DS(631) 정밀점검","2017-04-03 10:00","2017-04-04 14:00","2017-04-24T10:00:00","2017-04-25T14:00:00","연속",null,null,null,201702160234,"-"]
[12,"서울","중부","당인리S/S 154kV #65 BUS","2017년 중부PO 170kV GIS 정밀점검공사","당인리S/S 중부-당인리#1T/L GIS 2DS(632) 정밀점검","2017-04-04 14:00","2017-04-05 18:00","2017-04-25T14:00:00","2017-04-26T18:00:00","연속",null,null,null,201702160238,"-"]
[13,"서울","중부","당인리S/S 154kV #60 BUS","2017년 중부PO 170kV GIS 정밀점검공사","당인리S/S 중부-당인리#2T/L GIS 1DS(641) 정밀점검","2017-04-06 10:00","2017-04-07 14:00","2017-04-27T10:00:00","2017-04-28T14:00:00","연속",null,null,null,201702160254,"-"]
[14,"서울","중부","당인리S/S 154kV #65 BUS","2017년 중부PO 170kV GIS 정밀점검공사","당인리S/S 중부-당인리#2T/L GIS 2DS(642) 정밀점검","2017-04-07 14:00","2017-04-08 18:00","2017-04-28T14:00:00","2017-04-29T18:00:00","연속",null,null,null,201702160257,"-"]
[15,"서울","중부","중부당인리#1 T/L","2017년 중부PO 170kV GIS 정밀점검공사","당인리S/S 중부-당인리#1T/L GIS(637) 정밀점검","2017-04-03 10:00","2017-04-05 18:00","2017-04-24T10:00:00","2017-04-26T18:00:00","연속",null,null,null,201702160230,"-"]
[16,"서울","중부","아현서소문 T/L","2017년 중부PO 170kV GIS 정밀점검공사","아현S/S 아현-서소문T/L GIS(627) 정밀점검","2017-04-11 10:00","2017-04-13 18:00","2017-04-11T10:00:00","2017-04-13T18:00:00","연속",null,null,null,201702160263,"-"]
[17,"서울","중부","옥인운니#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","170kV GIS 하자점검","2017-04-04 10:00","2017-04-04 17:00","2017-04-04T10:00:00","2017-04-04T17:00:00","당일",null,null,null,201702130323,"-"]
[18,"서울","중부","옥인운니#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사",3,"2017-04-05 10:00","2017-04-05 17:00","2017-04-05T10:00:00","2017-04-05T17:00:00","당일",null,null,null,201702130324,"-"]
[19,"서울","중부","양주은평#2 T/L","2017년 중부PO 170kV GIS 정밀점검공사","은평S/S 양주-은평#1T/L GIS(627) 정밀점검","2017-04-27 10:00","2017-04-29 18:00","2017-04-06T10:00:00","2017-04-08T18:00:00","연속",null,null,"신뢰도 개선",201702160278,"-"]
[20,"서울","중부","양주은평#1 T/L","2017년 중부PO 170kV GIS 정밀점검공사","은평S/S 양주-은평#1T/L GIS(617) 정밀점검","2017-04-24 10:00","2017-04-26 18:00","2017-04-03T10:00:00","2017-04-05T18:00:00","연속",null,null,"신뢰도 개선",201702160273,"-"]
[21,"서울","직할","불광서대문#2 T/L","'17년 직할 변전협력 총액공사","170kV GIS 및 Line PT 보통점검","2017-04-11 10:00","2017-04-11 19:00","취소","취소","당일",null,null,"신뢰도 개선",201702170119,"-"]
[22,"서울","직할","종로서소문 T/L","'17년 직할 변전협력 총액공사","170kV GIS 초기점검","2017-04-07 10:00","2017-04-07 19:00","2017-04-07T10:00:00","2017-04-07T19:00:00","당일",null,null,null,201702170118,"-"]
[23,"서울","직할","중앙서소문 T/L","'17년 직할 변전협력 총액공사","170kV GIS 초기점검","2017-04-10 10:00","2017-04-10 19:00","2017-04-10T10:00:00","2017-04-10T19:00:00","당일",null,null,null,201702170117,"-"]
[24,"서울","직할","서소문S/S 154kV #1 BUS TIE CB","'17년 직할 변전협력 총액공사","170kV GIS 초기점검","2017-04-11 10:00","2017-04-11 19:00","2017-04-11T10:00:00","2017-04-11T19:00:00","당일",null,null,null,201702170121,"-"]
[25,"서울","직할","원남S/S 154kV #1 BUS TIE CB","'17년 직할 변전협력 총액공사","모선보호반 대체 및 170kV GIS 실리콘 러버 히터 설치","2017-04-18 10:00","2017-04-20 19:00","2017-04-18T10:00:00","2017-04-20T19:00:00","연속",null,null,null,201702170122,"-"]
[26,"남서울","강남","신사S/S 154kV #1 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문","신사S/S 170kV GIS 정밀점검 - 신사S/S 6100 BUS TIE GIS 정밀점검","2017-04-28 10:00","2017-04-29 18:00","취소","취소","연속",null,null,null,201702160145,"-"]
[27,"남서울","강남","신사S/S 154kV #2 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문","- 신사S/S 6100 BUS TIE GIS 정밀점검","2017-04-27 10:00","2017-04-28 10:00","취소","취소","연속",null,null,null,201702160146,"-"]
[28,"남서울","강남","신사S/S 154kV #1 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문","신사S/S 170kV GIS 정밀점검 - 신사S/S 신사-반포#2T/L GIS 정밀점검","2017-04-25 10:00","2017-04-26 18:00","취소","취소","연속",null,null,null,201702160141,"-"]
[29,"남서울","강남","신사S/S 154kV #2 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문","신사S/S 170kV GIS 정밀점검 - 신사S/S 신사-반포#2T/L 정밀점검","2017-04-24 10:00","2017-04-25 10:00","취소","취소","연속",null,null,null,201702160142,"-"]
[30,"남서울","강남","신사S/S 154kV #1 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문","신사S/S 170kV GIS 정밀점검 - 신사S/S 신사-반포#1T/L GIS 정밀점검","2017-04-20 10:00","2017-04-21 18:00","취소","취소","연속",null,null,null,201702160140,"-"]
[31,"남서울","강남","신사S/S 154kV #2 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문","신사S/S 170kV GIS 정밀점검 - 신사S/S 신사-반포#1T/L GIS 정밀점검","2017-04-18 10:00","2017-04-19 18:00","취소","취소","연속",null,null,null,201702160139,"-"]
[32,"남서울","동서울","동서울S/S 154kV #1 BUS TIE CB","새롬제 154kV 모선보호반 성능개선","50BF 로직 개선","2017-04-10 10:00","2017-04-10 18:00","2017-04-10T10:00:00","2017-04-10T18:00:00","당일",null,null,null,201702210016,"○"]
[33,"남서울","동서울","동서울S/S 154kV #2 BUS TIE CB","새롬제 154kV 모선보호반 성능개선","50BF 로직 개선","2017-04-10 10:00","2017-04-10 18:00","2017-04-10T10:00:00","2017-04-10T18:00:00","당일",null,null,null,201702210017,"○"]
[34,"남서울","동서울","동서울송파#1 T/L","154kV동서울-가락(송파)T/L 송전선로 가이설공사","공사구간 : No.5~7 긍장 : 1.25km 철탑 신설 3기, 철거 3기","2017-04-25 08:00","2017-05-01 18:00","2017-04-25T08:00:00","2017-05-01T18:00:00","연속",null,null,null,201702160316,"-"]
[35,"남서울","동서울","동서울가락#1 T/L","154kV동서울-가락(송파)T/L 송전선로 가이설공사","공사구간 : No.5~7 긍장 : 1.25km 철탑 철거 3기, 신설 3기","2017-04-25 08:00","2017-05-01 18:00","2017-04-25T08:00:00","2017-05-01T18:00:00","연속",null,null,null,201702160315,"-"]
[36,"남서울","영등포","가양S/S 154kV #1 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#1T/L)","- 170kV GIS 정밀점검(마곡-가양#1T/L) ※ 병행휴전작업 : 마곡S/S GIS 초기점검","2017-04-10 09:00","2017-04-11 11:00","2017-04-10T09:00:00","2017-04-11T11:00:00","연속",null,null,null,201702130316,"-"]
[37,"남서울","영등포","마곡가양#1 T/L","154kV마곡-가양T/L 지중선로 이설공사","○ 이설 선로명 : 154kV마곡-가양#1T/L ○ 이설 구간 : 맨홀#15-1 ~맨홀#15 - 철거 : 110m, 설치 : 197m ○ 접속개소 : 절연접속 1, 보통접속 1개소.","2017-04-10 09:00","2017-05-02 18:00","2017-04-10T09:00:00","2017-05-02T18:00:00","연속",null,null,"신뢰도개선",201702210190,"-"]
[38,"남서울","영등포","가양S/S 154kV #2 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#1T/L)","- 170kV GIS 정밀점검(마곡-가양#1T/L) ※ 병행휴전작업 : 마곡S/S GIS 초기점검","2017-04-11 11:00","2017-04-12 18:00","2017-04-11T11:00:00","2017-04-12T18:00:00","연속",null,null,null,201702130320,"-"]
[39,"남서울","영등포","가양S/S 154kV #1 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#2T/L)","- 170kV GIS 정밀점검(마곡-가양#2T/L) ※ 병행휴전작업 : 마곡S/S GIS 초기점검","2017-04-13 09:00","2017-04-14 11:00","2017-04-13T09:00:00","2017-04-14T11:00:00","연속",null,null,null,201702130333,"-"]
[40,"남서울","영등포","가양S/S 154kV #2 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#2T/L)","- 170kV GIS 정밀점검(마곡-가양#2T/L) ※ 병행휴전작업 : 마곡S/S GIS 초기점검","2017-04-14 11:00","2017-04-15 18:00","2017-04-14T11:00:00","2017-04-15T18:00:00","연속",null,null,null,201702130336,"-"]
[41,"남서울","영등포","마곡가양#2 T/L","154kV마곡-가양T/L 지중선로 이설공사","1. 케이블철거 : 110m*6상 2. 케이블설치 : 197m*6상 3. 접속개소 : 2개소","2017-04-07 09:00","2017-04-30 18:00","취소","취소","연속",null,null,null,201701180116,"-"]
[42,"남서울","영등포","당인리목동#1 T/L","154kV 당인리-목동#1T/L 정밀점검 시행","철탑 4개(현수애자포함)","2017-04-11 09:00","2017-04-11 13:00","2017-04-11T09:00:00","2017-04-11T13:00:00","당일",null,null,null,201702220178,"-"]
[43,"남서울","영등포","당인리목동#2 T/L","154kV 당인리-목동#2T/L 정밀점검 시행","철탑 4개(송전선로용피뢰기, 현수애자포함)","2017-04-11 13:00","2017-04-11 18:00","2017-04-11T13:00:00","2017-04-11T18:00:00","당일",null,null,null,201702220179,"-"]
[44,"남서울","영등포","영서S/S 154kV #61 T BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","T-BUS 철거","2017-04-17 08:00","2018-06-30 18:00","2017-04-17T08:00:00","2018-06-30T18:00:00","연속",null,null,null,201702160084,"-"]
[45,"남서울","영등포","영서광명#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-04-26 08:00","2017-04-26 18:00","2017-04-26T08:00:00","2017-04-26T18:00:00","당일",null,null,null,201702160107,"-"]
[46,"남서울","영등포","영서시흥#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-04-20 08:00","2017-04-20 18:00","2017-04-20T08:00:00","2017-04-20T18:00:00","당일",null,null,null,201702160108,"-"]
[47,"남서울","영등포","영서S/S 154kV #65 BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","65BUS LA 철거","2017-04-13 13:00","2017-04-14 18:00","2017-04-13T13:00:00","2017-04-14T18:00:00","연속",null,null,null,201702160081,"-"]
[48,"남서울","영등포","영서S/S 154kV #60 T BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","T-BUS 철거","2017-04-17 08:00","2018-06-30 18:00","2017-04-17T08:00:00","2018-06-30T18:00:00","연속",null,null,null,201702160083,"-"]
[49,"남서울","영등포","영서S/S 154kV #60 BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","60BUS LA 철거","2017-04-12 08:00","2017-04-13 13:00","2017-04-12T08:00:00","2017-04-13T13:00:00","연속",null,null,null,201702160076,"-"]
[50,"남서울","영등포","영서시흥#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-04-19 08:00","2017-04-19 18:00","2017-04-19 08:00","2017-04-19 18:00","당일",null,null,null,201702160105,"-"]
[51,"남서울","영등포","영서광명#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-04-25 08:00","2017-04-25 18:00","2017-04-25 08:00","2017-04-25 18:00","당일",null,null,null,201702160100,"-"]
[52,"남서울","직할","신양재사당#2 T/L","17년 가공송전협력회사공사(송전선로 정밀점검)","17년 가공송전협력회사공사(송전선로 정밀점검)","2017-04-20 08:00","2017-04-22 18:00","2017-04-20T08:00:00","2017-04-22T18:00:00","연속",null,null,null,201702170044,"-"]
[53,"남서울","직할","신양재사당#1 T/L","17년 가공송전협력회사공사(송전선로 정밀점검)","17년 가공송전협력회사공사(송전선로 정밀점검)","2017-04-17 08:00","2017-04-19 18:00","2017-04-17T08:00:00","2017-04-19T18:00:00","연속",null,null,null,201702170041,"-"]
[54,"인천","김포","345kV신김포S/S 154kV #1 BUS TIE GIS","신김포S/S 154kV #1 BUS TIE 6100 CB 기기점검","신김포S/S 154kV #1 BUS TIE 6100 CB 기기점검","2017-04-27 09:00","2017-04-27 18:00","2017-04-27T09:00:00","2017-04-27T18:00:00","당일",null,null,null,201702070035,"-"]
[55,"인천","김포","신김포장기#2 T/L","신김포S/S 154kV 신김포장기#2 T/L기기점검","신김포S/S 154kV 신김포장기#2 T/L (627 CB) 기기점검","2017-04-26 10:00","2017-04-26 18:00","2017-04-26T10:00:00","2017-04-26T18:00:00","당일",null,null,null,201702070033,"-"]
[56,"인천","김포","신김포양곡#2 T/L","신김포S/S 154kV 신김포양곡#2 T/L 기기점검","신김포S/S 154kV 신김포양곡#2 T/L (647 CB) 기기점검","2017-04-13 10:00","2017-04-13 18:00","2017-04-13T10:00:00","2017-04-13T18:00:00","당일",null,null,null,201702210011,"-"]
[57,"인천","김포","신김포양곡#1 T/L","신김포S/S 154kV 신김포양곡#1 T/L 기기점검","신김포S/S 154kV 신김포양곡#1 T/L (637 CB) 기기점검","2017-04-12 10:00","2017-04-12 18:00","2017-04-12T10:00:00","2017-04-12T18:00:00","당일",null,null,null,201702210010,"-"]
[58,"인천","김포","신김포장기#1 T/L","신김포S/S 154kV 신김포장기#1 T/L기기점검","신김포S/S 154kV 신김포장기#1 T/L (617 CB) 기기점검","2017-04-25 10:00","2017-04-25 18:00","2017-04-25T10:00:00","2017-04-25T18:00:00","당일",null,null,null,201702070031,"-"]
[59,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 북시화서시화#2T/L GIS 정밀점검","북시화S/S 북시화서시화#2T/L GIS 정밀점검","2017-04-14 14:00","2017-04-15 18:00","2017-04-14T14:00:00","2017-04-15T18:00:00","연속",null,null,null,201702130307,"-"]
[60,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 북시화서시화#2T/L GIS 정밀점검","북시화S/S 북시화서시화#2T/L GIS 정밀점검","2017-04-13 08:00","2017-04-14 14:00","2017-04-13T08:00:00","2017-04-14T14:00:00","연속",null,null,null,201702130306,"-"]
[61,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 북시화서시화#1T/L GIS 정밀점검","북시화S/S 북시화서시화#1T/L GIS 정밀점검","2017-04-11 14:00","2017-04-12 18:00","2017-04-11T14:00:00","2017-04-12T18:00:00","연속",null,null,null,201702130276,"-"]
[62,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 북시화서시화#1T/L GIS 정밀점검","북시화S/S 북시화서시화#1T/L GIS 정밀점검","2017-04-10 08:00","2017-04-11 14:00","2017-04-10T08:00:00","2017-04-11T14:00:00","연속",null,null,null,201702130274,"-"]
[63,"인천","시흥","북시화서시화#1 T/L","북시화S/S 북시화서시화#1T/L GIS 정밀점검","북시화S/S 북시화서시화#1T/L GIS 정밀점검","2017-04-10 08:00","2017-04-12 18:00","2017-04-10T08:00:00","2017-04-12T18:00:00","연속",null,null,null,201702130277,"-"]
[64,"인천","시흥","북시화서시화#2 T/L","북시화S/S 북시화서시화#2T/L GIS 정밀점검","북시화S/S 북시화서시화#2T/L GIS 정밀점검","2017-04-13 08:00","2017-04-15 18:00","2017-04-13T08:00:00","2017-04-15T18:00:00","연속",null,null,null,201702130308,"-"]
[65,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 신시흥북시화#2 T/L GIS 정밀점검","신시흥#2S/S 신시흥북시화#2 T/L GIS 정밀점검","2017-04-21 14:00","2017-04-22 18:00","2017-04-21T14:00:00","2017-04-22T18:00:00","연속",null,null,null,201702130335,"-"]
[66,"인천","시흥","신시흥#2S/S 154kV #68 BUS","신시흥#2S/S 신시흥북시화#2 T/L GIS 정밀점검","신시흥#2S/S 신시흥북시화#2 T/L GIS 정밀점검","2017-04-20 08:00","2017-04-21 14:00","2017-04-20T08:00:00","2017-04-21T14:00:00","연속",null,null,null,201702130334,"-"]
[67,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 154kV #66 Sh.C GIS 정밀점검","신시흥#2S/S 154kV #66 Sh.C GIS 정밀점검","2017-04-18 14:00","2017-04-19 18:00","2017-04-18T14:00:00","2017-04-19T18:00:00","연속",null,null,null,201702130314,"-"]
[68,"인천","시흥","신시흥#2S/S 154kV #68 BUS","신시흥#2S/S 154kV #66 Sh.C GIS 정밀점검","신시흥#2S/S 154kV #66 Sh.C GIS 정밀점검","2017-04-17 08:00","2017-04-18 14:00","2017-04-17T08:00:00","2017-04-18T14:00:00","연속",null,null,null,201702130313,"-"]
[69,"인천","시흥","신시흥#2S/S 154kV #66 Sh.C GIS","신시흥#2S/S 154kV #66 Sh.C GIS 정밀점검","신시흥#2S/S 154kV #66 Sh.C GIS 정밀점검","2017-04-17 08:00","2017-04-19 18:00","2017-04-17T08:00:00","2017-04-19T18:00:00","연속",null,null,null,201702130311,"-"]
[70,"인천","시흥","신시흥#2S/S 154kV #68 BUS","신시흥#2S/S 신시흥북시화#1 T/L GIS 정밀점검","신시흥#2S/S 신시흥북시화#1 T/L GIS 정밀점검","2017-04-24 08:00","2017-04-25 14:00","2017-04-24T08:00:00","2017-04-25T14:00:00","연속",null,null,null,201702130338,"-"]
[71,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 신시흥북시화#1 T/L GIS 정밀점검","신시흥#2S/S 신시흥북시화#1 T/L GIS 정밀점검","2017-04-25 14:00","2017-04-26 18:00","2017-04-25T14:00:00","2017-04-26T18:00:00","연속",null,null,null,201702130339,"-"]
[72,"인천","시흥","신시흥#2S/S 154kV #67 BUS","신시흥#2S/S 신시흥시화#1 T/L GIS 정밀점검","신시흥#2S/S 신시흥시화#1 T/L GIS 정밀점검","2017-04-27 08:00","2017-04-28 14:00","2017-04-27T08:00:00","2017-04-28T14:00:00","연속",null,null,null,201702130344,"-"]
[73,"인천","시흥","신시흥#2S/S 154kV #62 BUS","신시흥#2S/S 신시흥시화#1 T/L GIS 정밀점검","신시흥#2S/S 신시흥시화#1 T/L GIS 정밀점검","2017-04-28 14:00","2017-04-29 18:00","2017-04-28T14:00:00","2017-04-29T18:00:00","연속",null,null,null,201702130345,"-"]
[74,"인천","시흥","신시흥북시화#2 T/L","신시흥#2S/S 신시흥북시화#2 T/L GIS 정밀점검","신시흥#2S/S 신시흥북시화#2 T/L GIS 정밀점검","2017-04-20 08:00","2017-04-22 18:00","2017-04-20T08:00:00","2017-04-22T18:00:00","연속",null,null,null,201702130332,"-"]
[75,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S 신시흥북시화#1 T/L GIS 정밀점검","신시흥#2S/S 신시흥북시화#1 T/L GIS 정밀점검","2017-04-24 08:00","2017-04-26 18:00","2017-04-24T08:00:00","2017-04-26T18:00:00","연속",null,null,null,201702130337,"-"]
[76,"인천","시흥","신시흥시화#1 T/L","신시흥#2S/S 신시흥시화#1 T/L GIS 정밀점검","신시흥#2S/S 신시흥시화#1 T/L GIS 정밀점검","2017-04-27 08:00","2017-04-29 18:00","2017-04-27T08:00:00","2017-04-29T18:00:00","연속",null,null,null,201702130341,"-"]
[77,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 신시흥오봉T/L GIS 정밀점검","오봉S/S 신시흥오봉T/L GIS 정밀점검","2017-04-03 08:00","2017-04-04 14:00","2017-04-03T08:00:00","2017-04-04T14:00:00","연속",null,null,null,201702130258,"-"]
[78,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 도림오봉T/L GIS 정밀점검","오봉S/S 도림오봉T/L GIS 정밀점검","2017-04-06 08:00","2017-04-07 14:00","2017-04-06T08:00:00","2017-04-07T14:00:00","연속",null,null,null,201702130262,"-"]
[79,"인천","시흥","오봉S/S 154kV #1 BUS","오봉S/S 도림오봉T/L GIS 정밀점검","오봉S/S 도림오봉T/L GIS 정밀점검","2017-04-07 14:00","2017-04-08 18:00","2017-04-07T14:00:00","2017-04-08T18:00:00","연속",null,null,null,201702130263,"-"]
[80,"인천","시흥","신시흥오봉 T/L","오봉S/S 신시흥오봉T/L GIS 정밀점검","오봉S/S 신시흥오봉T/L GIS 정밀점검","2017-04-03 08:00","2017-04-05 18:00","취소","취소","연속",null,null,"신뢰도 개선",201702130260,"-"]
[81,"인천","시흥","도림오봉 T/L","오봉S/S 도림오봉T/L GIS 정밀점검","오봉S/S 도림오봉T/L GIS 정밀점검","2017-04-06 08:00","2017-04-08 18:00","취소","취소","연속",null,null,"신뢰도 개선",201702130261,"-"]
[82,"인천","시흥","오봉S/S 154kV #1 BUS","오봉S/S 신시흥오봉T/L GIS 정밀점검","오봉S/S 신시흥오봉T/L GIS 정밀점검","2017-04-04 14:00","2017-04-05 18:00","2017-04-04T14:00:00","2017-04-05T18:00:00","연속",null,null,null,201702130259,"-"]
[83,"인천","인천","신가좌S/S 154kV #60 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - #61M.Tr 1차 GIS 관련 모선휴전","2017-04-18 09:00","2017-04-18 18:00","2017-04-18T09:00:00","2017-04-18T18:00:00","연속",null,null,null,201702200060,"-"]
[84,"인천","인천","신가좌S/S 154kV #65 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - #61M.Tr 1차 GIS 관련 모선휴전","2017-04-19 09:00","2017-04-19 18:00","2017-04-19T09:00:00","2017-04-19T18:00:00","연속",null,null,null,201702200061,"-"]
[85,"인천","인천","신가좌S/S 154kV #61 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - #62M.Tr 1차 GIS 관련 모선휴전","2017-04-24 09:00","2017-04-24 18:00","2017-04-24T09:00:00","2017-04-24T18:00:00","연속",null,null,null,201702200062,"-"]
[86,"인천","인천","신가좌S/S 154kV #66 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - #62M.Tr 1차 GIS 관련 모선휴전","2017-04-25 09:00","2017-04-25 18:00","2017-04-25T09:00:00","2017-04-25T18:00:00","연속",null,null,null,201702200063,"-"]
[87,"인천","인천","신현S/S 154kV #2 BUS","154kV 신현-포스코CC #2T/L M/H#4~#5 지장이설공사","154kV 신현-포스코CC #2T/L 지장이설관련 상체크시험","2017-04-12 13:00","2017-04-12 18:00","2017-04-12T13:00:00","2017-04-12T18:00:00","당일",null,null,null,201701130014,"-"]
[88,"인천","인천","신경서영종#2 T/L","154kV 영종-중산 지중T/L 건설공사","154kV XLPE 2000㎟(평활), 2C-6.8km (154kV 신경서-영종#2T/L 직결)","2017-04-03 09:00","2017-04-18 18:00","2017-04-03T09:00:00","2017-04-28T18:00:00","연속",null,null,null,201701310273,"-"]
[89,"인천","인천","인천남인천#1 T/L","인천S/S 인천남인천#1T/L GIS 보통점검 및 보조계전기 교체공사","인천S/S 인천남인천#1T/L GIS 보통점검 및 보조계전기 교체공사 - GIS 보통점검 및 보조계전기 교체공사","2017-04-14 09:00","2017-04-14 18:00","2017-04-14T09:00:00","2017-04-14T18:00:00","당일",null,null,null,201702130401,"-"]
[90,"인천","인천","인천S/S 154kV #1 BUS TIE GIS","인천S/S 6100 BUS TIE GIS 보통점검 및 보조계전기 교체","인천S/S 154kV 6100 BUS TIE GIS 보통점검 및 보조계전기 교체 - 6100 BUS TIE GIS 보통점검 및 보조계전기 교체공사","2017-04-28 09:00","2017-04-28 18:00","2017-04-28T09:00:00","2017-04-28T18:00:00","당일",null,null,null,201701130054,"-"]
[91,"인천","인천","인천남인천#2 T/L","인천S/S 인천남인천#2T/L GIS 보통점검 및 보조계전기 교체공사","인천S/S 인천남인천#2T/L GIS 보통점검 및 보조계전기 교체공사 - GIS 보통점검 및 보조계전기 교체공사","2017-04-17 09:00","2017-04-17 18:00","2017-04-17T09:00:00","2017-04-17T18:00:00","당일",null,null,null,201702130402,"-"]
[92,"인천","인천","인천CC S/Y 154kV #1 BUS TIE GIS","인천CC 6100BUSTIE GIS 보통점검 공사","인천CC 6100BUSTIE GIS 보통점검 공사 - GIS 보통점검 공사 등","2017-04-18 09:00","2017-04-18 18:00","2017-04-18T09:00:00","2017-04-18T18:00:00","당일",null,null,null,201702130404,"-"]
[93,"인천","인천","인천CC S/Y 154kV #2 BUS TIE GIS","인천CC 6200 BUSTIE GIS 보통점검 공사","인천CC 6200 BUSTIE GIS 보통점검 공사 - GIS 보통점검 공사 등","2017-04-20 09:00","2017-04-20 18:00","2017-04-20T09:00:00","2017-04-20T18:00:00","당일",null,null,null,201702130405,"-"]
[94,"인천","인천","인천CC S/Y 60-61 SEC GIS","인천CC 60-61 SEC GIS 보통점검 공사","인천CC 60-61 SEC GIS 보통점검 공사 - GIS 보통점검 공사 등","2017-04-21 09:00","2017-04-21 18:00","2017-04-21T09:00:00","2017-04-21T18:00:00","당일",null,null,null,201702130406,"-"]
[95,"인천","인천","인천CC S/Y 65-66 SEC GIS","인천CC 65-66 SEC GIS 보통점검 공사","인천CC 65-66 SEC GIS 보통점검 공사 - GIS 보통점검 공사 등","2017-04-24 09:00","2017-04-24 18:00","2017-04-24T09:00:00","2017-04-24T18:00:00","당일",null,null,null,201702130407,"-"]
[96,"인천","인천","인천CC북인천#1 T/L","인천CC 인천CC북인천#1T/L GIS 보통점검 공사","인천CC 인천CC북인천#1T/L GIS 보통점검 공사 - GIS 보통점검 공사 등","2017-04-25 09:00","2017-04-25 18:00","2017-04-25T09:00:00","2017-04-25T18:00:00","당일",null,null,null,201702130410,"-"]
[97,"인천","인천","인천CC북인천#2 T/L","인천CC 인천CC북인천#2T/L GIS 보통점검 공사","인천CC 인천CC북인천#2T/L GIS 보통점검 공사 - GIS 보통점검 공사 등","2017-04-26 09:00","2017-04-26 18:00","2017-04-26T09:00:00","2017-04-26T18:00:00","당일",null,null,null,201702130411,"-"]
[98,"인천","인천","주안S/S 154kV #1 BUS TIE GIS","주안S/S 6100 BUSTIE GIS 조작시험","주안S/S 6100 BUSTIE GIS 조작시험 - GIS 조작시험 등","2017-04-27 09:00","2017-04-27 14:00","2017-04-27T09:00:00","2017-04-27T14:00:00","당일",null,null,null,201702130417,"-"]
[99,"인천","직할","계양북인천 T/L","스페이서 간격조정 공사","스페이서 간격조정 공사(28경간)","2017-04-17 08:00","2017-04-20 18:00","2017-04-17T08:00:00","2017-04-20T18:00:00","매일",null,null,null,201702140436,"-"]
[100,"인천","직할","계양원창 T/L","계양S/S 계양원창T/L 차단기 아크접촉자 교체","계양S/S 계양원창T/L 차단기 아크접촉자 교체","2017-04-05 09:00","2017-04-06 18:00","2017-04-05T09:00:00","2017-04-06T18:00:00","연속",null,null,null,201702160204,"-"]
[101,"인천","직할","임학계양#2 T/L","스페이서 간격조정 공사","스페이서 간격조정 공사(28경간)","2017-04-17 08:00","2017-04-20 18:00","2017-04-17T08:00:00","2017-04-20T18:00:00","매일",null,null,null,201702140437,"-"]
[102,"인천","직할","부천S/S 154kV #1 BUS","부천S/S #4M.Tr 1차 GIS 정밀점검","부천S/S #4M.Tr 1차 GIS 정밀점검","2017-04-26 08:00","2017-04-27 10:00","2017-04-26T08:00:00","2017-04-27T10:00:00","연속",null,null,null,201702140715,"-"]
[103,"인천","직할","부천S/S 154kV #2 BUS","부천S/S #3M.Tr 1차 GIS 정밀점검","부천S/S #3M.Tr 1차 GIS 정밀점검","2017-04-20 10:00","2017-04-20 20:00","2017-04-20T10:00:00","2017-04-20T20:00:00","연속",null,null,null,201702140712,"-"]
[104,"인천","직할","부천S/S 154kV #1 BUS","부천S/S #3M.Tr 1차 GIS 정밀점검","부천S/S #3M.Tr 1차 GIS 정밀점검","2017-04-19 08:00","2017-04-20 10:00","2017-04-19T08:00:00","2017-04-20T10:00:00","연속",null,null,null,201702140710,"-"]
[105,"인천","직할","부천S/S 154kV #1 BUS","부천S/S #2M.Tr 1차 GIS 정밀점검","부천S/S #2M.Tr 1차 GIS 정밀점검","2017-04-12 08:00","2017-04-13 10:00","2017-04-12T08:00:00","2017-04-13T10:00:00","연속",null,null,null,201702140693,"-"]
[106,"인천","직할","부천S/S 154kV #2 BUS","부천S/S #1M.Tr 1차 GIS 정밀점검","부천S/S #1M.Tr 1차 GIS 정밀점검","2017-04-06 10:00","2017-04-06 20:00","2017-04-06T10:00:00","2017-04-06T20:00:00","연속",null,null,null,201702140686,"-"]
[107,"인천","직할","부천S/S 154kV #1 BUS","부천S/S #1M.Tr 1차 GIS 정밀점검","부천S/S #1M.Tr 1차 GIS 정밀점검","2017-04-05 08:00","2017-04-06 10:00","2017-04-05T08:00:00","2017-04-06T10:00:00","연속",null,null,null,201702140684,"-"]
[108,"인천","직할","부천S/S 154kV #2 BUS","부천S/S #4M.Tr 1차 GIS 정밀점검","부천S/S #4M.Tr 1차 GIS 정밀점검","2017-04-27 10:00","2017-04-27 20:00","2017-04-27T10:00:00","2017-04-27T20:00:00","연속",null,null,null,201702140716,"-"]
[109,"인천","직할","부천S/S 154kV #1 BUS","부천S/S #5M.Tr 1차 GIS 정밀점검","부천S/S #5M.Tr 1차 GIS 정밀점검","2017-04-28 08:00","2017-04-29 10:00","2017-04-28T08:00:00","2017-04-29T10:00:00","연속",null,null,null,201702140718,"-"]
[110,"인천","직할","부천S/S 154kV #2 BUS","부천S/S #5M.Tr 1차 GIS 정밀점검","부천S/S #5M.Tr 1차 GIS 정밀점검","2017-04-29 10:00","2017-04-29 20:00","2017-04-29T10:00:00","2017-04-29T20:00:00","연속",null,null,null,201702140719,"-"]
[111,"인천","직할","부천S/S 154kV #2 BUS","부천S/S #2M.Tr 1차 GIS 정밀점검","부천S/S #2M.Tr 1차 GIS 정밀점검","2017-04-13 10:00","2017-04-13 20:00","2017-04-13T10:00:00","2017-04-13T20:00:00","연속",null,null,null,201702140702,"-"]
[112,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-04-07 08:00","2017-04-08 10:00","취소","취소","연속",null,null,"신뢰도 개선",201702130408,"-"]
[113,"인천","직할","신부평중동#1 T/L","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-04-07 08:00","2017-04-08 20:00","취소","취소","연속",null,null,null,201702130403,"-"]
[114,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S #62M.Tr 1차 GIS 정밀점검","신부평S/S #62M.Tr 1차 GIS 정밀점검","2017-04-04 10:00","2017-04-04 20:00","취소","취소","연속",null,null,null,201702130396,"-"]
[115,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S #62M.Tr 1차 GIS 정밀점검","신부평S/S #62M.Tr 1차 GIS 정밀점검","2017-04-03 08:00","2017-04-04 10:00","취소","취소","연속",null,null,null,201702130395,"-"]
[116,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-04-02 10:00","2017-04-02 20:00","취소","취소","연속",null,null,null,201702130418,"-"]
[117,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-04-01 08:00","2017-04-02 10:00","취소","취소","연속",null,null,null,201702130416,"-"]
[118,"인천","직할","신부평부천#2 T/L","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-04-01 08:00","2017-04-02 20:00","취소","취소","연속",null,null,null,201702130415,"-"]
[119,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-04-25 10:00","2017-04-25 20:00","취소","취소","연속",null,null,null,201702130436,"-"]
[120,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-04-24 08:00","2017-04-25 10:00","취소","취소","연속",null,null,null,201702130435,"-"]
[121,"인천","직할","신부평S/S 154kV #1 BUS TIE GIS","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-04-24 08:00","2017-04-25 20:00","취소","취소","연속",null,null,null,201702130434,"-"]
[122,"인천","직할","신부평S/S 154kV #66 BUS","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-04-22 10:00","2017-04-22 20:00","취소","취소","연속",null,null,null,201702130433,"-"]
[123,"인천","직할","신부평S/S 65-66 SEC GIS","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-04-21 08:00","2017-04-22 20:00","취소","취소","연속",null,null,null,201702130431,"-"]
[124,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-04-21 08:00","2017-04-22 10:00","취소","취소","연속",null,null,null,201702130432,"-"]
[125,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-04-18 10:00","2017-04-18 20:00","취소","취소","연속",null,null,null,201702130429,"-"]
[126,"인천","직할","신부평S/S 60-61 SEC GIS","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-04-17 08:00","2017-04-18 20:00","취소","취소","연속",null,null,null,201702130427,"-"]
[127,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-04-17 08:00","2017-04-18 10:00","취소","취소","연속",null,null,null,201702130428,"-"]
[128,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-04-11 10:00","2017-04-11 20:00","취소","취소","연속",null,null,null,201702130414,"-"]
[129,"인천","직할","신부평부천#1 T/L","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-04-10 08:00","2017-04-11 20:00","취소","취소","연속",null,null,null,201702130412,"-"]
[130,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-04-10 08:00","2017-04-11 10:00","취소","취소","연속",null,null,null,201702130413,"-"]
[131,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-04-08 10:00","2017-04-08 20:00","취소","취소","연속",null,null,null,201702130409,"-"]
[132,"경기북부","구리","미금구리#2 T/L","154kV 구리S/S 미금구리#2T/L GIS 정밀점검","CB,DS 정밀점검","2017-04-27 09:00","2017-04-29 18:00","2017-04-27T09:00:00","2017-04-29T18:00:00","연속",null,null,null,201702170082,"-"]
[133,"경기북부","구리","미금덕소#2 T/L","154kV미금덕소#2T/L OPGW 증설공사","대상 : 154kV미금덕소#2T/L 내용 : AWS 97SQ를 OPGW 100SQ 로 교체","2017-04-10 09:00","2017-04-16 18:00","2017-04-10T09:00:00","2017-04-16T18:00:00","연속",null,null,null,201702100198,"-"]
[134,"경기북부","구리","덕소별내#1 T/L","154kV 덕소별내#1 T/L 정밀점검","154kV 덕소별내#1 T/L 송전선로 정밀점검(철탑 및 충전부 등)","2017-04-24 08:00","2017-04-26 18:00","2017-04-24T08:00:00","2017-04-26T18:00:00","연속",null,null,null,201702140011,"○"]
[135,"경기북부","구리","별내도봉 T/L","154kV 별내도봉 T/L 정밀점검","154kV 별내도봉 T/L 정밀점검","2017-04-13 08:00","2017-04-15 18:00","취소","취소","연속",null,null,"신뢰도 개선",201702140008,"○"]
[136,"경기북부","구리","별내진접 T/L","일진제 조립식접속함(PMJ) 교체공사","대상 : 154kV 별내-진접T/L J/B#1~#3 총 3개소(9상) 내용 : 구형 중간접속함 전량 교체(R-Type→Flat-Type)","2017-04-17 08:00","2017-04-23 18:00","취소","취소","연속",null,null,"신뢰도 개선",201702070397,"-"]
[137,"경기북부","구리","신포천덕계#1 T/L","170kV 신포천-덕계 #1T/L GIS 보통점검","170kV 신포천-덕계 #1T/L GIS 보통점검","2017-04-04 10:00","2017-04-04 18:00","2017-04-04T10:00:00","2017-04-04T18:00:00","당일",null,null,null,201701160177,"-"]
[138,"경기북부","구리","신포천덕계#2 T/L","170kV 신포천-덕계 #2T/L GIS 보통점검 및 유면계 보수","170kV 신포천-덕계 #2T/L GIS 보통점검 및 유면계 보수","2017-04-05 10:00","2017-04-05 18:00","2017-04-05T10:00:00","2017-04-05T18:00:00","당일",null,null,null,201701160168,"-"]
[139,"경기북부","구리","지제S/S 문막-지제T/L CB","170kV 문막-지제T/L GIS 보통점검","170kV 문막-지제T/L GIS 보통점검","2017-04-11 10:00","2017-04-11 18:00","2017-04-11T10:00:00","2017-04-11T18:00:00","당일",null,null,null,201702140242,"-"]
[140,"경기북부","구리","도봉진접 T/L","154kV 도봉진접 T/L 정밀점검","154kV 도봉진접 T/L 정밀점검","2017-04-10 08:00","2017-04-12 18:00","취소","취소","연속",null,null,"신뢰도 개선",201702140007,"-"]
[141,"경기북부","구리","청평P/P 남춘천-청평PPT/L CB","170kV 남춘천-청평PP T/L GIS 보통점검","170kV 남춘천-청평PP T/L GIS 보통점검","2017-04-19 10:00","2017-04-19 18:00","2017-04-19T10:00:00","2017-04-19T18:00:00","당일",null,null,null,201702140245,"-"]
[142,"경기북부","구리","청평P/P 서홍천-청평PPT/L CB","170kV 서홍천-청평PP T/L GIS 보통점검","170kV 서홍천-청평PP T/L GIS 보통점검","2017-04-18 10:00","2017-04-18 18:00","2017-04-18T10:00:00","2017-04-18T18:00:00","당일",null,null,null,201702140244,"-"]
[143,"경기북부","직할","양주쌍문#1 T/L","154kV 양주-쌍문#1T/L 정밀점검","154kV 양주-쌍문#1T/L No.1~27 정밀점검","2017-04-10 09:00","2017-04-15 18:00","2017-04-10T09:00:00","2017-04-15T18:00:00","연속",null,null,null,201702170094,"-"]
[144,"경기북부","직할","양주녹양#1 T/L","직할 변전총액공사 (양주-녹양#1T/L 보호반 교체)","직할 변전총액공사 (양주-녹양#1T/L 보호반 교체) 양주S/S 양주-녹양#1T/L 녹양S/S 양주-녹양#1T/L","2017-04-24 10:00","2017-04-28 18:00","2017-04-24T10:00:00","2017-04-28T18:00:00","연속",null,null,null,201702140229,"-"]
[145,"경기북부","직할","양주쌍문#2 T/L","154kV 양주-쌍문#2T/L 정밀점검","154kV 양주-쌍문#2T/L No.1~27 정밀점검","2017-04-17 09:00","2017-04-22 18:00","2017-04-17T09:00:00","2017-04-22T18:00:00","연속",null,null,null,201702170095,"-"]
[146,"경기북부","파주","신파주송포#2 T/L","송포S/S 신파주-송포#2T/L GIS 정밀점검공사","송포S/S 신파주-송포#2T/L GIS 정밀점검공사","2017-04-20 09:00","2017-04-22 18:00","2017-04-20T09:00:00","2017-04-22T18:00:00","연속",null,null,null,201702160356,"-"]
[147,"경기북부","파주","신파주송포#1 T/L","송포S/S 신파주-송포#1T/L GIS 정밀점검공사","송포S/S 신파주-송포#1T/L GIS 정밀점검공사","2017-04-17 09:00","2017-04-19 18:00","2017-04-17T09:00:00","2017-04-19T18:00:00","연속",null,null,null,201702160355,"-"]
[148,"경기","군포","관양평촌#2 T/L","154kV 관양평촌T/L 선도제 보호계전기 오동작방지 대책 시행","154kV 관양평촌#2T/L 선도제 보호계전기 오동작방지 대책 시행 - 제작사 보호계전기 펌웨어 업그레이드 개선","2017-04-17 13:00","2017-04-17 18:00","2017-04-17T13:00:00","2017-04-17T18:00:00","당일",null,null,null,201702060270,"-"]
[149,"경기","군포","서서울S/S 154kV #67 BUS","345kV 서서울S/S 구내전력구 공사","- 구내전력구 파일항타 작업 간섭휴전","2017-04-04 07:00","2017-04-04 18:00","2017-04-04T07:00:00","2017-04-04T18:00:00","당일",null,null,null,201702100413,"-"]
[150,"경기","군포","서서울S/S 154kV #62 BUS","345kV 서서울S/S 구내전력구 공사","- 구내전력구 파일항타 작업 간섭휴전","2017-04-03 07:00","2017-04-03 18:00","2017-04-03T07:00:00","2017-04-03T18:00:00","당일",null,null,null,201702100411,"-"]
[151,"경기","군포","안산C/C 154kV #2 BUS TIE CB","안산복합S/Y 154kV 6200 Bus-TIE 하자점검 공사","안산복합S/Y 154kV 6200 Bus-TIE 하자점검 공사","2017-04-04 09:00","2017-04-04 18:00","2017-04-04T09:00:00","2017-04-04T18:00:00","당일",null,null,null,201702020035,"-"]
[152,"경기","군포","안산C/C 154kV #1 BUS TIE CB","안산복합S/Y 154kV 6100 Bus-TIE 하자점검 공사","안산복합S/Y 154kV 6100 Bus-TIE 하자점검 공사","2017-04-03 09:00","2017-04-03 18:00","2017-04-03T09:00:00","2017-04-03T18:00:00","당일",null,null,null,201702020034,"-"]
[153,"경기","군포","안산CCS안산#3 T/L","안산복합S/Y 154kV 안산안산복합#3T/L 하자점검 공사","안산복합S/Y 154kV 안산안산복합#3T/L 하자점검 공사 목내변전소 병행점검","2017-04-13 09:00","2017-04-13 18:00","2017-04-13T09:00:00","2017-04-13T18:00:00","당일",null,null,null,201702020042,"-"]
[154,"경기","군포","목내안산복합#1 T/L","안산복합S/Y 154kV 목내안산복합#1T/L 하자점검 공사","안산복합S/Y 154kV 목내안산복합#1T/L 하자점검 공사 목내변전소 병행점검","2017-04-07 09:00","2017-04-07 18:00","2017-04-07T09:00:00","2017-04-07T18:00:00","당일",null,null,null,201702020038,"-"]
[155,"경기","군포","안산CCS안산#2 T/L","안산복합S/Y 154kV 안산안산복합#2T/L 하자점검 공사","안산복합S/Y 154kV 안산안산복합#2T/L 하자점검 공사 목내변전소 병행점검","2017-04-12 09:00","2017-04-12 18:00","2017-04-12T09:00:00","2017-04-12T18:00:00","당일",null,null,null,201702020041,"-"]
[156,"경기","군포","안산C/C #60-61 BUS SEC CB","안산복합S/Y 154kV 60-61 SEC CB 하자점검 공사","안산복합S/Y 154kV 60-61 SEC CB 하자점검 공사","2017-04-05 09:00","2017-04-05 18:00","2017-04-05T09:00:00","2017-04-05T18:00:00","당일",null,null,null,201702020036,"-"]
[157,"경기","군포","안산CCS안산#1 T/L","안산복합S/Y 154kV 안산안산복합#1T/L 하자점검 공사","안산복합S/Y 154kV 안산안산복합#1T/L 하자점검 공사 목내변전소 병행점검","2017-04-11 09:00","2017-04-11 18:00","2017-04-11T09:00:00","2017-04-11T18:00:00","당일",null,null,null,201702020040,"-"]
[158,"경기","군포","목내안산복합#2 T/L","안산복합S/Y 154kV 목내안산복합#2T/L 하자점검 공사","안산복합S/Y 154kV 목내안산복합#2T/L 하자점검 공사 목내변전소 병행점검","2017-04-10 09:00","2017-04-10 18:00","2017-04-10T09:00:00","2017-04-10T18:00:00","당일",null,null,null,201702020039,"-"]
[159,"경기","군포","안산C/C #65-66 BUS SEC CB","안산복합S/Y 154kV 65-66 SEC CB 하자점검 공사","안산복합S/Y 154kV 65-66 SEC CB 하자점검 공사","2017-04-06 09:00","2017-04-06 18:00","2017-04-06T09:00:00","2017-04-06T18:00:00","당일",null,null,null,201702020037,"-"]
[160,"경기","군포","산본안양#1 T/L","154kV 안양S/S 옥내화공사","산본-안양#1,2T/L EBA 기초작업을 위하여 기설 LA 이설","2017-04-20 09:00","2017-04-20 18:00","2017-04-20T09:00:00","2017-04-20T18:00:00","당일",null,null,null,201702100067,"-"]
[161,"경기","군포","안양평촌#1 T/L","154kV 안양S/S 옥내화 관련 인출 정비공사","내 용 : 154㎸ 안양변전소 옥내화에 따른 구내 인출정비 선종/회선길이 : 154㎸ XLPE 1,200/2,000㎟, 각 2회선-0.1㎞ 모선연계케이블 1회선- 0.15km","2017-03-31 09:00","2017-04-14 18:00","2017-03-31T09:00:00","2017-04-14T18:00:00","연속",null,null,"신뢰도개선",201701060023,"-"]
[162,"경기","군포","산본안양#2 T/L","154kV 안양S/S 옥내화공사","산본-안양#1,2T/L EBA 기초작업을 위하여 기설 LA 이설","2017-04-21 09:00","2017-04-21 18:00","2017-04-21T09:00:00","2017-04-21T18:00:00","당일",null,null,null,201702100069,"-"]
[163,"경기","군포","관양평촌#1 T/L","154kV 관양평촌#1T/L 선도제 보호계전기 오동작방지 대책 시행","154kV 관양평촌#1T/L 선도제 보호계전기 오동작방지 대책 시행 - 제작사 보호계전기 펌웨어 업그레이드 개선 - 선도제 보호계전기 오동작방지 대책 시행 병행작업(선도전기)","2017-04-17 09:00","2017-04-17 18:00","2017-04-17T09:00:00","2017-04-17T18:00:00","연속",null,null,null,201702090305,"-"]
[164,"경기","동부","감곡여주#1 T/L","154kV 감곡-여주#1T/L 전선교체공사","전선접속개소 전선교체공사","2017-04-13 08:00","2017-04-21 18:00","2017-04-13T08:00:00","2017-04-21T18:00:00","연속",null,null,null,201702100040,"-"]
[165,"경기","동부","감곡여주#2 T/L","154kV 감곡-여주#2T/L 전선교체공사","전선접속개소 전선교체공사","2017-04-03 08:00","2017-04-12 18:00","2017-04-03T08:00:00","2017-04-12T18:00:00","연속",null,null,null,201702100043,"-"]
[166,"경기","동부","율현용인#1 T/L","율현S/S 율현-용인#1T/L DS 절연로드 교체","율현S/S 율현-용인#1T/L DS 절연로드 교체","2017-04-03 09:00","2017-04-05 18:00","2017-04-03T09:00:00","2017-04-05T18:00:00","연속",null,null,null,201702100087,"-"]
[167,"경기","동부","율현용인#2 T/L","율현S/S 율현-용인#2T/L DS 절연로드 교체","율현S/S 율현-용인#2T/L DS 절연로드 교체","2017-04-10 09:00","2017-04-12 18:00","2017-04-10T09:00:00","2017-04-12T18:00:00","연속",null,null,null,201702100089,"-"]
[168,"경기","동부","이천율현#1 T/L","154kV 이천-율현T/L 계통보강공사","문서번호 영업(기획)-48(2017.1.18) SK하이닉스 전력공급방안관련 계통보강공사 시행 1.선종교체 - 기존 : ACSR 330㎟*S, 변경 : HSTACIR 330㎟*S - 교체구간 : 이천S/S ~ 율현S/S 4.96km 2. 철탑교체 : 8기","2017-04-03 09:00","2017-08-31 18:00","2017-04-03T09:00:00","2017-08-31T18:00:00","연속",null,null,null,201702130160,"-"]
[169,"경기","동부","이천율현#2 T/L","154kV 이천-율현T/L 계통보강공사","문서번호 영업(기획)-48(2017.1.18) SK하이닉스 전력공급방안관련 계통보강공사 시행 1.선종교체 - 기존 : ACSR 330㎟*S, 변경 : HSTACIR 330㎟*S - 교체구간 : 이천S/S ~ 율현S/S 4.96km 2. 철탑교체 : 8기","2017-04-03 09:00","2017-08-31 18:00","2017-04-03T09:00:00","2017-08-31T18:00:00","연속",null,null,null,201702130237,"-"]
[170,"경기","동부","이천가남#2 T/L","154kV 이천-가남T/L 송전선로 정밀점검","송전선로 정밀점검","2017-04-20 09:00","2017-04-21 18:00","2017-04-20T09:00:00","2017-04-21T18:00:00","매일",null,null,null,201702100049,"-"]
[171,"경기","동부","이천가남#1 T/L","154kV 이천-가남T/L 송전선로 정밀점검","송전선로 정밀점검","2017-04-18 09:00","2017-04-19 18:00","2017-04-18T09:00:00","2017-04-19T18:00:00","매일",null,null,null,201702100048,"-"]
[172,"경기","성남","신용인S/S 154kV #65 BUS","2017년 성남전력 154kV GIS 점밀점검 및 UHF센서 설치공사","신용인S/S 154kV #61M.Tr 6133 GIS 정밀점검 보조Ry 교체, UHF센서 설치","2017-04-04 14:00","2017-04-05 18:00","2017-04-04T14:00:00","2017-04-05T18:00:00","연속",null,null,null,201702100030,"-"]
[173,"경기","성남","신용인S/S 154kV #65 BUS","2017년 성남전력 154kV GIS 점밀점검 및 UHF센서 설치공사","신용인S/S 154kV #62M.Tr 6233 GIS 정밀점검 보조Ry 교체, UHF센서 설치","2017-04-07 10:04","2017-04-08 18:00","2017-04-07T10:04:00","2017-04-08T18:00:00","연속",null,null,null,201702100042,"-"]
[174,"경기","성남","신용인S/S 154kV #60 BUS","2017년 성남전력 154kV GIS 점밀점검 및 UHF센서 설치공사","신용인S/S 154kV #62M.Tr 6233 GIS 정밀점검 보조Ry 교체, UHF센서 설치","2017-04-06 09:00","2017-04-07 14:00","2017-04-06T09:00:00","2017-04-07T14:00:00","연속",null,null,null,201702100041,"-"]
[175,"경기","성남","신용인S/S 154kV #60 BUS","2017년 성남전력 154kV GIS 점밀점검 및 UHF센서 설치공사","신용인S/S 154kV #61M.Tr 6133 GIS 정밀점검 보조Ry 교체, UHF센서 설치","2017-04-03 09:00","2017-04-04 14:00","2017-04-03T09:00:00","2017-04-04T14:00:00","연속",null,null,null,201702100029,"-"]
[176,"경기","직할","서서울남수원#2 T/L","남수원S/S 서서울남수원#2T/L GIS 보통점검","남수원S/S 서서울남수원#2T/L GIS,PT 보통점검, LA교체","2017-04-05 09:00","2017-04-05 18:00","취소","취소","당일",null,null,null,201702100145,"-"]
[177,"경기","직할","서서울남수원#1 T/L","남수원S/S 서서울남수원#1T/L GIS 보통점검","남수원S/S 서서울남수원#1T/L GIS,PT 보통점검","2017-04-04 09:00","2017-04-04 18:00","취소","취소","당일",null,null,null,201702100144,"-"]
[178,"경기","직할","의왕동안양#2 T/L","동안양S/S 의왕동안양#2T/L GCB,LA,P보통점검","동안양S/S 의왕동안양#2T/L GCB,LA,P보통 의왕S/S 의왕동안양S/S #2T/L GIS보통, LA교체","2017-04-19 09:00","2017-04-19 18:00","2017-04-19T09:00:00","2017-04-19T18:00:00","당일",null,null,null,201702100165,"-"]
[179,"경기","직할","의왕동안양#1 T/L","동안양S/S 의왕동안양#1T/L GCB,LA,P보통점검","동안양S/S 의왕동안양#1T/L GCB,LA,P보통 의왕S/S 의왕동안양S/S #1T/L GIS보통, LA교체","2017-04-18 09:00","2017-04-18 18:00","2017-04-18T09:00:00","2017-04-18T18:00:00","당일",null,null,null,201702100163,"-"]
[180,"경기","직할","화성조암#2 T/L","345kV 아산-화성T/L 전력선교체 안전확보","○ 전력선교체 : No.91~136(136호 병가철탑 전력선교체시 안전확보)","2017-04-26 07:00","2017-05-03 18:00","취소","취소","연속",null,null,null,201702080031,"-"]
[181,"경기","직할","화성S/S 154kV #60 BUS","화성S/S 화성조암#1T/L GIS 정밀점검 공사","화성S/S 화성조암#1T/L GIS 정밀점검 공사","2017-04-03 09:00","2017-04-04 14:00","2017-04-03T09:00:00","2017-04-04T14:00:00","연속",null,null,null,201702100124,"-"]
[182,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 화성조암#2T/L GIS 정밀점검 공사","화성S/S 화성조암#2T/L GIS 정밀점검 공사","2017-04-27 14:00","2017-04-28 18:00","2017-04-27T14:00:00","2017-04-28T18:00:00","연속",null,null,null,201702100129,"-"]
[183,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 화성조암#2T/L GIS 정밀점검 공사","화성S/S 화성조암#2T/L GIS 정밀점검 공사","2017-04-26 09:00","2017-04-27 14:00","2017-04-26T09:00:00","2017-04-27T14:00:00","연속",null,null,null,201702100127,"-"]
[184,"경기","직할","화성조암#1 T/L","화성S/S 화성조암#1T/L GIS 정밀점검 공사","화성S/S 화성조암#1T/L GIS 정밀점검 공사","2017-04-03 09:00","2017-04-05 18:00","2017-04-03T09:00:00","2017-04-05T18:00:00","연속",null,null,null,201702100115,"-"]
[185,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","2017-04-25 14:00","2017-04-26 18:00","취소","취소","연속",null,null,null,201702100142,"-"]
[186,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","2017-04-24 09:00","2017-04-25 14:00","취소","취소","연속",null,null,null,201702100141,"-"]
[187,"경기","직할","화성S/S 154kV #67 BUS","화성S/S 154kV #67SC GIS 정밀점검 공사","화성S/S 154kV #67SC GIS 정밀점검 공사","2017-04-18 14:00","2017-04-19 18:00","2017-04-18T14:00:00","2017-04-19T18:00:00","연속",null,null,null,201702100137,"-"]
[188,"경기","직할","화성S/S 154kV #62 BUS","화성S/S 154kV #67SC GIS 정밀점검 공사","화성S/S 154kV #67SC GIS 정밀점검 공사","2017-04-17 09:00","2017-04-18 14:00","2017-04-17T09:00:00","2017-04-18T14:00:00","연속",null,null,null,201702100138,"-"]
[189,"경기","직할","화성S/S 154kV #67 BUS","화성S/S 154kV #68SC GIS 정밀점검 공사","화성S/S 154kV #68SC GIS 정밀점검 공사","2017-04-11 14:00","2017-04-12 18:00","2017-04-11T14:00:00","2017-04-12T18:00:00","연속",null,null,null,201702100136,"-"]
[190,"경기","직할","화성S/S 154kV #62 BUS","화성S/S 154kV #68SC GIS 정밀점검 공사","화성S/S 154kV #68SC GIS 정밀점검 공사","2017-04-10 09:00","2017-04-11 14:00","2017-04-10T09:00:00","2017-04-11T14:00:00","연속",null,null,null,201702100135,"-"]
[191,"경기","직할","화성S/S 154kV #65 BUS","화성S/S 화성조암#1T/L GIS 정밀점검 공사","화성S/S 화성조암#1T/L GIS 정밀점검 공사","2017-04-04 14:00","2017-04-05 18:00","2017-04-04T14:00:00","2017-04-05T18:00:00","연속",null,null,null,201702100121,"-"]
[192,"경기","평택","송탄S/S 송탄-오성복합#1T/L(627) GIS","송탄S/S 송탄-오성복합T/L GIS 대체공사","송탄S/S 송탄-오성복합T/L GIS 대체공사","2017-04-03 09:00","2017-04-19 18:00","2017-04-03T09:00:00","2017-04-19T18:00:00","연속",null,null,null,201702080075,"-"]
[193,"경기","평택","평택S/S 평택-오성복합#1T/L CB","평택S/S 평택-오성복합#1T/L GCB 정밀점검","평택S/S 평택-오성복합#1T/L GCB 정밀점검","2017-04-22 09:00","2017-04-23 18:00","2017-04-22T09:00:00","2017-04-23T18:00:00","연속",null,null,null,201702080059,"-"]
[194,"강원","강릉","동해강릉 T/L","2017년 가공송전선로 순시점검 위탁공사","154kV 동해분기T/L 정밀점검 - 회선명 : 동해-강릉 T/L - 구간 : No.1~53-1","2017-04-10 09:00","2017-04-14 18:00","2017-04-10 09:00","2017-04-14 18:00","매일",null,null,null,201702140529,"-"]
[195,"강원","강릉","동해영동TP T/L","2017년 가공송전선로 순시점검 위탁공사","154kV 동해분기T/L 정밀점검 - 회선명 : 동해-영동TP T/L - 구간 : No.1~53-1","2017-04-03 09:00","2017-04-07 18:00","2017-04-03 09:00","2017-04-07 18:00","매일",null,null,null,201702140485,"-"]
[196,"강원","강릉","횡계평창#2 T/L","154kV 평창올림픽분기T/L 건설공사","154kV 평창올림픽분기T/L 건설 154kV 평창올림픽분기T/L OPGW 및 광단국 설치 154kV 평창올림픽분기변전소 보호배전반 설치 *변전소 최초가압 별도 승인신청 예정","2017-04-18 07:00","2017-04-25 14:00","2017-04-18 07:00","2017-04-25 14:00","연속",null,null,null,201702150038,"-"]
[197,"강원","동해","삼척동해TP T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해화력측 LA 보통점검 2. 삼척S/S측 LA 보통점검 3. 장기미동작차단기 조작시험(타임테스트 측정)","2017-04-18 09:30","2017-04-18 18:00","2017-04-18 09:30","2017-04-18 18:00","당일",null,null,null,201702140083,"-"]
[198,"강원","동해","이원동해TP T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해화력측 LA 보통점검 2. 이원S/S측 LA 보통점검 3. 장기미동작차단기 조작시험(타임테스트 측정)","2017-04-17 09:30","2017-04-17 18:00","2017-04-17 09:30","2017-04-17 18:00","당일",null,null,null,201702140081,"-"]
[199,"강원","동해","이원삼척 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. GIS 보통점검 2. LA 보통점검 3. 장기미동작차단기 조작시험(타임테스트 측정) 4. 유압계통 점검","2017-04-19 09:30","2017-04-19 18:00","2017-04-19 09:30","2017-04-19 18:00","당일",null,null,null,201702140088,"-"]
[200,"강원","원주","홍천상남#1 T/L","홍천변전소 170kV GIS 설치공사","○ 170kV 송전선로 LINE측 붓싱 조립 - 진공 및 가스 주입 - 각종 시험 - 무부하 가압 ○ 기존 옥외철구 설비 철거 - GCB, DS 철거 - LINE CVT, LA 이설","2017-04-03 11:00","2017-04-10 09:30","2017-04-03 11:00","2017-04-10 09:30","연속",null,null,null,201701160139,"-"]
[201,"강원","원주","홍천상남#2 T/L","홍천변전소 170kV GIS 설치공사","○ 170kV 송전선로 LINE측 붓싱 조립 - 진공 및 가스 주입 - 각종 시험 - 무부하 가압 ○ 기존 옥외철구 설비 철거 - GCB, DS 철거 - LINE CVT, LA 이설","2017-04-03 11:00","2017-04-10 09:30","2017-04-03 11:00","2017-04-10 09:30","연속",null,null,null,201701160140,"-"]
[202,"강원","직할","남춘천춘천열병합#1 T/L","2016-17년 강원지역본부 직할 변전정비 협력회사 총액공사","남춘천S/S 154kV 남춘천-춘천열병합#1T/L GIS, LA 보통점검","2017-04-06 09:00","2017-04-06 18:00","2017-04-06 09:00","2017-04-06 18:00","당일",null,null,null,201702030066,"-"]
[203,"강원","직할","남춘천춘천열병합#2 T/L","2016-17년 강원지역본부 직할 변전정비 협력회사 총액공사","남춘천S/S 154kV 남춘천-춘천열병합#2T/L GIS, LA 보통점검","2017-04-10 09:00","2017-04-10 18:00","2017-04-10 09:00","2017-04-10 18:00","당일",null,null,null,201702030069,"-"]
[204,"강원","직할","남춘천춘천 T/L","2016-17년 강원지역본부 직할 변전정비 협력회사 총액공사","남춘천S/S 154kV 남춘천-춘천T/L GIS, LA 보통점검","2017-04-07 09:00","2017-04-07 18:00","2017-04-07 09:00","2017-04-07 18:00","당일",null,null,null,201702030067,"-"]
[205,"강원","태백","동영월영월CC T/L","2016~2017 태백전력지사 변전정비 협력회사 총액공사","동영월-영월CCT/L 조작시험","2017-04-17 10:00","2017-04-17 14:00","2017-04-17 10:00","2017-04-17 14:00","당일",null,null,null,201702140291,"-"]
[206,"강원","태백","고한영월 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","고한영월T/L GIS 보통점검(고한S/S측 조작시험)","2017-04-14 10:00","2017-04-14 18:00","2017-04-14 10:00","2017-04-14 18:00","당일",null,null,null,201702140281,"-"]
[207,"강원","태백","제천영월#1 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","영월S/S 제천-영월#1T/L GIS 보통점검","2017-04-18 10:00","2017-04-18 18:00","2017-04-18 10:00","2017-04-18 18:00","당일",null,null,null,201702140293,"-"]
[208,"강원","태백","제천영월#2 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","영월S/S 제천-영월#2T/L GIS 보통점검","2017-04-19 10:00","2017-04-19 18:00","2017-04-19 10:00","2017-04-19 18:00","당일",null,null,null,201702140294,"-"]
[209,"강원","태백","태백영월 T/L","2016~2017 태백전력지사 변전정비 협력회사 총액공사","영월S/S 태백영월T/L GIS보통점검 및 LA점검 OPGW 순시 및 불량개소 정비","2017-04-19 10:00","2017-04-20 18:00","2017-04-19 10:00","2017-04-20 18:00","연속",null,null,null,201702140302,"-"]
[210,"강원","태백","태백삼척GP#1 T/L","OPGW 특별점검 및 위해개소 조치","OPGW 특별점검 및 위해개소 조치","2017-04-11 10:00","2017-04-12 18:00","2017-04-11 10:00","2017-04-12 18:00","연속",null,null,null,201702210012,"-"]
[211,"충북","직할","신제천제천#2 T/L","154kV 신제천-제천TL 안전이격확보공사","No.27.6, 27.7, 27.9 철탑 교체 #2T/L No.27.5~27.10 전력선 교체 (슬리브제거)","2017-04-01 08:00","2017-04-07 18:00","2017-04-01 08:00","2017-04-07 18:00","연속",null,null,null,201702160328,"-"]
[212,"충북","직할","신제천제천#1 T/L","154kV 신제천-제천TL 안전이격확보공사","No.27.6, 27.7, 27.9 철탑 교체 #2T/L No.27.5~27.10 전력선 교체 (슬리브제거)","2017-04-01 08:00","2017-04-07 18:00","2017-04-01 08:00","2017-04-07 18:00","연속",null,null,null,201702160327,"-"]
[213,"충북","청주","상주보은 T/L","2017년 가공송전선로 순시점검 위탁공사","154kV 상주-보은T/L 정밀점검","2017-04-11 09:00","2017-04-12 18:00","2017-04-11 09:00","2017-04-12 18:00","매일",null,null,null,201702100326,"-"]
[214,"충북","청주","상주영동 T/L","2017년 가공송전선로 순시점검 위탁공사","154kV 상주-영동T/L 정밀점검","2017-04-03 09:00","2017-04-05 18:00","2017-04-03 09:00","2017-04-05 18:00","매일",null,null,null,201702100325,"-"]
[215,"충북","청주","청원부강#1 T/L","17년 변전정비 총액공사","154kV 청원부강#1T/L GIS 보통점검","2017-04-03 09:30","2017-04-03 18:00","2017-04-03 09:30","2017-04-03 18:00","당일",null,null,null,201702130107,"-"]
[216,"충북","청주","청원부강#2 T/L","17년 변전정비 총액공사","154kV 청원부강#2T/L GIS 보통점검","2017-04-04 09:30","2017-04-04 18:00","2017-04-04 09:30","2017-04-04 18:00","당일",null,null,null,201702130108,"-"]
[217,"충북","충주","서운만승 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사 피뢰기 보통점검","2017-04-05 09:00","2017-04-05 18:00","2017-04-05 09:00","2017-04-05 18:00","매일",null,null,null,201702070110,"○"]
[218,"충북","충주","진천덕산#2 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사","2017-04-24 09:00","2017-04-24 18:00","2017-04-24 09:00","2017-04-24 18:00","매일",null,null,null,201702070105,"○"]
[219,"충북","충주","진천만승#1 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사 피뢰기 보통점검","2017-04-25 09:00","2017-04-26 18:00","2017-04-25 09:00","2017-04-26 18:00","매일",null,null,null,201702070113,"○"]
[220,"충북","충주","진천만승#2 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사 피뢰기 보통점검","2017-04-27 09:00","2017-04-28 18:00","2017-04-27 09:00","2017-04-28 18:00","매일",null,null,null,201702070114,"○"]
[221,"충북","충주","진천덕산#1 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사","2017-04-21 09:00","2017-04-21 18:00","2017-04-21 09:00","2017-04-21 18:00","매일",null,null,null,201702070104,"○"]
[222,"충북","충주","충주풍동 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2017-04-18 09:00","2017-04-24 18:00","2017-04-18 09:00","2017-04-24 18:00","매일",null,null,null,201702200055,"○"]
[223,"충북","충주","풍동음성#1 T/L","154kV 풍동-음성 등 8개T/L 전력선 교체공사","전선접속개소 해소를 위한 전력선교체 공사","2017-04-19 08:00","2017-04-23 18:00","2017-04-19 08:00","2017-04-23 18:00","연속",null,null,null,201702200056,"○"]
[224,"충북","충주","풍동음성#2 T/L","154kV 풍동-음성 등 8개T/L 전력선 교체공사","전선접속개소 해소를 위한 전력선교체 공사","2017-04-24 08:00","2017-04-28 18:00","2017-04-24 08:00","2017-04-28 18:00","연속",null,null,null,201702200057,"○"]
[225,"대전충남","대전","신옥천남대전#3 T/L","154kV 용운-대화 등 8개T/L 피뢰기 설치공사","154kV 신옥천-남대전#3T/L 송전용 피뢰기 설치","2017-04-12 07:00","2017-04-13 18:00","2017-04-12T07:00:00","2017-04-13T18:00:00","매일",null,null,null,201702090010,"-"]
[226,"대전충남","대전","신계룡가수원#2 T/L","154kV 신계룡-가수원 등 2개T/L 성능저하 애자교체공사","성능저하 애자교체","2017-04-23 07:00","2017-04-28 18:00","2017-04-23T07:00:00","2017-04-28T18:00:00","매일",null,null,null,201702090018,"-"]
[227,"대전충남","대전","신계룡가수원#1 T/L","154kV 신계룡-가수원 등 2개T/L 성능저하 애자교체공사","성능저하 애자교체","2017-04-17 07:00","2017-04-22 18:00","2017-04-17T07:00:00","2017-04-22T18:00:00","매일",null,null,null,201702090017,"-"]
[228,"대전충남","서산","신당진당진#1 T/L","당진S/S 154kV 신당진-당진 #1T/L GCB 대체","당진S/S 154kV 신당진-당진 #1T/L GCB 대체","2017-04-17 09:00","2017-04-19 18:00","취소","취소","연속",null,null,null,201702230143,"-"]
[229,"대전충남","서산","당진T/P 154kV #1 BUS TIE CB","당진T/P 154kV #1 BUS TIE GIS(6100) 정밀점검","당진T/P 154kV #1 BUS TIE GIS(6100) 정밀점검","2017-04-26 09:00","2017-04-27 18:00","2017-04-26T09:00:00","2017-04-27T18:00:00","연속",null,null,null,201702060275,"-"]
[230,"대전충남","서산","GSEPS#2 T/L","송악S/S GSEPS#2T/L GIS 및 LA 보통점검","송악S/S GSEPS#2T/L GIS 및 LA 보통점검","2017-04-27 09:00","2017-04-27 18:00","2017-04-27T09:00:00","2017-04-27T18:00:00","당일",null,null,null,201702060276,"-"]
[231,"대전충남","서산","신당진당진#2 T/L","신당진S/S 154kV 신당진-당진 #2T/L GIS 정밀점검","신당진S/S 154kV 신당진-당진 #2T/L GIS 정밀점검","2017-04-10 09:00","2017-04-12 18:00","취소","취소","연속",null,null,null,201702060268,"-"]
[232,"대전충남","세종","신풍공주#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2017-04-03 09:30","2017-04-03 18:00","2017-04-03T09:30:00","2017-04-03T18:00:00","당일",null,null,null,201702230033,"-"]
[233,"대전충남","세종","조치원전의#2 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검 ○ LA대체공사","2017-04-17 09:30","2017-04-17 18:00","2017-04-17T09:30:00","2017-04-17T18:00:00","당일",null,null,null,201702230031,"-"]
[234,"대전충남","세종","천안전의#1 T/L","[송전] 154kV 천안-전의T/L 안전거리 확보공사","[송전] 철탑교체 : 3기(No.23~25), 전선교체 : 1.083km(No.22~26) - #1T/L 본철탑으로 전선이설","2017-04-10 07:00","2017-04-12 19:00","2017-04-10T07:00:00","2017-04-12T19:00:00","연속",null,null,null,201702070001,"-"]
[235,"대전충남","세종","조치원전의#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검 ○ LA대체공사","2017-04-18 09:30","2017-04-18 18:00","2017-04-18T09:30:00","2017-04-18T18:00:00","당일",null,null,null,201702230030,"-"]
[236,"대전충남","세종","서세종조치원 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2017-04-13 09:30","2017-04-13 18:00","2017-04-13T09:30:00","2017-04-13T18:00:00","당일",null,null,null,201702230032,"-"]
[237,"대전충남","아산","신온양1석곡#1 T/L","[송전]154kV 신온양-한샘T/L 경과지 변경 건설공사","[송전] 전력선 연선 및 긴선에 따른 No.7호 활선근접에 따른 휴전 및 S/T~No.7간 항공장애표시구 취부 (작업내용) - No.7 ~ 13호간 전력선 연선 및 긴선 * 2.013km - 애자금구류 및 피뢰기 설치 * 1식 - 기타 부대작업","2017-04-26 08:00","2017-05-01 18:00","2017-04-26T08:00:00","2017-05-01T18:00:00","연속",null,null,null,201702090104,"-"]
[238,"대전충남","아산","신온양1석곡#2 T/L","[송전]154kV 신온양-한샘T/L 경과지 변경 건설공사","[송전] 전력선 연선 및 긴선에 따른 No.7호 활선근접에 따른 휴전 및 S/T~No.7간 항공장애표시구 취부 (작업내용) - No.7 ~ 13호간 전력선 연선 및 긴선 * 2.013km - 애자금구류 및 피뢰기 설치 * 1식 - 기타 부대작업","2017-04-26 08:00","2017-05-01 18:00","2017-04-26T08:00:00","2017-05-01T18:00:00","연속",null,null,null,201702090107,"-"]
[239,"대전충남","아산","신온양한샘#1 T/L","345kV 신온양-신탕정T/L 전선교체공사","○ 구간: 345kV 신온양-신탕정T/L No.3~신탕정S/T [하단선 교체] - 해당선로 : 신온양-한샘T/L No.3~12 구간","2017-04-05 06:00","2017-04-17 18:30","2017-04-05T06:00:00","2017-04-17T18:30:00","연속",null,null,null,201612070191,"-"]
[240,"대전충남","아산","신온양한샘#2 T/L","345kV 신온양-신탕정T/L 전선교체공사","○ 전선교체작업 안전이격확보 - 신온양-신탕정T/L 12호 횡단구간(신온양-한샘T/L)","2017-04-10 06:00","2017-04-13 18:30","2017-04-10T06:00:00","2017-04-13T18:30:00","연속",null,null,null,201612070193,"-"]
[241,"대전충남","아산","아산인주#2 T/L","[송전]154kV 아산-인주#2T/L 피뢰기 설치공사","- 154kV 송전용 피뢰기 설치 10기","2017-04-01 09:00","2017-04-03 18:00","취소","취소","매일",null,null,null,201702090232,"-"]
[242,"대전충남","아산","아산인주#1 T/L","아산S/S 154kV 아산-인주#1T/L 보통점검","○ 154kV 아산-인주#1T/L 보통점검 및 CVT 보통점검, 노후 LA 대체","2017-04-01 09:00","2017-04-02 18:00","취소","취소","당일",null,null,null,201702080171,"-"]
[243,"대전충남","아산","장재천안#1 T/L","[송전]154kV 장재-천안T/L 임시선로 변경공사","154kV 장재-천안T/L 임시선로 변경공사[요청자 직접시행]","2017-04-17 07:00","2017-04-18 18:00","2017-04-17T07:00:00","2017-04-18T18:00:00","연속",null,null,null,201702020007,"-"]
[244,"대전충남","아산","장재천안#2 T/L","[송전]154kV 장재-천안T/L 임시선로 변경공사","154kV 장재-천안T/L 임시선로 변경공사[요청자 직접시행]","2017-04-19 07:00","2017-04-20 08:00","2017-04-17T07:00:00","2017-04-17T08:00:00","연속",null,null,null,201702020008,"-"]
[245,"대전충남","아산","인주탕정#2 T/L","탕정S/S 옥상 배수구(우수관) 탈락 보수","탕정S/S 옥상 배수구 탈락 보수관련 인접T/L 휴전","2017-04-15 09:00","2017-04-15 18:00","2017-04-15T09:00:00","2017-04-15T18:00:00","당일",null,null,null,201702200049,"-"]
[246,"대전충남","아산","풍세장재#2 T/L","[송전]154kV 풍세-장재#2T/L 피뢰기 설치공사","- 154kV 송전용 피뢰기 설치 3기","2017-04-04 09:00","2017-04-04 18:00","2017-04-17T09:00:00","2017-04-17T18:00:00","매일",null,null,null,201702090244,"-"]
[247,"대전충남","직할","대덕둔산#2 T/L","154 대덕-둔지 지중T/L 증설공사","154kV XLPE 2,000㎟ 1C-0.4㎞ 포설 및 접속2개소 154kV XLPE 2,000㎟ 1C-0.3㎞(J/B#8~둔산S/S)철거","2017-04-10 09:00","2017-04-30 18:00","2017-04-10T09:00:00","2017-04-30T18:00:00","연속",null,null,null,201702130137,"-"]
[248,"대전충남","청양","옥산서천화력#1 T/L","154kV 대천-서천화력T/L OPGW 항공장애표시구 시설공사","- 시설구간 : No.2-No.4 - 항공장애표시구 30개 설치 : No.2~3 구간 13개, No.3~4 구간 17개","2017-04-11 07:00","2017-04-11 18:00","2017-04-11T07:00:00","2017-04-11T18:00:00","당일",null,null,null,201702080080,"-"]
[249,"전북","군산","내초SE열병합#2 T/L","군산P/O 154kV 차단기 보통점검","SE열병합S/Y 내초SE열병합#2 T/L","2017-04-25 10:00","2017-04-25 18:00","2017-04-25 10:00","2017-04-25 18:00","당일",null,null,null,201702130343,"-"]
[250,"전북","군산","내초SE열병합#1 T/L","군산P/O 154kV 차단기 보통점검","SE열병합S/Y 내초SE열병합#1 T/L","2017-04-24 10:00","2017-04-24 18:00","2017-04-24 10:00","2017-04-24 18:00","당일",null,null,null,201702130340,"-"]
[251,"전북","군산","군공S/S 154kV #1 BUS TIE CB","군공S/S 154kV #1 BUS TIE CB","군산P/O 170kv 차단기 정밀점검 공사","2017-04-05 09:00","2017-04-08 18:00","2017-04-05 09:00","2017-04-08 18:00","연속",null,null,null,201702150024,"-"]
[252,"전북","군산","군공군산CC#1 T/L","154kV 군공-군산복합T/L SVL 교체공사","링크박스 철거 및 SVL 설치공사","2017-04-27 09:00","2017-05-14 18:00","2017-04-27 09:00","2017-05-14 18:00","연속",null,null,null,201702150041,"-"]
[253,"전북","군산","군산동군산#1 T/L","군산동군산T/L 안전이격확보공사","가선로 구성 가철탑조립 및 전선공중이동 : 4기(28,29,30,31)","2017-04-10 07:00","2017-04-14 18:00","2017-04-10 07:00","2017-04-14 18:00","연속",null,null,null,201702140541,"-"]
[254,"전북","군산","군산동군산#1 T/L","군산동군산T/L 안전이격확보공사","철탑조립 및 전선공중이동 : 4기(28,29,30,31)","2017-04-23 07:00","2017-04-28 18:00","2017-04-23 07:00","2017-04-28 18:00","연속",null,null,null,201702140549,"-"]
[255,"전북","군산","군산동군산#2 T/L","군산동군산T/L 안전이격확보공사","철탑조립 및 전선공중이동 : 4기(28,29,30,31)","2017-04-15 07:00","2017-04-22 18:00","2017-04-15 07:00","2017-04-22 18:00","연속",null,null,null,201702140545,"-"]
[256,"전북","군산","군산이리#2 T/L","군산영등#2T/L 정밀점검공사 안전이격거리 확보","군산영등#2T/L 정밀점검공사 안전이격거리 확보","2017-04-13 07:00","2017-04-13 18:00","2017-04-13 07:00","2017-04-13 18:00","매일",null,null,null,201702140508,"-"]
[257,"전북","군산","군산영등#2 T/L","군산영등#2T/L 정밀점검공사","정밀점검 : 56기","2017-04-13 07:00","2017-04-15 18:00","2017-04-13 07:00","2017-04-15 18:00","매일",null,null,null,201702140501,"-"]
[258,"전북","군산","군산영등#1 T/L","군산영등#1 T/L 정밀점검공사","정밀점검 : 56기","2017-04-10 07:00","2017-04-12 18:00","2017-04-10 07:00","2017-04-12 18:00","매일",null,null,null,201702140498,"-"]
[259,"전북","군산","군산이리#1 T/L","군산영등#1T/L 정밀점검공사 안전이격거리 확보","정밀점검 : 56기","2017-04-10 07:00","2017-04-10 18:00","2017-04-10 07:00","2017-04-10 18:00","매일",null,null,null,201702140506,"-"]
[260,"전북","군산","동군산장항#1 T/L","군산P/O 154kV 차단기 보통점검","동군산-장항#1 T/L","2017-04-06 09:00","2017-04-06 18:00","2017-04-06 09:00","2017-04-06 18:00","당일",null,null,null,201702130319,"-"]
[261,"전북","군산","군산서군산#2 T/L","효성제 옥외차단기 특별점검","군산, 서군산S/S 군산서군산#2T/L CB","2017-04-05 09:00","2017-04-05 18:00","2017-04-05 09:00","2017-04-05 18:00","당일",null,null,null,201702150023,"-"]
[262,"전북","군산","군산서군산#1 T/L","효성제 옥외차단기 특별점검","군산, 서군산S/S 군산서군산#1 T/L CB","2017-04-04 09:00","2017-04-04 18:00","2017-04-04 09:00","2017-04-04 18:00","당일",null,null,null,201702150022,"-"]
[263,"전북","군산","팔봉영등#2 T/L","군산P/O 154kV 차단기 보통점검","팔봉영등#2 T/L","2017-04-19 09:00","2017-04-19 18:00","취소","취소","당일",null,null,null,201702130329,"-"]
[264,"전북","군산","군산영등#1 T/L","군산P/O 154kV 차단기 보통점검","군산영등#1 T/L","2017-04-18 09:00","2017-04-18 18:00","2017-04-18 09:00","2017-04-18 18:00","당일",null,null,null,201702130328,"-"]
[265,"전북","군산","이리전주#2 T/L","154kV 군산-이리 등 3개T/L C/H 설치공사","이리백산#2 T/L, 이리전주#2T/L 도장작업","2017-04-03 08:00","2017-04-04 18:00","2017-04-03 08:00","2017-04-04 10:00","매일",null,null,null,201702150003,"-"]
[266,"전북","군산","이리백산#2 T/L","154kV 군산-이리 등 3개T/L C/H 설치공사","이리백산#2 T/L, 이리전주#2T/L 도장작업","2017-04-03 08:00","2017-04-04 18:00","2017-04-03 10:00","2017-04-04 12:00","매일",null,null,null,201702150002,"-"]
[267,"전북","군산","이리백산#1 T/L","154kV 이리-백산#1T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-04-17 07:00","2017-04-27 18:00","2017-04-17 07:00","2017-04-27 18:00","연속",null,null,null,201701190022,"-"]
[268,"전북","군산","이리전주#1 T/L","154kV 이리-전주#1T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-04-17 07:00","2017-04-27 18:00","2017-04-17 07:00","2017-04-27 18:00","연속",null,null,null,201701190023,"-"]
[269,"전북","군산","팔봉봉동#2 T/L","팔봉봉동T/L 정밀점검공사","공사구간 : 1~37","2017-04-27 09:00","2017-04-29 18:00","2017-04-27 09:00","2017-04-29 18:00","매일",null,null,null,201701180078,"-"]
[270,"전북","군산","팔봉봉동#1 T/L","팔봉봉동T/L 정밀점검공사","공사구간 : 1~37","2017-04-24 09:00","2017-04-26 18:00","2017-04-24 09:00","2017-04-26 18:00","매일",null,null,null,201701180077,"-"]
[271,"전북","군산","군공S/S 154kV #1 BUS TIE CB","군공S/S 154kV #1 BUS TIE CB","군산P/O 170kv 차단기 정밀점검 공사","2017-04-05 09:00","2017-04-08 18:00","취소","취소","연속",null,null,null,201702150024,"-"]
[272,"전북","김제","정주고창#1 T/L","154kV 차단기 정밀점검","154kV #1 BUS 시험가압","2017-04-11 11:00","2017-04-11 13:00","취소","취소","당일",null,null,null,201701180192,"-"]
[273,"전북","김제","정주고창#1 T/L","154kV 차단기 정밀점검","154kV #2 BUS 시험가압","2017-04-12 16:00","2017-04-12 18:00","취소","취소","연속",null,null,null,201701180193,"-"]
[274,"전북","김제","고창영광 T/L","154kV 영고T/L 송전선로 정밀점검","154kV 영고T/L 정밀점검","2017-04-03 09:00","2017-04-07 18:00","취소","취소","매일",null,null,null,201702140633,"-"]
[275,"전북","김제","정주고창#1 T/L","154kV 영고T/L 송전선로 정밀점검","154kV 영고T/L 정밀점검 (병가선로)","2017-04-07 09:00","2017-04-07 18:00","취소","취소","당일",null,null,null,201702140636,"-"]
[276,"전북","김제","고창홍농 T/L","154kV 영고T/L 송전선로 정밀점검","154kV 홍고T/L 정밀점검","2017-04-10 09:00","2017-04-14 18:00","취소","취소","매일",null,null,null,201702140634,"-"]
[277,"전북","김제","정주고창#2 T/L","154kV 홍고T/L 송전선로 정밀점검","154kV 홍고T/L 정밀점검 (병가선로)","2017-04-14 09:00","2017-04-14 18:00","취소","취소","당일",null,null,null,201702140638,"-"]
[278,"전북","김제","정주고창#2 T/L","154kV 차단기 정밀점검","차단기 정밀점검","2017-04-21 09:00","2017-04-23 18:00","취소","취소","연속",null,null,null,201702170205,"-"]
[279,"전북","김제","정주고창#1 T/L","154kV 차단기 정밀점검","차단기 정밀점검","2017-04-18 09:00","2017-04-20 18:00","취소","취소","연속",null,null,null,201702170203,"-"]
[280,"전북","김제","섬진강H/P #1 M.Tr 1차 CB","154kV 차단기 정밀점검","차단기 내부 정밀점검","2017-04-03 09:00","2017-04-06 18:00","2017-04-03 09:00","2017-04-06 18:00","연속",null,null,null,201701180170,"○"]
[281,"전북","김제","신김제S/S 65-66-0 SEC CB","신김제S/S 65-66-0 SEC CB","신김제S/S 모선보호반 교체공사","2017-04-10 09:00","2017-04-17 18:00","취소","취소","연속",null,null,null,201702140401,"-"]
[282,"전북","김제","신김제S/S 60-61-0 SEC CB","신김제S/S 60-61-0 SEC CB","신김제S/S 모선보호반 교체공사","2017-04-10 09:00","2017-04-17 18:00","취소","취소","연속",null,null,null,201702140399,"-"]
[283,"전북","김제","신김제남전주#1 T/L","신김제남전주#1 T/L","장기미동작 차단기 특별점검","2017-04-05 09:00","2017-04-05 18:00","2017-04-21 09:00","2017-04-21 18:00","당일",null,null,null,201702160396,"-"]
[284,"전북","김제","신김제S/S 61-62-0 SEC CB","신김제S/S 61-62-0 SEC CB","신김제S/S 모선보호반 교체공사","2017-04-10 09:00","2017-04-17 18:00","취소","취소","연속",null,null,null,201702140406,"-"]
[285,"전북","김제","신김제S/S 66-67-0 SEC CB","신김제S/S 66-67-0 SEC CB","신김제S/S 모선보호반 교체공사","2017-04-10 09:00","2017-04-17 18:00","취소","취소","연속",null,null,null,201702140407,"-"]
[286,"전북","김제","정공정주#2 T/L","154kV 정공-정주#2T/L 점퍼지지애자 교체공사","154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 154kV 정공-담양T/L 점퍼지지애자 교체(3기) 병행","2017-04-17 07:00","2017-04-17 18:00","취소","취소","당일",null,null,null,201701160124,"-"]
[287,"전북","김제","정공담양 T/L","154kV 정공-담양T/L 점퍼지지애자 교체공사","154kV 정공-담양T/L 점퍼지지애자 교체(3기) 154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 병행","2017-04-17 07:00","2017-04-17 18:00","2017-04-17 07:00","2017-04-17 18:00","당일",null,null,null,201701160121,"○"]
[288,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 점퍼지지애자 교체공사","154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 병행","2017-04-15 07:00","2017-04-16 18:00","취소","취소","매일",null,null,null,201701160120,"-"]
[289,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강수력T/L 점퍼지지애자 교체공사","154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 병행","2017-04-15 07:00","2017-04-16 18:00","2017-04-15 07:00","2017-04-16 18:00","매일",null,null,null,201701160118,"○"]
[290,"전북","직할","북전주진안 T/L","154kV 북전주-진안T/L 차단기 점검공사","북전주S/S 154kV 북전주-진안T/L CVT 점검 진안S/S 154kV 북전주-진안T/L 차단기 보통점검","2017-04-04 09:30","2017-04-04 18:00","2017-04-04 09:30","2017-04-04 18:00","당일",null,null,null,201702150026,"-"]
[291,"광주전남","강진","강진남창#2 T/L","154kV 강진-남창#2T/L(강진 변전협력회사 총액공사)","남창S/S 강진-남창#2T/L LA,CVT 대체 강진S/S 강진-남창#2T/L LA 하자점검","2017-04-24 09:00","2017-04-24 18:00","2017-04-24 09:00","2017-04-24 18:00","당일",null,null,null,201702130136,"-"]
[292,"광주전남","강진","강진남창#1 T/L","154kV 강진-남창#1T/L(강진 변전협력회사 총액공사)","강진S/S 강진-남창#1T/L LA 하자점검","2017-04-25 09:00","2017-04-25 18:00","2017-04-25 09:00","2017-04-25 18:00","당일",null,null,null,201702130138,"-"]
[293,"광주전남","강진","신강진대불#1 T/L","154kV 대불-남악 등 3개TL 접속개소 해소공사","가. 구 간 ○ 154kV 대불-남악 T/L No.7∼10 등 2구간 ○ 154kV 신강진-대불 T/L No.8∼11 등 9구간 나. 전선교체 ○ ACSR/AW 410㎟ × 2B, 26.464㎞","2017-04-04 07:00","2017-05-16 18:00","2017-04-04 07:00","2017-05-16 18:00","연속",null,null,null,201702070390,"-"]
[294,"광주전남","강진","신강진대불#2 T/L","신강진S/S 154kV 신강진-대불#2T/L(T-BUS 철거)","신강진S/S 154kV 옥외철구 GIS화 공사 2017. 4. 3 : 신강진S/S 154kV 신강진-대불#2T/L","2017-04-03 09:00","2017-04-03 18:00","2017-04-03 09:00","2017-04-03 18:00","당일",null,null,null,201702140378,"-"]
[295,"광주전남","강진","해남진도#2 T/L","154kV 해남-진도#2T/L(정밀점검)","154kV 해남-진도#2T/L(정밀점검) - '17년도 가공송전 순시점검 위탁공사","2017-04-24 09:00","2017-04-28 18:00","2017-04-24 09:00","2017-04-28 18:00","매일",null,null,null,201702060251,"-"]
[296,"광주전남","강진","해남진도#1 T/L","154kV 해남-진도#1T/L(정밀점검)","154kV 해남-진도#1T/L(정밀점검) - '17년도 가공송전 순시점검 위탁공사","2017-04-17 09:00","2017-04-21 18:00","2017-04-17 09:00","2017-04-21 18:00","매일",null,null,null,201702060250,"-"]
[297,"광주전남","광주","신광주장성#2 T/L","신광주장성#2 T/L(인출변경 및 인출GIS연결)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-04-29 07:00","2017-05-08 18:00","2017-05-09 07:00","2017-05-18 18:00","연속",null,null,null,201701250012,"-"]
[298,"광주전남","광주","신광주곡성#2 T/L","신광주곡성#2 T/L(인출변경및인출GIS연결)","- 인출변경및인출GIS연결 - 제어케이불 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시첨","2017-04-01 07:00","2017-04-11 18:00","2017-04-21 07:00","2017-05-04 18:00","연속",null,null,null,201701250003,"-"]
[299,"광주전남","광주","신광주계림#2 T/L","신광주계림#2 T/L(인출변경및인출GIS연결)","-인출변경및 인출GIS연결 - 제어케이불 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시첨","2017-04-01 07:00","2017-04-11 18:00","2017-04-21 07:00","2017-05-04 18:00","연속",null,null,null,201701250002,"-"]
[300,"광주전남","광주","신광주S/S 154kV #66 BUS","신광주S/S 154kV #66 BUS(인출변경및인출GIS연결)","- 인출변경및인출GIS연결 - 제어케이불 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시첨","2017-04-01 07:00","2017-04-11 18:00","2017-04-21 07:00","2017-05-04 18:00","연속",null,null,null,201701250004,"-"]
[301,"광주전남","광주","신광주계림#1 T/L","신광주계림#1 T/L(인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-04-12 07:00","2017-04-15 18:00","2017-05-10 07:00","2017-05-13 18:00","연속",null,null,null,201701250005,"-"]
[302,"광주전남","광주","신광주장성#2 T/L","신광주장성#2 T/L(일곡#2T/L 인출변경,송전선교차로병행휴전)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험 - 일곡#2T/L 인출변경,송전선교차로병행휴전","2017-04-16 07:00","2017-04-16 18:00","2017-05-26 07:00","2017-06-03 18:00","당일",null,null,null,201701250011,"-"]
[303,"광주전남","광주","신광주일곡#2 T/L","신광주일곡#2 T/L(인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-04-16 07:00","2017-04-26 18:00","2017-05-26 07:00","2017-06-03 18:00","연속",null,null,null,201701250009,"○"]
[304,"광주전남","광주","신광주곡성#1 T/L","신광주곡성#1 T/L(인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-04-16 07:00","2017-04-26 18:00","2017-05-26 07:00","2017-06-03 18:00","연속",null,null,null,201701250010,"-"]
[305,"광주전남","순천","순천승주#2 T/L","154kV 순천옥내화 건설공사","순천옥내화 건설공사 - #4M.Tr 무부하 가압","2017-04-14 15:00","2017-04-16 15:00","취소","취소","연속",null,null,null,201701260043,"-"]
[306,"광주전남","순천","순천(옥내)S/S 154kV #2 BUS CB","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-04-29 13:00","2017-04-29 18:00","2017-04-29 13:00","2017-04-29 18:00","연속",null,null,null,201702070232,"-"]
[307,"광주전남","순천","순천(옥내)S/S 154kV #2 BUS CB","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-04-26 13:00","2017-04-26 18:00","2017-04-26 13:00","2017-04-26 18:00","연속",null,null,null,201702070225,"-"]
[308,"광주전남","순천","광양순천#2 T/L","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-04-24 08:00","2017-04-26 18:00","2017-04-24 08:00","2017-04-26 18:00","연속",null,null,null,201702070212,"-"]
[309,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2 T/L(배전반 이설:옥내화)","배전반 대체(순천변전소 옥내화_ -순천옥내 배전반 이설 -율촌 배전반 대체","2017-04-22 09:00","2017-04-23 18:00","2017-04-22 09:00","2017-04-23 18:00","연속",null,null,null,201702140637,"○"]
[310,"광주전남","순천","순천승주#1 T/L","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-04-27 00:08","2017-04-29 18:00","2017-04-27 00:08","2017-04-29 18:00","연속",null,null,null,201702070239,"-"]
[311,"광주전남","순천","여수산단개폐소 154kV #2 BUS TIE CB","여수산단개폐소 154kV #2 BUS TIE(GIS 보통점검)","17년 순천전력 변전협력 총액공사","2017-04-05 09:00","2017-04-05 18:00","2017-04-05 09:00","2017-04-05 18:00","당일",null,null,null,201702140626,"-"]
[312,"광주전남","순천","여수산단개폐소 60-61 SEC CB","154kV 여수산단개폐소 60-61 SEC GIS(보통점검)","17년 순천전력 변전협력 총액공사","2017-04-06 09:00","2017-04-06 18:00","2017-04-06 09:00","2017-04-06 18:00","당일",null,null,null,201702140627,"-"]
[313,"광주전남","순천","여수산단개폐소 65-66 SEC CB","154kV 여수산단개폐소 65-66 SEC GIS(보통점검)","17년 순천전력 변전협력 총액공사","2017-04-07 09:00","2017-04-07 18:00","2017-04-07 09:00","2017-04-07 18:00","당일",null,null,null,201702140629,"-"]
[314,"광주전남","순천","여수산단여천#2 T/L","154kV 여수산단-여천#2 T/L(여수산단 GIS 보통점검)","17년 순천전력 변전협력 총액공사","2017-04-04 09:00","2017-04-04 18:00","2017-04-04 09:00","2017-04-04 18:00","당일",null,null,null,201702140624,"-"]
[315,"광주전남","순천","여수산단여천#1 T/L","154kV 여수산단-여천#1 T/L(여수산단 GIS 보통점검)","17년 순천전력 변전협력 총액공사","2017-04-03 09:00","2017-04-03 18:00","2017-04-03 09:00","2017-04-03 18:00","당일",null,null,null,201702140622,"-"]
[316,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천#1 T/L(여천S/S 피뢰기 대체)","17년 순천전력 변전협력 총액공사","2017-04-14 09:00","2017-04-14 18:00","2017-04-14 09:00","2017-04-14 18:00","당일",null,null,null,201702140632,"-"]
[317,"광주전남","직할","나주금천#2 T/L","154kV 나주-금천#2T/L 이도조정","154kV 나주-금천#2T/L 이도조정","2017-04-05 09:00","2017-04-05 18:00","2017-04-05 09:00","2017-04-05 18:00","당일",null,null,null,201702170131,"-"]
[318,"광주전남","직할","신화순나주#2 T/L","154kV 신화순-나주#2T/L 이도조정","154kV 신화순-나주#2T/L No.44~48 이도조정","2017-04-05 09:00","2017-04-05 18:00","2017-04-05 09:00","2017-04-05 18:00","당일",null,null,null,201702150057,"-"]
[319,"대구경북","경산","경산S/S ESS #1 EM.Tr CB","경산S/S 154kV #1EM.Tr 휴전","경산s/s #1EM.Tr 및 23k DAIS, 5권선 변압기 초기점검","2017-04-03 09:00","2017-04-05 18:00","2017-04-03 09:00","2017-04-05 18:00","연속",null,null,null,201702210199,"-"]
[320,"대구경북","경산","노변효목#2 T/L","2017년 직할 가공송전 위탁","- 정밀점검: 전개소(철탑 19기)","2017-04-13 09:00","2017-04-14 18:00","2017-04-13 09:00","2017-04-14 18:00","연속",null,null,null,201702090099,"-"]
[321,"대구경북","경산","노변효목#1 T/L","2017년 직할 가공송전 위탁","- 정밀점검: 전개소(철탑 19기)","2017-04-10 09:00","2017-04-11 18:00","2017-04-10 09:00","2017-04-11 18:00","연속",null,null,null,201702090098,"-"]
[322,"대구경북","경산","범물남대구#2 T/L","2017년 직할 가공송전 위탁","- 노변-효목 정밀점검간 안전확보","2017-04-13 09:00","2017-04-13 18:00","2017-04-13 09:00","2017-04-13 18:00","당일",null,null,null,201702090101,"-"]
[323,"대구경북","경산","범물남대구#1 T/L","2017년 직할 가공송전 위탁","- 노변-효목 정밀점검간 안전확보","2017-04-10 09:00","2017-04-10 18:00","2017-04-10 09:00","2017-04-10 18:00","당일",null,null,null,201702090100,"-"]
[324,"대구경북","경산","신경산S/S 154kV #60 BUS","신경산S/S 154kV #60BUS 휴전","#1DS, LCP, CB, 상부BUS 철거/설치","2017-04-26 09:00","2017-05-05 09:00","취소","취소","연속",null,null,null,201702100009,"-"]
[325,"대구경북","경산","신경산노변 T/L","154kV 신경산-노변T/L 보호배전반 대체공사","보호반 대체","2017-04-06 09:00","2017-04-07 18:00","2017-04-06 09:00","2017-04-07 18:00","연속",null,null,null,201702060022,"-"]
[326,"대구경북","경산","진량노변 T/L","진량S/S 154kV 진량-노변T/L 휴전","진량-노변T/L 보호 PNL 대체(진량S/S,노변S/S)","2017-04-08 09:00","2017-04-09 18:00","2017-04-08 09:00","2017-04-09 18:00","연속",null,null,null,201702060014,"-"]
[327,"대구경북","구미","구미광평#1 T/L","구미S/S 154kV 구미-광평#1 T/L GIS 정밀점검 공사","-2017년 구미전력지사 GIS정밀점검 공사","2017-04-24 09:00","2017-04-26 18:00","2017-04-24 09:00","2017-04-26 18:00","연속",null,null,null,201701260025,"-"]
[328,"대구경북","달성","강창성서#1 T/L","2017년 달성전력지사 상반기 정밀점검","강창정밀(21~23)","2017-04-21 09:30","2017-04-23 18:00","취소","취소","연속",null,null,null,201702140145,"-"]
[329,"대구경북","달성","북대구다사#1 T/L","154kV 왜관분기T/L 건설사업","○ 구 간 : (기설)154kV 북대구-다사T/L No.17,18 ∼ (신설)154kV 왜관S/S ○ 지지물 : 철탑 2기 ○ 전력선 : ACSR410㎟*2B*4C - 0.075 ㎞","2017-04-17 08:00","2017-04-30 18:00","취소","취소","연속",null,null,null,201702080157,"-"]
[330,"대구경북","달성","북대구다사#2 T/L","154kV 왜관분기T/L 건설사업","○ 구 간 : (기설)154kV 북대구-다사T/L No.17,18 ∼ (신설)154kV 왜관S/S ○ 지지물 : 철탑 2기 ○ 전력선 : ACSR410㎟*2B*4C - 0.075 ㎞","2017-04-17 08:00","2017-04-30 18:00","취소","취소","연속",null,null,null,201702080159,"-"]
[331,"대구경북","달성","대구청도#1 T/L","2017년 달성전력지사 상반기 정밀점검","6244GIS정밀점검테스트선로","2017-04-06 12:00","2017-04-07 18:00","2017-04-06 12:00","2017-04-07 18:00","매일",null,null,null,201702070050,"-"]
[332,"대구경북","달성","대구청도#2 T/L","대구청도#2 T/L 정밀점검","No.1-55 정밀점검","2017-04-17 08:30","2017-04-20 18:00","2017-04-17 08:30","2017-04-20 18:00","연속",null,null,null,201702060039,"-"]
[333,"대구경북","달성","대구청도#1 T/L","대구청도#1 T/L 정밀점검","No.1~55 정밀점검","2017-04-10 08:30","2017-04-13 18:00","2017-04-10 08:30","2017-04-13 18:00","연속",null,null,null,201702060034,"-"]
[334,"대구경북","달성","강창성서#2 T/L","2017년 달성전력지사 상반기 정밀점검","GIS정밀점검(무부하25~26,정밀28~30)","2017-04-25 13:00","2017-04-30 18:00","2017-04-25 13:00","2017-04-30 18:00","연속",null,null,null,201702140167,"-"]
[335,"대구경북","달성","강창성서#1 T/L","2017년 달성전력지사 상반기 정밀점검","GIS정밀점검 성서정밀(14~16)","2017-04-14 09:30","2017-04-16 18:00","2017-04-15 07:30","2017-04-16 22:00","연속",null,null,null,201702140141,"-"]
[336,"대구경북","안동","동안동임하HP T/L","동안동S/S 동안동-임하HP T/L GIS 정밀점검공사","동안동S/S 동안동-임하HP T/L GIS 정밀점검공사 - 04.24 : 변전 병행작업 LA 교체 및 점검","2017-04-24 09:00","2017-04-26 18:00","취소","취소","연속",null,null,null,201702130165,"-"]
[337,"대구경북","직할","남대구동인#1 T/L","동인S/S 인출 OF선종교체공사","동인S/S 인출 OF선종교체공사 - 대상선로 : 154kV 남대구-동인#1T/L - 공사구간 : 남대구S/S~S/J, #8 ~ 동인S/S","2017-04-03 08:00","2017-05-31 20:00","2017-04-10 08:00","2017-06-07 20:00","연속",null,null,null,201702140351,"-"]
[338,"대구경북","포항","건천천북#2 T/L","건천천북#2 T/L GIS 보통점검","건천천북#2 T/L GIS 보통점검","2017-04-10 09:30","2017-04-10 18:00","2017-04-10 09:30","2017-04-10 18:00","당일",null,null,null,201702130087,"-"]
[339,"대구경북","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.27-34)","2017-04-14 08:00","2017-04-22 18:00","취소","취소","연속",null,null,null,201702160027,"-"]
[340,"대구경북","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.27-34)","2017-04-14 08:00","2017-04-22 18:00","취소","취소","연속",null,null,null,201702160026,"-"]
[341,"부산울산","동부산","신양산S/S 154kV #67 BUS","신양산S/S 154kV #67BUS CVT 및 LA 보통점검","신양산S/S 154kV #67BUS CVT 및 LA 보통점검","2017-04-07 13:30","2017-04-07 17:00","2017-04-07 13:30","2017-04-07 17:00","당일",null,null,null,201702100513,"-"]
[342,"부산울산","동부산","신양산S/S 154kV #61 BUS","신양산S/S 154kV #61BUS CVT 보통점검","신양산S/S 154kV #61BUS CVT 보통점검","2017-04-07 09:30","2017-04-07 13:30","2017-04-07 09:30","2017-04-07 13:30","당일",null,null,null,201702100508,"-"]
[343,"부산울산","동부산","신양산S/S 154kV #65 BUS","신양산S/S 154kV #65BUS LA 보통점검","신양산S/S 154kV #65BUS LA 보통점검","2017-04-06 13:30","2017-04-06 17:00","2017-04-06 13:30","2017-04-06 17:00","당일",null,null,null,201702100510,"-"]
[344,"부산울산","동부산","신양산S/S 154kV #60 BUS","신양산S/S 154kV #60BUS LA 보통점검","신양산S/S 154kV #60BUS LA 보통점검","2017-04-06 09:30","2017-04-06 13:30","2017-04-06 09:30","2017-04-06 13:30","당일",null,null,null,201702100507,"-"]
[345,"부산울산","동부산","신양산S/S 154kV #62 BUS","신양산S/S 154kV #62BUS CVT 및 LA 보통점검","1.신양산 154kV #62BUS CVT 및 LA 보통점검 2. 6200GCB 보통점검","2017-04-05 09:30","2017-04-05 17:00","2017-04-05 09:30","2017-04-05 17:00","당일",null,null,null,201702100511,"-"]
[346,"부산울산","동부산","우동대연 T/L","우동S/S 170kV GIS 정밀점검공사","우동S/S 170kV 627 GIS 정밀점검(우동-대연T/L)","2017-04-17 09:00","2017-04-19 18:00","2017-04-17 09:00","2017-04-19 18:00","연속",null,null,null,201702100514,"-"]
[347,"부산울산","북부산","매리호포#2 T/L","2017년 북부산변전협력회사 총액공사","호포-매리#2T/L GIS 보통점검 (매리S/S 617 휴전)","2017-04-16 10:00","2017-04-16 18:00","2017-04-16 10:00","2017-04-16 18:00","당일",null,null,null,201702090379,"-"]
[348,"부산울산","북부산","매리호포#1 T/L","2017년 북부산변전협력회사 총액공사","호포-매리#1T/L GIS 보통점검 (매리S/S 647 휴전)","2017-04-15 10:00","2017-04-15 18:00","2017-04-15 10:00","2017-04-15 18:00","당일",null,null,null,201702090378,"-"]
[349,"부산울산","북부산","모라엄궁#2 T/L","모라-엄궁#2T/L 보호계전기 성능개선","모라-엄궁#2T/L 보호계전기 성능개선 (모라667,엄궁657 양측작업)","2017-04-04 10:00","2017-04-04 18:00","2017-04-04 10:00","2017-04-04 18:00","당일",null,null,null,201702090381,"-"]
[350,"부산울산","북부산","북부산호포 T/L","북부산S/S 154kV 취약설비 현대화 공사","북부산S/S 북부산-호포T/L GIS Line PT 설치 안전이격 확보","2017-04-08 09:00","2017-04-08 18:00","2017-04-08 09:00","2017-04-08 18:00","당일",null,null,null,201702210139,"-"]
[351,"부산울산","북부산","북부산삼랑진PP#2 T/L","북부산S/S 154kV 취약설비 현대화 공사","북부산S/S 북부산-삼랑진PP#2T/L GIS Line PT 설치 안전이격 확보","2017-04-06 09:00","2017-04-06 18:00","2017-04-06 09:00","2017-04-06 18:00","당일",null,null,null,201702210137,"-"]
[352,"부산울산","북부산","북부산삼랑진PP#1 T/L","북부산S/S 154kV 취약설비 현대화 공사","북부산S/S 북부산-삼랑진PP#1T/L GIS Line PT 설치 안전이격 확보","2017-04-07 09:00","2017-04-07 18:00","2017-04-07 09:00","2017-04-07 18:00","당일",null,null,null,201702210138,"○"]
[353,"부산울산","북부산","북부산양산 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 62,67BUS PT 설치 안전이격 관련 6G7 휴전","2017-04-03 08:00","2017-04-03 18:00","2017-04-03 08:00","2017-04-03 18:00","당일",null,null,null,201702090371,"-"]
[354,"부산울산","북부산","양산삼랑진PP T/L","양산S/S 취약설비 현대화공사","- 양산S/S 154kV 양산-삼랑진T/L 가수전 GIS 설치 - 제어케이블 이설 - 인입전력선 연결, 시험가압(48H)","2017-04-24 09:00","2017-04-30 18:00","2017-04-24 09:00","2017-04-30 18:00","연속",null,null,null,201702080161,"-"]
[355,"부산울산","북부산","북부산양산 T/L","양산S/S 취약설비 현대화공사","- 양산S/S 154kV 북부산-양산T/L 가수전 GIS 설치 - 제어케이블 이설 - 인입전력선 연결, 시험가압(48H)","2017-04-19 09:00","2017-04-23 18:00","2017-04-19 09:00","2017-04-23 18:00","연속",null,null,null,201702080153,"-"]
[356,"부산울산","북부산","양산삼랑진PP T/L","양산S/S 취약설비 현대화공사","양산S/S 154kV 북부산-양산T/L 가수전 GIS 설치 시 안전이격 확보","2017-04-19 09:00","2017-04-21 18:00","2017-04-19 09:00","2017-04-21 18:00","연속",null,null,null,201702080158,"-"]
[357,"부산울산","북부산","양산산막#1 T/L","17년 가공송전 협력업체 공사","양산-산막#1 10호 중단 부하측 압축인류크램프 교체","2017-04-10 08:00","2017-04-10 18:00","2017-04-10 08:00","2017-04-10 18:00","당일",null,null,null,201702080286,"-"]
[358,"부산울산","북부산","호포S/S 154kV #1 BUS","2017년 북부산변전협력회사 총액공사","호포S/S 노후 CPD PNL 교체","2017-04-01 09:00","2017-04-01 14:00","취소","취소","당일",null,null,null,201702150148,"-"]
[359,"부산울산","북부산","호포물금 T/L","호포-물금T/L 보호계전기 성능개선","호포-물금T/L 보호계전기 성능개선 (호포657,물금647 양측작업)","2017-04-05 10:00","2017-04-05 18:00","2017-04-05 10:00","2017-04-05 18:00","당일",null,null,null,201702090382,"-"]
[360,"부산울산","북부산","호포S/S 154kV #1 BUS","2017년 북부산변전협력회사 총액공사","호포S/S 노후 CPD PNL 교체","2017-04-02 09:00","2017-04-02 14:00","취소","취소","당일",null,null,null,201702150150,"-"]
[361,"부산울산","북부산","호포S/S 154kV #2 BUS","2017년 북부산변전협력회사 총액공사","호포S/S 노후 CPD PNL 교체","2017-04-01 14:00","2017-04-01 18:00","취소","취소","당일",null,null,null,201702150149,"-"]
[362,"부산울산","서부산","서부산S/S 154kV #66 BUS","서부산S/S #2M.Tr 2차 GIS 정밀점검","서부산S/S #2M.Tr 2차 GIS 정밀점검 (#2M.Tr 2차 CB(6244)+2DS(6242) 정밀점검)","2017-04-11 08:00","2017-04-12 20:00","2017-04-11 08:00","2017-04-12 20:00","연속",null,null,null,201702090081,"○"]
[363,"부산울산","서부산","서부산S/S 154kV #66 BUS","서부산S/S 서부산-엄궁#2 T/L GIS 정밀점검","서부산S/S 서부산-엄궁#2 T/L GIS 정밀점검 (서부산-엄궁#2T/L CB(6G7) + 2DS(6G2) 정밀점검)","2017-04-28 08:00","2017-04-29 20:00","2017-04-28 08:00","2017-04-29 20:00","연속",null,null,null,201702090094,"○"]
[364,"부산울산","서부산","서부산S/S #3 S/T CB","서부산S/S #3 S/T(657) GIS 보통점검","서부산S/S #3 S/T(657) GIS 보통점검","2017-04-28 10:00","2017-04-28 18:00","2017-04-28 10:00","2017-04-28 18:00","당일",null,null,null,201702140165,"-"]
[365,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산S/S #1M.Tr 2차 GIS 정밀점검","서부산S/S #1M.Tr 2차 GIS 정밀점검 (#1M.Tr 2차 1DS(6141) 정밀점검)","2017-04-21 08:00","2017-04-21 20:00","2017-04-21 08:00","2017-04-21 20:00","당일",null,null,null,201702090086,"-"]
[366,"부산울산","서부산","서부산S/S 154kV #65 BUS","서부산S/S #1M.Tr 2차 GIS 정밀점검","서부산S/S #1M.Tr 2차 GIS 정밀점검 (#1M.Tr 2차 CB(6144)+2DS(6142) 정밀점검)","2017-04-22 08:00","2017-04-23 20:00","2017-04-22 08:00","2017-04-23 20:00","연속",null,null,null,201702090087,"-"]
[367,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산S/S 서부산-엄궁#1 T/L GIS 정밀점검","서부산S/S 서부산-엄궁#1 T/L GIS 정밀점검 (서부산-엄궁#1T/L 1DS(6F1) 정밀점검)","2017-04-24 08:00","2017-04-24 20:00","2017-04-24 08:00","2017-04-24 20:00","당일",null,null,null,201702090089,"○"]
[368,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 서부산-엄궁#1 T/L GIS 정밀점검","서부산S/S 서부산-엄궁#1 T/L GIS 정밀점검 (6F7 CB 정밀점검)","2017-04-24 08:00","2017-04-26 20:00","2017-04-24 08:00","2017-04-26 20:00","연속",null,null,null,201702090088,"○"]
[369,"부산울산","서부산","서부산S/S 154kV #66 BUS","서부산S/S 서부산-엄궁#1 T/L GIS 정밀점검","서부산S/S 서부산-엄궁#1 T/L GIS 정밀점검 (서부산-엄궁#1T/L CB(6F7) + 2DS(6F2) 정밀점검)","2017-04-25 08:00","2017-04-26 20:00","2017-04-25 08:00","2017-04-26 20:00","연속",null,null,null,201702090090,"○"]
[370,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산S/S 서부산-엄궁#2 T/L GIS 정밀점검","서부산S/S 서부산-엄궁#2 T/L GIS 정밀점검 (서부산-엄궁#2T/L 1DS(6G1) 정밀점검)","2017-04-27 08:00","2017-04-27 20:00","2017-04-27 08:00","2017-04-27 20:00","당일",null,null,null,201702090093,"○"]
[371,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 서부산-엄궁#2 T/L GIS 정밀점검","서부산S/S 서부산-엄궁#2 T/L GIS 정밀점검 (6G7 CB 정밀점검)","2017-04-27 08:00","2017-04-29 20:00","2017-04-27 08:00","2017-04-29 20:00","연속",null,null,null,201702090092,"-"]
[372,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산S/S #2M.Tr 2차 GIS 정밀점검","서부산S/S #2M.Tr 2차 GIS 정밀점검 (#2M.Tr 2차 1DS(6241) 정밀점검)","2017-04-10 08:00","2017-04-10 20:00","2017-04-10 08:00","2017-04-10 20:00","당일",null,null,null,201702090080,"○"]
[373,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S #2M.Tr 2차 GIS 정밀점검(시험가압)","서부산S/S #2M.Tr 2차 GIS 정밀점검 시험가압 (#2M.Tr 2차 1DS(6241) 정밀점검)","2017-04-10 19:00","2017-04-10 20:00","2017-04-10 19:00","2017-04-10 20:00","당일",null,null,null,201702200054,"○"]
[374,"부산울산","서부산","신녹산명지#2 T/L","R-Type 조립식 접속함 교체작업","R-Type 조립식접속함을 Flat Tpye으로 교체작업 시행(7개소, 21set)","2017-04-01 09:00","2017-04-15 18:00","2017-04-01 09:00","2017-04-15 18:00","연속",null,null,null,201702100512,"-"]
[375,"부산울산","울산","신울산울산#2 T/L","2017년 울산전력지사 170kV 개폐장치 정밀점검공사","신울산S/S 6300 GCB 시험가압","2017-04-28 17:00","2017-04-28 18:00","2017-04-28 17:00","2017-04-28 18:00","당일",null,null,null,201702100571,"-"]
[376,"부산울산","울산","신울산S/S 154kV #68 BUS","2017년 울산전력지사 170kV 개폐장치 정밀점검공사","신울산S/S 6300 GCB 시험가압","2017-04-28 17:00","2017-04-28 18:00","2017-04-28 17:00","2017-04-28 18:00","당일",null,null,null,201702220144,"○"]
[377,"부산울산","울산","신울산S/S 154kV #3 BUS TIE CB","2017년 울산전력지사 170kV 개폐장치 정밀점검공사","신울산S/S 6300 GCB 정밀점검","2017-04-27 08:00","2017-04-28 18:00","2017-04-27 08:00","2017-04-28 18:00","연속",null,null,null,201702100570,"○"]
[378,"부산울산","울산","방어진영남TP#1 T/L","2017년 울산전력지사 170kV 개폐장치 정밀점검","영남화력 637 GIS 정밀점검 및 방어진 647 GIS 초기점검","2017-04-22 08:00","2017-04-23 18:00","2017-04-22 08:00","2017-04-23 18:00","연속",null,null,null,201702100568,"-"]
[379,"부산울산","울산","방어진영남TP#2 T/L","2017년 울산전력지사 170kV 개폐장치 정밀점검","영남화력 647 GIS 정밀점검 및 방어진 637 GIS 초기점검","2017-04-29 08:00","2017-04-30 18:00","2017-04-29 08:00","2017-04-30 18:00","연속",null,null,null,201702100569,"-"]
[380,"부산울산","울산","옥동외동#2 T/L","'16-17년 울산전력지사 변전협력회사 총액공사","옥동S/S 축소형Mosaic(687) 철거","2017-04-04 11:00","2017-04-04 13:00","2017-04-04 11:00","2017-04-04 13:00","당일",null,null,null,201702100563,"-"]
[381,"부산울산","울산","옥동외동#1 T/L","'16-17년 울산전력지사 변전협력회사 총액공사","옥동S/S 축소형Mosaic 657 철거","2017-04-04 09:00","2017-04-04 11:00","2017-04-04 09:00","2017-04-04 11:00","당일",null,null,null,201702100562,"-"]
[382,"부산울산","울산","용연처용#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 651DS 대체관련 651DS(미투입) 및 #1BUS 시험가압","2017-04-04 18:00","2017-04-05 18:00","2017-04-04 18:00","2017-04-05 18:00","연속",null,null,null,201702100552,"-"]
[383,"부산울산","직할","학장개금#1 T/L","2017년 직할 관내 170kV GIS 정밀점검공사","개금S/S 학장-개금 #1T/L GIS 정밀점검","2017-04-25 08:00","2017-04-27 18:00","2017-04-25 08:00","2017-04-27 18:00","연속",null,null,null,201702090154,"-"]
[384,"부산울산","직할","학장개금#2 T/L","2017년 직할 관내 170kV GIS 정밀점검공사","개금S/S 학장-개금 #2T/L GIS 정밀점검","2017-04-20 08:00","2017-04-22 18:00","2017-04-20 08:00","2017-04-22 18:00","연속",null,null,null,201702090155,"-"]
[385,"부산울산","직할","정보대연 T/L","2017년 직할 관내 170kV GIS 정밀점검공사","대연S/S 정보-대연 T/L GIS 정밀점검","2017-04-13 08:00","2017-04-15 18:00","2017-04-13 08:00","2017-04-15 18:00","연속",null,null,null,201702090165,"-"]
[386,"부산울산","직할","범일서면#1 T/L","2017년도 직할 변전협력회사 총액공사","범일,서면S/S 범일-서면#1T/L 보호배전반 대체","2017-04-17 09:00","2017-04-19 18:00","2017-04-17 09:00","2017-04-19 18:00","연속",null,null,null,201702080216,"-"]
[387,"부산울산","직할","범일서면#2 T/L","2017년도 직할 변전협력회사 총액공사","범일,서면S/S 범일-서면#2T/L 보호배전반 대체","2017-04-24 09:00","2017-04-26 18:00","2017-04-24 09:00","2017-04-26 18:00","연속",null,null,null,201702080235,"-"]
[388,"경남","직할","신김해삼정#1 T/L","신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체공사","안전거리확보휴전(345kV 신김해-삼천포화력T/L 전력선 교체공사)","2017-04-30 07:00","2017-04-30 19:00","2017-04-30 07:00","2017-04-30 19:00","당일",null,null,null,201702070326,"-"]
[389,"경남","직할","신김해삼정#2 T/L","신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체공사","안전거리확보휴전(345kV 신김해-삼천포화력T/L 전력선 교체공사)","2017-04-30 07:00","2017-04-30 19:00","2017-04-30 07:00","2017-04-30 19:00","당일",null,null,null,201702070327,"-"]
[390,"경남","직할","신김해삼정#1 T/L","신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체공사","안전거리확보휴전(345kV 신김해-삼천포화력T/L 전력선 교체공사)","2017-04-16 07:00","2017-04-16 19:00","2017-04-16 07:00","2017-04-16 19:00","당일",null,null,null,201702070327,"-"]
[391,"경남","직할","신김해삼정#2 T/L","신김해-삼천포화력T/L 214-217호 등 6개구간 전력선 교체공사","안전거리확보휴전(345kV 신김해-삼천포화력T/L 전력선 교체공사)","2017-04-16 07:00","2017-04-16 19:00","2017-04-16 07:00","2017-04-16 19:00","당일",null,null,null,201702070327,"-"]
[392,"경남","직할","완암안민#1 T/L","154kV 삼정-완암T/L 8~10호 등 4개구간 전력선 교체공사","안전이격확보휴전(154kV 삼정-완암 #1T/L 전력선 교체공사)","2017-04-23 07:00","2017-04-27 18:00","2017-04-23 07:00","2017-04-27 18:00","연속",null,null,null,201702070327,"-"]
[393,"경남","직할","완암안민#2 T/L","154kV 삼정-완암T/L 8~10호 등 4개구간 전력선 교체공사","안전이격확보휴전(154kV 삼정-완암 #2T/L 전력선 교체공사)","2017-04-19 07:00","2017-04-23 18:00","2017-04-19 07:00","2017-04-23 18:00","연속",null,null,null,201702070327,"-"]
[394,"경남","직할","차룡창공#2 T/L","2017년 경남 직할 개폐장치 정밀점검","차룡S/S #4M.Tr 1차 GIS 정밀점검(시험가압)","2017-04-29 16:30","2017-04-29 17:30","2017-04-29 16:30","2017-04-29 17:30","당일",null,null,null,201702070327,"-"]
[395,"경남","진주","함양거창#1 T/L","154kV거창-합천#1T/L SB댐퍼 교체","154kV거창-합천#1T/L SB댐퍼 교체(1~82호) 안전이격 확보용","2017-04-30 07:00","2017-04-30 18:00","2017-04-30 07:00","2017-04-30 18:00","매일",null,null,null,201702070327,"-"]
[396,"경남","진주","함양거창#2 T/L","154kV거창-합천#2T/L SB댐퍼 교체","154kV거창-합천#2T/L SB댐퍼 교체(1~82호) 안전이격 확보용","2017-04-23 07:00","2017-04-23 18:00","2017-04-23 07:00","2017-04-23 18:00","매일",null,null,null,201702070327,"-"]
[397,"경남","진주","의령산청 T/L","의령S/S 154kV 의령-산청T/L CPD 초기점검","의령S/S 154kV 의령-산청T/L CPD 초기점검 - 병행작업(러버히터 설치)","2017-04-30 14:00","2017-04-30 18:30","2017-04-30 14:00","2017-04-30 18:30","당일",null,null,null,201702070327,"-"]
[398,"경남","진주","의령함양 T/L","의령S/S 154kV 의령-함양T/L CPD 초기점검","의령S/S 154kV 의령-함양T/L CPD 초기점검 - 병행작업(러버히터 설치)","2017-04-30 09:30","2017-04-30 14:00","2017-04-30 09:30","2017-04-30 14:00","당일",null,null,null,201702070327,"-"]
[399,"경남","진주","합천수력#2 T/L","154kV거창-합천#1T/L SB댐퍼 교체","154kV거창-합천#1T/L SB댐퍼 교체(1~82호) 안전이격 확보용","2017-04-30 07:00","2017-04-30 18:00","2017-04-30 07:00","2017-04-30 18:00","매일",null,null,null,201702070327,"-"]
[400,"경남","진주","합천수력#1 T/L","154kV거창-합천#2T/L SB댐퍼 교체","154kV거창-합천#2T/L SB댐퍼 교체(1~82호) 안전이격 확보용","2017-04-23 07:00","2017-04-23 18:00","2017-04-23 07:00","2017-04-23 18:00","매일",null,null,null,201702070327,"-"]
[401,"경남","통영","고성통영 T/L","154kV 고성안정#2T/L SB댐퍼 설치 안전확보","154kV 고성안정#2T/L SB댐퍼 설치 병가선로 안전확보","2017-04-09 07:00","2017-04-09 18:00","2017-04-09 07:00","2017-04-09 18:00","당일",null,null,null,201702070327,"-"]
[402,"경남","통영","신고성삼천포#1 T/L","신고성S/S 신고성-삼천포#1T/L GIS 보통점검","신고성S/S 신고성-삼천포#1T/L GIS 보통점검 신고성S/S 신고성-삼천포#1T/L LA 보통점검","2017-04-03 09:30","2017-04-03 18:30","2017-04-03 09:30","2017-04-03 18:30","당일",null,null,null,201702070327,"-"]
[403,"경남","통영","신고성거제#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","154kV 신고성-거제T/L 2호 설치 및 전력선 이설","2017-04-01 07:00","2017-04-02 18:00","2017-04-01 07:00","2017-04-02 18:00","연속",null,null,null,201702070327,"-"]
[404,"경남","통영","신고성삼천포#2 T/L","신고성S/S 신고성-삼천포#2T/L GIS 보통점검","신고성S/S 신고성-삼천포#2T/L GIS 보통점검 신고성S/S 신고성-삼천포#2T/L LA 보통점검","2017-04-07 09:30","2017-04-07 18:30","2017-04-07 09:30","2017-04-07 18:30","당일",null,null,null,201702070327,"-"]
[405,"경남","통영","신고성통영 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 철탑 설치 및 전선이설","2017-04-30 07:00","2017-04-30 19:00","2017-04-30 07:00","2017-04-30 19:00","당일",null,null,null,201702070327,"-"]
[406,"경남","통영","신고성거제#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 철탑 설치 및 전선이설","2017-04-23 07:00","2017-04-23 19:00","2017-04-23 07:00","2017-04-23 19:00","당일",null,null,null,201702070327,"-"]
[407,"경남","통영","신고성거제#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 철탑 설치 및 전선이설","2017-04-22 07:00","2017-04-22 19:00","2017-04-22 07:00","2017-04-22 19:00","당일",null,null,null,201702070327,"-"]
[408,"경남","통영","신고성고성 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 철탑 설치 및 전선이설","2017-04-29 07:00","2017-04-29 19:00","2017-04-29 07:00","2017-04-29 19:00","당일",null,null,null,201702070327,"-"]
[409,"경남","함안","마산수출#1 T/L","마산S/S 마산-수출#1T/L GIS 정밀점검","마산S/S 마산-수출#1T/L GIS 정밀점검","2017-04-01 08:30","2017-04-02 19:30","2017-04-01 08:30","2017-04-02 19:30","연속",null,null,null,201702070327,"-"]
[410,"경남","함안","신마산마산#2 T/L","마산S/S 마산-수출#1T/L GIS 정밀점검 시험가압","마산S/S 마산-수출#1T/L GIS 정밀점검 시험가압","2017-04-01 18:30","2017-04-01 19:30","2017-04-01 18:30","2017-04-01 19:30","당일",null,null,null,201702070327,"-"]
[411,"경남","함안","신마산마산#2 T/L","마산S/S 마산-수출#1T/L GIS 정밀점검 시험가압","마산S/S 마산-수출#1T/L GIS 정밀점검 시험가압","2017-04-02 18:30","2017-04-02 19:30","2017-04-02 18:30","2017-04-02 19:30","당일",null,null,null,201702070327,"-"]
[412,"경남","함안","마산수출#2 T/L","마산S/S 마산-수출#2T/L GIS 정밀점검","마산S/S 마산-수출#2T/L GIS 정밀점검","2017-04-08 08:30","2017-04-09 19:30","2017-04-08 08:30","2017-04-09 19:30","연속",null,null,null,201702070327,"-"]
[413,"경남","함안","신마산마산#2 T/L","마산S/S 마산-수출#2T/L GIS 정밀점검 시험가압","마산S/S 마산-수출#2T/L GIS 정밀점검 시험가압","2017-04-08 18:30","2017-04-08 19:30","2017-04-08 18:30","2017-04-08 19:30","당일",null,null,null,201702070327,"-"]
[414,"경남","함안","신마산마산#2 T/L","마산S/S 마산-수출#2T/L GIS 정밀점검 시험가압","마산S/S 마산-수출#2T/L GIS 정밀점검 시험가압","2017-04-09 18:30","2017-04-09 19:30","2017-04-09 18:30","2017-04-09 19:30","당일",null,null,null,201702070327,"-"]
[415,"경남","함안","마산수출#2 T/L","마산S/S 신마산-마산#2T/L GIS 정밀점검 시험가압","마산S/S 신마산-마산#2T/L GIS 정밀점검 시험가압","2017-04-16 18:30","2017-04-16 19:30","2017-04-16 18:30","2017-04-16 19:30","당일",null,null,null,201702070327,"-"]
[416,"경남","함안","신마산마산#2 T/L","마산S/S 신마산-마산#2T/L GIS 정밀점검","마산S/S 신마산-마산#2T/L GIS 정밀점검","2017-04-15 08:30","2017-04-16 19:30","2017-04-15 08:30","2017-04-16 19:30","연속",null,null,null,201702070327,"-"]
[417,"경남","함안","마산수출#2 T/L","마산S/S 신마산-마산#2T/L GIS 정밀점검 시험가압","마산S/S 신마산-마산#2T/L GIS 정밀점검 시험가압","2017-04-15 18:30","2017-04-15 19:30","2017-04-15 18:30","2017-04-15 19:30","당일",null,null,null,201702070327,"-"]
[418,"경남","함안","청도밀양#1 T/L","청도밀양#1,2T/L 정밀점검","청도밀양#1,2T/L 정밀점검","2017-04-14 08:30","2017-04-16 18:30","2017-04-08 08:30","2017-04-08 18:30","연속",null,null,null,201702070327,"-"]
[419,"경남","함안","청도밀양#2 T/L","청도밀양#1,2T/L 정밀점검","청도밀양#1,2T/L 정밀점검","2017-04-14 08:30","2017-04-16 18:30","2017-04-09 08:30","2017-04-10 18:30","연속",null,null,null,201702070327,"-"]
[420,"경남","함안","신마산S/S 154kV #60 BUS","신마산S/S #60BUS PT 초기점검","신마산S/S #60BUS PT 초기점검","2017-04-09 09:30","2017-04-09 17:30","2017-04-09 09:30","2017-04-09 17:30","당일",null,null,null,201702070327,"-"]
[421,"경남","함안","신마산S/S 60-61-0 SEC CB","신마산S/S 60-61-0 SEC GCB 보통점검","신마산S/S 60-61-0 SEC GCB 보통점검","2017-04-02 09:30","2017-04-02 17:30","2017-04-02 09:30","2017-04-02 17:30","당일",null,null,null,201702070327,"-"]

{"sheet":"한수원","index":3,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,12,3,12],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,19,3,19],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18]]}
["2017년도 4월 휴전계획표(한국수력원자력)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","한빛3발","#5 주변압기","5호기 11차 계획예방정비\n#5 주변압기 점검\n* 조작차단기 : PCB 7D00, 7D71","○ 소내자동전원절체 시험 수행\n○ SAT 실부하 위상각 측정\n○ 보호계전기 개체/연동시험 등","2017-04-03T09:00:00","2017-04-03T17:00:00","2017-04-03T09:00:00","2017-04-03T17:00:00","연속","Y"]
[2,"한울본부","한울3발","#6 대기보조변압기","6호기 9차 계획예방정비 \n* 조작차단기 : PCB 7B00, 7B72","○ 대기보조변압기(02M) 교체","2017-04-30T18:00:00","2017-06-05T18:00:00","2017-04-30T18:00:00","2017-06-05T18:00:00","연속","Y"]

{"sheet":"중부","index":4,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,8,2,9],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,17,3,17],[2,18,3,18],[2,19,3,19],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,15,3,15],[2,16,3,16],[2,14,3,14]]}
["2017년도 4월 휴전계획(신보령화력건설본부)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"청양변전소","신보령","청양-신보령화력T/L 송전선로","청양-신보령화력T/L 송전선로 초기점검","송전선로 최초가압 후 초기점검 실시","2017-04-03T09:00:00","2017-04-03T18:00:00","2017-04-03T09:00:00","2017-04-03T18:00:00","연속"]
[2,"청양변전소","신보령","청양-신보령화력T/L 송전선로","청양-신보령화력T/L 송전선로 초기점검","송전선로 최초가압 후 초기점검 실시","2017-04-04T09:00:00","2017-04-04T18:00:00","2017-04-04T09:00:00","2017-04-04T18:00:00","연속"]