{"text_format":"2","workbook":"xlsx","n_sheets":6,"sheets":["765송부","345송부","154송부","한수원","남부","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":10,"n_cols":16,"rows_kept":10,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 5월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr A-1","신가평S/S M.Tr 2차측 장경간 GIB 구조개선 공사","신가평S/S M.Tr 2차측 장경간 GIB 구조개선 공사","2017-05-15 09:00","2017-06-30 18:00","2017-05-15 09:00","2017-06-30 18:00","연속",null,null,null,201702160135]
[2,"경기","성남","신안성S/S #4 M.Tr A-1","신안성S/S 765kV #4M.Tr 정밀점검","신안성S/S #4M.Tr 정밀점검 신안성S/S 8772,8700 GIS 정밀점검 신안성S/S #4M.Tr 345kV GIS 구조개선","2017-05-15 10:00","2017-07-15 18:00","2017-05-15 10:00","2017-07-15 18:00","연속",null,null,null,201703140488]
[3,"강원","태백","신태백S/S #3 M.Tr A-1","2017년 신태백S/S 765kV M.Tr 정밀점검 공사","○ 신태백S/S 765kV #3M.Tr 정밀점검 공사 ○ 신태백S/S 800kV #3M.Tr 1차 GIS 정밀점검 공사 ○ 신태백S/S 362kV #3M.Tr 2차 GIS 정밀점검 공사","2017-05-15 09:00","2017-07-31 18:00","2017-05-15 09:00","2017-07-31 18:00","연속",null,null,null,201703130302]
[4,"대전충남","서산","당진T/P 6호기 1차 CB","'17년 서산P/O 765kV GIS 보통점검 공사","당진화력 765kV 6호기 1차(8571) GIS 보통점검","2017-05-29 09:00","2017-05-30 18:00","2017-05-29 09:00","2017-05-30 18:00","연속",null,null,null,201703090080]
[5,"대구경북","영주","신한울S/S #1 M.Tr A-1","신한울S/S 765kV #1M.Tr휴전","7144, 4189-1, 4189-2 CB 초기점검","2017-05-24 09:00","2017-05-24 18:00","2017-05-24 09:00","2017-05-24 18:00","당일",null,null,null,201703070358]
[6,"대구경북","영주","신한울S/S #2 M.Tr A-1","신한울S/S 765kV #2M.Tr휴전","7244, 4289-1, 4289-2 CB 초기점검","2017-05-25 09:00","2017-05-25 18:00","2017-05-25 09:00","2017-05-25 18:00","당일",null,null,null,201703070359]

{"sheet":"345송부","index":1,"n_rows":251,"n_cols":16,"rows_kept":251,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 5월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S #2 M.Tr A","신양재S/S 소내변압기 대체공사 - 변전협력","신양재S/S #2S.Tr 대체공사","2017-05-29 10:00","2017-05-31 18:00","2017-05-29 10:00","2017-05-31 18:00","연속",null,null,null,201703170173]
[2,"남서울","강남","신양재S/S #1 M.Tr A","신양재S/S 소내변압기 대체공사 - 변전협력","신양재S/S #1S.Tr 대체공사","2017-05-22 10:00","2017-05-24 18:00","2017-05-22 10:00","2017-05-24 18:00","연속",null,null,null,201703170172]
[3,"남서울","영등포","영서S/S #1 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-05-22 08:00","2017-05-22 18:00","2017-05-22 08:00","2017-05-22 18:00","당일",null,null,null,201703170030]
[4,"인천","김포","신김포S/S #2 M.Tr","신김포S/S #2M.Tr 362kV GIS 보통점검","신김포S/S #1M.Tr 1,2.3차(7472, 6244, 4289) CB 보통점검","2017-05-15 10:00","2017-05-19 18:00","2017-05-15 10:00","2017-05-19 18:00","연속",null,null,null,201703130487]
[5,"인천","김포","신김포S/S 345KV 70-71 SEC CB","신김포S/S 345KV 70-71 SEC GIS 기기점검","신김포S/S 345KV 70-71 SEC GIS 기기점검","2017-05-30 10:00","2017-05-30 18:00","2017-05-30 10:00","2017-05-30 18:00","당일",null,null,null,201703200110]
[6,"인천","김포","신김포S/S 345KV 75-76 SEC CB","신김포S/S 345KV 75-76 SEC GIS 기기점검","신김포S/S 345KV 75-76 SEC GIS 기기점검","2017-05-31 10:00","2017-05-31 18:00","2017-05-31 10:00","2017-05-31 18:00","당일",null,null,null,201703200111]
[7,"인천","김포","신김포S/S #1 M.Tr","신김포S/S #1M.Tr 362kV GIS 보통점검","신김포S/S #1M.Tr 1,2.3차(7372, 6144, 4189) CB 보통점검","2017-05-22 10:00","2017-05-26 18:00","2017-05-22 10:00","2017-05-26 18:00","연속",null,null,null,201703130485]
[8,"인천","시흥","신시흥#1S/S #1 M.Tr A","신시흥#1S/S #1 M.Tr 3차 GPT 교체","신시흥#1S/S #1 M.Tr 3차 GPT 교체","2017-05-29 09:30","2017-05-31 18:00","2017-05-29 09:30","2017-05-31 18:00","연속",null,null,null,201703090417]
[9,"인천","시흥","신시흥영흥TP#4 T/L","345kV 신시흥신안산T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 관련 안전이격거리확보 기(101호)","2017-05-12 09:00","2017-05-12 12:00","취소","취소","당일",null,null,null,201703080124]
[10,"인천","시흥","신시흥영흥TP#3 T/L","345kV 신시흥영흥T/L 피뢰기설치 및 전선접속개소 교체공사","345kV 신시흥영흥T/L 피뢰기설치(35기) 및 전선접속개소 교체공사","2017-05-16 08:00","2017-05-20 18:00","2017-05-16 08:00","2017-05-20 18:00","연속",null,null,null,201703100163]
[11,"인천","시흥","신시흥영흥TP#4 T/L","345kV 신시흥영흥T/L 피뢰기설치 공사","345kV 신시흥영흥T/L 피뢰기설치(35기)","2017-05-11 08:00","2017-05-15 18:00","2017-05-11 08:00","2017-05-15 18:00","연속",null,null,null,201703100166]
[12,"인천","시흥","신시흥#2S/S #5M.Tr A","신시흥#2S/S #5M.Tr 정밀점검","신시흥#2S/S #5M.Tr 정밀점검","2017-05-10 08:00","2017-05-21 18:00","2017-05-10 08:00","2017-05-21 18:00","연속",null,null,null,201703090286]
[13,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥영흥T/L 피뢰기설치 및 전선접속개소 교체공사","345kV 신시흥영흥T/L 피뢰기설치(35기) 및 전선접속개소 교체공사","2017-05-16 08:00","2017-05-21 18:00","2017-05-16 08:00","2017-05-21 18:00","연속",null,null,null,201703100168]
[14,"인천","시흥","신시흥영흥TP#2 T/L","345kV 신시흥영흥T/L 피뢰기설치 공사","345kV 신시흥영흥T/L 피뢰기설치(35기)","2017-05-11 08:00","2017-05-15 18:00","2017-05-11 08:00","2017-05-15 18:00","연속",null,null,null,201703100167]
[15,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 7400 CB CT 교체공사 이격거리 확보","영흥S/Y 7400 CB CT 교체공사 이격거리 확보","2017-05-11 08:00","2017-05-11 20:00","취소","취소","당일",null,null,null,201703090293]
[16,"인천","시흥","영흥1TP-영흥2TP #1T/L","345kV 신시흥영흥T/L 피뢰기설치공사 및 정밀점검","345kV 신시흥영흥T/L 피뢰기설치공사(6기) 및 정밀점검","2017-05-21 08:00","2017-05-21 18:00","2017-05-21 08:00","2017-05-21 18:00","연속",null,null,null,201703100171]
[17,"인천","시흥","영흥1TP-영흥2TP #2T/L","345kV 신시흥영흥T/L 피뢰기설치공사 및 정밀점검","345kV 신시흥영흥T/L 피뢰기설치공사(6기) 및 정밀점검","2017-05-20 08:00","2017-05-20 18:00","2017-05-20 08:00","2017-05-20 18:00","연속",null,null,null,201703100170]
[18,"인천","인천","서인천C/C 신김포서인천CC T/L CB (7171)","서인천CC 7171 GIS 하자점검 공사","서인천CC 7171 GIS 하자점검 공사","2017-05-25 08:00","2017-05-25 18:00","2017-05-25 08:00","2017-05-25 18:00","당일",null,null,null,201703140373]
[19,"인천","인천","서인천C/C 신김포서인천CCT/L-#1 M.Tr1차CB (7100)","서인천CC 7100 GIS 하자점검 공사","서인천CC 7100 GIS 하자점검 공사","2017-05-26 08:00","2017-05-26 18:00","2017-05-26 08:00","2017-05-26 18:00","당일",null,null,null,201703140375]
[20,"인천","인천","서인천CC신부평#1 T/L","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 7A Bay(7A71, 7A00) GIS 대체","2017-05-11 10:00","2017-06-09 17:00","2017-05-11 10:00","2017-06-09 17:00","연속",null,null,null,201703150109]
[21,"인천","인천","서인천C/C #1 M.Tr 1차 CB (7172)","서인천CC 7172 GIS 하자점검 공사","서인천CC 7172 GIS 하자점검 공사","2017-05-29 08:00","2017-05-29 18:00","2017-05-29 08:00","2017-05-29 18:00","당일",null,null,null,201703140377]
[22,"인천","인천","신가좌가정#1 T/L","SB댐퍼 설치공사","SB댐퍼 설치공사","2017-05-29 08:00","2017-05-29 18:00","2017-05-29 08:00","2017-05-29 18:00","당일",null,null,null,201703150181]
[23,"인천","인천","신가좌가정#2 T/L","SB댐퍼 설치공사","SB댐퍼 설치공사","2017-05-30 08:00","2017-05-30 18:00","2017-05-30 08:00","2017-05-30 18:00","당일",null,null,null,201703150182]
[24,"인천","인천","신경서S/S #1 M.Tr 1차 CB (7172)","인천전력지사 362kV GIS 정밀점검 공사(신경서S/S 7172)","인천전력지사 362kV GIS 정밀점검 공사(신경서S/S 7172) - 362kV GIS 정밀점검 공사","2017-05-10 08:00","2017-05-12 18:00","2017-05-10 08:00","2017-05-12 18:00","연속",null,null,null,201703140340]
[25,"인천","인천","신경서S/S #1 Sh.R (이설) CB","신경서S/S #1Sh.R 하자점검 및 7179 GIS 하자점검공사","신경서S/S #1Sh.R 하자점검 및 7179 GIS 하자점검공사 - #1Sh.R 하자점검공사 - 7179 GIS 하자점검공사","2017-05-11 08:00","2017-05-12 18:00","2017-05-11 08:00","2017-05-12 18:00","연속",null,null,null,201703140343]
[26,"인천","인천","신경서S/S #1Sh.R CB (7179)","신경서S/S 7179 GIS 하자점검공사","신경서S/S 7179 GIS 하자점검공사","2017-05-11 08:00","2017-05-12 18:00","2017-05-11 08:00","2017-05-12 18:00","연속",null,null,null,201703140478]
[27,"인천","인천","신인천C/C 신김포신인천CC T/L-4MT101 CB (7700)","신인천CC 7700 GIS 하자점검 공사","신인천CC 7700 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-18 08:00","2017-05-18 18:00","2017-05-18 08:00","2017-05-18 18:00","당일",null,null,null,201703140358]
[28,"인천","인천","신인천C/C 신김포신인천CC T/L CB (7771)","신인천CC 7771 GIS 하자점검 공사","신인천CC 7771 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-17 08:00","2017-05-17 18:00","2017-05-17 08:00","2017-05-17 18:00","당일",null,null,null,201703140354]
[29,"인천","인천","신인천C/C TIE-3MT101 CB (7500)","신인천CC 7500 GIS 하자점검 공사","신인천CC 7500 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-15 08:00","2017-05-15 18:00","2017-05-15 08:00","2017-05-15 18:00","당일",null,null,null,201703140349]
[30,"인천","인천","신인천C/C 3MT101 CB (7572)","신인천CC 7572 GIS 하자점검 공사","신인천CC 7572 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-16 08:00","2017-05-16 18:00","2017-05-16 08:00","2017-05-16 18:00","당일",null,null,null,201703140350]
[31,"인천","인천","인천CC S/Y 인천복합 #1 S/T CB (7672)","인천CC 7672 GIS 하자점검 공사","인천CC 7672 GIS 하자점검 공사","2017-05-10 08:00","2017-05-10 18:00","2017-05-10 08:00","2017-05-10 18:00","당일",null,null,null,201703140249]
[32,"인천","인천","인천T/P 인천복합 #2 S/T CB (7671)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7671)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7671) - 362kV GIS 정밀점검 공사","2017-05-18 08:00","2017-05-20 18:00","2017-05-18 08:00","2017-05-20 18:00","연속",null,null,null,201703140466]
[33,"인천","인천","인천T/P 인천복합 #3,4 G/T CB (7571)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7571)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7571) - 362kV GIS 정밀점검 공사","2017-05-15 08:00","2017-05-17 18:00","2017-05-15 08:00","2017-05-17 18:00","연속",null,null,null,201703140463]
[34,"인천","인천","인천CC S/Y #1Tie-Tr A","인천CC #1Tie-Tr 휴전작업","인천CC #1Tie-Tr 휴전작업 - #1TIE-TR 보통점검 및 2차 LA보통점검 - 2차 GIS(6144) 보통점검","2017-05-30 08:00","2017-05-31 18:00","2017-05-30 08:00","2017-05-31 18:00","연속",null,null,null,201703140370]
[35,"인천","인천","인천CC S/Y 345kV #76 BUS","인천CC 7452DS 이음발생관련 보수공사(#76BUS 휴전)","인천CC 7452DS 이음발생관련 보수공사 - 362kV GIS 하자점검(병행, 7472)","2017-05-29 08:00","2017-06-01 18:00","2017-05-29 08:00","2017-06-01 18:00","연속",null,null,null,201703140368]
[36,"인천","인천","인천CC SY 인천복합#2ST-인천복합#1ST CB (7600)","인천CC 7600 GIS 하자점검 공사","인천CC 7600 GIS 하자점검 공사","2017-05-12 08:00","2017-05-12 18:00","2017-05-12 08:00","2017-05-12 18:00","당일",null,null,null,201703140251]
[37,"인천","인천","인천CC 인천복합#3,4GT-인천복합#1,2GT CB (7500)","인천CC 7500 GIS 하자점검 공사","인천CC 7500 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-22 08:00","2017-05-22 18:00","2017-05-22 08:00","2017-05-22 18:00","당일",null,null,null,201703140363]
[38,"인천","인천","인천CC S/Y 인천복합 #1,2 G/T CB (7572)","인천CC 7572 GIS 하자점검 공사","인천CC 7572 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-23 08:00","2017-05-23 18:00","2017-05-23 08:00","2017-05-23 18:00","당일",null,null,null,201703140365]
[39,"인천","인천","신경서인천CC#2T/L-가정인천CC#1T/L CB (7400)","인천CC 7400 GIS 하자점검 공사","인천CC 7400 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-24 08:00","2017-05-24 18:00","2017-05-24 08:00","2017-05-24 18:00","당일",null,null,null,201703140366]
[40,"인천","인천","인천CC S/Y 가정인천CC#1T/L CB (7472)","인천CC 7452DS 이음발생관련 보수공사","인천CC 7452DS 이음발생관련 보수공사 - 362kV GIS 하자점검(병행, 7472)","2017-05-29 08:00","2017-06-01 18:00","2017-05-29 08:00","2017-06-01 18:00","연속",null,null,null,201703140367]
[41,"인천","인천","포스코S/Y 포스코#4Step-Up-Tr T/L CB (7472)","포스코S/Y 7472 GIS 하자점검 공사","포스코S/Y 7472 GIS 하자점검 공사 - 362kV GIS 하자점검","2017-05-19 08:00","2017-05-19 18:00","2017-05-19 08:00","2017-05-19 18:00","당일",null,null,null,201703140360]
[42,"인천","인천","포스코SY인천CC#2T/L-#2GEN STEP UP TR CB (7200)","362kV GIS 정밀점검 공사(포스코S/Y 7200)","362kV GIS 정밀점검 공사(포스코S/Y 7200) - 362kV GIS 정밀점검 공사","2017-05-29 08:00","2017-05-31 18:00","2017-05-29 08:00","2017-05-31 18:00","연속",null,null,null,201703210181]
[43,"인천","인천","인천CC포스코CC#2T/L","362kV GIS 정밀점검 공사 (포스코S/Y 7271 , 과열보수공사)","362kV GIS 정밀점검 공사 (포스코S/Y 7271 CB) - GIS 정밀점검 공사 - 72BAY 인입붓싱 과열보수공사","2017-05-23 08:00","2017-05-26 18:00","2017-05-23 08:00","2017-05-26 18:00","연속",null,null,null,201703210179]
[44,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 보호반 대체","신부평S/S #3M.Tr 보호반 대체","2017-05-22 09:30","2017-05-26 18:00","2017-05-22 09:30","2017-05-26 18:00","연속",null,null,null,201703100550]
[45,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 보호반 대체","신부평S/S #2M.Tr 보호반 대체","2017-05-15 09:30","2017-05-19 18:00","2017-05-15 09:30","2017-05-19 18:00","연속",null,null,null,201703100549]
[46,"경기북부","구리","미금S/S 345kV #5 Sh.R","미금S/S #5 Sh.R 교체공사","○ 장기사용 노후 조상설비 교체 ○ 지정 폐기물 및 절연유 성능저하에 따른 설비 교체","2017-05-29 09:00","2017-06-10 18:00","2017-05-29 09:00","2017-06-10 18:00","연속",null,null,null,201703130384]
[47,"경기북부","구리","미금S/S #1 M.Tr A","미금S/S 345kV #1M.Tr 정밀점검공사","미금S/S 345kV #1M.Tr 정밀점검공사. 3차 GPT 점검, 3차 LA 대체","2017-05-15 09:00","2017-06-02 18:00","2017-05-15 09:00","2017-06-02 18:00","연속",null,null,null,201703090290]
[48,"경기북부","구리","신가평미금#2 T/L","345kV 신가평-미금T/L 접속함 교체공사","- 대상선로 : 345kV 신가평-미금#2TL - 교체대상 : J/B#1,2 접속함 12상 - 내용 : 접속함 교체(PJ Type -> PMJ Type 교체)","2017-05-29 09:00","2017-06-16 18:00","2017-05-29 09:00","2017-06-16 18:00","연속",null,null,null,201703070068]
[49,"경기북부","구리","신가평신의정부#1 T/L","345kV 신가평-미금#2T/L 정밀점검","345kV 신가평-미금#2T/L 병가구간 송전선로 정밀점검, 스페이서댐퍼 점검 등","2017-05-29 08:00","2017-05-29 18:00","2017-05-29 08:00","2017-05-29 18:00","당일",null,null,null,201701260207]
[50,"경기북부","구리","신가평신의정부#2 T/L","345kV 신가평-미금#1T/L 정밀점검","345kV 신가평-미금#1T/L 병가구간 송전선로 정밀점검, 스페이서댐퍼 점검 등","2017-05-15 08:00","2017-05-15 18:00","2017-05-15 08:00","2017-05-15 18:00","당일",null,null,null,201702210216]
[51,"경기북부","구리","신가평미금#1 T/L","345kV 신가평-미금T/L 접속함 교체공사","- 대상선로 : 345kV 신가평-미금#1TL - 교체대상 : J/B#1,2 접속함 12상 - 내용 : 접속함 교체(PJ Type -> PMJ Type 교체)","2017-05-08 09:00","2017-05-26 18:00","2017-05-08 09:00","2017-05-26 18:00","연속",null,null,null,201703070066]
[52,"경기북부","구리","포천C/C #3S/U Tr 1차 GIS","포천C/C #3S/U Tr 1차 GIS 하자점검 (7272)","포천C/C #3S/U Tr 1차 GIS 하자점검 (7272)","2017-05-17 10:00","2017-05-17 18:00","2017-05-18 10:00","2017-05-18 18:00","당일",null,null,null,201702270102]
[53,"경기북부","구리","포천C/C #2S/U Tr-#3S/U Tr GIS","포천C/C #2S/U Tr-#3S/U Tr GIS 하자점검 (7200)","포천C/C #2S/U Tr-#3S/U Tr GIS 하자점검 (7200)","2017-05-16 10:00","2017-05-16 18:00","2017-05-11 10:00","2017-05-11 18:00","당일",null,null,null,201702270095]
[54,"경기북부","구리","포천C/C #1S/U Tr 1차 GIS","포천C/C #1S/U Tr 1차 GIS 하자점검 (7172)","포천C/C #1S/U Tr 1차 GIS 하자점검 (7172)","2017-05-11 10:00","2017-05-11 18:00","2017-05-17 10:00","2017-05-17 18:00","당일",null,null,null,201702270090]
[55,"경기북부","구리","포천C/C #2S/U Tr 1차 GIS","포천C/C #2S/U Tr 1차 GIS 하자점검 (7271)","포천C/C #2S/U Tr 1차 GIS 하자점검 (7271)","2017-05-30 10:00","2017-05-30 18:00","2017-05-10 10:00","2017-05-10 18:00","당일",null,null,null,201702270092]
[56,"경기북부","구리","포천C/C #4S/U Tr 1차 GIS","포천C/C #4S/U Tr 1차 GIS 하자점검 (7372)","포천C/C #4S/U Tr 1차 GIS 하자점검 (7372)","2017-05-10 10:00","2017-05-10 18:00","2017-05-16 10:00","2017-05-16 18:00","당일",null,null,null,201702270104]
[57,"경기북부","직할","신의정부S/S #2 M.Tr A","신의정부S/S #1 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출","2017-05-16 09:00","2017-05-16 18:00","2017-05-16 09:00","2017-05-16 18:00","연속",null,null,null,201703080017]
[58,"경기북부","직할","신의정부S/S #3 M.Tr A","신의정부S/S #3 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","연속",null,null,null,201703080021]
[59,"경기북부","직할","신의정부S/S #4 M.Tr A","신의정부S/S #4 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출","2017-05-18 09:00","2017-05-18 18:00","2017-05-18 09:00","2017-05-18 18:00","연속",null,null,null,201703080022]
[60,"경기북부","직할","신의정부S/S #1 M.Tr A","신의정부S/S #1 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출, 가스이상발생 원인분석","2017-05-15 09:00","2017-05-15 18:00","2017-05-15 09:00","2017-05-15 18:00","연속",null,null,null,201703080020]
[61,"경기북부","직할","양주S/S #1 M.Tr A","17년 경기북부 직할 362kV GIS 정밀점검","362kV GIS 정밀점검 -7200,7272","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201703210246]
[62,"경기북부","직할","양주중부#2 T/L","345kV 양주-중부#2T/L 전선교체공사","345kV 양주-중부#2T/L No.3~5 등 2구간 전선교체공사","2017-05-16 07:00","2017-05-18 18:00","2017-05-16 07:00","2017-05-18 18:00","연속",null,null,null,201702170174]
[63,"경기북부","직할","양주중부#1 T/L","345kV 양주-중부#1T/L 전선교체공사","345kV 양주-중부#1T/L No.3~5 등 2구간 전선교체공사","2017-05-19 07:00","2017-05-21 18:00","2017-05-19 07:00","2017-05-21 18:00","연속",null,null,null,201702170175]
[64,"경기북부","직할","양주S/S #3 M.Tr A","17년 경기북부 직할 362kV GIS 정밀점검","362kV GIS 정밀점검 -7700,7772","2017-05-22 09:00","2017-05-26 18:00","2017-05-22 09:00","2017-05-26 18:00","연속",null,null,null,201703210248]
[65,"경기북부","직할","양주S/S #4 M.Tr A","17년 경기북부 직할 362kV GIS 정밀점검","362kV GIS 정밀점검 -7172, 7100","2017-05-29 09:00","2017-06-02 18:00","2017-05-29 09:00","2017-06-02 18:00","연속",null,null,null,201703210251]
[66,"경기북부","직할","양주S/S 345kV #4 Sh.R CB","양주S/S 345kV #4,5,6Sh.R용 CB 공장반입 개조공사","362kV #4Sh.R용 CB 공장반입 균압콘덴서 교체","2017-05-01 09:00","2017-05-28 18:00","2017-05-01 09:00","2017-05-28 18:00","연속",null,null,null,201703210130]
[67,"경기북부","파주","신파주신덕은#1 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","신덕은-원흥T/L No.62-68 장기사용전력선 교체 4회선 병가구간","2017-05-10 08:00","2017-05-15 18:00","2017-05-10 08:00","2017-05-15 18:00","연속",null,null,null,201703060158]
[68,"경기북부","파주","신파주신덕은#2 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","신덕은-수색T/L No.62-68 장기사용전력선 교체 4회선 병가구간","2017-05-16 08:00","2017-05-21 18:00","2017-05-16 08:00","2017-05-21 18:00","연속",null,null,null,201703060159]
[69,"경기북부","파주","신파주S/S 75-76 SEC GIS","신파주S/S #75-76 SEC GIS 정밀점검공사","신파주S/S #75-76SEC CB 및 관련DS 정밀점검","2017-05-29 08:00","2017-06-02 18:00","2017-05-01 09:00","2017-05-28 18:00","연속",null,null,null,201702280194]
[70,"경기북부","파주","신파주S/S 345kV #75 BUS","신파주S/S #75-76 SEC GIS 정밀점검공사","신파주S/S #75-76SEC CB 및 관련DS 정밀점검","2017-05-29 08:00","2017-05-31 18:00","2017-05-29 08:00","2017-05-31 18:00","연속",null,null,null,201702280190]
[71,"경기북부","파주","신파주S/S 345kV #70 BUS","신파주S/S #70-71 SEC GIS 정밀점검공사","신파주S/S #70-71 SEC CB 및 관련DS 정밀점검","2017-05-25 09:30","2017-05-26 18:00","2017-05-25 09:30","2017-05-26 18:00","연속",null,null,null,201702280198]
[72,"경기북부","파주","신파주S/S 70-71 SEC GIS","신파주S/S #70-71 SEC GIS 정밀점검공사","신파주S/S #70-71 SEC CB 및 관련DS 정밀점검","2017-05-22 08:00","2017-05-26 18:00","2017-05-22 08:00","2017-05-26 18:00","연속",null,null,null,201702280195]
[73,"경기북부","파주","신파주S/S 345kV #71 BUS","신파주S/S #70-71 SEC GIS 정밀점검공사","신파주S/S #70-71 SEC CB 및 관련DS 정밀점검","2017-05-22 08:00","2017-05-24 18:00","2017-05-22 08:00","2017-05-24 18:00","연속",null,null,null,201702280197]
[74,"경기북부","파주","신파주S/S 345kV #71 BUS","신파주신덕은#2T/L GIS 정밀점검공사","신파주S/S 신파주신덕은#2T/L(7571CB 및 관련DS) 정밀점검","2017-05-16 08:00","2017-05-17 16:00","2017-05-16 08:00","2017-05-17 16:00","연속",null,null,null,201702280188]
[75,"경기북부","파주","장문복합S/S 장문-발전단#3T/L CB (7372)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7372 GIS 유압시스템 보수","2017-05-16 09:00","2017-05-16 18:00","2017-05-16 09:00","2017-05-16 18:00","연속",null,null,null,201703290223]
[76,"경기북부","파주","장문복합S/S 장문-발전단#3T/L-신덕은-장문 CB (7300)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7300 GIS 유압시스템 보수","2017-05-15 09:00","2017-05-15 18:00","2017-05-15 09:00","2017-05-15 18:00","연속",null,null,null,201703290220]
[77,"경기북부","파주","장문복합S/S 신덕은-장문#2T/L CB (7371)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7371 GIS 유압시스템 보수","2017-05-12 09:00","2017-05-12 18:00","2017-05-12 09:00","2017-05-12 18:00","연속",null,null,null,201703290219]
[78,"경기북부","파주","장문복합S/S 장문-발전단#2T/L CB (7272)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7272 GIS 유압시스템 보수","2017-05-11 09:00","2017-05-11 18:00","2017-05-11 09:00","2017-05-11 18:00","연속",null,null,null,201703290218]
[79,"경기북부","파주","장문복합S/S 장문-발전단#4T/L CB (7472)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7472 GIS 유압시스템 보수","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","연속",null,null,null,201703290225]
[80,"경기북부","파주","장문복합S/S 신덕은-장문#1T/L CB (7471)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7471 GIS 유압시스템 보수","2017-05-23 09:00","2017-05-23 18:00","2017-05-23 09:00","2017-05-23 18:00","연속",null,null,null,201703300010]
[81,"경기북부","파주","장문복합S/S 장문-발전단#2T/L-TIE CB (7200)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7200GIS 유압시스템 보수","2017-05-22 09:00","2017-05-22 18:00","2017-05-22 09:00","2017-05-22 18:00","당일",null,null,null,201703300009]
[82,"경기북부","파주","장문복합S/S 장문-발전단#4T/L-신덕은-장문 CB (7400)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7400 GIS 유압시스템 보수","2017-05-19 09:00","2017-05-19 18:00","2017-05-19 09:00","2017-05-19 18:00","당일",null,null,null,201703290262]
[83,"경기북부","파주","장문복합S/S 장문-발전단#1T/L-TIE CB (7100)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O 7100GIS 유압시스템 보수","2017-05-18 09:00","2017-05-18 18:00","2017-05-18 09:00","2017-05-18 18:00","연속",null,null,null,201703290257]
[84,"경기북부","파주","장문복합S/S 장문-발전단#1T/L CB (7172)","장문CC 362kV GIS 제작사 유압시스템 보수공사","O7172 GIS 유압시스템 보수","2017-05-10 09:00","2017-05-10 18:00","2017-05-10 09:00","2017-05-10 18:00","연속",null,null,null,201703290217]
[85,"경기","군포","서서울영서#2 T/L","서서울S/S 345kV 서서울영서#2T/L CVT 보통점검 공사","서서울S/S 345kV 서서울영서#2T/L CVT 보통점검","2017-05-22 10:00","2017-05-22 18:00","2017-05-22 10:00","2017-05-22 18:00","당일",null,null,null,201703130514]
[86,"경기","군포","신시흥신안산 T/L","345kV 신시흥신안산T/L 피뢰기 설치공사","피뢰기 설치 : 1기(101호)","2017-05-12 09:00","2017-05-12 12:00","2017-05-12 09:00","2017-05-12 12:00","당일",null,null,null,201703080123]
[87,"경기","동부","곤지암동서울#2 T/L","17년 동부변전 주기도래 점검","곤지암S/S 곤지암-동서울#2T/L 7471,7400 GIS(보통)","2017-05-11 09:00","2017-05-11 20:00","2017-05-11 09:00","2017-05-11 20:00","당일",null,null,null,201703140194]
[88,"경기","동부","곤지암동서울#1 T/L","17년 동부변전 주기도래 점검","곤지암S/S 곤지암-동서울#1T/L 7371,7300 GIS(보통)","2017-05-12 09:00","2017-05-12 20:00","2017-05-12 09:00","2017-05-12 20:00","당일",null,null,null,201703140201]
[89,"경기","성남","서안성신진천#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.14 ~ 서안성S/S OPGW 증설(7기)","2017-05-14 07:00","2017-05-16 18:00","2017-05-14 07:00","2017-05-16 18:00","연속",null,null,null,201703140330]
[90,"경기","성남","신안성서안성#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.14 ~ 서안성S/S OPGW 증설(7기)","2017-05-14 07:00","2017-05-16 18:00","2017-05-14 07:00","2017-05-16 18:00","연속",null,null,null,201703140338]
[91,"경기","성남","서안성신진천#2 T/L","345kV 서안성-신진천#2T/L 가공송전선로 정밀점검","345kV 서안성-신진천#2T/L 가공송전선로 정밀점검(63기)","2017-05-18 09:00","2017-05-20 17:00","2017-05-18 09:00","2017-05-20 17:00","연속",null,null,null,201703160044]
[92,"경기","성남","신성남S/S #3M.Tr 1차 GIS","17년 성남변전협력회사 총액공사","신성남S/S #3M.Tr 1차 7372 GIS 보통점검","2017-05-08 10:00","2017-05-08 18:00","2017-05-08 10:00","2017-05-08 18:00","당일",null,null,null,201703140532]
[93,"경기","성남","신수원S/S #4 M.Tr A","17년 성남변전협력회사 총액공사","신수원S/S #4M.Tr A상 누유보수","2017-05-13 10:00","2017-05-14 18:00","2017-05-13 10:00","2017-05-14 18:00","연속",null,null,null,201703140482]
[94,"경기","성남","신안성서안성#2 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-05-05 08:00","2017-05-05 18:00","2017-05-05 08:00","2017-05-05 18:00","당일",null,null,null,201703130424]
[95,"경기","성남","신안성신수원#1 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-05-05 09:00","2017-05-05 18:00","2017-05-05 09:00","2017-05-05 18:00","당일",null,null,null,201703130428]
[96,"경기","성남","신용인삼성 T/L","17년 성남변전협력회사 총액공사","신용인S/S 7671, 7600 GIS 초기점검 및 LA, CVT 보통점검","2017-05-08 10:00","2017-05-08 18:00","2017-05-08 10:00","2017-05-08 18:00","당일",null,null,null,201703140475]
[97,"경기","성남","신용인S/S #1 M.Tr A","17년 성남변전협력회사 총액공사","신용인S/S #1M.Tr 보통점검 신용인S/S 7272,7200 GIS 초기점검, 3차 PT 보통점검","2017-05-15 10:00","2017-05-16 18:00","2017-05-15 10:00","2017-05-16 18:00","연속",null,null,null,201703140505]
[98,"경기","직할","화성평택TP#2T/L","345kV화성-평택TPT/L 20호 안전이격확보공사","○ 철탑상향(인클로징 공법) : 1기(No. 20) ○ 전력선 교체 : ACSR 480㎟×4B×2.577km(No.20∼25, 37∼38, 62∼63) ○ 가공지선 교체 : ACSR 120㎟×S×2.577km(No.20∼25, 37∼38, 62∼63)","2017-05-27 09:00","2017-06-01 18:00","2017-05-25 09:00","2017-06-02 18:00","연속",null,null,null,201703150015]
[99,"경기","직할","화성평택TP#1T/L","345kV화성-평택TPT/L 20호 안전이격확보공사","○ 철탑상향(인클로징 공법) : 1기(No. 20) ○ 전력선 교체 : ACSR 480㎟×4B×2.577km(No.20∼25, 37∼38, 62∼63) ○ 가공지선 교체 : ACSR 120㎟×S×2.577km(No.20∼25, 37∼38, 62∼63)","2017-05-15 09:00","2017-05-26 18:00","2017-05-15 09:00","2017-05-24 18:00","연속",null,null,null,201703150014]
[100,"경기","직할","화성S/S #3M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-05-29 09:00","2017-06-04 18:00","2017-05-29 09:00","2017-06-04 18:00","연속",null,null,null,201703140424]
[101,"경기","직할","화성S/S #1M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-05-15 09:00","2017-05-21 18:00","2017-05-15 09:00","2017-05-21 18:00","연속",null,null,null,201703140421]
[102,"경기","직할","화성S/S #2M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-05-22 09:00","2017-05-28 18:00","2017-05-22 09:00","2017-05-28 18:00","연속",null,null,null,201703140423]
[103,"강원","강릉","동해신양양 T/L","2017년 가공송전선로 순시점검 위탁공사","○ 345kV 동해-신양양T/L 정밀점검(No.72~142, 71기)","2017-05-22 09:00","2017-05-26 18:00","2017-05-22 09:00","2017-05-26 18:00","매일",null,null,null,201703210242]
[104,"강원","강릉","동해양양PP T/L","2017년 가공송전선로 순시점검 위탁공사","○ 345kV 동해-양양PP T/L 정밀점검(No.72~142, 71기)","2017-05-29 09:00","2017-06-02 18:00","2017-05-29 09:00","2017-06-02 18:00","매일",null,null,null,201703210244]
[105,"강원","동해","신제천동해#2 T/L","2016~17년 동해전력지사 송전정비 협력회사 총액공사","345kV 신제천-동해#2T/L No.8~39 스페이서댐퍼 교체","2017-05-29 08:00","2017-06-02 18:00","2017-05-29 08:00","2017-06-02 18:00","매일",null,null,null,201703130408]
[106,"강원","동해","동해S/S #1 M.Tr A","2017년 동해변전소 주변압기 정밀점검공사","1. 동해S/S #1M.Tr 정밀점검 2. 동해S/S #1M.Tr OLTC 정밀점검 3. 동해S/S #1M.Tr C상 유격실 교체 등","2017-05-10 09:30","2017-05-31 18:00","2017-05-10 09:30","2017-05-31 18:00","연속",null,null,null,201703130167]
[107,"강원","태백","신태백한울NP2#2 T/L","신태백S/S 362kV GIS 정밀점검공사","7622, 7602, 7662DS 및 7672 CB 정밀점검","2017-05-21 10:00","2017-05-27 18:00","2017-05-21 10:00","2017-05-27 18:00","연속",null,null,null,201703140021]
[108,"강원","태백","신태백한울NP3 T/L","신태백S/S 362kV GIS 정밀점검 공사","7422, 7462DS 및 7472CB 정밀점검 및 7400CB 보통점검","2017-05-28 10:00","2017-06-02 18:00","2017-05-28 10:00","2017-06-02 18:00","연속",null,null,null,201703140029]
[109,"강원","태백","신태백S/S 345kV #2 BUS","신태백S/S 362kV GIS 정밀점검공사","7452, 7652DS 정밀점검","2017-05-11 10:00","2017-05-14 18:00","2017-05-11 10:00","2017-05-14 18:00","연속",null,null,null,201703140023]
[110,"충북","직할","신제천신영주#2 T/L","345kV 신제천-신영주T/L 전력선 교체공사","전력선 교체 : 6.471km(No.131-146) 가공지선 교체: 4.863km (No.131-139, 143-146) 스페이서댐퍼교체: 624개(전력선교체구간)","2017-05-18 07:00","2017-06-02 18:00","2017-05-18 07:00","2017-06-02 18:00","연속",null,null,null,201703090451]
[111,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S GIS화 공사","345kV GIS 모선 및 73, 74Bay GIS 설치","2017-05-01 00:08","2017-05-08 18:00","2017-05-04 08:00","2017-05-13 18:00","연속",null,null,null,201703060092]
[112,"충북","직할","신충주S/S 신제천-신충주 #1 T/L-#2 M.Tr 1 CB (7300)","직할 변전협력 총액공사","7300 GIS 보통점검","2017-05-11 10:00","2017-05-11 18:00","취소","취소","당일",null,null,null,201703060231]
[113,"충북","직할","신충주S/S 곤지암-신충주 #2 T/L-#1 M.Tr 1 CB (7100)","직할 변전협력 총액공사","7100 GIS 보통점검","2017-05-08 10:00","2017-05-08 18:00","2017-05-08 10:00","2017-05-08 18:00","당일",null,null,null,201703060221]
[114,"충북","직할","신충주S/S 신제천-신충주 #2 T/L-TIE CB (7400)","직할 변전협력 총액공사","7400 GIS 보통점검","2017-05-12 10:00","2017-05-12 18:00","취소","취소","당일",null,null,null,201703060233]
[115,"충북","직할","신충주S/S #1 M.Tr A","직할 변전협력 총액공사","7172, 6144 GIS 보통점검 변압기 보통점검","2017-05-23 10:00","2017-05-24 18:00","2017-05-23 10:00","2017-05-24 18:00","연속",null,null,null,201703060234]
[116,"충북","직할","신충주S/S #2 M.Tr A","직할 변전협력 총액공사","7372, 6344 GIS 보통점검 변압기 보통점검","2017-05-25 10:00","2017-05-26 18:00","2017-05-25 10:00","2017-05-26 18:00","연속",null,null,null,201703060236]
[117,"충북","직할","신충주S/S #3 M.Tr A","제작사 하자보수 공사","변압기 냉각팬 단자대 교체 및 점검","2017-05-29 10:00","2017-06-02 18:00","2017-05-29 10:00","2017-06-02 18:00","연속",null,null,null,201703150042]
[118,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 차단기 용량대체공사","#2BUS 기설 모선과 분리작업","2017-05-14 08:00","2017-05-14 18:00","2017-05-14 08:00","2017-05-14 18:00","당일",null,null,null,201703060133]
[119,"충북","청주","신옥천S/S 345kV #1 BUS","신옥천S/S 345 용량부족차단기 대체공사","- #1BUS 기설모선 신설모선과 분리 및 철거 - #1BUS GIB 종단 처리","2017-05-11 08:00","2017-05-13 18:00","2017-05-11 08:00","2017-05-13 18:00","연속",null,null,null,201703060130]
[120,"충북","청주","신옥천청양 T/L","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 76Bay #2BUS측으로 인출 변경 - 기설 인출GIB 철거 및 신설 인출GIB 설치 - Post 보강 & Beam 교체 및 미사용분 철거 - 가선(인하선 연결) - 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-05-11 08:00","2017-06-09 18:00","2017-05-11 08:00","2017-06-09 18:00","연속"]
[121,"충북","청주","신옥천신계룡 T/L","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 77Bay #2BUS측으로 인출 변경 - 기설 인출GIB 철거 및 신설 인출GIB 설치 - Post 보강 및 미사용분 철거 - 가선(인하선 연결) - 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-05-11 08:00","2017-06-09 18:00","2017-05-11 08:00","2017-06-09 18:00","연속"]
[122,"충북","청주","신옥천S/S #3 M.Tr A","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 76Bay #1BUS측으로 인출 변경 - 가선(인하선 연결) - 변압기 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-05-11 08:00","2017-05-18 18:00","2017-05-11 08:00","2017-05-18 18:00","연속"]
[123,"충북","청주","세종청원#1 T/L","345kV 세종-청원T/L 전선접속개소 전선교체공사","345kV 세종-청원T/L#1 46호~49호간 전선접속개소 전선교체공사","2017-05-10 08:00","2017-05-13 18:00","2017-05-10 08:00","2017-05-13 18:00","연속"]
[124,"충북","청주","청원S/S #1 M.Tr A","170kV 장기사용 GIS 대체 공사","170kV 장기사용 GIS 대체 공사","2017-05-15 09:30","2017-05-30 18:00","2017-05-15 09:30","2017-05-30 18:00","연속",null,null,null,201702230185]
[125,"충북","충주","신진천S/S #3 M.Tr A","2017년 충주전력지사 345kV 주변압기 정밀점검공사","신진천S/S #3M.Tr A,B,C상 본체 및 OLTC정밀점검","2017-05-10 08:30","2017-05-29 18:00","2017-05-10 08:30","2017-05-29 18:00","연속",null,null,null,201702280149]
[126,"대전충남","서산","신당진S/S 연락#2T/L-신서산#2T/L TIE CB (7700)","'17년 서산P/O 345kV GIS 정밀점검 공사","신당진S/S 345kV 연락#2-신서산#2T/L TIE GIS(7700) 정밀점검","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201703090072]
[127,"대전충남","서산","신당진S/S 신서산-신당진#2T/L CB (7772)","'17년 서산P/O 345kV GIS 정밀점검 공사","신당진S/S 345kV 신서산-신당진#2T/L(7772) GIS 정밀점검","2017-05-22 09:00","2017-05-26 18:00","2017-05-22 09:00","2017-05-26 18:00","연속",null,null,null,201703090076]
[128,"대전충남","서산","신당진개폐소-태안화력#1 T/L","'17년도 태안화력 접속설비 보강공사","- 345kV 75bay 차단기 동작실패보호반 노후 대체 1면","2017-05-20 09:00","2017-05-23 18:00","2017-05-13 09:00","2017-05-15 18:00","연속",null,null,null,201703080209]
[129,"대전충남","서산","태안T/P 5호기 1차 TIE CB (7500)","태안화력 5호기 계획예방정비공사","- 태안화력 5호기 계획예방정비공사(발전소측) - 태안화력 345kV 75bay 차단기 동작실패보호반 노후 대체 1면","2017-05-20 00:00","2017-05-26 23:59","2017-05-20 00:00","2017-05-26 23:59","연속",null,null,null,201703080206]
[130,"대전충남","서산","태안T/P TIE - 4호기 1차 CB (7400)","'17년 서산P/O 변전협력회사 총액공사","태안화력 345kV TIE-4호기 1차(7400) GIS 초기점검","2017-05-15 09:00","2017-05-15 18:00","2017-05-15 09:00","2017-05-15 18:00","당일",null,null,null,201703090085]
[131,"대전충남","서산","태안T/P 4호기 1차 CB (7472)","'17년 서산P/O 변전협력회사 총액공사","태안화력 345kV 4호기 1차(7472) GIS 초기점검","2017-05-16 09:00","2017-05-16 18:00","2017-05-16 09:00","2017-05-16 18:00","당일",null,null,null,201703090087]
[132,"대전충남","서산","신당진개폐소-태안화력#2 T/L","154kV 태안화력(서산-태안화력)T/L 전력선 교체공사","154kV 태안화력(서산-태안화력)T/L 전력선 교체공사 4회선 병가구간 안전거리 확보 휴전","2017-05-16 07:00","2017-05-19 18:00","2017-05-16 07:00","2017-05-19 18:00","연속",null,null,null,201703090545]
[133,"대전충남","서산","태안T/P #1 M.Tr A","'17년 서산P/O 154kV GIS 정밀점검 공사","태안화력 345kV #1M.Tr 2차 GIS 정밀점검 공사","2017-05-13 09:00","2017-05-14 18:00","2017-05-13 09:00","2017-05-14 18:00","당일",null,null,null,201703170016]
[134,"대전충남","서산","태안T/P 5호기 1차 CB (7572)","태안화력 5호기 계획예방정비공사","- 태안화력 5호기 계획예방정비공사(발전소측) - 태안화력 345kV 75bay 차단기 동작실패보호반 노후 대체 1면","2017-05-20 00:00","2017-05-26 23:59","2017-05-20 00:00","2017-05-26 23:59","연속",null,null,null,201703080204]
[135,"대전충남","서산","북당진현대제철 T/L","[송전] 345kV북당진-현대제철T/L 간이정비","345kV북당진-현대제철T/L No.2, 6 간이정비","2017-05-25 08:00","2017-05-25 18:00","2017-05-25 08:00","2017-05-25 18:00","당일",null,null,null,201703130325]
[136,"대전충남","서산","신당진개폐소-태안화력#1 T/L","'17년도 태안화력 접속설비 보강공사","- 345kV 75bay 차단기 동작실패보호반 노후 대체 1면","2017-05-20 09:00","2017-05-23 18:00","취소","취소","연속",null,null,null,201703080209]
[137,"대전충남","아산","아산S/S #2 M.Tr A","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-05-16 09:00","2017-06-01 10:00","2017-05-16 09:00","2017-06-01 10:00","연속",null,null,null,201703160073]
[138,"대전충남","아산","신서산아산#2 T/L","[송전]154kV 아산-송악#2T/L 피뢰기 설치공사","-154kV 아산-송악#2T/L 송전용 피뢰기 48기 설치 -기타 부대공사 -345kV 신서산-아산#2T/L 안전이격확보로 휴전신청","2017-05-22 09:00","2017-05-28 18:00","2017-05-22 09:00","2017-05-28 18:00","매일",null,null,null,201703170152]
[139,"대전충남","청양","보령TP보령CC#1 T/L","보령C/C 71Bay B/F 보호반 교체","71Bay B/F 보호반 교체","2017-05-22 09:30","2017-05-26 18:00","2017-05-22 09:30","2017-05-26 18:00","연속",null,null,null,201703070111]
[140,"대전충남","청양","보령C/C #1 M.Tr 1차 CB (7172)","보령C/C 71Bay B/F 보호반 교체","71Bay B/F 보호반 교체","2017-05-22 09:30","2017-05-26 18:00","2017-05-22 09:30","2017-05-26 18:00","연속",null,null,null,201703070112]
[141,"대전충남","청양","보령T/P #4 M.Tr 1차 CB (7472)","보령화력 362kV GIS 보통점검","○ 345kV 7472 GIS 보통점검","2017-05-23 09:00","2017-05-24 18:00","2017-05-23 09:00","2017-05-24 18:00","연속",null,null,null,201702100277]
[142,"대전충남","청양","보령T/P #5,6 SU Tr 1차-#4 M.Tr 1차 CB (7400)","보령화력 362kV GIS 보통점검","○ 345kV 7400 GIS 보통점검","2017-05-23 09:00","2017-05-24 18:00","2017-05-23 09:00","2017-05-24 18:00","연속",null,null,null,201702100276]
[143,"대전충남","청양","보령T/P 345kV #75 BUS","보령T/P #75BUS 보호반 교체","#75BUS 보호반 교체","2017-05-17 13:00","2017-05-19 18:00","2017-05-17 13:00","2017-05-19 18:00","연속",null,null,null,201703070095]
[144,"대전충남","청양","보령T/P 345kV #70 BUS","보령T/P #70BUS 보호반 교체","#70BUS 보호반 교체","2017-05-15 09:30","2017-05-17 13:00","2017-05-15 09:30","2017-05-17 13:00","연속",null,null,null,201703070089]
[145,"대전충남","청양","청양S/S 345kV #71 BUS","청양S/S #71BUS 보호반 교체","#71BUS 보호반 교체","2017-05-10 09:00","2017-05-12 18:00","2017-05-10 09:00","2017-05-12 18:00","연속",null,null,null,201703080397]
[146,"대전충남","청양","청양보령TP#2 T/L","345kV청양-보령화력#2T/L 휴전요청(발전소 요청)","-보령화력 항공장애 표시구 설치공사(발전소 작업)","2017-05-22 09:00","2017-05-28 17:00","2017-05-22 09:00","2017-05-28 17:00","연속",null,null,null,201703160101]
[147,"전북","군산","군산S/S #1 M.Tr A","군산S/S #1 M.Tr","변압기 보통점검","2017-05-15 09:00","2017-05-16 18:00","2017-05-15 09:00","2017-05-16 18:00","연속",null,null,null,201703100075]
[148,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2 M.Tr","변압기 보통점검","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","당일",null,null,null,201703100077]
[149,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1M.Tr 1차 LA 교체","장기사용기타설비 대체","2017-05-08 10:00","2017-05-08 18:00","2017-05-08 10:00","2017-05-08 18:00","당일",null,null,null,201703200230]
[150,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2M.Tr 1차 LA 교체","장기사용기타설비 대체","2017-05-10 10:00","2017-05-10 18:00","2017-05-10 10:00","2017-05-10 18:00","당일",null,null,null,201703200231]
[151,"전북","직할","신남원신광주#1 T/L","신남원S/S 345kV 차단기 정밀점검공사(7771) 시험가압","- GIS(차단기) 정밀점검","2017-05-25 13:30","2017-05-25 16:00","2017-05-26 13:30","2017-05-26 16:00","연속",null,null,null,201703170082]
[152,"전북","직할","신남원S/S 신남원-신광주#1 T/L GIS","신남원S/S 345kV 차단기 정밀점검공사(7771)","- GIS(차단기) 정밀점검","2017-05-22 09:30","2017-05-25 18:00","2017-05-22 09:30","2017-05-26 18:00","연속",null,null,null,201703160049]
[153,"전북","직할","신남원한빛NP#2 T/L","345kV 신남원-한빛#2T/L 전력선 교체공사","No.20~24호 등 8개 내장-내장 구간 6.314C-km 전선교체 34~36호 등 3개 내장-내장구간 154kV 고창-홍농T/L과 병행선로내 작업","2017-05-16 07:00","2017-06-11 18:00","2017-05-18 07:00","2017-06-13 18:00","연속",null,null,null,201703070337]
[154,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.58~83)","○ 전력선 교체 : 16.954C-km - 대상구간 : No.58~73, 75~83 ○ 가공지선 교체 : 4.224km - 대상구간 : No.68~71, 75~83 ○ 스페이서 댐퍼 설치/철거 : 780개/714개 ○ 아마롯드 설치 및 기타 부대공사","2017-05-10 07:00","2017-05-23 18:00","2017-05-10 07:00","2017-05-23 18:00","연속",null,null,null,201703210169]
[155,"전북","직할","신남원S/S 신남원-신광주#1 - TIE GIS","신남원S/S 345kV 차단기 정밀점검공사(7700)","- GIS(차단기) 정밀점검","2017-05-29 09:30","2017-06-01 18:00","2017-05-29 09:30","2017-06-01 18:00","연속",null,null,null,201703160051]
[156,"광주전남","강진","신화순신강진#2 T/L","345kV 신화순-신강진T/L 접속개소 해소공사","○ 구 간 : 345kV 신화순-신강진T/L No.132∼133 등 9구간 ○ 전선교체 : ACSR 480㎟ × 4B × 2C, 16.666㎞ ○ 스페이서 댐퍼 설치 및 철거 ○ 연가해소 : No.171, 신강진 S/T 인출변경","2017-05-26 07:00","2017-06-30 18:00","2017-05-26 07:00","2017-06-30 18:00","연속",null,null,null,201703070219]
[157,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1 M.Tr (인출변경 및 인출GIS연결)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-05-26 07:00","2017-06-03 18:00","2017-05-26 07:00","2017-06-03 18:00","연속",null,null,null,201701250013]
[158,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S #4 M.Tr (인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-05-14 07:00","2017-05-25 18:00","2017-05-14 07:00","2017-05-25 18:00","연속",null,null,null,201701250008]
[159,"광주전남","목포","한빛2NP-한빛3NP #3T/L","한빛-연락#3T/L(LS산전제 유사고장)","- LS산전제 유사고장 공사 - 한빛-연락#3T/L CVT 대체공사","2017-05-29 09:00","2017-06-09 18:00","2017-05-29 09:00","2017-06-09 18:00","연속",null,null,null,201703080016]
[160,"광주전남","순천","광양여수TP(구 광양여수TP#2) T/L CB","345kV 광양-여수TP T/L(전력선 교체)","345kV 신남원-광양 등 4개T/L 전선접속개소 해소공사 - 광양-여수TP T/L 103~136호간 전력선 교체","2017-05-15 07:00","2017-06-05 18:00","2017-05-15 07:00","2017-06-05 18:00","연속",null,null,null,201703140005]
[161,"광주전남","순천","여수T/P #3 Tie-Tr","345kV 여수T/P #3 M.Tr C(절연유 누유 보수)","17년 변전협력 총액공사 - 여수T/P #3 M.Tr C 상 절연유 누유 보수","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","당일",null,null,null,201703150191]
[162,"대구경북","경산","신경산S/S #2 M.Tr A","신경산S/S 345kV #2M.Tr 휴전","6244 GIS 대체공사","2017-05-10 09:00","2017-05-26 09:00","2017-05-10 09:00","2017-05-28 09:00","연속",null,null,null,201703090496]
[163,"대구경북","경산","울주신경산#2 T/L","345kV 울주-신경산 등 3개T/L 전선교체공사","345kV 울주-신경산T/L 전선교체공사 (#2T/L No.106-118)","2017-05-03 08:00","2017-05-12 18:00","2017-05-03 08:00","2017-05-13 18:00","연속",null,null,null,201703090115]
[164,"대구경북","경산","신경산대구#2 T/L","345kV 울주-신경산 등 3개 T/L 전선교체공사","154kV 경산-자인T/L 전선교체공사 안전확보 (#1T/L No.16-24)","2017-05-13 08:00","2017-05-21 18:00","취소","취소","연속",null,null,null,201703090119]
[165,"대구경북","경산","신경산대구#1 T/L","345kV 울주-신경산 등 3개 T/L 전선교체공사","154kV 경산-자인T/L 전선교체공사 안전확보 (#2T/L No.16-24)","2017-05-22 08:00","2017-05-29 18:00","취소","취소","연속",null,null,null,201703090118]
[166,"대구경북","구미","선산S/S #2 M.Tr A","선산S/S 345kV #2M.Tr 정밀점검","- 345kV #2M.Tr , OLTC 정밀점검","2017-05-04 09:00","2017-05-19 18:00","2017-05-10 09:00","2017-05-19 18:00","연속",null,null,null,201703170021]
[167,"대구경북","구미","서대구선산#2 T/L","345kV 서대구-선산T/L 전선접속개소 전력선교체공사","o 구간 : 345kV 서대구-선산T/L No.2~27 o 전력선 : ACSR 480*4B o 긍장 : 5.043km o 시공사 : 태성산업사","2017-05-04 08:00","2017-05-19 18:00","2017-05-04 08:00","2017-05-19 18:00","연속",null,null,null,201702130392]
[168,"대구경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화공사","T-BUS 및 8DS 철거작업","2017-05-22 09:00","2017-05-23 18:00","2017-05-22 09:00","2017-05-23 18:00","연속",null,null,null,201703130344]
[169,"대구경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화공사","T-BUS 및 8DS 철거작업","2017-05-30 09:00","2017-06-02 18:00","2017-05-30 09:00","2017-06-02 18:00","연속",null,null,null,201703130349]
[170,"대구경북","달성","북경남고령#2 T/L","345kV 북경남-고령#2 T/L 초기점검","No.1~39 초기점검","2017-05-29 09:00","2017-06-02 18:00","2017-05-29 09:00","2017-06-02 18:00","연속",null,null,null,201703080197]
[171,"대구경북","달성","북경남고령#1 T/L","345kV 북경남-고령#1 T/L 초기점검","No.1~39 초기점검","2017-05-22 09:00","2017-05-26 18:00","2017-05-22 09:00","2017-05-26 18:00","연속",null,null,null,201703080196]
[172,"대구경북","달성","대구S/S 북경남-대구#1T/L-TIE CB (7400)","2017년 달성전력 GIS 정밀(7400CB)","GIS정밀(7400CB)","2017-05-30 09:30","2017-06-02 18:00","2017-05-30 09:30","2017-06-02 18:00","연속",null,null,null,201703070177]
[173,"대구경북","달성","북경남대구#2 T/L","345kV 북경남-대구#2 T/L 초기점검","No.1~39 초기점검","2017-05-29 09:00","2017-06-02 18:00","2017-05-29 09:00","2017-06-02 18:00","연속",null,null,null,201703080199]
[174,"대구경북","달성","북경남대구#1 T/L","345kV 북경남-대구#1 T/L 초기점검","No.1~39 초기점검","2017-05-22 09:00","2017-05-26 18:00","2017-05-22 09:00","2017-05-26 18:00","연속",null,null,null,201703080201]
[175,"대구경북","안동","신영주안동CC T/L","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS *3 CB 170kV GIS * 5CCT","2017-05-17 15:00","2017-05-19 15:00","2017-05-23 15:00","2017-05-24 15:00","연속",null,null,null,201703130101,"○"]
[176,"대구경북","안동","안동복합S/Y 345kV #1 BUS","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS * 3CB 170kV GIS * 5CCT.","2017-05-10 10:00","2017-05-19 18:00","2017-05-15 10:00","2017-05-24 18:00","연속",null,null,null,201703130100]
[177,"대구경북","안동","신포항청송PP T/L","345kV 청송분기T/L 정밀점검","345kV 신포항-청송PP T/L 정밀점검 No.1-45 청송양수S/Y 7271 GIS 정밀점검공사 병행","2017-05-16 07:00","2017-05-19 18:00","2017-05-16 07:00","2017-05-19 18:00","연속",null,null,null,201703080221,"○"]
[178,"대구경북","영주","신영주한울NP2#2 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선 교체공사","전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-05-02 07:00","2017-05-16 18:00","2017-05-17 07:00","2017-05-31 18:00","연속",null,null,null,201703150106]
[179,"대구경북","영주","한울2NP-한울3NP #3T/L","한울 3발S/Y 362kV GIS 7B Bay 초기점검","한울 3발S/Y 362kV GIS 7B71,7B00,7B72 CB 초기점검","2017-05-22 10:00","2017-05-23 18:00","2017-05-08 09:00","2017-05-10 18:00","연속",null,null,null,201703070357]
[180,"대구경북","칠곡","북대구선산 T/L","345kV 선산분기 등 2개T/L 접속개소 전선교체 공사","345kV 북대구-선산 및 선산-신포항 전선교체공사(선종 : 480SQ*2B) - 북대구-선산 기준 : No.67-69[선산분기 No.38-40] No.85-90[선산분기 No.56-61] - 선산-신포항 기준 : No.38-43[선산분기 No.56-61] No.59-61[선산분기 No.38-40]","2017-05-01 08:00","2017-05-10 18:00","2017-05-01 08:00","2017-05-10 18:00","연속",null,null,null,201703080381]
[181,"대구경북","칠곡","서대구S/S #4 M.Tr 1차 CB (7771)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S #4 M.Tr 1차 CB(7771) 정밀점검","2017-05-15 09:00","2017-05-17 18:00","2017-05-15 09:00","2017-05-17 18:00","연속",null,null,null,201703030038]
[182,"대구경북","칠곡","서대구S/S #2 M.Tr 1차-TIE CB (7572)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S #2 M.Tr 1차-TIE CB(7572) 정밀점검","2017-05-11 09:00","2017-05-13 18:00","2017-05-11 09:00","2017-05-13 18:00","연속",null,null,null,201703030037]
[183,"대구경북","칠곡","서대구S/S #4 M.Tr-북,서대구#2T/L-TIE CB (7700)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S #4 M.Tr-북,서대구#2T/L-TIE CB(7700) 정밀점검","2017-05-18 09:00","2017-05-20 18:00","2017-05-18 09:00","2017-05-20 18:00","연속",null,null,null,201703030039]
[184,"대구경북","칠곡","서대구S/S #2 M.Tr 1차 CB (7571)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S #2 M.Tr 1차 CB(7571) 정밀점검","2017-05-22 09:00","2017-05-24 18:00","2017-05-22 09:00","2017-05-24 18:00","연속",null,null,null,201703030036]
[185,"대구경북","포항","신포항북대구(기존) T/L CB","345kV 신포항-북대구T/L 전력선교체공사","전력선교체(No.167~183, 192~202, 272~276)","2017-05-23 08:00","2017-06-03 18:00","2017-05-23 08:00","2017-06-03 18:00","연속",null,null,null,201703100043]
[186,"대구경북","포항","선산신포항 T/L","345kV 신포항-북대구T/L 전력선교체공사","전력선교체(No.167~183, 192~202, 272~276)","2017-05-11 08:00","2017-05-22 18:00","2017-05-11 08:00","2017-05-22 18:00","연속",null,null,null,201703100035]
[187,"대구경북","포항","신포항S/S #2 M.Tr A","신포항S/S #2 M.Tr 보통점검","신포항S/S #2 M.Tr 보통점검","2017-05-01 09:00","2017-05-02 18:00","취소","취소","연속",null,null,null,201703090390]
[188,"대구경북","포항","동울산월성NP#2 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","철탑 1기 철거/설치, 철탑보강 3기, 전력선교체","2017-05-29 08:00","2017-06-07 18:00","2017-05-29 08:00","2017-06-07 18:00","연속",null,null,null,201703100063]
[189,"대구경북","포항","월성2N/P #1 M.Tr 2차 CB (7272)","월성S/Y 7272 CB 보통점검","월성S/Y 7272 CB 보통점검","2017-05-29 09:30","2017-05-29 18:00","2017-05-29 09:30","2017-05-29 18:00","당일",null,null,null,201703090449]
[190,"대구경북","포항","울주월성NP#1 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","철탑 1기 철거/설치, 철탑보강 3기, 전력선교체","2017-05-29 08:00","2017-06-17 18:00","2017-05-29 08:00","2017-06-17 18:00","연속",null,null,null,201703100065]
[191,"대구경북","포항","울주월성NP#2 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","철탑 1기 철거/설치, 철탑보강 3기, 전력선교체","2017-05-29 08:00","2017-06-11 18:00","2017-05-29 08:00","2017-06-11 18:00","연속",null,null,null,201703100066]
[192,"부산울산","동부산","신양산S/S #2 M.Tr A","신양산S/S 345kV M.Tr 정밀점검공사","1.신양산 #2M.Tr 본체 및 OLTC 정밀점검 2.7372GIS 보통점검 3.6244GCB 보통점검 4.CVT 및 LA 보통점검","2017-05-22 09:00","2017-06-02 18:00","2017-05-31 09:00","2017-06-14 18:00","연속",null,null,null,201703100539]
[193,"부산울산","동부산","신양산S/S #3 M.Tr A","신양산S/S 345kV M.Tr 정밀점검공사","1.신양산 #3M.Tr 본체 및 OLTC 정밀점검 2.1,2차LA 보통점검","2017-05-10 09:00","2017-05-21 18:00","2017-05-15 09:00","2017-05-27 18:00","연속",null,null,null,201703100538]
[194,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 전선교체 및 피뢰기 설치공사","-전선교체:8호-9호, 22호-27호,28호-36호 -피뢰기설치:1호-110호","2017-05-27 07:00","2017-06-05 18:00","2017-05-29 07:00","2017-06-02 18:00","연속",null,null,"신뢰도개선",201703230044]
[195,"부산울산","북부산","신양산북부산#1 T/L","345kV 북부산S/S 차단기용량대체공사","서부산-북부산#2T/L 신설 GIS 79BAY 연결작업 시험가압 선로","2017-05-31 13:00","2017-06-01 13:00","2017-05-31 13:00","2017-06-01 13:00","연속",null,null,null,201703070258]
[196,"부산울산","북부산","서부산북부산#2 T/L","345kV 북부산S/S 차단기용량대체공사","서부산-북부산#2T/L 신설GIS 79BAY 연결작업(인출변경), C/H 대체, PNL 대체","2017-05-23 18:00","2017-06-02 18:00","2017-05-23 18:00","2017-06-02 18:00","연속",null,null,null,201703070252]
[197,"부산울산","북부산","북부산S/S 서부산-북부산#2T/L Sh.R CB","345kV 북부산S/S 차단기용량대체공사","서부산-북부산#2T/L #2Sh.R용 GIS 대체작업, 기초보강 및 CB 대체","2017-05-23 18:00","2017-06-22 18:00","2017-05-23 18:00","2017-06-22 18:00","연속",null,null,null,201703070254]
[198,"부산울산","북부산","북부산S/S 345kV #75 BUS","345kV 북부산S/S 차단기용량대체공사","#75BUS 기존AL 모선-신설 GIS 연결 임시모선 설치 및 연결","2017-05-24 09:00","2017-06-01 13:00","2017-05-24 09:00","2017-06-01 13:00","연속",null,null,null,201703070257]
[199,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","신설 78, 79BAY GIS 및 서부산-북부산#3T/L인출변경분 시험가압 선로","2017-05-21 13:00","2017-05-22 13:00","2017-05-21 13:00","2017-05-22 13:00","연속",null,null,null,201703070245]
[200,"부산울산","북부산","북부산신온산 T/L","345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사","가. 공사명 : 345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사 나. 공사개요 1) 공사구간 → 345kV 북부산-울산TP 및 북부산-신온산T/L No.49~82호 → 345kV 신김해-북부산#1,2T/L No.10∼22호 2) 전선교체 : 12.87㎞ (ACSR 480㎟×4B×2C) 3) 교체물량 : 162가닥 (237,415m)","2017-05-12 07:00","2017-05-26 18:00","2017-05-12 07:00","2017-05-26 18:00","연속",null,null,null,201703060137]
[201,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","70BUS 기존 AL모선-신설 GIS 연결 임시모선 설치","2017-05-12 09:00","2017-05-22 13:00","2017-05-12 09:00","2017-05-22 13:00","연속",null,null,null,201703070192]
[202,"부산울산","북부산","서부산북부산#3 T/L","345kV 북부산S/S 차단기용량대체공사","서부산-북부산#3T/L 신설GIS 78BAY 연결작업(C/H대체, PNL대체)","2017-05-11 09:00","2017-05-23 18:00","2017-05-11 09:00","2017-05-23 18:00","연속",null,null,null,201703070191]
[203,"부산울산","서부산","서부산S/S #7,8 G/T CB (7572)","서부산S/S #7,8G/T(7572) GIS 보통점검","서부산S/S #7,8G/T(7572) GIS 보통점검","2017-05-18 10:00","2017-05-18 18:00","2017-05-18 10:00","2017-05-18 18:00","당일",null,null,null,201703140461]
[204,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산#1 등 7개 T/L 전선접속개소 전선교체공사","- 전선접속개소 전선교체공사 : 75~81호(전체 12가닥), 81~88호(상단 3가닥, 중단 4가닥, 하단 4가닥), 113~116(중단 4가닥, 하단 2가닥)","2017-05-20 08:00","2017-05-31 18:00","2017-05-20 08:00","2017-05-31 18:00","연속",null,null,null,201703090189]
[205,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산#1 등 7개 T/L 전선접속개소 전선교체공사","- 전선접속개소 전선교체공사 : 81~88호(전체 12가닥), 104~107(하단 2가닥)","2017-05-10 08:00","2017-05-19 18:00","2017-05-10 08:00","2017-05-19 18:00","연속",null,null,null,201703090185,"○"]
[206,"부산울산","울산","신온산S/S 345kV #1 BUS","345kV 신온산S/S S-OIL SW 증설공사","75Bay 신설 #1BUS (63kA) 및 7571CB 설치","2017-05-27 09:00","2017-06-06 18:00","2017-05-27 09:00","2017-06-06 18:00","연속",null,null,"신뢰도개선",201703100114]
[207,"부산울산","울산","신온산S/S #3 M.Tr 1차-TIE CB (7500)","345kV 신온산S/S S-OIL SW 증설공사","345kV S-OIL #6T/L(7571) 증설","2017-05-27 09:00","2017-06-20 18:00","2017-05-27 09:00","2017-06-20 18:00","연속",null,null,null,201703100116]
[208,"부산울산","울산","울산C/C 신온산T/L-기력6호기 1차 CB (7600)","'16~17년도 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7600CB 접점확인","2017-05-08 16:00","2017-05-08 18:00","2017-05-08 16:00","2017-05-08 18:00","당일",null,null,null,201703100513]
[209,"부산울산","울산","울산C/C 북부산-울산TPT/L CB (7571)","'16~17년도 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7571CB 접점확인","2017-05-08 09:00","2017-05-08 11:00","2017-05-08 09:00","2017-05-08 11:00","당일",null,null,null,201703100509]
[210,"부산울산","울산","울산C/C 북부산T/L-기력5호기 1차 CB (7500)","'16~17년도 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7500CB 접점확인","2017-05-08 11:00","2017-05-08 13:00","2017-05-08 11:00","2017-05-08 13:00","당일",null,null,null,201703100511]
[211,"부산울산","울산","울산C/C 신온산-울산TPT/L CB (7671)","'16~17년도 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7671CB 접점확인","2017-05-08 14:00","2017-05-08 16:00","2017-05-08 14:00","2017-05-08 16:00","당일",null,null,null,201703100512]
[212,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","345kV 신김해-북부산#2T/L 59~74, 97~99, 104~105, 110~129호 전력선교체, 345kV 신마산-신김해#1T/L 5~12, 15~18, 28~29호 전력선교체","2017-05-01 07:00","2017-05-10 18:00","2017-05-01 07:00","2017-05-10 18:00","연속",null,null,null,201703070300]
[213,"경남","직할","신김해S/S #1 M.Tr A","신김해S/S 345kV #1M.Tr 보통점검","신김해S/S 345kV #1M.Tr 보통점검","2017-05-15 09:30","2017-05-17 18:00","2017-05-15 09:30","2017-05-17 18:00","연속",null,null,null,201703060080]
[214,"경남","직할","신마산신김해#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","345kV 신김해-북부산#2T/L 59~74, 97~99, 104~105, 110~129호 전력선교체, 345kV 신마산-신김해#1T/L 5~12, 15~18, 28~29호 전력선교체","2017-05-15 07:00","2017-05-22 18:00","2017-05-15 07:00","2017-05-22 18:00","연속",null,null,null,201703150047]
[215,"경남","직할","신김해S/S #4 M.Tr","신김해S/S 345kV #4M.Tr 보통점검","신김해S/S 345kV #4M.Tr 보통점검","2017-05-10 09:30","2017-05-12 18:00","2017-05-10 09:30","2017-05-12 18:00","연속",null,null,null,201703060081]
[216,"경남","직할","신마산신김해#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","345kV 신김해-북부산#2T/L 59~74, 97~99, 104~105, 110~129호 전력선교체, 345kV 신마산-신김해#1T/L 5~12, 15~18, 28~29호 전력선교체","2017-05-06 07:00","2017-05-14 18:00","2017-05-06 07:00","2017-05-14 18:00","연속",null,null,null,201703070301]
[217,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","안전이격 거리확보 전선교체(39~43, 129~136호)","2017-05-27 07:00","2017-06-09 20:00","2017-05-27 07:00","2017-06-09 20:00","연속",null,null,null,201703090135]
[218,"경남","진주","의령S/S #1 M.Tr A","의령S/S #1 M.Tr 2차측 DS(6146)축 교체작업","의령S/S #1 M.Tr 2차측 DS(6146)축 교체작업","2017-05-22 09:30","2017-05-22 18:00","2017-05-22 09:30","2017-05-22 18:00","당일",null,null,null,201703140506]
[219,"경남","진주","의령S/S #1 M.Tr 1차 CB (7372)","의령S/S #1 M.Tr 1차 CB(7372) 정밀점검","의령S/S #1 M.Tr 1차 CB(7372) 정밀점검 -시송전선로 차단기","2017-05-22 09:00","2017-05-24 18:00","2017-05-22 09:00","2017-05-24 18:00","연속",null,null,null,201703060294]
[220,"경남","진주","의령S/S #2 M.Tr A","의령S/S #2 M.Tr 1,2차 부싱 절연유 시료채취","의령S/S #2 M.Tr 1,2차 부싱 절연유 시료채취","2017-05-12 09:30","2017-05-12 15:00","2017-05-12 09:30","2017-05-12 15:00","당일",null,null,null,201703060291]
[221,"경남","진주","고령의령#2 T/L","고령-의령 T/L 가공지선 항공장애표시구 교체작업","고령-의령 T/L 가공지선 항공장애표시구 교체작업 (37~40호, 79, 80호, 94~96호, 111~113호)","2017-05-10 08:30","2017-05-11 17:30","2017-05-10 08:30","2017-05-11 17:30","연속",null,null,null,201703030015]
[222,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","철탑 인클로징 : 7기(42,43,130,131,132,134,135호) 조립","2017-05-08 07:00","2017-05-26 20:00","2017-05-08 07:00","2017-05-26 20:00","연속",null,null,null,201703070087]
[223,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","철탑 인클로징 : 7기(42,43,130,131,132,134,135호) 조립","2017-05-02 07:00","2017-05-07 20:00","2017-05-02 07:00","2017-05-07 20:00","연속",null,null,null,201703070086]
[224,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 6-8호 지장이설공사(요청자시행)","#1T/L측 부적합사항 조치","2017-05-01 07:00","2017-05-01 19:00","2017-05-01 07:00","2017-05-01 19:00","당일",null,null,null,201703020107]
[225,"경남","진주","하동T/P TIE-#8 M.Tr 1차 CB (7800)","하동T/P TIE-#8 M.Tr 1차 CB(7800) 정밀점검","하동T/P TIE-#8 M.Tr 1차 CB(7800) 정밀점검","2017-05-30 09:00","2017-06-01 18:00","2017-05-30 09:00","2017-06-01 18:00","연속",null,null,null,201703060295]
[226,"경남","통영","신고성S/S #4M.Tr A","신고성S/S 154kV #4M.Tr 2차 GIS 정밀점검","신고성S/S 154kV #4M.Tr 2차 GIS 정밀점검","2017-05-10 09:30","2017-05-12 18:30","2017-05-10 09:30","2017-05-12 18:30","연속",null,null,null,201703050010]
[227,"경남","통영","신고성S/S #1 M.Tr A","신고성S/S 345kV #1M.Tr 1차 CB 보통점검","신고성S/S 345kV #1M.Tr 1차 CB 보통점검 신고성S/S 345kV 신고성#1T/L-#1M.Tr 1차 CB 보통점검 신고성S/S 345kV 신고성-삼천포화력#1T/L CB 보통점검","2017-05-23 09:30","2017-05-25 18:30","2017-05-23 09:30","2017-05-25 18:30","연속",null,null,null,201703050018]
[228,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S 345kV #2M.Tr 2차 GIS 보통점검","신고성S/S 345kV #2M.Tr 2차 GIS 보통점검,3차 LA,PT 보통점검 신고성S/S 345kV 신고성-삼천포화력#2T/L CB 보통점검 345kV #2M.Tr 3차모선 지지애자닦기","2017-05-29 09:30","2017-05-31 18:30","2017-05-29 09:30","2017-05-31 18:30","연속",null,null,null,201703070160]
[229,"경남","함안","북경남무주양수 T/L","345kV 북경남-무주양수 T/L 초기점검","No.1-113 초기점검","2017-05-10 08:30","2017-05-19 18:00","2017-05-10 08:30","2017-05-19 18:00","연속",null,null,null,201703080161]
[230,"경남","함안","북경남서대구#1 T/L","345kV 북경남-서대구#1 T/L 초기점검","No.1-113 초기점검","2017-05-10 08:30","2017-05-19 18:00","2017-05-10 08:30","2017-05-19 18:00","연속",null,null,null,201703080160]
[231,"경남","함안","신옥천북경남 T/L","345kV 신옥천-북경남 T/L 초기점검","No.1-113 초기점검","2017-05-22 08:30","2017-05-31 18:00","2017-05-22 08:30","2017-05-31 18:00","연속",null,null,null,201703080193]
[232,"경남","함안","북경남서대구#2 T/L","345kV 북경남-서대구#2 T/L 초기점검","No.1-113 초기점검","2017-05-22 08:30","2017-05-31 18:00","2017-05-22 08:30","2017-05-31 18:00","연속",null,null,null,201703080163]
[233,"경남","함안","신마산삼천포화력#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","345kV 신마산-삼천포화력#1T/L 전선설치(2~5호)","2017-05-24 07:00","2017-05-30 19:00","2017-05-24 07:00","2017-05-30 19:00","연속",null,null,null,201703060014]
[234,"경남","함안","신마산S/S #4 M.Tr A","신마산S/S #4 M.Tr 보통점검","신마산S/S #4 M.Tr 보통점검 2차 LA 보통점검","2017-05-04 09:30","2017-05-06 17:30","2017-05-04 09:30","2017-05-06 17:30","연속",null,null,null,201703080112]
[235,"경남","함안","신마산S/S #3 M.Tr A","신마산S/S #3M.Tr 주변압기 정밀점검","신마산S/S #3M.Tr 주변압기 정밀점검 신마산S/S #3M.Tr 2차 LA 보통점검 신마산S/S 4379 VCB 보통점검","2017-05-08 08:00","2017-05-17 18:30","2017-05-08 08:00","2017-05-17 18:30","연속",null,null,null,201703080090]
[236,"경남","함안","신마산삼천포화력#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","345kV 신마산-삼천포화력#2T/L 전선설치(2~5호)","2017-05-17 07:00","2017-05-23 19:00","2017-05-17 07:00","2017-05-23 19:00","연속",null,null,null,201703060010]
[237,"경남","함안","신마산S/S #5 M.Tr A","신마산S/S #5M.Tr 주변압기 정밀점검","신마산S/S #5M.Tr 주변압기 정밀점검 신마산S/S #5M.Tr 2차 LA 보통점검","2017-05-18 08:00","2017-05-27 18:30","2017-05-18 08:00","2017-05-27 18:30","연속",null,null,null,201703080091]
[1,"대구경북","월성본부","월성1호기 주변압기(7200,7272) CB","월성 1호기  제25차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7200,7272","- 주변압기/소내용변압기 일반점검\n- 주발전기, 주/소내보조변압기 보호계전기 \n   정기시험(차단기 연동시험 포함)\n- 한전 철탑 이설공사","2017-05-26 09:00","2017-06-10 18:00","2017-05-26 09:00","2017-06-10 18:00","연속",null,null,null,201703070160]
[2,"광주전남","한빛본부","한빛4호기 주변압기(7A00,7A71) CB","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7A00, 7A71 ","○ OH관련 주변압기, 보조변압기 점검\n○ 보호계전기 개체/연동시험 등","2017-05-18T10:00:00","2017-07-28T22:00:00","2017-05-18T10:00:00","2017-07-28T22:00:00","연속",null,null,null,201703080161]
[3,"광주전남","한빛본부","한빛4호기 기동변압기(7900,7971) CB","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7900, 7971 ","○ OH관련 기동변압기 03XN 점검\n○ 보호계전기 개체/연동시험 등","2017-05-29T09:00:00","2017-06-07T18:00:00","2017-05-29T09:00:00","2017-06-07T18:00:00","연속",null,null,null,201703080160]
[4,"광주전남","한빛본부","한빛4호기 기동변압기(7800,7871) CB","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7800, 7871 ","○ OH관련 기동변압기 04XN 점검\n○ 보호계전기 개체/연동시험 등","2017-06-14T18:00:00","2017-06-22T17:30:00","2017-06-14T18:00:00","2017-06-22T17:30:00","연속",null,null,null,201703080193]
[1,"인천","신인천본부","4MT001 주변압기 CB","갑종 보호계전기 정기시험 등","갑종 보호계전기 정기시험 등","2017-05-12T09:00:00","2017-05-16T18:00:00","2017-05-12T09:00:00","2017-05-16T18:00:00","연속",null,null,null,201703080163]
[2,"인천","신인천본부","4MT201 주변압기 CB","갑종 보호계전기 정기시험 등","갑종 보호계전기 정기시험 등","2017-05-12T09:00:00","2017-05-20T18:00:00","2017-05-12T09:00:00","2017-05-20T18:00:00","연속",null,null,null,201703060014]
[1,"대전충남","보령화력","345kV 청양-보령화력 #2T/L CB(7771)","항공장애표시구\n설치공사","#7, 8 항공장애표시구 설치공사","2017-05-22T09:00:00","2017-05-28T17:00:00","2017-05-22T09:00:00","2017-05-28T17:00:00","연속",null,null,null,201703080112]
[2,"대전충남","보령화력","보령 7,8호기 #1BUS CB(7771, 7871)","갑종보호계전기 시험\nGIS 77Bay 보통점검","갑종보호계전기(모선보호반) 시험\nGIS 77Bay 보통점검","2017-05-22T09:00:00","2017-05-26T17:00:00","2017-05-22T09:00:00","2017-05-26T17:00:00","연속",null,null,null,201703080090]
[3,"인천","인천복합","인천GT #1, 2 주변압기 CB(7500, 7572)","간이점검, 정기검사","간이점검, 정기검사(갑종보호계전기 시험 포함)","2017-05-07T09:00:00","2017-05-10T13:00:00","2017-05-07T09:00:00","2017-05-10T13:00:00","연속",null,null,null,201703060010]
[4,"인천","인천복합","인천ST #1 주변압기 CB(7600, 7672)","간이점검, 정기검사","간이점검, 정기검사(갑종보호계전기 시험 포함)","2017-05-10T14:00:00","2017-05-12T14:00:00","2017-05-10T14:00:00","2017-05-12T14:00:00","연속",null,null,null,201703080091]

{"sheet":"154송부","index":2,"n_rows":470,"n_cols":16,"rows_kept":470,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 5월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","마장한남 T/L","17년 마장S/S 마장한남T/L GIS 대체공사","17년 마장S/S 마장한남T/L GIS 대체공사","2017-05-29 09:00","2017-06-14 18:00","2017-05-29T09:00:00","2017-06-14T18:00:00","연속",null,null,null,201702160193]
[2,"서울","성동","마장신당 T/L","17년 마장S/S 마장신당T/L GIS 대체공사","17년 마장S/S 마장신당T/L GIS 대체공사","2017-05-10 09:30","2017-05-26 18:00","2017-05-10T09:30:00","2017-05-26T18:00:00","연속",null,null,null,201702160215]
[3,"서울","성동","상계노원열병합T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (상계S/S 노원열병합T/L)","2017-05-12 10:00","2017-05-12 17:00","2017-05-12T10:00:00","2017-05-12T17:00:00","당일",null,null,null,201703090591]
[4,"서울","성동","성수뚝도#1 T/L","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (성수S/S 성수뚝도#1T/L)","2017-05-25 09:20","2017-05-26 17:40","2017-05-25T09:20:00","2017-05-26T17:40:00","연속",null,null,null,201703090595]
[5,"서울","중부","당인리목동#1 T/L","154kV 당인리목동T/L EBA 자기애관 교체공사","154kV 당인리목동T/L EBA 자기애관 교체공사 - 자기애관 → 폴리머애관 교체","2017-05-23 09:00","2017-05-25 18:00","2017-05-23T09:00:00","2017-05-25T18:00:00","연속",null,null,null,201703200166]
[6,"서울","중부","당인리목동#2 T/L","154kV 당인리목동T/L EBA 자기애관 교체공사","154kV 당인리목동T/L EBA 자기애관 교체공사 - 자기애관 → 폴리머애관 교체","2017-05-23 09:00","2017-05-25 18:00","2017-05-23T09:00:00","2017-05-25T18:00:00","연속",null,null,null,201703200167]
[7,"서울","중부","옥인S/S 154kV #1 BUS","2017년 중부P/O 170kV GIS 정밀점검공사","옥인S/S 154kV BUS-TIE (6100) Bay 1DS (6101) 정밀점검","2017-05-10 10:00","2017-05-11 14:00","2017-05-10T10:00:00","2017-05-11T14:00:00","연속",null,null,null,201703210146]
[8,"서울","중부","옥인S/S 154kV #2 BUS","2017년 중부P/O 170kV GIS 정밀점검공사","옥인S/S 154kV BUS-TIE (6100) Bay 2DS (6102) 정밀점검","2017-05-11 14:00","2017-05-12 18:00","2017-05-11T14:00:00","2017-05-12T18:00:00","연속",null,null,null,201703210147]
[9,"서울","중부","옥인S/S 154kV #2 BUS","2017년 중부P/O 170kV GIS 정밀점검공사","옥인S/S 154kV 녹번옥인T/L (617) Bay 2DS (612) 정밀점검","2017-05-16 14:00","2017-05-17 18:00","2017-05-16T14:00:00","2017-05-17T18:00:00","연속",null,null,null,201703210144]
[10,"서울","중부","옥인S/S 154kV #1 BUS","2017년 중부P/O 170kV GIS 정밀점검공사","옥인S/S 154kV 옥인서대문T/L (627) Bay 1DS (621) 정밀점검","2017-05-18 10:00","2017-05-19 14:00","2017-05-18T10:00:00","2017-05-19T14:00:00","연속",null,null,null,201703210139]
[11,"서울","중부","옥인S/S 154kV #2 BUS","2017년 중부P/O 170kV GIS 정밀점검공사","옥인S/S 154kV 옥인서대문T/L (627) Bay 2DS (622) 정밀점검","2017-05-19 14:00","2017-05-20 18:00","2017-05-19T14:00:00","2017-05-20T18:00:00","연속",null,null,null,201703210142]
[12,"서울","중부","옥인S/S 154kV #1 BUS","2017년 중부P/O 170kV GIS 정밀점검공사","옥인S/S 154kV 녹번옥인T/L (617) Bay 1DS (611) 정밀점검","2017-05-15 10:00","2017-05-16 14:00","2017-05-15T10:00:00","2017-05-16T14:00:00","연속",null,null,null,201703210145]
[13,"남서울","강남","신사논현#2 T/L","154kV 신사-논일 지중T/L 건설공사","1. 구간 : 기설 154kV 신사논현T/L 분기점~154kV 논일S/S 2. 선종/회선길이 : XLPE2000, 2C-1.7km 3. 공사기간 : 2016.12 ~ 2017. 09 (10개월) 4. 준공목표 : 2017. 04","2017-05-11 09:00","2017-05-26 18:00","2017-05-11T09:00:00","2017-05-26T18:00:00","연속",null,null,"신뢰도 개선",201703080215]
[14,"남서울","강남","신사논현#1 T/L","154kV 논일-역삼, 논현-대치 지중T/L 건설공사","1. 구간 : 154kV 논일S/S, 논현S/S~기설 154kV 역삼대치T/L 분기점 2. 선종/회선길이 : XLPE1200, 2C-3.7km(논일-역삼),2C-3km(논현-대치) 3. 공사기간 : 2016.10 ~ 2017. 10 (12개월) 4. 준공목표 : 2017. 04(휴전에 따라 순연)","2017-05-27 09:00","2017-06-26 18:00","2017-05-27T09:00:00","2017-06-26T18:00:00","연속",null,null,"신뢰도 개선",201703080219]
[15,"남서울","강남","염곡개포#2 T/L","154kV 염곡-개포T/L OF케이블 선종교체공사","1. 염곡S/S~M/H#1 케이블 교체(367m, OF-&gtXLPE 2000mm2) - 2C*0.367m 2. 염곡s/s PT철거(6Set) 3. 공사기간 2017. 4 ~ 2017. 6","2017-05-25 13:00","2017-06-16 13:00","2017-06-27T13:00:00","2017-07-17T13:00:00","매일",null,null,null,201702160325]
[16,"남서울","강남","염곡개포#1 T/L","154kV 염곡-개포T/L OF케이블 선종교체공사","1. 염곡S/S~M/H#1 케이블 교체(367m, OF-&gtXLPE 2000mm2) - 2C*0.367m 2. 염곡s/s PT철거(6Set) 3. 공사기간 2017. 4 ~ 2017. 6","2017-05-01 09:00","2017-05-25 10:00","2017-06-01T09:00:00","2017-06-27T10:00:00","매일",null,null,null,201702160324]
[17,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(강동-천호#2T/L)","170kV GIS 정밀점검(강동-천호#2T/L)","2017-05-18 14:00","2017-05-19 14:00","2017-05-18T14:00:00","2017-05-19T14:00:00","연속",null,null,null,201703210228]
[18,"남서울","동서울","강동천호#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-05-17 13:00","2017-05-19 18:00","2017-05-17T13:00:00","2017-05-19T18:00:00","연속",null,null,null,201703210218]
[19,"남서울","동서울",0,"170kV GIS 정밀점검(강동-천호#1,2T/L)","170kV GIS 정밀점검(강동-천호#1,2T/L)","2017-05-16 14:00","2017-05-18 14:00","2017-05-16T14:00:00","2017-05-18T14:00:00","연속",null,null,null,201703210227]
[20,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(강동-천호#1T/L)","170kV GIS 정밀점검(강동-천호#1T/L)","2017-05-15 09:00","2017-05-16 14:00","2017-05-15T09:00:00","2017-05-16T14:00:00","연속",null,null,null,201703210226]
[21,"남서울","동서울","강동천호#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-05-15 09:00","2017-05-17 12:00","2017-05-15T09:00:00","2017-05-17T12:00:00","연속",null,null,null,201703210217]
[22,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(강동-암사T/L)","170kV GIS 정밀점검(강동-암사T/L)","2017-05-13 14:00","2017-05-14 18:00","2017-05-13T14:00:00","2017-05-14T18:00:00","연속",null,null,null,201703220078]
[23,"남서울","동서울","강동S/S 154kV #2 BUS","170kV GIS 정밀점검(6100,강동-암사T/L)","170kV GIS 정밀점검(6100,강동-암사T/L)","2017-05-11 14:00","2017-05-13 14:00","2017-05-11T14:00:00","2017-05-13T14:00:00","연속",null,null,null,201703210225]
[24,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(6100)","170kV GIS 정밀점검(6100)","2017-05-10 09:00","2017-05-11 14:00","2017-05-10T09:00:00","2017-05-11T14:00:00","연속",null,null,null,201703210224]
[25,"남서울","동서울","강동상일#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-05-22 09:00","2017-05-24 12:00","2017-05-22T09:00:00","2017-05-24T12:00:00","연속",null,null,null,201703210220]
[26,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(강동-상일#1T/L)","170kV GIS 정밀점검(강동-상일#1T/L)","2017-05-22 09:00","2017-05-23 14:00","2017-05-22T09:00:00","2017-05-23T14:00:00","연속",null,null,null,201703210231]
[27,"남서울","동서울","강동S/S 154kV #2 BUS","170kV GIS 정밀점검(강동-상일#1,2T/L)","170kV GIS 정밀점검(강동-상일#1,2T/L)","2017-05-23 14:00","2017-05-25 14:00","2017-05-23T14:00:00","2017-05-25T14:00:00","연속",null,null,null,201703210229]
[28,"남서울","동서울","강동상일#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-05-24 13:00","2017-05-26 18:00","2017-05-24T13:00:00","2017-05-26T18:00:00","연속",null,null,null,201703210221]
[29,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(강동-상일#2T/L)","170kV GIS 정밀점검(강동-상일#2T/L)","2017-05-25 14:00","2017-05-26 14:00","2017-05-25T14:00:00","2017-05-26T14:00:00","연속",null,null,null,201703210232]
[30,"남서울","동서울","강동S/S 154kV #2 BUS","170kV GIS 정밀점검(동서울-강동#1,2T/L)","170kV GIS 정밀점검(동서울-강동#1,2T/L)","2017-05-30 14:00","2017-06-01 14:00","2017-05-30T14:00:00","2017-06-01T14:00:00","연속",null,null,null,201703210230]
[31,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(동서울-강동#1T/L)","170kV GIS 정밀점검(동서울-강동#1T/L)","2017-05-29 09:00","2017-05-30 14:00","2017-05-29T09:00:00","2017-05-30T14:00:00","연속",null,null,null,201703210233]
[32,"남서울","영등포","마곡가양#1 T/L","154kV마곡-가양T/L 지중선로 이설공사","○ 이설 선로명 : 154kV마곡-가양#2T/L ○ 이설 구간 : 맨홀#15-1 ~맨홀#15 - 철거 : 110m, 설치 : 197m ○ 접속개소 : 절연접속 1, 보통접속 1개소.","2017-05-08 09:00","2017-06-06 18:00","2017-05-10T09:00:00","2017-06-08T18:00:00","연속",null,null,null,201703140001]
[33,"남서울","영등포","가양S/S 154kV #2 BUS","가양S/S 170kV 안천T/L GIS 대체공사","가양S/S 170kV 안천T/L GIS 대체공사","2017-05-10 09:00","2017-05-12 14:00","2017-05-10T09:00:00","2017-05-12T14:00:00","연속",null,null,null,201703210035]
[34,"남서울","영등포","가양S/S 154kV #1 BUS","가양S/S 170kV 안천T/L GIS 대체공사","가양S/S 170kV 안천T/L GIS 대체공사","2017-05-12 14:00","2017-05-19 14:00","2017-05-12T14:00:00","2017-05-19T14:00:00","연속",null,null,null,201703210043]
[35,"남서울","영등포","가양S/S 154kV #2 BUS","가양S/S 170kV 안천T/L GIS 대체공사","가양S/S 170kV 안천T/L GIS 대체공사","2017-05-19 14:00","2017-05-26 18:00","2017-05-19T14:00:00","2017-05-26T18:00:00","연속",null,null,null,201703210044]
[36,"남서울","영등포","광명구공#3 T/L","154kV GIS 보통점검","154kV GIS 보통점검","2017-05-23 09:00","2017-05-23 18:00","2017-05-23T09:00:00","2017-05-23T18:00:00","당일",null,null,null,201703200122]
[37,"남서울","직할","사당봉천#2 T/L","2017년 직할 관내SS 170kV GIS 정밀점검 공사","154kV 사당-봉천#2T/L GIS 정밀점검","2017-05-22 08:00","2017-05-24 18:00","2017-05-22T08:00:00","2017-05-24T18:00:00","당일",null,null,null,201703240091]
[38,"남서울","직할","사당S/S 154kV #1BUS","직할 관내SS 170kV GIS 정밀점검 공사(사당봉천2)","154kV 사당-봉천#2T/L GIS 정밀점검","2017-05-22 08:00","2017-05-23 13:00","2017-05-22T08:00:00","2017-05-23T13:00:00","연속",null,null,null,201703240092]
[39,"남서울","직할","사당S/S 154kV #2BUS","직할 관내SS 170kV GIS 정밀점검 공사(사당봉천2)","154kV 사당-봉천#2T/L GIS 정밀점검","2017-05-23 13:00","2017-05-24 18:00","2017-05-23T13:00:00","2017-05-24T18:00:00","연속",null,null,null,201703240093]
[40,"남서울","영등포","사당봉천#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2017-05-08 09:00","2017-05-08 18:00","2017-05-08T09:00:00","2017-05-08T18:00:00","당일",null,null,null,201703200102]
[41,"남서울","영등포","영서시흥#2 T/L","'17년 가공송전위탁공사(전력선부착 표시찰 설치공사)","구간 : No.12-14 수량 : 5개","2017-05-11 13:00","2017-05-11 18:00","2017-05-11T13:00:00","2017-05-11T18:00:00","당일",null,null,null,201703220042]
[42,"남서울","영등포","영서S/S 154kV #60 T BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","T-BUS 철거","2017-05-15 08:00","2018-06-30 18:00","취소","취소","연속",null,null,null,201703170026]
[43,"남서울","영등포","영서S/S 154kV #61 T BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","T-BUS 철거","2017-05-15 08:00","2018-06-30 18:00","취소","취소","연속",null,null,null,201703170025]
[44,"남서울","영등포","영서시흥#1 T/L","'17년 가공송전위탁공사(전력선부착 표시찰 설치공사)","구간 : No.12-14 수량 : 5개","2017-05-11 09:00","2017-05-11 13:00","2017-05-11T09:00:00","2017-05-11T13:00:00","당일",null,null,null,201703220041]
[45,"남서울","영등포","영서S/S 154kV #60 BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","60BUS LA 철거","2017-05-10 08:00","2017-05-11 13:00","2017-05-10T08:00:00","2017-05-11T13:00:00","연속",null,null,null,201703170018]
[46,"남서울","영등포","영서S/S 154kV #65 BUS","영서S/S 154kV이하 옥외철구 GIS화 공사","65BUS LA 철거","2017-05-11 13:00","2017-05-12 18:00","2017-05-11T13:00:00","2017-05-12T18:00:00","연속",null,null,null,201703170024]
[47,"남서울","영등포","영서시흥#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-05-17 08:00","2017-05-17 18:00","2017-05-17T08:00:00","2017-05-17T18:00:00","당일",null,null,null,201703170028]
[48,"남서울","영등포","영서시흥#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-05-18 08:00","2017-05-18 18:00","2017-05-18T08:00:00","2017-05-18T18:00:00","당일",null,null,null,201703170029]
[49,"남서울","영등포","영서광명#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-05-23 08:00","2017-05-23 18:00","2017-05-23T08:00:00","2017-05-23T18:00:00","당일",null,null,null,201703170031]
[50,"남서울","영등포","영서광명#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","T-BUS DS 철거","2017-05-24 08:00","2017-05-24 18:00","2017-05-24T08:00:00","2017-05-24T18:00:00","당일",null,null,null,201703170032]
[51,"남서울","영등포","천왕구로#2 T/L","17-18 영서전력지사 지중송전설비 위탁정비공사","154kV 천왕-구로T/L SVL 보강공사","2017-05-29 09:00","2017-06-02 18:00","2017-05-29T09:00:00","2017-06-02T18:00:00","연속",null,null,null,201703140063]
[52,"남서울","영등포","천왕구로#1 T/L","17-18 영서전력지사 지중송전설비 위탁정비공사","154kV 천왕-구로T/L SVL 보강공사","2017-05-15 09:00","2017-05-19 18:00","2017-05-15T09:00:00","2017-05-19T18:00:00","연속",null,null,null,201703140058]
[53,"인천","김포","신경서경서#3 T/L","경서S/S 154kV 신경서-경서#3T/L GIS 보통점검","경서S/S 154kV 신경서-경서#3T/L GIS(677) 보통점검","2017-05-12 10:00","2017-05-12 18:00","2017-05-12T10:00:00","2017-05-12T18:00:00","당일",null,null,null,201703130480]
[54,"인천","김포","계양김포#2 T/L","154kV 계양-김포#2T/L EBA 절연유 채유","○ 종단접속(EBA) 절연유 분석 - 내용 : 내부 절연유(실리콘유) 채취 후 성분분석을 통한 열화상태 진단 - 적용대상 : 철구형 또는 수평배치형 C/H에 설치된 EBA - 시행방법 : 시료채취(위탁전문회사) 후 설비진단처 분석 의뢰","2017-05-24 09:00","2017-05-25 18:00","2017-05-24T09:00:00","2017-05-25T18:00:00","연속",null,null,null,201703080228]
[55,"인천","김포","계양김포#1 T/L","154kV 계양-김포#1T/L EBA 절연유 채유","○ 종단접속(EBA) 절연유 분석 - 내용 : 내부 절연유(실리콘유) 채취 후 성분분석을 통한 열화상태 진단 - 적용대상 : 철구형 또는 수평배치형 C/H에 설치된 EBA - 시행방법 : 시료채취(위탁전문회사) 후 설비진단처 분석 의뢰","2017-05-22 09:00","2017-05-23 18:00","2017-05-22T09:00:00","2017-05-23T18:00:00","연속",null,null,null,201703080227]
[56,"인천","김포","신경서왕길#2 T/L","154kV 신경서-왕길#2T/L 피뢰기 열화진단 및 EBA 절연유 채유","○ 종단접속(EBA) 절연유 분석 - 내용 : 내부 절연유(실리콘유) 채취 후 성분분석을 통한 열화상태 진단 - 적용대상 : 철구형 또는 수평배치형 C/H에 설치된 EBA - 시행방법 : 시료채취(위탁전문회사) 후 설비진단처 분석 의뢰 ○ 피뢰기 열화진단 - 내 용 : 도블테스트, 절연저항, 누설전류, 금구류 오결합 여부 점검","2017-05-17 09:00","2017-05-18 18:00","2017-05-17T09:00:00","2017-05-18T18:00:00","연속",null,null,null,201703080223]
[57,"인천","김포","신경서왕길#1 T/L","154kV 신경서-왕길#1T/L 피뢰기 열화진단 및 EBA 절연유 채유","○ 종단접속(EBA) 절연유 분석 - 내용 : 내부 절연유(실리콘유) 채취 후 성분분석을 통한 열화상태 진단 - 적용대상 : 철구형 또는 수평배치형 C/H에 설치된 EBA - 시행방법 : 시료채취(위탁전문회사) 후 설비진단처 분석 의뢰 ○ 피뢰기 열화진단 - 내 용 : 도블테스트, 절연저항, 누설전류, 금구류 오결합 여부","2017-05-15 09:00","2017-05-16 18:00","2017-05-15T09:00:00","2017-05-16T18:00:00","연속",null,null,null,201703070352]
[58,"인천","시흥","신시흥남동#2 T/L","SVL 교체공사","SVL 교체공사","2017-05-24 09:00","2017-05-25 18:00","2017-05-24 09:00","2017-05-25 18:00","연속",null,null,null,201703090303]
[59,"인천","시흥","신시흥남동#1 T/L","SVL 교체공사","SVL 교체공사","2017-05-22 09:00","2017-05-23 18:00","2017-05-22 09:00","2017-05-23 18:00","연속",null,null,null,201703090300]
[60,"인천","시흥","시화동시화#1 T/L","SVL 교체공사","SVL 교체공사","2017-05-11 09:00","2017-05-11 18:00","2017-05-11T09:00:00","2017-05-11T18:00:00","당일",null,null,null,201703090298]
[61,"인천","시흥","시화동시화#2 T/L","SVL 교체공사","SVL 교체공사","2017-05-12 09:00","2017-05-12 18:00","2017-05-12T09:00:00","2017-05-12T18:00:00","당일",null,null,null,201703090299]
[62,"인천","시흥","동시화서시화 T/L","SVL 교체공사","SVL 교체공사","2017-05-10 09:00","2017-05-10 12:00","2017-05-10T09:00:00","2017-05-10T12:00:00","당일",null,null,null,201703090295]
[63,"인천","시흥","신시흥도림 T/L","신시흥#1S/S 154kV 신시흥도림 T/L GIS 보통점검","신시흥#1S/S 154kV 신시흥도림 T/L GIS 보통점검","2017-05-26 09:30","2017-05-26 18:00","2017-05-15T09:30:00","2017-05-15T18:00:00","당일",null,null,null,201703090392]
[64,"인천","시흥","신시흥#1S/S 154kV #61 Sh.C CB","신시흥#1S/S 154kV #61 Sh.C GIS 정밀점검","신시흥#1S/S 154kV #61 Sh.C GIS 정밀점검","2017-05-11 08:00","2017-05-13 18:00","2017-05-11T08:00:00","2017-05-13T18:00:00","연속",null,null,null,201703090296]
[65,"인천","시흥","신시흥#1S/S 154kV #65 BUS","신시흥#1S/S 154kV #61 Sh.C GIS 정밀점검","신시흥#1S/S 154kV #61 Sh.C GIS 정밀점검","2017-05-11 08:00","2017-05-12 14:00","2017-05-11T08:00:00","2017-05-12T14:00:00","연속",null,null,null,201703090321]
[66,"인천","시흥","신시흥#1S/S 154kV #60 BUS","신시흥#1S/S 154kV #61 Sh.C GIS 정밀점검","신시흥#1S/S 154kV #61 Sh.C GIS 정밀점검","2017-05-12 14:00","2017-05-13 18:00","2017-05-12T14:00:00","2017-05-13T18:00:00","연속",null,null,null,201703090323]
[67,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S 154kV 신시흥시화#2 T/L GIS 보통점검","신시흥#2S/S 154kV 신시흥시화#2 T/L GIS 보통점검","2017-05-23 09:30","2017-05-23 18:00","2017-05-23T09:30:00","2017-05-23T18:00:00","당일",null,null,null,201703090395]
[68,"인천","시흥","신시흥#2S/S 67-68 SEC GIS","신시흥#2S/S 67-68 SEC GIS 보통점검","신시흥#2S/S 67-68 SEC GIS 보통점검","2017-05-24 09:30","2017-05-24 18:00","2017-05-24T09:30:00","2017-05-24T18:00:00","당일",null,null,null,201703090397]
[69,"인천","인천","남동관교#2 T/L","SB댐퍼 설치공사","SB댐퍼 설치공사","2017-05-23 08:00","2017-05-23 18:00","2017-05-23T08:00:00","2017-05-23T18:00:00","당일",null,null,null,201703150179]
[70,"인천","인천","남동관교#1 T/L","SB댐퍼 설치공사","SB댐퍼 설치공사","2017-05-22 08:00","2017-05-22 18:00","2017-05-22T08:00:00","2017-05-22T18:00:00","당일",null,null,null,201703150178]
[71,"인천","인천","남인천학익#1 T/L","SVL 교체공사","SVL 교체공사","2017-05-01 09:00","2017-05-01 18:00","2017-05-01T09:00:00","2017-05-01T18:00:00","당일",null,null,null,201703090278]
[72,"인천","인천","남인천학익#2 T/L","SVL 교체공사","SVL 교체공사","2017-05-02 09:00","2017-05-02 18:00","2017-05-02T09:00:00","2017-05-02T18:00:00","당일",null,null,null,201703090279]
[73,"인천","인천","인천CC북인천#2 T/L","일진제 구형 154kV PMJ 교체공사(인천CC-북인천#2T/L)","일진제 154kV R-type PMJ 교체(21개 접속함)","2017-05-29 09:00","2017-06-17 18:00","2017-05-31T09:00:00","2017-06-20T18:00:00","연속",null,null,null,201703130490]
[74,"인천","인천","인천CC북인천#1 T/L","일진제 구형 154kV PMJ 교체공사(인천CC-북인천#1T/L)","일진제 154kV R-type PMJ 교체(21개 접속함)","2017-05-08 09:00","2017-05-27 18:00","2017-05-08T09:00:00","2017-05-30T18:00:00","연속",null,null,null,201703130489]
[75,"인천","인천","서인천C/C 65-66 SEC GIS","서인천CC 65-66 BUS SEC GIS 조작시험","서인천CC 65-66 BUS SEC GIS 조작시험","2017-05-26 13:00","2017-05-26 18:00","2017-05-26T13:00:00","2017-05-26T18:00:00","당일",null,null,null,201703140236]
[76,"인천","인천","서인천C/C 60-61 SEC GIS","서인천CC 60-61 BUS SEC GIS 조작시험","서인천CC 60-61 BUS SEC GIS 조작시험","2017-05-26 09:00","2017-05-26 13:00","2017-05-26T09:00:00","2017-05-26T13:00:00","당일",null,null,null,201703140235]
[77,"인천","인천","송현포스코CC#2 T/L","송현S/S 송현-포스코CC#2T/L 보호반 대체공사","송현S/S 송현-포스코CC#2T/L 보호반 대체공사 - 보호반 대체공사 - 170kV GIS 보통점검","2017-05-22 08:00","2017-05-27 18:00","2017-05-22T08:00:00","2017-05-27T18:00:00","연속",null,null,null,201703140346]
[78,"인천","인천","송현포스코CC#1 T/L","송현S/S 송현-포스코CC#1T/L 보호반 대체공사","송현S/S 송현-포스코CC#1T/L 보호반 대체공사 - 보호반 대체공사 - 170kV GIS 보통점검","2017-05-15 08:00","2017-05-20 18:00","2017-05-15T08:00:00","2017-05-20T18:00:00","연속",null,null,null,201703140345]
[79,"인천","인천","신가좌S/S 154kV #60 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - #60-61-0SEC GIS 정밀점검 관련 모선휴전","2017-05-10 09:00","2017-05-11 10:00","2017-05-10T09:00:00","2017-05-11T10:00:00","연속",null,null,null,201703150227]
[80,"인천","인천","신가좌S/S 60-61 SEC GIS","2017년도 170kV GIS 정밀점검 공사","신가좌S/S #60-61-0SEC 정밀점검 공사","2017-05-10 09:00","2017-05-12 18:00","2017-05-10T09:00:00","2017-05-12T18:00:00","연속",null,null,null,201703150226]
[81,"인천","인천","신가좌S/S 154kV #66 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 신가좌부개#2T/L GIS 정밀점검 관련 모선휴전","2017-05-19 10:00","2017-05-20 18:00","2017-05-19T10:00:00","2017-05-20T18:00:00","연속",null,null,null,201703160025]
[82,"인천","인천","신가좌S/S 154kV #61 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 60-61-0 GIS 관련 모선휴전","2017-05-11 10:00","2017-05-12 09:00","2017-05-11T10:00:00","2017-05-12T09:00:00","연속",null,null,null,201703150228]
[83,"인천","인천","신가좌부개#1 T/L","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 신가좌부개#1T/L GIS 정밀점검","2017-05-15 09:00","2017-05-17 18:00","2017-05-15T09:00:00","2017-05-17T18:00:00","연속",null,null,null,201703160018]
[84,"인천","인천","신가좌S/S 154kV #66 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 신가좌부개#1T/L GIS 정밀점검 관련 모선휴전","2017-05-16 10:00","2017-05-17 18:00","2017-05-16T10:00:00","2017-05-17T18:00:00","연속",null,null,null,201703160020]
[85,"인천","인천","신가좌S/S 154kV #61 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 신가좌부개#1T/L GIS 관련 모선휴전","2017-05-15 10:00","2017-05-16 09:00","2017-05-15T10:00:00","2017-05-16T09:00:00","연속",null,null,null,201703160019]
[86,"인천","인천","신가좌S/S 154kV #61 BUS","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 신가좌부개#2T/L GIS 관련 모선휴전","2017-05-18 10:00","2017-05-19 09:00","2017-05-18T10:00:00","2017-05-19T09:00:00","연속",null,null,null,201703160024]
[87,"인천","인천","신가좌부개#2 T/L","2017년도 170kV GIS 정밀점검 공사","2017년도 170kV GIS 정밀점검 공사 - 신가좌부개#2T/L GIS 정밀점검","2017-05-18 09:00","2017-05-20 18:00","2017-05-18T09:00:00","2017-05-20T18:00:00","연속",null,null,null,201703160023]
[88,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-05-30 08:00","2017-06-03 18:00","2017-05-30T08:00:00","2017-06-03T18:00:00","연속",null,null,null,201703150146]
[89,"인천","인천","신가좌신현#2 T/L","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-05-15 08:00","2017-06-08 18:00","2017-05-15T08:00:00","2017-06-08T18:00:00","연속",null,null,"신뢰도개선",201703150026]
[90,"인천","인천","신현포스코CC#2 T/L","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-05-15 08:00","2017-06-08 18:00","2017-05-15T08:00:00","2017-06-08T18:00:00","연속",null,null,"신뢰도개선",201703150029]
[91,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-05-15 08:00","2017-05-19 18:00","2017-05-15T08:00:00","2017-05-19T18:00:00","연속",null,null,null,201703150143]
[92,"인천","인천","신현송현#2 T/L","SVL 교체공사","SVL 교체공사","2017-05-08 14:00","2017-05-08 18:00","2017-05-08T14:00:00","2017-05-08T18:00:00","당일",null,null,"신뢰도개선",201703090285]
[93,"인천","인천","신현송현#1 T/L","SVL 교체공사","SVL 교체공사","2017-05-08 09:00","2017-05-08 12:00","2017-05-08T09:00:00","2017-05-08T12:00:00","당일",null,null,"신뢰도개선",201703090284]
[94,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-05-20 08:00","2017-05-29 18:00","2017-05-20T08:00:00","2017-05-29T18:00:00","연속",null,null,null,201703150144]
[95,"인천","인천","신경서영종#2 T/L","154kV 영종-중산 지중T/L 건설공사","154kV XLPE 2000㎟(평활), 2C-6.8km (154kV 신경서-영종#2T/L 직결)","2017-05-10 09:00","2017-06-08 18:00","2017-05-10T09:00:00","2017-06-08T18:00:00","당일",null,null,null,201703290060]
[96,"인천","직할","계양원창 T/L","SB댐퍼 설치공사","345kV 신가좌가정#2T/L SB댐퍼 설치공사 작업안전 확보를 위한 일시 휴전","2017-05-30 08:00","2017-05-30 11:00","2017-05-30T08:00:00","2017-05-30T11:00:00","당일",null,null,null,201703160123]
[97,"인천","직할","계양북인천 T/L","SB댐퍼 설치공사","345kV 신가좌가정#1T/L SB댐퍼 설치공사 작업안전 확보를 위한 일시 휴전","2017-05-29 08:00","2017-05-29 11:00","2017-05-29T08:00:00","2017-05-29T11:00:00","당일",null,null,null,201703160122]
[98,"인천","직할","신부평고강#1 T/L","신부평-임학 등 8개 T/L 접지선 정비(신부평-고강#1T/L)","지중송전케이블 접지선 정비(150SQ→240SQ)","2017-05-15 09:00","2017-05-16 18:00","2017-05-15T09:00:00","2017-05-16T18:00:00","매일",null,null,null,201703130473]
[99,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 신가좌부개 #2T/L 170kV GIS 정밀점검","부개S/S 신가좌부개 #2T/L 170kV GIS 정밀점검","2017-05-18 08:00","2017-05-19 14:00","2017-05-18T08:00:00","2017-05-19T14:00:00","연속",null,null,null,201703100568]
[100,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 부흥부개#1T/L 170kV GIS 정밀점검","부개S/S 부흥부개#1T/L 170kV GIS 정밀점검","2017-05-22 08:00","2017-05-23 10:00","2017-05-22T08:00:00","2017-05-23T10:00:00","연속",null,null,null,201703100574]
[101,"인천","직할","부흥부개#1 T/L","부개S/S 부흥부개#1T/L 170kV GIS 정밀점검","부개S/S 부흥부개#1T/L 170kV GIS 정밀점검","2017-05-22 08:00","2017-05-23 20:00","2017-05-22T08:00:00","2017-05-23T20:00:00","연속",null,null,null,201703100573]
[102,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 부흥부개#1T/L 170kV GIS 정밀점검","부개S/S 부흥부개#1T/L 170kV GIS 정밀점검","2017-05-23 10:00","2017-05-23 20:00","2017-05-23T10:00:00","2017-05-23T20:00:00","연속",null,null,null,201703100575]
[103,"인천","직할","부흥부개#2 T/L","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","2017-05-24 08:00","2017-05-25 20:00","2017-05-24T08:00:00","2017-05-25T20:00:00","연속",null,null,null,201703100576]
[104,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","2017-05-24 08:00","2017-05-25 10:00","2017-05-24T08:00:00","2017-05-25T10:00:00","연속",null,null,null,201703100577]
[105,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","2017-05-25 10:00","2017-05-25 20:00","2017-05-25T10:00:00","2017-05-25T20:00:00","연속",null,null,null,201703100578]
[106,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 6100 TIE 170kV GIS 정밀점검","부개S/S 6100 TIE 170kV GIS 정밀점검","2017-05-31 08:00","2017-05-31 20:00","2017-05-31T08:00:00","2017-05-31T20:00:00","연속",null,null,null,201703100571]
[107,"인천","직할","부개S/S 154kV #1 BUS TIE GIS","부개S/S 6100 TIE 170kV GIS 정밀점검","부개S/S 6100 TIE 170kV GIS 정밀점검","2017-05-31 08:00","2017-06-01 20:00","2017-05-31T08:00:00","2017-06-01T20:00:00","연속",null,null,null,201703100570]
[108,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 6100 TIE 170kV GIS 정밀점검","부개S/S 6100 TIE 170kV GIS 정밀점검","2017-05-31 20:00","2017-06-01 20:00","2017-05-31T20:00:00","2017-06-01T20:00:00","연속",null,null,null,201703100572]
[109,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 신가좌부개 #1T/L 170kV GIS 정밀점검","부개S/S 신가좌부개 #1T/L 170kV GIS 정밀점검","2017-05-15 08:00","2017-05-16 14:00","2017-05-15T08:00:00","2017-05-16T14:00:00","연속",null,null,null,201703100565]
[110,"인천","직할","부개원미#2 T/L","154kV 신부평-임학 등 8개 T/L 접지선 정비(부개-원미#2T/L)","지중송전케이블 접지선 정비(150SQ→240SQ)","2017-05-11 09:00","2017-05-12 18:00","2017-05-11T09:00:00","2017-05-12T18:00:00","매일",null,null,null,201703130469]
[111,"인천","직할","부개원미#1 T/L","154kV 신부평-임학 등 8개T/L 접지선정비(부개-원미#1T/L)","지중송전케이블 접지선 정비(150SQ→240SQ)","2017-05-08 09:00","2017-05-10 18:00","2017-05-08T09:00:00","2017-05-10T18:00:00","매일",null,null,null,201703130452]
[112,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 신가좌부개 #2T/L 170kV GIS 정밀점검","부개S/S 신가좌부개 #2T/L 170kV GIS 정밀점검","2017-05-19 14:00","2017-05-20 18:00","2017-05-19T14:00:00","2017-05-20T18:00:00","연속",null,null,null,201703100569]
[113,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 신가좌부개 #1T/L 170kV GIS 정밀점검","부개S/S 신가좌부개 #1T/L 170kV GIS 정밀점검","2017-05-16 14:00","2017-05-17 18:00","2017-05-16T14:00:00","2017-05-17T18:00:00","연속",null,null,null,201703100566]
[114,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 6100TIE 170kV GIS 정밀점검","부천S/S 6100TIE 170kV GIS 정밀점검","2017-05-13 08:00","2017-05-14 10:00","2017-05-13T08:00:00","2017-05-14T10:00:00","연속",null,null,null,201703100562]
[115,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 6100TIE 170kV GIS 정밀점검","부천S/S 6100TIE 170kV GIS 정밀점검","2017-05-14 10:00","2017-05-14 20:00","2017-05-14T10:00:00","2017-05-14T20:00:00","연속",null,null,null,201703100563]
[116,"인천","직할","부천S/S 154kV #1 BUS TIE GIS","부천S/S 6100TIE 170kV GIS 정밀점검","부천S/S 6100TIE 170kV GIS 정밀점검","2017-05-13 08:00","2017-05-14 20:00","2017-05-13T08:00:00","2017-05-14T20:00:00","연속",null,null,null,201703100561]
[117,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","2017-05-30 10:00","2017-05-30 20:00","2017-05-30T10:00:00","2017-05-30T20:00:00","연속",null,null,null,201703100560]
[118,"인천","직할","부천신정#1 T/L","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","2017-05-26 08:00","2017-05-27 20:00","2017-05-26T08:00:00","2017-05-27T20:00:00","연속",null,null,null,201703100555]
[119,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","2017-05-27 10:00","2017-05-27 20:00","2017-05-27T10:00:00","2017-05-27T20:00:00","연속",null,null,null,201703100557]
[120,"인천","직할","부천신정#2 T/L","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","2017-05-29 08:00","2017-05-30 20:00","2017-05-29T08:00:00","2017-05-30T20:00:00","연속",null,null,null,201703100558]
[121,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","2017-05-29 08:00","2017-05-30 10:00","2017-05-29T08:00:00","2017-05-30T10:00:00","연속",null,null,null,201703100559]
[122,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","2017-05-26 08:00","2017-05-27 10:00","2017-05-26T08:00:00","2017-05-27T10:00:00","연속",null,null,null,201703100556]
[123,"경기북부","구리","구리신내#1 T/L","154kV GIS 보통점검","154kV GIS 보통점검","2017-05-11 10:00","2017-05-11 18:00","2017-05-11T10:00:00","2017-05-11T18:00:00","당일",null,null,null,201703130419]
[124,"경기북부","구리","신의정부내촌#1 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","35호 중단애자 교체","2017-05-25 08:00","2017-05-25 18:00","2017-05-25T08:00:00","2017-05-25T18:00:00","당일",null,null,null,201703140294]
[125,"경기북부","구리","덕소S/S 신장-덕소#1T/L CB","154kV GCB 보통점검 공사","154kV GCB 보통점검 공사","2017-05-08 10:00","2017-05-08 18:00","2017-05-08T10:00:00","2017-05-08T18:00:00","당일",null,null,null,201703130400]
[126,"경기북부","구리","덕소팔당HP T/L","자기제 기중종단접속함(EB-A) 애관 교체공사","대상 : 154kV 덕소-팔당HP T/L 팔당C/H 1개소(3상) 내용 : 구형 자기제 애관 철거 및 신형 대체용 폴리머애관 설치","2017-05-30 08:00","2017-06-02 18:00","2017-05-30T08:00:00","2017-06-02T18:00:00","연속",null,null,null,201703130251]
[127,"경기북부","구리","서종청평PP#1 T/L","154kV 서종-청평PPT/L 전선접속개소 전선교체공사","154kv 서종-청평PP T/L No.12~13등 5개구간","2017-05-29 08:00","2017-06-13 18:00","2017-05-29T08:00:00","2017-06-13T18:00:00","연속",null,null,null,201703140394,"○"]
[128,"경기북부","구리","신의정부송우#2 T/L","154kV GIS 보통점검","154kV GIS 보통점검","2017-05-16 09:00","2017-05-16 18:00","2017-05-16T09:00:00","2017-05-16T18:00:00","당일",null,null,null,201703130423]
[129,"경기북부","구리","곤지암용문#2 T/L","154kV GIS 보통점검","154kV GIS 보통점검","2017-05-24 09:00","2017-05-24 18:00","2017-05-24T09:00:00","2017-05-24T18:00:00","당일",null,null,null,201703130430]
[130,"경기북부","구리","내촌포천#2 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","7호 중단 부하외측 애자 교체","2017-05-24 13:00","2017-05-24 18:00","2017-05-24T13:00:00","2017-05-24T18:00:00","당일",null,null,null,201703140259]
[131,"경기북부","구리","내촌포천#1 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","6호 중단 부하외측 애자 교체","2017-05-24 08:00","2017-05-24 13:00","2017-05-24T08:00:00","2017-05-24T13:00:00","당일",null,null,null,201703140256]
[132,"경기북부","구리","신포천포천#1 T/L","154kV 포천S/S 포천열병합T/L 증설공사","○ 154kV 옥외 단로기 3대 이설(의정부S/S → 포천S/S) ○ 154kV GCB설치 ○ 송전선로보호배전반 1면 설치 × 1식 ○ 철구조립 및 모선배선 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 접지장치 및 변전기기 기초공사 × 1식 ○ 기타 부대공사 1식","2017-05-18 08:00","2017-05-19 17:00","2017-05-18T08:00:00","2017-05-19T17:00:00","연속",null,null,null,201703200052]
[133,"경기북부","구리","신포천포천#2 T/L","154kV 포천S/S 포천열병합T/L 증설공사","○ 154kV 옥외 단로기 3대 이설(의정부S/S → 포천S/S) ○ 154kV GCB설치 ○ 송전선로보호배전반 1면 설치 × 1식 ○ 철구조립 및 모선배선 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 접지장치 및 변전기기 기초공사 × 1식 ○ 기타 부대공사 1식","2017-05-24 08:00","2017-05-26 17:00","2017-05-24T08:00:00","2017-05-26T17:00:00","연속",null,null,null,201703200054]
[134,"경기북부","직할","녹양백석#2 T/L","154kV 남면, 백석S/S SW 증설공사","154kV 남면, 백석S/S SW 증설공사 (#2BUS 무부하가압)","2017-05-26 18:00","2017-05-29 10:00","2017-05-26T18:00:00","2017-05-29T10:00:00","연속",null,null,null,201703200060]
[135,"경기북부","직할","녹양백석#1 T/L","154kV 남면, 백석S/S SW 증설공사","#1 BUS 무부하가압","2017-05-19 18:00","2017-05-22 10:00","2017-05-19T18:00:00","2017-05-22T10:00:00","연속",null,null,null,201703140239]
[136,"경기북부","직할","양주녹양#2 T/L","직할 변전총액공사 (양주-녹양#2T/L 보호반 교체)","직할 변전총액공사 (양주-녹양#2T/L 보호반 교체) 양주S/S 양주-녹양#2T/L 녹양S/S 양주-녹양#2T/L","2017-05-15 10:00","2017-05-19 18:00","2017-05-15T10:00:00","2017-05-19T18:00:00","연속",null,null,null,201702140231]
[137,"경기북부","파주","양주고양#1 T/L","154kV 양주-고양#1T/L 전선교체공사","154kV 양주-고양#1T/L No.28~29 등 5개소 전선교체공사","2017-05-16 07:00","2017-05-22 18:00","취소","취소","연속",null,null,null,201702170185,"○"]
[138,"경기북부","파주","양주고양#2 T/L","154kV 양주-고양#2T/L 전선교체공사","154kV 양주-고양#2T/L No.28~29 등 5개소 전선교체공사","2017-05-11 07:00","2017-05-16 18:00","취소","취소","연속",null,null,null,201702170183,"○"]
[139,"경기북부","파주","양주금촌#1 T/L","345kV 양주-중부#2T/L 전선교체공사","345kV 양주-중부#2T/L No.3~5 등 2구간 전선교체공사 관련 하부선로 안전 휴전","2017-05-16 07:00","2017-05-16 18:00","취소","취소","당일",null,null,null,201703200123]
[140,"경기북부","파주","양주금촌#2 T/L","345kV 양주-중부#2T/L 전선교체공사","345kV 양주-중부#2T/L No.3~5 등 2구간 전선교체공사 관련 하부선로 안전 휴전","2017-05-16 07:00","2017-05-16 18:00","취소","취소","당일",null,null,null,201703200124]
[141,"경기북부","파주","송포S/S 신파주-송포#1T/L GIS","17년 파주전력지사 170kV GIS 정밀점검공사","송포S/S 신파주-송포#1T/L GIS 정밀점검","2017-05-10 09:00","2017-05-12 18:00","2017-05-10T09:00:00","2017-05-12T18:00:00","연속",null,null,null,201703210296]
[142,"경기북부","파주","송포S/S 신파주-송포#2T/L GIS","17년 파주전력지사 170kV GIS 정밀점검공사","송포S/S 신파주-송포#2T/L GIS 정밀점검","2017-05-18 09:00","2017-05-20 18:00","2017-05-18T09:00:00","2017-05-20T18:00:00","연속",null,null,null,201703210297]
[143,"경기북부","파주","신덕은원흥#1 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","전력선교체 : 4.319km","2017-05-10 08:00","2017-05-15 18:00","취소","취소","연속",null,null,null,201703060160]
[144,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","전력선교체 : 4.319km","2017-05-16 08:00","2017-05-21 18:00","취소","취소","연속",null,null,null,201703060161]
[145,"경기북부","파주","원흥수색#1 T/L","154kV 원흥-수색T/L 송전용량증대 전선교체공사","No.9~12, No.14~16","2017-05-22 08:00","2017-05-25 18:00","취소","취소","연속",null,null,null,201703060162]
[146,"경기북부","파주","원흥수색#2 T/L","154kV 원흥-수색T/L 송전용량증대 전선교체공사","No.9~12, No.14~16","2017-05-26 08:00","2017-05-29 18:00","취소","취소","연속",null,null,null,201703060163]
[147,"경기북부","파주","일산S/S 154kV #66 BUS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-05-16 08:30","2017-05-26 08:00","2017-05-16T08:30:00","2017-05-26T08:00:00","연속",null,null,null,201703140124]
[148,"경기북부","파주","일산S/S 154kV #61 BUS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-05-11 08:30","2017-05-16 08:00","2017-05-11T08:30:00","2017-05-16T08:00:00","연속",null,null,null,201703140119]
[149,"경기북부","파주","일산S/S 154kV #61 BUS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-05-26 08:30","2017-06-01 08:00","2017-05-26T08:30:00","2017-06-01T08:00:00","연속",null,null,null,201703140130]
[150,"경기북부","파주","일산S/S #5G/T GIS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-05-23 08:30","2017-06-07 08:00","2017-05-23T08:30:00","2017-06-07T08:00:00","연속",null,null,null,201703140105]
[151,"경기북부","파주","일산S/S #2S/T GIS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-05-08 08:00","2017-05-22 08:00","2017-05-08T08:00:00","2017-05-22T08:00:00","연속",null,null,null,201703140099]
[152,"경기북부","파주","일산S/S 154kV #66 BUS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-05-08 08:00","2017-05-11 08:00","2017-05-08T08:00:00","2017-05-11T08:00:00","연속",null,null,null,201703140115]
[153,"경기","군포","목내안산에너지T/L","안산도시개발주식회사 보호PNL 교체공사 (05/15~20)","안산도시개발주식회사 보호PNL 교체공사 (05/15~20) 병행작업 : 목내S/S 154kV GIS 안산에너지T/L 정밀점검공사(05/15~17)","2017-05-15 09:00","2017-05-20 18:00","2017-05-15T09:00:00","2017-05-20T18:00:00","연속",null,null,null,201703080312]
[154,"경기","군포","서서울산본#1 T/L","154kV 서서울산본#1T/L 가공송전선로 정밀점검","154kV 서서울산본#1T/L 가공송전선로 정밀점검(1~19호, 19기)","2017-05-25 09:00","2017-05-25 18:00","2017-05-25T09:00:00","2017-05-25T18:00:00","당일",null,null,"신뢰도개선",201703090063]
[155,"경기","군포","서서울산본#2 T/L","154kV 서서울산본#2T/L 가공송전선로 정밀점검","154kV 서서울산본#2T/L 가공송전선로 정밀점검(1~19호, 19기)","2017-05-26 09:00","2017-05-26 18:00","2017-05-26T09:00:00","2017-05-26T18:00:00","당일",null,null,"신뢰도개선",201703090065]
[156,"경기","군포","서서울소래 T/L","345kV 신군포S/S 건설공사","서서울-소래T/L 이설(→서서울2S/S)","2017-05-31 07:00","2017-06-05 18:00","2017-05-31T07:00:00","2017-06-05T18:00:00","연속",null,null,null,201703200095]
[157,"경기","군포","서서울남수원#2 T/L","345kV 신군포S/S 건설공사","서서울-남수원 #2T/L 이설(→서서울2S/S)","2017-05-16 07:00","2017-05-21 18:00","2017-05-16T07:00:00","2017-05-21T18:00:00","연속",null,null,null,201703140527]
[158,"경기","군포","서서울남수원#1 T/L","345kV 신군포S/S 건설공사","서서울-남수원 #1T/L 이설(→서서울2S/S)","2017-05-10 07:00","2017-05-15 18:00","2017-05-10T07:00:00","2017-05-15T18:00:00","연속",null,null,null,201703140528]
[159,"경기","군포","서서울서안양 T/L","345kV 신군포S/S 건설공사","서서울-서안양T/L 이설(→서서울2S/S)","2017-05-24 07:00","2017-05-29 18:00","2017-05-24T07:00:00","2017-05-29T18:00:00","연속",null,null,null,201703200094]
[160,"경기","군포","성곡중시화 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 중시화S/S 성곡중시화T/L","2017-05-25 09:00","2017-05-27 18:00","2017-05-25T09:00:00","2017-05-27T18:00:00","연속",null,null,null,201703080323]
[161,"경기","동부","성현분당#2 T/L","154kV 성현-분당T/L 전선교체공사","전선접속개소 전선교체공사","2017-05-20 08:00","2017-05-26 18:00","2017-05-20T08:00:00","2017-05-26T18:00:00","연속",null,null,null,201703140043]
[162,"경기","동부","성현분당#1 T/L","154kV 성현-분당T/L 전선교체공사","전선접속개소 전선교체공사","2017-05-13 08:00","2017-05-18 18:00","2017-05-13T08:00:00","2017-05-18T18:00:00","연속",null,null,null,201703140041]
[163,"경기","동부","분당오포#2 T/L","154kV 성현-분당T/L 전선교체공사","전선접속개소 전선교체공사(4회선구간 안전거리 확보차)","2017-05-13 08:00","2017-05-18 18:00","2017-05-13T08:00:00","2017-05-18T18:00:00","연속",null,null,null,201703140052]
[164,"경기","동부","분당오포#1 T/L","154kV 성현-분당T/L 전선교체공사","전선접속개소 전선교체공사(4회선구간 안전거리 확보차)","2017-05-20 08:00","2017-05-26 18:00","2017-05-20T08:00:00","2017-05-26T18:00:00","연속",null,null,null,201703140046]
[165,"경기","성남","동탄C/C G/T#2 GIS","17년 성남변전협력회사 총액공사","동탄2열병합S/Y #2G/T 6433 GIS 초기점검","2017-05-18 10:00","2017-05-18 18:00","2017-05-18T10:00:00","2017-05-18T18:00:00","당일",null,null,null,201703160140]
[166,"경기","성남","동탄C/C G/T#1 GIS","17년 성남변전협력회사 총액공사","동탄2열병합S/Y #1G/T 6133 GIS 초기점검","2017-05-11 10:00","2017-05-11 18:00","2017-05-11T10:00:00","2017-05-11T18:00:00","당일",null,null,null,201703160139]
[167,"경기","성남","서안성S/S 154kV #3BUS-TIE(6300) GIS","17년 성남변전협력회사 총액공사","서안성S/S 6300 GIS 초기점검","2017-05-11 10:00","2017-05-11 18:00","2017-05-11T10:00:00","2017-05-11T18:00:00","당일",null,null,null,201703140474]
[168,"경기","성남","서안성S/S 61-62 SEC(61-62-0) GIS","17년 성남변전협력회사 총액공사","서안성S/S 61-62 GIS 초기점검","2017-05-08 10:00","2017-05-08 18:00","2017-05-08T10:00:00","2017-05-08T18:00:00","당일",null,null,null,201703140472]
[169,"경기","성남","서안성S/S 66-67 SEC(66-67-0) GIS","17년 성남변전협력회사 총액공사","서안성S/S 66-67 GIS 초기점검","2017-05-12 10:00","2017-05-12 18:00","2017-05-12T10:00:00","2017-05-12T18:00:00","당일",null,null,null,201703140473]
[170,"경기","성남","신성남정자#2 T/L","17년 성남변전협력회사 총액공사","신성남S/S 신성남-정자#2T/L GIS 보통점검","2017-05-10 10:00","2017-05-10 18:00","2017-05-10T10:00:00","2017-05-10T18:00:00","당일",null,null,null,201703140479]
[171,"경기","성남","신성남정자#1 T/L","17년 성남변전협력회사 총액공사","신성남S/S 신성남-정자#1T/L GIS 보통점검","2017-05-25 10:00","2017-05-25 18:00","2017-05-25T10:00:00","2017-05-25T18:00:00","당일",null,null,null,201703140529]
[172,"경기","성남","신수원S/S 154kV #60 BUS","154kV 신수원S/S 신수원-농서#1T/L GIS 정밀점검","154kV 신수원S/S 신수원-농서#1T/L GIS 정밀점검","2017-05-16 09:00","2017-05-17 14:00","2017-05-16T09:00:00","2017-05-17T14:00:00","연속",null,null,null,201703210069]
[173,"경기","성남","신수원S/S 154kV #65 BUS","154kV 신수원S/S 신수원-농서#2T/L GIS 정밀점검","154kV 신수원S/S 신수원-농서#2T/L GIS 정밀점검","2017-05-24 14:00","2017-05-25 18:00","2017-05-24T14:00:00","2017-05-25T18:00:00","연속",null,null,null,201703210071]
[174,"경기","성남","신수원S/S 154kV #60 BUS","154kV 신수원S/S 신수원-농서#2T/L GIS 정밀점검","154kV 신수원S/S 신수원-농서#2T/L GIS 정밀점검","2017-05-23 09:00","2017-05-24 14:00","2017-05-23T09:00:00","2017-05-24T14:00:00","연속",null,null,null,201703210072]
[175,"경기","성남","신수원S/S 154kV #65 BUS","154kV 신수원S/S 신수원-농서#1T/L GIS 정밀점검","154kV 신수원S/S 신수원-농서#1T/L GIS 정밀점검","2017-05-17 14:00","2017-05-18 18:00","2017-05-17T14:00:00","2017-05-18T18:00:00","연속",null,null,null,201703210070]
[176,"경기","성남","신용인용인#1 T/L","17년 성남변전협력회사 총액공사","용인S/S 신용인-용인#1T/L GIS 초기점검","2017-05-30 10:00","2017-05-30 18:00","2017-05-30T10:00:00","2017-05-30T18:00:00","당일",null,null,"신뢰도개선",201703140518]
[177,"경기","성남","신용인용인#2 T/L","17년 성남변전협력회사 총액공사","용인S/S 신용인-용인#2T/L GIS 초기점검","2017-05-31 10:00","2017-05-31 18:00","2017-05-31T10:00:00","2017-05-31T18:00:00","당일",null,null,"신뢰도개선",201703140517]
[178,"경기","성남","용인남사#2 T/L","17년 성남변전협력회사 총액공사","용인S/S 용인-남사#2T/L GIS 초기점검","2017-05-12 10:00","2017-05-12 18:00","2017-05-12T10:00:00","2017-05-12T18:00:00","당일",null,null,null,201703140515]
[179,"경기","성남","용인남사#1 T/L","17년 성남변전협력회사 총액공사","용인S/S 용인-남사#1T/L GIS 초기점검","2017-05-29 10:00","2017-05-29 18:00","2017-05-29T10:00:00","2017-05-29T18:00:00","당일",null,null,null,201703140516]
[180,"경기","직할","율전의왕#2 T/L","의왕S/S 율전의왕#2T/L LA교체","의왕S/S 율전의왕#2T/L LA교체","2017-05-30 10:00","2017-05-30 18:00","2017-05-30T10:00:00","2017-05-30T18:00:00","당일",null,null,null,201703140446]
[181,"경기","직할","율전의왕#1 T/L","의왕S/S 율전의왕#1T/L LA교체","의왕S/S 율전의왕#1T/L LA교체","2017-05-29 10:00","2017-05-29 18:00","2017-05-29T10:00:00","2017-05-29T18:00:00","당일",null,null,null,201703140445]
[182,"경기","직할","발안향남#2 T/L","향남S/S 발안향남#2T/L GIS 하자점검","향남S/S 발안향남#2T/L GIS 하자점검","2017-05-11 10:00","2017-05-11 18:00","2017-05-11T10:00:00","2017-05-11T18:00:00","당일",null,null,null,201703140432]
[183,"경기","직할","발안향남#1 T/L","향남S/S 발안향남#1T/L GIS 하자점검","향남S/S 발안향남#1T/L GIS 하자점검","2017-05-10 10:00","2017-05-10 18:00","2017-05-10T10:00:00","2017-05-10T18:00:00","당일",null,null,null,201703140430]
[184,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검 공사","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검 공사","2017-05-23 09:00","2017-05-24 14:00","2017-05-23T09:00:00","2017-05-24T14:00:00","연속",null,null,null,201703140403]
[185,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","2017-05-11 14:00","2017-05-12 18:00","2017-05-11T14:00:00","2017-05-12T18:00:00","연속",null,null,null,201703140400]
[186,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검 공사","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검 공사","2017-05-24 14:00","2017-05-25 18:00","2017-05-24T14:00:00","2017-05-25T18:00:00","연속",null,null,null,201703140404]
[187,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검 공사","2017-05-10 09:00","2017-05-11 14:00","2017-05-10T09:00:00","2017-05-11T14:00:00","연속",null,null,null,201703140399]
[188,"경기","평택","만호청북#1 T/L","전선접속개소 전력선 교체공사","전력선 교체 : 2개소 ( 2회선 구간, 4회선 구간)","2017-05-04 07:00","2017-05-08 18:00","2017-05-04T07:00:00","2017-05-08T18:00:00","연속",null,null,null,201703140317]
[189,"경기","평택","송탄소사벌 T/L","지제역세권 지장송전선로 지중화 공사","154kV 송탄-오성CCT/L No.18~24 지중화 154kV 송탄-안성T/L No.4~6 이설","2017-05-20 07:00","2017-05-21 18:00","2017-05-20T07:00:00","2017-05-21T18:00:00","연속",null,null,null,201703100138]
[190,"경기","평택","송탄S/S 송탄-오성복합T/L(627) GIS","송탄S/S 송탄-오성복합T/L, #2M.Tr GIS 대체공사","송탄S/S 송탄-오성복합T/L, #2M.Tr GIS 대체공사","2017-05-02 09:00","2017-05-19 18:00","2017-05-02T09:00:00","2017-05-19T18:00:00","연속",null,null,null,201703140492]
[191,"경기","평택","송탄S/S 송탄-진위#1T/L(697) GIS","송탄S/S 송탄-진위 #1T/L(170kV GIS 대체공사 무부하가압)","송탄S/S 송탄-진위 #1T/L(170kV GIS 대체공사 무부하가압)","2017-05-17 09:00","2017-05-18 18:00","2017-05-17T09:00:00","2017-05-18T18:00:00","연속",null,null,null,201703140504]
[192,"경기","평택","송탄안성 T/L","지제역세권 지장송전선로 지중화공사","154kV 송탄-오성CCT/L No.18~24 지중화 154kV 송탄-안성T/L No.4~6 이설","2017-05-03 07:00","2017-05-04 18:00","2017-05-03T07:00:00","2017-05-04T18:00:00","연속",null,null,null,201703100137]
[193,"경기","평택","서운안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측(#1BUS-SEC, 안성-남안성#1T/L BAY 설치)안전이격거리확보","2017-05-25 09:30","2017-05-27 18:00","2017-05-25T09:30:00","2017-05-27T18:00:00","연속",null,null,null,201703140542]
[194,"경기","평택","안성S/S 154kV #1 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측(#1BUS-SEC, 안성-남안성#1T/L BAY 설치)","2017-05-24 09:30","2017-05-30 18:00","2017-05-24T09:30:00","2017-05-30T18:00:00","연속",null,null,null,201703140534]
[195,"경기","평택","서안성안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측(#1BUS-SEC, 안성-남안성#1T/L BAY 설치) 무부하가압","2017-05-29 09:30","2017-05-30 18:00","2017-05-29T09:30:00","2017-05-30T18:00:00","연속",null,null,null,201703170164]
[196,"경기","평택","안성S/S 154kV #2 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측(#2BUS-SEC, 안성-남안성#1T/L BAY 설치)","2017-05-31 09:30","2017-06-06 18:00","2017-05-31T09:30:00","2017-06-06T18:00:00","연속",null,null,null,201703140536]
[197,"경기","평택","오산평택#1 T/L","154kV 오산-평택T/L 안전이격 확보공사","○ 공사규모 : 철탑 3기 교체(No.54, 55, 57) ○ 공사내용 : 2회선 임시선로 구성","2017-05-22 07:00","2017-05-23 18:00","2017-05-22T07:00:00","2017-05-23T18:00:00","연속",null,null,null,201703150099]
[198,"경기","평택","오산평택#2 T/L","154kV 오산-평택T/L 안전이격 확보공사","○ 공사규모 : 철탑 3기 교체(No.54, 55, 57) ○ 공사내용 : 2회선 임시선로 구성","2017-05-20 07:00","2017-05-21 18:00","2017-05-20T07:00:00","2017-05-21T18:00:00","연속",null,null,null,201703150096]
[199,"경기","평택","송탄오성CC#2 T/L","지제역세권 지장송전선로 지중화공사","154kV 송탄-오성CCT/L No.18~24 지중화 154kV 송탄-안성T/L No.4~6 이설","2017-05-01 07:00","2017-05-01 18:00","2017-05-01T07:00:00","2017-05-01T18:00:00","연속",null,null,null,201703130103]
[200,"경기","평택","포승청북#2 T/L","전선접속개소 전력선 교체공사","전력선 교체 : 3개소 ( 2회선 1구간, 4회선 2구간)","2017-05-10 07:00","2017-05-15 18:00","2017-05-10T07:00:00","2017-05-15T18:00:00","연속",null,null,null,201703140331]
[201,"경기","평택","포승평택TP#2T/L","전선접속개소 전력선 교체공사","전력선 교체 : 1개소 (4회선 구간)","2017-05-04 07:00","2017-05-08 18:00","2017-05-04T07:00:00","2017-05-08T18:00:00","연속",null,null,null,201703140326]
[202,"경기","평택","포승평택TP#1T/L","전선접속개소 전력선 교체공사","전력선 교체 : 2개소 (4회선 2구간)","2017-05-10 07:00","2017-05-15 18:00","2017-05-10T07:00:00","2017-05-15T18:00:00","연속",null,null,null,201703140337]
[203,"경기","평택","포승평택TP#2T/L","전선접속개소 전력선 교체공사","전력선 교체 : 2개소 (4회선 2구간)","2017-05-16 07:00","2017-05-19 18:00","2017-05-16T07:00:00","2017-05-19T18:00:00","연속",null,null,null,201703140339]
[204,"경기","평택","포승만호 T/L","전선접속개소 전력선 교체공사","전력선 교체 : 1개소 (4회선 1구간)","2017-05-16 07:00","2017-05-19 18:00","2017-05-16T07:00:00","2017-05-19T18:00:00","연속",null,null,null,201703140341]
[205,"강원","강릉","신양양속초#2 T/L","2016~17년 송전정비협력회사 총액공사","○ 상간스페이서 보수작업(No.5~6 등 13개소)","2017-05-10 07:00","2017-05-14 18:00","2017-05-10 07:00","2017-05-14 18:00","매일",null,null,null,201703210239]
[206,"강원","강릉","신양양_양양#1 T/L","2016~17년 송전정비협력회사 총액공사","○ 협력회사전선교체(No.32~36, 49~56, 13기) ○ 상간스페이서 보수작업(No.5~6 등 13개소)","2017-05-10 07:00","2017-05-14 18:00","2017-05-10 07:00","2017-05-14 18:00","연속",null,null,null,201703210237]
[207,"강원","강릉","신양양속초#1 T/L","2016~17년 송전정비협력회사 총액공사","○ 상간스페이서 보수작업(No.5~6 등 13개소)","2017-05-15 07:00","2017-05-19 18:00","2017-05-15 07:00","2017-05-19 18:00","매일",null,null,null,201703210241]
[208,"강원","강릉","신양양_양양#2 T/L","2016~17년 송전정비협력회사 총액공사","○ 협력회사전선교체(No.32~36, 49~56, 13기) ○ 상간스페이서 보수작업(No.5~6등 13개소)","2017-05-15 07:00","2017-05-19 18:00","2017-05-15 07:00","2017-05-19 18:00","연속",null,null,null,201703210240]
[209,"강원","강릉","영동T/P 154kV BUS TIE CB","2017년 변전협력회사 총액공사","154kV 모선보호반 교체","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201703220005]
[210,"강원","강릉","강릉횡계#1 T/L","2017년 변전협력회사 총액공사","강릉횡계TL 인출 부싱단자 교체","2017-05-12 09:00","2017-05-12 14:00","2017-05-12 09:00","2017-05-12 14:00","당일",null,null,null,201703210309]
[211,"강원","강릉","강릉횡계#2 T/L","2017년 변전협력회사 총액공사","강릉횡계TL 인출 부싱단자 교체","2017-05-12 14:00","2017-05-12 18:00","2017-05-12 14:00","2017-05-12 18:00","당일",null,null,null,201703210310]
[212,"강원","동해","동해정선 T/L","2016~17년도 동해전력지사 송전정비협력회사 총액공사","○ 154kV 동해-정선T/L 전선접속개소 전선교체공사 - No.112~117","2017-05-10 08:00","2017-05-16 18:00","2017-05-10 08:00","2017-05-16 18:00","연속",null,null,null,201703130334]
[213,"강원","동해","삼척동해TP T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해화력측 LA 보통점검 2. 삼척S/S측 LA 보통점검 3. 장기미동작차단기 조작시험(타임테스트 측정)","2017-05-11 09:30","2017-05-11 18:00","2017-05-11 09:30","2017-05-11 18:00","당일",null,null,null,201702140083]
[214,"강원","동해","이원동해TP T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해화력측 LA 보통점검 2. 이원S/S측 LA 보통점검 3. 장기미동작차단기 조작시험(타임테스트 측정)","2017-05-10 09:30","2017-05-10 18:00","2017-05-10 09:30","2017-05-10 18:00","당일",null,null,null,201702140081]
[215,"강원","동해","삼척GP 154kV 기동#1T/L CB","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP 기동#1Tr GIS 하자점검(6B7)","2017-05-12 09:00","2017-05-12 13:00","2017-05-12 09:00","2017-05-12 13:00","당일",null,null,null,201703130165]
[216,"강원","동해","울진삼척GP#2T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP 울진-삼척GP#2T/L GIS 하자점검 2. 삼척GP 울진-삼척GP#2T/L LA 하자점검 3. 삼척GP 울진-삼척GP#2T/L PT 하자점검","2017-05-11 10:00","2017-05-11 18:00","2017-05-11 10:00","2017-05-11 18:00","당일",null,null,null,201703130164]
[217,"강원","동해","울진삼척GP#1T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP 울진-삼척GP#1T/L GIS 하자점검 2. 삼척GP 울진-삼척GP#1T/L LA 하자점검 3. 삼척GP 울진-삼척GP#1T/L PT 하자점검","2017-05-10 10:00","2017-05-10 18:00","2017-05-10 10:00","2017-05-10 18:00","당일",null,null,null,201703130163]
[218,"강원","동해","삼척GP 154kV 기동#2T/L CB","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP 기동#2Tr GIS 하자점검(677)","2017-05-12 13:30","2017-05-12 18:00","2017-05-12 13:30","2017-05-12 18:00","당일",null,null,null,201703130166]
[219,"강원","동해","태백삼척GP#2T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP 태백-삼척GP#2T/L GIS 하자점검","2017-05-08 10:00","2017-05-08 18:00","2017-05-08 10:00","2017-05-08 18:00","당일",null,null,null,201703130162]
[220,"강원","원주","신제천남원주#2 T/L","2017년 원주전력지사 170kV GIS 정밀점검 공사","남원주S/S 신제천남원주#2T/L GIS 정밀점검","2017-05-15 09:00","2017-05-17 18:00","2017-05-15 09:00","2017-05-17 18:00","연속",null,null,null,201703230027]
[221,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","○ 철탑교체 : No.41,43,45(철탑철거 : No.42,44) ○ 전선교체 : 2c-1.706km(No.40~45)","2017-05-22 07:00","2017-05-25 18:00","2017-05-22 07:00","2017-05-25 18:00","연속",null,null,null,201703170115]
[222,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","○ 철탑교체 : No.41,43,45(철탑철거 : No.42,44) ○ 전선교체 : 2c-1.706km(No.40~45)","2017-05-26 07:00","2017-05-29 18:00","2017-05-26 07:00","2017-05-29 18:00","연속",null,null,null,201703170118]
[223,"강원","직할","북춘천화천HP T/L","16-17년 직할 변전정비 협력회사 총액공사","154kV 북춘천-화천HP T/L GIS 보통점검","2017-05-11 10:00","2017-05-11 18:00","2017-05-11 10:00","2017-05-11 18:00","당일",null,null,null,201703070198]
[224,"강원","직할","춘천소양강HP T/L","16-17년 직할 변전정비 협력회사 총액공사","154kV 춘천-소양강HP T/L GIS 보통점검","2017-05-19 10:00","2017-05-19 18:00","2017-05-19 10:00","2017-05-19 18:00","당일",null,null,null,201703070220]
[225,"강원","직할","북춘천춘천HP T/L","2017년 차단기 정밀점검공사","춘천HP 북춘천-춘천HP T/L 정밀점검공사","2017-05-23 10:00","2017-05-25 18:00","2017-05-23 10:00","2017-05-25 18:00","연속",null,null,null,201703100012]
[226,"강원","직할","가평춘천HP T/L","2017년 차단기 정밀점검공사","춘천HP 가평-춘천HP T/L 정밀점검공사","2017-05-22 10:00","2017-05-23 18:00","2017-05-22 10:00","2017-05-23 18:00","연속",null,null,null,201703100010]
[227,"강원","직할","철원화천#1 T/L","2016-17년 강원지역본부 직할 변전정비 협력회사 총액공사","화천S/S 철원-화천#1T/L GIS, LA 보통점검","2017-05-15 10:00","2017-05-15 18:00","2017-05-15 10:00","2017-05-15 18:00","당일",null,null,null,201703100008]
[228,"강원","직할","철원화천#2 T/L","2016-17년 강원지역본부 직할 변전정비 협력회사 총액공사","화천S/S 철원-화천#2T/L GIS, LA 보통점검","2017-05-16 10:00","2017-05-16 18:00","2017-05-16 10:00","2017-05-16 18:00","당일",null,null,null,201703100009]
[229,"강원","직할","화천화천HP#2 T/L","16-17년 직할 변전정비 협력회사 총액공사","154kV 화천-화천HP #2T/L GCB 초기점검","2017-05-31 10:00","2017-05-31 18:00","2017-05-31 10:00","2017-05-31 18:00","당일",null,null,null,201703070231]
[230,"강원","직할","화천화천HP#1 T/L","2017년 차단기 정밀점검공사","화천HP 화천-화천HP #1T/L 정밀점검공사","2017-05-29 10:00","2017-05-30 18:00","2017-05-29 10:00","2017-05-30 18:00","연속",null,null,null,201703100015]
[231,"강원","태백","동영월영월CC T/L","16~17 태백전력지사 송전정비 총액공사","동영월-영월CCT/L 스페이서 및 SB댐퍼 교체공사","2017-05-24 08:00","2017-05-26 18:00","2017-05-24 08:00","2017-05-26 18:00","연속",null,null,null,201703140004]
[232,"강원","태백","동해동영월 T/L","16~17 태백전력지사 송전정비 총액공사","동해-동영월T/L 스페이서 및 SB댐퍼 교체공사","2017-05-17 08:00","2017-05-23 18:00","2017-05-17 08:00","2017-05-23 18:00","연속",null,null,null,201703100282]
[233,"강원","태백","신제천영월CC#1 T/L","신제천-영월CC #1T/L GIS 내부 코일교체공사","신제천-영월CC #1T/L GIS 내부 코일교체공사","2017-05-30 10:00","2017-05-30 18:00","2017-05-30 10:00","2017-05-30 18:00","당일",null,null,null,201703100305]
[234,"강원","태백","신제천영월CC#2 T/L","신제천-영월CC #2T/L GIS 내부 코일교체공사","신제천-영월CC #2T/L GIS 내부 코일교체공사","2017-05-31 10:00","2017-05-31 18:00","2017-05-31 10:00","2017-05-31 18:00","당일",null,null,null,201703100306]
[235,"강원","태백","정선영월CC T/L","16~17 태백전력지사 송전정비 총액공사","정선-영월CC 스페이서 및 SB댐퍼 교체공사","2017-05-27 08:00","2017-06-05 18:00","2017-05-27 08:00","2017-06-05 18:00","연속",null,null,null,201703100272]
[236,"강원","태백","영월S/S 154kV #1 BUS TIE CB","2016~2017 태백전력지사 변전정비 협력회사 총액공사","영월S/S #1BUS-TIE GIS보통점검","2017-05-18 10:00","2017-05-18 18:00","2017-05-18 10:00","2017-05-18 18:00","당일",null,null,null,201702140303]
[237,"충북","직할","점촌단양 T/L","직할 송전정비 협력업체 총액공사","- 접속개소 전선교체(No. 9~47) - SB-댐퍼 교체(No. 13~47)","2017-05-22 08:00","2017-05-28 18:00","취소","취소","연속",null,null,null,201703090137]
[238,"충북","직할","왕암가남#1 T/L","2017년도 가공송전선로 순시점검 위탁공사","봉양전철 정밀점검에 따른 병가선로 휴전 (No.8-2)","2017-05-18 08:00","2017-05-18 18:00","2017-05-18 08:00","2017-05-18 18:00","당일",null,null,null,201703100073]
[239,"충북","직할","왕암가남#2 T/L","2017년도 가공송전선로 순시점검 위탁공사","봉양전철 정밀점검에 따른 병가선로 휴전 (No.8,8-1,8-2)","2017-05-19 08:00","2017-05-19 18:00","2017-05-19 08:00","2017-05-19 18:00","당일",null,null,null,201703100074]
[240,"충북","직할","음성금왕#1 T/L","충북직할 송전정비협력업체 총액공사","SB-댐퍼설치 안전확보","2017-05-19 13:00","2017-05-19 18:00","2017-05-19 13:00","2017-05-19 18:00","당일",null,null,null,201703090112]
[241,"충북","직할","제천영월#1 T/L","직할 송전정비 협력업체 총액공사","애자련보강 No.62,63전원","2017-05-16 08:00","2017-05-16 18:00","2017-05-16 08:00","2017-05-16 18:00","당일",null,null,null,201703090129]
[242,"충북","직할","제천영월#2 T/L","직할 송전정비 협력업체 총액공사","애자련보강 No.62,63전원","2017-05-17 08:00","2017-05-17 18:00","2017-05-17 08:00","2017-05-17 18:00","당일",null,null,null,201703090130]
[243,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","철탑 2기 교체, 전력선 1.1km 교체 / 회선직결","2017-05-11 09:00","2017-05-31 18:00","2017-05-11 09:00","2017-05-31 18:00","연속",null,null,null,201703100279]
[244,"충북","청주","신옥천남대전#4 T/L","17년 청주전력 변전정비 총액공사","신옥천남대전#4T/L CB 점검","2017-05-11 14:00","2017-05-11 18:00","2017-05-11 14:00","2017-05-11 18:00","당일",null,null,null,201703200030]
[245,"충북","청주","신옥천남대전#1 T/L","17년 청주전력 변전정비 총액공사","신옥천남대전#1T/L CB 점검","2017-05-10 09:30","2017-05-10 14:00","2017-05-10 09:30","2017-05-10 14:00","당일",null,null,null,201703200026]
[246,"충북","청주","신옥천남대전#2 T/L","17년 청주전력 변전정비 총액공사","신옥천남대전#2T/L CB 점검","2017-05-10 14:00","2017-05-10 18:00","2017-05-10 14:00","2017-05-10 18:00","당일",null,null,null,201703200028]
[247,"충북","청주","신옥천서대전#2 T/L","17년 청주전력 변전정비 총액공사","신옥천서대전#2T/L CB 점검","2017-05-12 09:30","2017-05-12 14:00","2017-05-12 09:30","2017-05-12 14:00","당일",null,null,null,201703200024]
[248,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","철탑 2기 교체, 전력선 1.1km 교체 / 회선직결","2017-05-11 09:00","2017-05-31 18:00","2017-05-11 09:00","2017-05-31 18:00","연속",null,null,null,201703100281]
[249,"충북","청주","청원오송#2 T/L","170kV 장기사용 GIS 대체 공사","170kV 장기사용 GIS 대체 공사","2017-05-01 09:30","2017-05-12 18:00","2017-05-01 09:30","2017-05-12 18:00","연속",null,null,null,201702230163]
[250,"충북","청주","청원신탄진 T/L","17년 청주전력 변전정비 총액공사","청원-신탄진T/L GIS 보통점검","2017-05-08 09:30","2017-05-08 18:00","2017-05-08 09:30","2017-05-08 18:00","당일",null,null,null,201703200116]
[251,"충북","청주","청원청주#3 T/L","170kV 장기사용 GIS 대체 공사","170kV 장기사용 GIS 대체 공사","2017-05-15 12:00","2017-05-30 18:00","2017-05-15 12:00","2017-05-30 18:00","연속",null,null,null,201702230184]
[252,"충북","청주","청원청주#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애구 풍소음 발생지역 항공구 교체","2017-05-15 12:00","2017-05-15 18:00","2017-05-15 12:00","2017-05-15 18:00","당일",null,null,null,201703220076]
[253,"충북","청주","청원청주#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애구 풍소음 발생지역 항공구 교체","2017-05-15 08:00","2017-05-15 12:00","2017-05-15 08:00","2017-05-15 12:00","당일",null,null,null,201703220083]
[254,"충북","충주","신진천오창#1 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사","2017-05-13 10:00","2017-05-14 18:00","2017-05-13 10:00","2017-05-14 18:00","연속",null,null,null,201703060042]
[255,"충북","충주","신진천오창#2 T/L","장기사용 송전선로용 피뢰기 교체공사","장기사용 송전선로용 피뢰기 교체공사","2017-05-21 10:00","2017-05-21 18:00","2017-05-21 10:00","2017-05-21 18:00","당일",null,null,null,201703060043]
[256,"충북","충주","진천만승#1 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사","154kV 진천-만승#1T/L No.3~10 전력선교체","2017-05-22 08:00","2017-05-28 18:00","2017-05-22 08:00","2017-05-28 18:00","연속",null,null,null,201703200086]
[257,"충북","충주","진천덕산#2 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사","154kV 진천-덕산#2T/L No.20~25 전력선교체","2017-05-16 08:00","2017-05-21 18:00","2017-05-16 08:00","2017-05-21 18:00","연속",null,null,null,201703200072]
[258,"충북","충주","진천만승#2 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사","154kV 진천-만승#1T/L No.3~10 전력선교체","2017-05-29 08:00","2017-06-04 18:00","2017-05-29 08:00","2017-06-04 18:00","연속",null,null,null,201703200088]
[259,"충북","충주","진천덕산#1 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사","154kV 진천-덕산#1T/L No.20~25 전력선교체","2017-05-10 08:00","2017-05-15 18:00","2017-05-10 08:00","2017-05-15 18:00","연속",null,null,null,201703200071]
[260,"대전충남","대전","신계룡S/S #1EM.Tr CB","신계룡S/S #1 EM.Tr 2차 전력케이블 종단접속재 재시공","신계룡S/S #1 EM.Tr 2차 전력케이블 종단접속재 재시공","2017-05-08 09:00","2017-05-08 18:00","2017-05-08T09:00:00","2017-05-08T18:00:00","당일",null,null,null,201703080475]
[261,"대전충남","서산","대산석문#1 T/L","[송전]154kV 대산-석문#1T/L 정밀점검","154kV 대산-석문#1T/L No.1-4,7-48 정밀점검","2017-05-11 08:00","2017-05-13 12:00","취소","취소","매일",null,null,null,201703090456]
[262,"대전충남","서산","서산태안 T/L","[송전]154kV 서산-태안T/L 정밀점검","154kV 서산-태안T/L No.1-80 정밀점검 (No.1-14, 154kV 서산-대산T/L 병가구간)","2017-05-29 08:00","2017-06-01 18:00","2017-05-29T08:00:00","2017-06-01T18:00:00","매일",null,null,null,201703100352]
[263,"대전충남","서산","석문당진TP#2 T/L","[송전]154kV 석문-당진화력#2T/L 정밀점검","154kV 석문-당진화력#2T/L No.1-26 정밀점검","2017-05-13 08:00","2017-05-13 18:00","취소","취소","당일",null,null,null,201703090459]
[264,"대전충남","서산","신당진S/S 154kV #60 BUS","'17년 서산P/O 154kV GIS 정밀점검 공사","신당진S/S 154kV #61M.Tr 1차 GIS 정밀점검 공사","2017-05-15 09:00","2017-05-17 18:00","2017-05-15T09:00:00","2017-05-17T18:00:00","당일",null,null,null,201703140034]
[265,"대전충남","서산","태안태안화력 T/L","[송전]154kV 태안-태안화력T/L 정밀점검","154kV 태안-태안화력T/L No.1-51 + 22기 정밀점검 (No.2-27, 345kV 신당진개폐소-태안화력T/L 병가구간)","2017-05-20 08:00","2017-05-23 18:00","2017-05-20T08:00:00","2017-05-23T18:00:00","매일",null,null,null,201703100310]
[266,"대전충남","서산","서산태안화력 T/L","154kV 태안화력(서산-태안화력)T/L 전력선 교체공사","154kV 태안화력(서산-태안화력)T/L 전력선 교체공사 No.2~6, 8~10","2017-05-16 07:00","2017-05-19 18:00","2017-05-16T07:00:00","2017-05-19T18:00:00","연속",null,null,null,201703090543]
[267,"대전충남","아산","아산예산#1 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-05-16 09:00","2017-06-04 18:00","2017-05-16T09:00:00","2017-06-04T18:00:00","연속",null,null,null,201703150208]
[268,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-05-16 09:00","2017-05-19 18:00","2017-05-16T09:00:00","2017-05-19T18:00:00","연속",null,null,null,201703150212]
[269,"대전충남","아산","아산송악#2 T/L","[송전]154kV 아산-송악#2T/L 피뢰기 설치공사","154kV 송전용 피뢰기 48기 설치 기타 부대공사","2017-05-22 09:00","2017-05-28 18:00","취소","취소","매일",null,null,"신뢰도개선",201703170150]
[270,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-05-29 09:00","2017-06-02 18:00","2017-05-29T09:00:00","2017-06-02T18:00:00","연속",null,null,null,201703150215]
[271,"대전충남","아산","아산인주#1 T/L","아산S/S 154kV 아산-인주#1T/L 보통점검","○ 154kV 아산-인주#1T/L 보통점검","2017-05-27 09:00","2017-05-28 18:00","2017-05-27T09:00:00","2017-05-28T18:00:00","연속",null,null,null,201703090467]
[272,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-05-22 09:00","2017-05-28 18:00","2017-05-22T09:00:00","2017-05-28T18:00:00","연속",null,null,null,201703150213]
[273,"대전충남","아산","아산인주#2 T/L","154kV 아산-인주#2T/L 피뢰기 설치공사","154kV 송전용 피뢰기 설치 10기분 기타 부대공사","2017-05-20 08:00","2017-05-21 18:00","2017-05-20T08:00:00","2017-05-21T18:00:00","매일",null,null,null,201703090461]
[274,"대전충남","아산","풍세장재#2 T/L","풍세S/S 154kV 풍세-장재#2T/L 보호배전반 교체","○ 154kV 풍세-장재#2T/L 보호배전반 교체","2017-05-29 09:00","2017-06-01 18:00","2017-05-29T09:00:00","2017-06-01T18:00:00","연속",null,null,null,201703090480]
[275,"대전충남","아산","풍세장재#1 T/L","풍세S/S 154kV 풍세-장재#1T/L 보호배전반 교체","○ 154kV 풍세-장재#1T/L 보호배전반 교체","2017-05-22 09:00","2017-05-25 18:00","2017-05-22T09:00:00","2017-05-25T18:00:00","연속",null,null,null,201703090479]
[276,"대전충남","직할","송강신일#1 T/L","신일S/S 170kV 장기사용 GIS 대체공사","○ 신일S/S 154kV 장기사용 GIS 대체공사 (대체공사로인한 장기휴전)","2017-05-15 08:00","2017-05-31 18:00","2017-05-15T08:00:00","2017-05-31T18:00:00","연속",null,null,"신뢰도개선",201702090280]
[277,"대전충남","청양","관창보령화력 T/L","보령화력 170kV GIS 보통점검","○ 보령화력 154kV 627 GIS 보통점검 (LA, CVT 보통점검 포함)","2017-05-11 09:00","2017-05-11 18:00","2017-05-11T09:00:00","2017-05-11T18:00:00","당일",null,null,null,201703070011]
[278,"대전충남","청양","보령T/P 154kV #1 BUS TIE CB","보령화력 170kV GIS 보통점검","○ 보령화력 154kV 6100 GIS 보통점검","2017-05-10 09:00","2017-05-10 18:00","2017-05-10T09:00:00","2017-05-10T18:00:00","당일",null,null,null,201703070016]
[279,"전북","군산","군공S/S 154kV #1 BUS","군공S/S 154kV #1 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-10 09:00","2017-05-11 11:00","2017-05-10 09:00","2017-05-11 11:00","연속",null,null,null,201703130374]
[280,"전북","군산","군공S/S 154kV #1 BUS","군공S/S 154kV #1 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-18 09:00","2017-05-19 11:00","2017-05-18 09:00","2017-05-19 11:00","연속",null,null,null,201703130376]
[281,"전북","군산","군공S/S 154kV #1 BUS TIE CB","군공S/S 154kV #1 BUS TIE CB","군산P/O 170kV 차단기 정밀점검","2017-05-18 09:00","2017-05-20 18:00","2017-05-18 09:00","2017-05-20 18:00","연속",null,null,null,201703130385]
[282,"전북","군산","군공S/S 154kV #2 BUS","군공S/S 154kV #2 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-19 11:00","2017-05-20 18:00","2017-05-19 11:00","2017-05-20 18:00","연속",null,null,null,201703130381]
[283,"전북","군산","군공S/S 154kV #1 BUS","군공S/S 154kV #1 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-22 09:00","2017-05-23 11:00","2017-05-22 09:00","2017-05-23 11:00","연속",null,null,null,201703130377]
[284,"전북","군산","군공S/S 154kV #1 BUS TIE CB","군공S/S 154kV #1 BUS TIE CB","군산P/O 170kV 차단기 정밀점검","2017-05-22 09:00","2017-05-24 18:00","2017-05-22 09:00","2017-05-24 18:00","연속",null,null,null,201703130086]
[285,"전북","군산","군공S/S 154kV #2 BUS","군공S/S 154kV #2 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-16 11:00","2017-05-17 18:00","2017-05-16 11:00","2017-05-17 18:00","연속",null,null,null,201703130380]
[286,"전북","군산","군공S/S 154kV #1 BUS TIE CB","군공S/S 154kV #1 BUS TIE CB","군산P/O 170kV 차단기 정밀점검","2017-05-10 09:00","2017-05-12 18:00","2017-05-10 09:00","2017-05-12 18:00","연속",null,null,null,201703130083]
[287,"전북","군산","군공S/S 154kV #2 BUS","군공S/S 154kV #2 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-11 11:00","2017-05-12 18:00","2017-05-11 11:00","2017-05-12 18:00","연속",null,null,null,201703130378]
[288,"전북","군산","군공S/S 154kV #1 BUS","군공S/S 154kV #1 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-15 09:00","2017-05-16 11:00","2017-05-15 09:00","2017-05-16 11:00","연속",null,null,null,201703130375]
[289,"전북","군산","군공S/S 154kV #1 BUS TIE CB","군공S/S 154kV #1 BUS TIE CB","군산P/O 170kV 차단기 정밀점검","2017-05-15 09:00","2017-05-17 18:00","2017-05-15 09:00","2017-05-17 18:00","연속",null,null,null,201703130085]
[290,"전북","군산","군공S/S 154kV #2 BUS","군공S/S 154kV #2 BUS","군산P/O 170kV 차단기 정밀점검 공사","2017-05-23 11:00","2017-05-24 18:00","2017-05-23 11:00","2017-05-24 18:00","연속",null,null,null,201703130382]
[291,"전북","군산","군공군산CC#2 T/L","154kV 군공-군산복합T/L SVL 교체공사","링크박스 철거 및 SVL 설치공사","2017-05-16 09:00","2017-06-02 18:00","2017-05-16 09:00","2017-06-02 18:00","연속",null,null,null,201702150042]
[292,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산S/S 154kV #1 BUSTIE CB 보통점검","군산P/O 차단기 보통점검","2017-05-30 10:00","2017-05-30 16:00","2017-05-30 10:00","2017-05-30 16:00","당일",null,null,null,201703170103]
[293,"전북","군산","군산동군산#1 T/L","군산동군산T/L 안전이격확보공사","철탑조립 및 전선공중이동 : 4기(28,29,30,31)","2017-05-05 07:00","2017-05-14 18:00","2017-05-05 07:00","2017-05-14 18:00","연속",null,null,null,201703210074]
[294,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 1차 공정 - #2BUS 시험가압","2017-05-11 18:00","2017-05-11 19:00","2017-05-11 18:00","2017-05-11 19:00","연속",null,null,null,201703190017]
[295,"전북","군산","동군산장항#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 1차 공정 - 동군산-장항#2T/L, #2M.Tr 1차 GIS","2017-05-10 08:00","2017-06-02 18:00","2017-05-10 08:00","2017-06-02 18:00","연속",null,null,null,201703190016]
[296,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 중 1차 공정 - #1BUS 시험가압 후 BUS 절체(#2 -> #1)","2017-05-23 08:00","2017-05-24 08:00","2017-05-23 08:00","2017-05-24 08:00","연속",null,null,null,201703190018]
[297,"전북","군산","소룡S/S 소룡-군장에너지T/L GIS","소룡S/S 소룡-군장에너지T/L 차단기 보통점검","군산P/O 154kV 차단기 보통점검","2017-05-15 09:00","2017-05-15 18:00","2017-05-15 09:00","2017-05-15 18:00","당일",null,null,null,201703170121]
[298,"전북","군산","군산영등#1 T/L","영등S/S 군산-영등#1T/L 차단기 보통점검","군산P/O 차단기 보통점검","2017-05-18 13:30","2017-05-18 18:00","취소","취소","당일",null,null,null,201703170094]
[299,"전북","군산","팔봉영등#2 T/L","영등S/S 팔봉-영등#2T/L 차단기 보통점검","군산P/O 차단기 보통점검","2017-05-19 09:00","2017-05-19 14:00","취소","취소","당일",null,null,null,201703170095]
[300,"전북","군산","이리전주#1 T/L","154kV 이리-전주#1T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-05-22 07:00","2017-06-11 18:00","2017-05-22 07:00","2017-06-11 18:00","당일",null,null,null,201701190023]
[301,"전북","군산","이리백산#1 T/L","154kV 이리-백산#1T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-05-22 07:00","2017-06-11 18:00","2017-05-22 07:00","2017-06-11 18:00","연속",null,null,null,201701190022]
[302,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 점퍼지지애자 교체공사","No.86,94호 2기 점퍼지지애자 교체 154kV 고창-홍농T/L 병행 구간","2017-05-24 07:00","2017-05-25 18:00","2017-05-24 07:00","2017-05-25 18:00","매일",null,null,null,201703150105]
[303,"전북","김제","고창홍농 T/L","154kV 고창-홍농T/L 전력선 교체공사","공사명 : 154kV 고창-홍농T/L 전력선 교체공사 공사구간 : No.61~65, No. 67~72 (ACSR/AW 330㎟ x S : 3.126C-km) 345kV 신남원-한빛#2T/L과 병행선로내 작업","2017-05-22 07:00","2017-06-11 18:00","취소","취소","연속",null,null,null,201703090031]
[304,"전북","김제","신김제동전주#1 T/L","신김제S/S 신김제-동전주#1T/L LA, CVT 교체","장기사용기타설비 대체","2017-05-11 10:00","2017-05-11 18:00","2017-05-11 10:00","2017-05-11 18:00","당일",null,null,null,201703200232]
[305,"전북","김제","신김제동전주#2 T/L","신김제S/S 신김제-동전주#2T/L LA, CVT 교체","장기사용기타설비 대체","2017-05-12 10:00","2017-05-12 18:00","2017-05-12 10:00","2017-05-12 18:00","당일",null,null,null,201703200233]
[306,"전북","김제","신김제정공#1 T/L","신김제S/S 신김제-정공#1T/L LA, CVT 교체","장기사용기타설비 대체","2017-05-19 10:00","2017-05-19 18:00","2017-05-19 10:00","2017-05-19 18:00","당일",null,null,null,201703200234]
[307,"전북","김제","신김제S/S 61-62-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201702160400]
[308,"전북","김제","신김제S/S 65-66-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201702160399]
[309,"전북","김제","신김제S/S 66-67-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201702160401]
[310,"전북","김제","신김제S/S 60-61-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201702160398]
[311,"전북","김제","정공정주#1 T/L","김제P/O 154kV 차단기 정밀점검공사","154kV 차단기 정밀점검","2017-05-25 09:00","2017-05-27 18:00","2017-05-25 09:00","2017-05-27 18:00","연속",null,null,null,201703200195]
[312,"전북","김제","정공정주#2 T/L","관내S/S 노후배전반 교체공사","신김제 및 정공S/S 보호반 교체","2017-05-22 09:00","2017-05-24 18:00","2017-05-22 09:00","2017-05-24 18:00","연속",null,null,null,201703200213]
[313,"전북","김제","신김제정공#1 T/L","김제P/O 154kV 차단기 정밀점검공사","모선 시험가압","2017-05-30 11:00","2017-05-30 13:00","2017-05-30 11:00","2017-05-30 13:00","당일",null,null,null,201703200204]
[314,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강T/L 정밀점검","154kV 정공-섬진강T/L 정밀점검(No.1~43)","2017-05-29 09:00","2017-05-31 18:00","2017-05-29 09:00","2017-05-31 18:00","매일",null,null,null,201703170092,"○"]
[315,"전북","김제","신김제정공#1 T/L","김제P/O 154kV 차단기 정밀점검공사","모선 시험가압","2017-05-31 15:00","2017-05-31 17:00","2017-05-31 15:00","2017-05-31 17:00","당일",null,null,null,201703200205]
[316,"전북","김제","정공정주#2 T/L","154kV 정공-정주T/L 점퍼지지애자 교체공사","154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 154kV 정공-담양T/L 점퍼지지애자 교체(3기) 병행","2017-05-12 07:00","2017-05-12 18:00","2017-05-12 07:00","2017-05-12 18:00","당일",null,null,null,201703230003]
[317,"전북","김제","정공담양 T/L","154kV 정공-담양T/L 점퍼지지애자 교체공사","154kV 정공-담양T/L 점퍼지지애자 교체(3기) 154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 병행","2017-05-12 07:00","2017-05-12 18:00","2017-05-12 07:00","2017-05-12 18:00","당일",null,null,null,201703230004]
[318,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강수력T/L 점퍼지지애자 교체공사","154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 병행","2017-05-10 07:00","2017-05-11 18:00","2017-05-10 07:00","2017-05-11 18:00","매일",null,null,null,201703230001]
[319,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 점퍼지지애자 교체공사","154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 병행","2017-05-10 07:00","2017-05-11 18:00","2017-05-10 07:00","2017-05-11 18:00","매일",null,null,null,201703230002]
[320,"전북","김제","정공정주#1 T/L","154kV 정공-섬진강T/L 정밀점검(병가구간)","154kV 정공-섬진강T/L 정밀점검(No.1~13)","2017-05-29 09:00","2017-05-29 18:00","2017-05-29 09:00","2017-05-29 18:00","매일",null,null,null,201703170093]
[321,"전북","김제","신김제정공#2 T/L","관내S/S 노후배전반 교체공사","신김제 및 정공S/S 보호반 교체","2017-05-22 09:00","2017-05-24 18:00","2017-05-22 09:00","2017-05-24 18:00","매일",null,null,null,201703240095]
[322,"전북","김제","정공S/S 154kV #1 BUS TIE CB","김제P/O 154kV 차단기 정밀점검공사","154kV 차단기 정밀점검","2017-05-25 09:00","2017-05-27 18:00","2017-05-25 09:00","2017-05-27 18:00","매일",null,null,null,201703240100]
[323,"전북","김제","정공S/S 154kV #1 BUS TIE CB","김제P/O 154kV 차단기 정밀점검공사","154kV 차단기 정밀점검","2017-05-29 09:00","2017-05-31 18:00","2017-05-29 09:00","2017-05-31 18:00","매일",null,null,null,201703240102]
[324,"전북","직할","곡성남원#2 T/L","154kV 곡성-남원#2T/L 점퍼지지애자 교체공사","96년 상반기 이전 국산 점퍼지지애자 교체 131개 154kV 곡성-남원#2T/L 피뢰기 설치공사 병행(No.10, 15)","2017-05-15 07:30","2017-05-18 18:00","2017-05-15 07:30","2017-05-18 18:00","매일",null,null,null,201701230103]
[325,"전북","직할","북전주봉동#2 T/L","154kV 차단기 보통점검","북전주S/S 154kV 북전주-봉동#2 차단기 보통점검","2017-05-11 09:30","2017-05-11 18:00","2017-05-07 09:30","2017-05-07 18:00","당일",null,null,null,201703130182]
[326,"전북","직할","이리전주#2 T/L","2017년 전북직할 170kV 차단기 정밀점검공사","- 170kV 차단기 내부 정밀점검, 흡습제 교체 및 기타 부대공사","2017-05-10 09:30","2017-05-12 18:00","2017-05-10 09:30","2017-05-12 18:00","연속",null,null,null,201703140342]
[327,"전북","직할","신김제전주#1 T/L","154kV 차단기 보통점검","전주S/S 154kV 신김제-전주#1 차단기 보통점검","2017-05-10 09:30","2017-05-10 18:00","2017-05-10 09:30","2017-05-10 18:00","당일",null,null,null,201703130185]
[328,"전북","직할","신김제전주#2 T/L","2017년 전북직할 170kV 차단기 정밀점검공사","- 170kV 차단기 내부 정밀점검, 흡습제 교체 및 기타 부대공사","2017-05-15 09:30","2017-05-17 18:00","2017-05-15 09:30","2017-05-17 18:00","연속",null,null,null,201703140344]
[329,"광주전남","강진","남창S/S 남창-해남CS#1T/L GIS","2017년 강진전력지사 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검","2017-05-15 09:00","2017-05-19 18:00","2017-05-15 09:00","2017-05-19 18:00","연속",null,null,null,201703160107]
[330,"광주전남","강진","남창S/S 남창-해남CS#2T/L GIS","2017년 강진전력지사 170kV GIS 정밀점검공사","-170kV GIS 정밀점검","2017-05-22 09:00","2017-05-26 18:00","2017-05-22 09:00","2017-05-26 18:00","연속",null,null,null,201703160115]
[331,"광주전남","강진","대불남악#2 T/L","154kV 대불-남악 등 3개TL 접속개소 해소공사","가. 구 간 ○ 154kV 대불-남악 T/L No.7∼10 등 2구간 ○ 154kV 신강진-대불 T/L No.8∼11 등 9구간 나. 전선교체 ○ ACSR/AW 410㎟ × 2B, 26.464㎞","2017-05-10 07:00","2017-05-16 18:00","2017-05-10 07:00","2017-05-16 18:00","연속",null,null,null,201703070268]
[332,"광주전남","강진","신강진대불#2 T/L","154kV 대불-남악 등 3개TL 접속개소 해소공사","가. 구 간 ○ 154kV 대불-남악 T/L No.7∼10 등 2구간 ○ 154kV 신강진-대불 T/L No.8∼11 등 9구간 나. 전선교체 ○ ACSR/AW 410㎟ × 2B, 26.464㎞","2017-05-01 07:00","2017-05-21 18:00","2017-04-22 07:00","2017-05-08 18:00","연속",null,null,null,201703070264]
[333,"광주전남","강진","화원진도#2 T/L","154kV 화원-진도#2T/L(강진 변전협력회사 총액공사)","보호배전반 대체","2017-05-22 09:00","2017-05-24 18:00","2017-05-22 09:00","2017-05-24 18:00","연속",null,null,null,201703090378]
[334,"광주전남","강진","신강진해남#2 T/L","154kV 해남S/S #4M.Tr 증설공사","○ 해남S/S #4M.Tr 증설공사 - #4M.Tr용 170kV GIS 1CCT 설치 - #1, 2BUS 무부하 가압","2017-05-10 10:00","2017-05-19 15:00","2017-05-10 10:00","2017-05-19 15:00","매일",null,null,null,201703150122]
[335,"광주전남","광주","신광주곡성#2 T/L","곡성S/S 170kV 장기사용 GIS 교체공사","곡성S/S 신광주-곡성#2T/L GIS 교체공사","2017-05-29 09:00","2017-06-28 18:00","2017-05-29 09:00","2017-06-28 18:00","연속",null,null,null,201703200138]
[336,"광주전남","광주","신광주곡성#1 T/L","154kV 곡성-남원#2T/L 점퍼지지애자 교체공사","154kV 곡성-남원#2T/L 점퍼지지애자 교체공사 안전이격거리 확보(작업無)","2017-03-16 07:30","2017-03-16 18:00","2017-05-16 07:30","2017-05-16 18:00","당일",null,null,null,201701230105]
[337,"광주전남","광주","신광주장성#2 T/L","신광주장성#2 T/L(일곡#2T/L 인출변경,송전선교차로병행휴전)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험 - 일곡#2T/L 인출변경,송전선교차로병행휴전","2017-05-14 07:00","2017-05-14 18:00","2017-05-14 07:00","2017-05-14 18:00","당일",null,null,null,201701250011]
[338,"광주전남","광주","신광주장성#2 T/L","신광주장성#2 T/L(인출변경 및 인출GIS연결)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-05-26 07:00","2017-06-03 18:00","2017-05-26 07:00","2017-06-03 18:00","연속",null,null,null,201701250012]
[339,"광주전남","광주","신광주곡성#1 T/L","신광주곡성#1 T/L(인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-05-14 07:00","2017-05-25 18:00","2017-05-14 07:00","2017-05-25 18:00","연속",null,null,null,201701250010]
[340,"광주전남","광주","신광주일곡#2 T/L","신광주일곡#2 T/L(인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-05-14 07:00","2017-05-25 18:00","2017-05-14 07:00","2017-05-25 18:00","연속",null,null,null,201701250009]
[341,"광주전남","광주","신광주계림#1 T/L","신광주계림#1 T/L(인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-05-10 07:00","2017-05-13 18:00","2017-05-10 07:00","2017-05-13 18:00","연속",null,null,null,201701250005]
[342,"광주전남","순천","서순천주암HP T/L","154kV 서순천-주암HP T/L(전력선교체)","345kV 신남원-광양 등 4개T/L 전선접속개소 해소공사 - 주암분기(서순천-주암HP) T/L 4~5호간 전력선 교체 - 17년 순천전력 변전협력 총액공사(보조계전기 교체)","2017-05-15 07:00","2017-05-16 18:00","2017-05-15 07:00","2017-05-16 18:00","당일",null,null,null,201703130299]
[343,"광주전남","순천","계림승주#2(서남권상수도T분기) T/L","154kV 계림-승주#2T/L(승주S/S 보조계전기교체)","17년 순천전력 변전협력 총액공사(보조계전기 교체)","2017-05-23 10:00","2017-05-23 18:00","2017-05-23 10:00","2017-05-23 18:00","당일",null,null,null,201703130296]
[344,"광주전남","순천","계림승주#1(서남권상수도T분기) T/L","154kV 계림-승주#1T/L(승주S/S 보조계전기교체)","17년 순천전력 변전협력 총액공사(보조계전기 교체)","2017-05-22 10:00","2017-05-22 18:00","2017-05-22 10:00","2017-05-22 18:00","당일",null,null,null,201703130295]
[345,"광주전남","순천","승주주암HP T/L","154kV 승주-주암HP T/L(승주S/S 보조계전기교체)","17년 순천전력 변전협력 총액공사(보조계전기 교체)","2017-05-24 10:00","2017-05-24 18:00","2017-05-24 10:00","2017-05-24 18:00","당일",null,null,null,201703130297]
[346,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TP#1 T/L(여수TP 피뢰기 보통)","17년 순천전력 변전협력 총액공사 - 호남TP-여수TP#2T/L(여수TP 피뢰기 보통점검) - 여수TP GIS 보조계전기 교체","2017-05-16 10:00","2017-05-16 18:00","2017-05-16 10:00","2017-05-16 18:00","당일",null,null,null,201703130281]
[347,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TP#2T/L(여수TP 피뢰기 보통)","17년 순천전력 변전협력 총액공사 - 호남TP-여수TP#2 T/L(여수TP 피뢰기 보통점검) - 여수TP GIS 보조계전기 교체","2017-05-15 10:00","2017-05-15 18:00","2017-05-15 10:00","2017-05-15 18:00","당일",null,null,null,201703130280]
[348,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성#1 T/L(보조계전기 교체)","17년 순천전력 변전협력 총액공사(보조계전기 교체) - 여수TP, 용성S/S 보조계전기 교체","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","당일",null,null,null,201703130284]
[349,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성#2T/L(보조계전기 교체)","17년 순천전력 변전협력 총액공사(보조계전기 교체) - 용성S/S 보조계전기 교체","2017-05-18 10:00","2017-05-18 18:00","2017-05-18 10:00","2017-05-18 18:00","당일",null,null,null,201703130287]
[350,"광주전남","직할","남광주화순#2 T/L","154kV남광주-화순#2T/L SB댐퍼설치공사","ㅇ16~17년 송전협력총액공사 - SB댐퍼설치공사(No.1,2,3,4,5,6,7,8,291호)","2017-05-17 08:00","2017-05-17 18:00","2017-05-17 08:00","2017-05-17 18:00","당일",null,null,null,201703100270]
[351,"광주전남","직할","남광주화순#1 T/L","154kV남광주-화순#1T/L SB댐퍼설치공사","ㅇ16~17년 송전협력총액공사 - SB댐퍼설치공사(No.1,2,3,4,5,6,7,8,291호)","2017-05-15 08:00","2017-05-15 18:00","2017-05-15 08:00","2017-05-15 18:00","당일",null,null,null,201703100266]
[352,"대구경북","경산","신경산S/S 154kV #62 BUS","신경산S/S 154kV #62BUS 휴전","#1DS, LCP, CB, 상부BUS 철거/설치","2017-05-29 09:00","2017-06-07 09:00","2017-05-29 09:00","2017-06-07 09:00","연속",null,null,null,201703090513]
[353,"대구경북","경산","신경산금호#1 T/L","신경산S/S 154kV 신경산-금호#1T/L 휴전","697 GIS 대체공사","2017-05-27 09:00","2017-06-16 18:00","2017-05-27 09:00","2017-06-16 18:00","연속",null,null,null,201703090504]
[354,"대구경북","경산","신경산노변 T/L","신경산S/S 154kV 신경산-노변T/L 휴전","#67BUS 무부하가압 관련선로","2017-05-28 18:00","2017-05-29 09:00","취소","취소","매일",null,null,null,201703090518]
[355,"대구경북","경산","신경산금호#2 T/L","신경산S/S 154kV 신경산-금호#2T/L 휴전","6A7 GIS 대체공사","2017-05-27 09:00","2017-06-16 18:00","2017-05-27 09:00","2017-06-16 18:00","연속",null,null,null,201703090505]
[356,"대구경북","구미","구미광평#2 T/L","2017년 구미P/O 170kV GIS 정밀점검공사","1. 170kV GIS 정밀점검","2017-05-10 09:00","2017-05-12 18:00","2017-05-10 09:00","2017-05-12 18:00","연속",null,null,null,201703140085]
[357,"대구경북","구미","산동선산#1 T/L","154kV 산동S/S #3M.Tr 증설공사 (무부하가압, 안전거리)","154kV 산동S/S #3M.Tr 증설공사 - 6333GIS 증설관련 안전거리확보 (즉시가압조건) - 6331DS, 6332DS, 6333CB부 무부하 가압선로(24시간무부하가압)","2017-05-10 09:30","2017-05-19 18:00","2017-05-10 09:30","2017-05-19 18:00","연속",null,null,null,201703140511]
[358,"대구경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화공사","T-BUS 및 8DS 철거작업","2017-05-26 09:00","2017-05-27 18:00","2017-05-26 09:00","2017-05-27 18:00","연속",null,null,null,201703130347]
[359,"대구경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화공사","T-BUS 및 8DS 철거작업","2017-05-29 09:00","2017-05-30 18:00","2017-05-29 09:00","2017-05-30 18:00","연속",null,null,null,201703130348]
[360,"대구경북","달성","고령쌍림#2 T/L","154kV 고령-쌍림T/L 전선접속개소 전선교체공사","- 154kV 고령-쌍림T/L 36-39, 42-49, 57-59호 전선교체","2017-05-23 08:00","2017-05-29 18:00","2017-05-23 08:00","2017-05-29 18:00","연속",null,null,null,201703090042]
[361,"대구경북","달성","고령쌍림#1 T/L","154kV 고령-쌍림T/L 전선접속개소 전선교체공사","- 154kV 고령-쌍림T/L 36-39, 42-49, 57-59호 전선교체","2017-05-16 08:00","2017-05-22 18:00","2017-05-16 08:00","2017-05-22 18:00","연속",null,null,null,201703090041]
[362,"대구경북","달성","상인봉덕#1 T/L","소선 풀림으로 인한 인입 전선교체","소선 풀림으로 인한 인입 전선교체","2017-05-22 15:00","2017-05-22 18:00","2017-05-22 15:00","2017-05-22 18:00","당일",null,null,null,201703160045]
[363,"대구경북","달성","성서달성#1 T/L","2017년 달성전력지사 상반기 정밀점검","GIS정밀점검(성서달성#1)","2017-05-03 09:30","2017-05-05 09:00","2017-05-03 09:30","2017-05-05 09:00","연속",null,null,null,201703190005]
[364,"대구경북","달성","강창성서#2 T/L","2017년 달성전력지사 상반기 정밀점검","GIS정밀점검(무부하11~12,강창정밀13~14)","2017-05-11 13:00","2017-05-14 18:00","2017-05-11 13:00","2017-05-14 18:00","연속",null,null,null,201703070162]
[365,"대구경북","달성","성서달성#2 T/L","2017년 달성전력지사 상반기 정밀점검","GIS정밀점검(성서달성#2)","2017-05-05 09:30","2017-05-07 18:00","2017-05-05 09:30","2017-05-07 18:00","연속",null,null,null,201703190006]
[366,"대구경북","안동","안동안동HP T/L","154kV 안동-안동HP T/L 정밀점검","154kV 안동-안동HP T/L 정밀점검 No.2-12","2017-05-15 07:00","2017-05-15 18:00","2017-05-15 07:00","2017-05-15 18:00","당일",null,null,null,201703080220]
[367,"대구경북","영주","신영주안동#2 T/L","154kV신영주-안동#2T/L 전선접속개소 정비공사","No.2-6, 11-13 전선접속개소 정비공사","2017-05-29 07:00","2017-06-04 18:00","취소","취소","연속",null,null,null,201703090536]
[368,"대구경북","영주","신영주안동#1 T/L","154kV신영주-안동#1T/L 전선접속개소 정비공사","No.2-6, 11-13 전선접속개소 정비공사","2017-05-22 07:00","2017-05-28 18:00","2017-05-22 07:00","2017-05-28 18:00","연속",null,null,null,201703090535]
[369,"대구경북","영주","영주봉화#2 T/L","154kV영주-봉화#2T/L 전선접속개소 정비공사, 지장철탑이설","No.2-76 전선접속교체, 지장철탑이설공사","2017-05-29 07:00","2017-06-11 18:00","취소","취소","연속",null,null,null,201703100313]
[370,"대구경북","직할","범물남대구#2 T/L","모선보호반 교체","모선보호반 교체","2017-05-25 09:30","2017-05-25 10:00","2017-05-25 09:30","2017-05-25 10:00","당일",null,null,null,201703100247]
[371,"대구경북","직할","범물남대구#1 T/L","모선보호반 교체","모선보호반 교체","2017-05-25 10:00","2017-05-25 10:30","2017-05-25 10:00","2017-05-25 10:30","당일",null,null,null,201703100249]
[372,"대구경북","칠곡","칠곡인동#1 T/L","154kV 칠곡-인동T/L No.57-58 안전이격확보공사","154kV 칠곡-인동T/L No.57-58 안전이격확보공사 철거 및 설치 각 2기","2017-05-04 08:00","2017-05-21 18:00","2017-05-04 08:00","2017-05-21 18:00","연속",null,null,null,201703080390]
[373,"대구경북","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.27-34 공사구간, 5기철거, 4기설치)-양회선 휴전시공","2017-05-18 08:00","2017-05-26 18:00","취소","취소","연속",null,null,null,201703090114]
[374,"대구경북","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.27-34 공사구간, 5기철거, 4기설치)-양회선 휴전시공","2017-05-18 08:00","2017-05-26 18:00","취소","취소","연속",null,null,null,201703090113]
[375,"대구경북","포항","입실양북 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","154kV 송전선로 횡단개소 안전확보","2017-05-29 08:00","2017-06-02 18:00","2017-05-29 08:00","2017-06-02 18:00","연속",null,null,null,201703100082]
[376,"대구경북","포항","영일입실 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","154kV 송전선로 횡단개소 안전확보","2017-05-29 08:00","2017-06-02 18:00","2017-05-29 08:00","2017-06-02 18:00","연속",null,null,null,201703100081]
[377,"대구경북","포항","건천천북#1 T/L","건천천북#1 T/L 677 GIS 공기조작부 정밀점검","건천천북#1 T/L 677 GIS 공기조작부 정밀점검","2017-05-08 09:00","2017-05-08 18:00","2017-05-08 09:00","2017-05-08 18:00","당일",null,null,null,201703090419]
[378,"대구경북","포항","청하영덕#2 T/L","154kV 청하-영덕 T/L 접속개소 전력선교체공사","154kV 청하-영덕T/L 33~116호 전력선교체 : 33~116호 ACSR 410㎟*2B*2C, 21C_km 가공지선교체 : 39~78호 ACSR 97㎟, 3.998C_km","2017-05-22 08:00","2017-06-02 18:00","취소","취소","연속",null,null,null,201703080296]
[379,"대구경북","포항","청하영덕#1 T/L","154kV 청하-영덕 T/L 접속개소 전력선교체공사","154kV 청하-영덕T/L 33~116호 전력선교체 : 33~116호 ACSR 410㎟*2B*2C, 21C_km 가공지선교체 : 39~78호 ACSR 97㎟, 3.998C_km","2017-05-10 08:00","2017-05-21 18:00","취소","취소","연속",null,null,null,201703080284]
[380,"부산울산","동부산","정관S/S 154kV #1 BUS","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 681DS 설치","2017-05-29 09:00","2017-06-03 16:00","2017-05-29 09:00","2017-06-03 16:00","연속",null,null,null,201703100014]
[381,"부산울산","동부산","노포정관#1 T/L","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 시험가압선로","2017-05-26 16:00","2017-05-27 16:00","2017-05-26 16:00","2017-05-27 16:00","연속",null,null,null,201703100017]
[382,"부산울산","동부산","정관S/S 154kV #2 BUS","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 682DS 설치","2017-05-22 09:00","2017-05-27 16:00","2017-05-22 09:00","2017-05-27 16:00","연속",null,null,null,201703100011]
[383,"부산울산","북부산","김해S/S 154kV BUS TIE GIS CB","2017년 북부산변전협력회사 총액공사","김해S/S 6100 GIS 초기점검","2017-05-15 10:00","2017-05-15 18:00","2017-05-15 10:00","2017-05-15 18:00","당일",null,null,null,201703090243]
[384,"부산울산","북부산","서창산막#2 T/L","154kV 서창산막T/L 2~9호 지장철탑이설공사","154kV 서창산막T/L 지장이설 가선로 구성 5~9호(철탑3기, 0.6km)","2017-05-15 08:00","2017-05-19 18:00","2017-05-15 08:00","2017-05-19 18:00","연속",null,null,null,201703100111]
[385,"부산울산","북부산","서창산막#1 T/L","154kV 서창산막T/L 2~9호 지장철탑이설공사","154kV 서창산막T/L 지장이설 가선로 구성 5~9호(철탑3기, 0.6km)","2017-05-20 09:00","2017-05-24 18:00","2017-05-20 09:00","2017-05-24 18:00","연속",null,null,null,201703100112]
[386,"부산울산","북부산","양산산막#2 T/L","양산S/S 취약설비 현대화공사","- #1M.Tr 1차 , 양산-산막T/L 공용단로기 전력선 접속 - #1M.Tr 1차 GCB 시험가압선로(1H)","2017-05-10 09:00","2017-05-12 16:00","2017-05-10 09:00","2017-05-12 16:00","연속",null,null,null,201703080335]
[387,"부산울산","북부산","양산S/S 154kV #2 BUS","양산S/S 취약설비 현대화공사","154kV #1M.Tr 1차 철구조립 안전이격 확보","2017-05-04 09:00","2017-05-04 18:00","2017-05-04 09:00","2017-05-04 18:00","당일",null,null,null,201703170181]
[388,"부산울산","북부산","양산S/S 154kV #2 BUS","양산S/S 취약설비 현대화공사","154kV #2BUS 옥외철구 모선 일부 분리","2017-05-02 09:00","2017-05-02 18:00","2017-05-02 09:00","2017-05-02 18:00","당일",null,null,null,201703170180]
[389,"부산울산","북부산","양산S/S 154kV #2 BUS","양산S/S 취약설비 현대화공사","154kV #2BUS 옥외철구 모선 일부 분리","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","당일",null,null,null,201703170183]
[390,"부산울산","북부산","양산S/S 154kV #2 BUS","양산S/S 취약설비 현대화공사","154kV #1M.Tr 1차 공용단로기 모선연결","2017-05-10 09:00","2017-05-12 18:00","2017-05-10 09:00","2017-05-12 18:00","연속",null,null,null,201703170182]
[391,"부산울산","북부산","엄궁학장#2 T/L","2017년 북부산변전협력회사 총액공사","학장S/S 엄궁학장#2T/L GIS초기점검 627휴전","2017-05-19 10:00","2017-05-19 18:00","2017-05-19 10:00","2017-05-19 18:00","당일",null,null,null,201703090248]
[392,"부산울산","북부산","엄궁학장#1 T/L","2017년 북부산변전협력회사 총액공사","학장S/S 엄궁학장#1T/L GIS초기점검 617휴전","2017-05-08 10:00","2017-05-08 18:00","2017-05-08 10:00","2017-05-08 18:00","당일",null,null,null,201703090247]
[393,"부산울산","북부산","호포S/S 154kV #2 BUS","2017년 북부산변전협력회사 총액공사","호포S/S 노후 CPD PNL 교체","2017-05-28 11:00","2017-05-28 15:00","2017-05-28 11:00","2017-05-28 15:00","당일",null,null,null,201703130076]
[394,"부산울산","북부산","호포S/S 154kV #1 BUS","2017년 북부산변전협력회사 총액공사","호포S/S 노후 CPD PNL 교체","2017-05-28 09:00","2017-05-28 11:00","2017-05-28 09:00","2017-05-28 11:00","당일",null,null,null,201703130075]
[395,"부산울산","북부산","호포S/S 154kV #1 BUS","2017년 북부산변전협력회사 총액공사","호포S/S 노후 CPD PNL 교체","2017-05-28 15:00","2017-05-28 19:00","2017-05-28 15:00","2017-05-28 19:00","당일",null,null,null,201703130077]
[396,"부산울산","북부산","북부산삼랑진PP#1 T/L","17년 가공송전 협력업체 총액공사","북부산삼랑진PP#1T/L(북부산S/T-64호 SB댐퍼 설치공사)","2017-05-29 07:30","2017-06-02 18:00","2017-05-29 07:30","2017-06-02 18:00","연속",null,null,null,201703100078,"○"]
[397,"부산울산","북부산","북부산삼랑진PP#2 T/L","17년 가공송전 협력업체 공사","북부산삼랑진PP#2 T/L 102호 금구류 교체","2017-05-08 07:30","2017-05-08 18:00","2017-05-08 07:30","2017-05-08 18:00","당일",null,null,null,201703100094]
[398,"부산울산","북부산","북부산양산 T/L","17년 가공송전 협력업체 총액공사","북부산삼랑진PP#1T/L - 북부산S/T-64호 SB댐퍼 설치공사 (4회선 구간 작업시 작업자 안전거리확보)","2017-05-29 07:30","2017-06-02 18:00","2017-05-29 07:30","2017-06-02 18:00","연속",null,null,null,201703240105]
[399,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산S/S 서부산-신평#1 T/L GIS 정밀점검","서부산S/S 서부산-신평#1 T/L GIS 정밀점검 (서부산-신평#1T/L 1DS(6B1) 정밀점검)","2017-05-22 08:00","2017-05-23 20:00","2017-05-22 08:00","2017-05-23 20:00","연속",null,null,null,201703090527,"○"]
[400,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산S/S #2 BUSTIE GIS 정밀점검","서부산S/S #2 BUSTIE GIS 정밀점검 (6201 DS 정밀점검)","2017-05-11 08:00","2017-05-12 20:00","2017-05-11 08:00","2017-05-12 20:00","연속",null,null,null,201703090539,"○"]
[401,"부산울산","서부산","서부산S/S 154kV #2 BUS TIE CB","서부산S/S #2 BUSTIE GIS 정밀점검","서부산S/S #2 BUSTIE GIS 정밀점검 (6200 CB 정밀점검)","2017-05-11 08:00","2017-05-13 18:00","2017-05-11 08:00","2017-05-13 18:00","연속",null,null,null,201703090537,"○"]
[402,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S #2 BUSTIE GIS 정밀점검","서부산S/S #2 BUSTIE GIS 정밀점검 (6201 DS 정밀점검관련 시험가압)","2017-05-12 18:00","2017-05-12 20:00","2017-05-12 18:00","2017-05-12 20:00","당일",null,null,null,201703090541,"○"]
[403,"부산울산","서부산","서부산S/S 154kV #66 BUS","서부산S/S #2 BUSTIE GIS 정밀점검","서부산S/S #2 BUSTIE GIS 정밀점검 (6200 CB + 6202 DS 정밀점검)","2017-05-13 08:00","2017-05-13 20:00","2017-05-13 08:00","2017-05-13 20:00","당일",null,null,null,201703090540]
[404,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S #2 BUSTIE GIS 정밀점검","서부산S/S #2 BUSTIE GIS 정밀점검 (6200 CB + 6202 DS 정밀점검관련 시험가압)","2017-05-13 18:00","2017-05-13 20:00","2017-05-13 18:00","2017-05-13 20:00","당일",null,null,null,201703090542]
[405,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산S/S 서부산-신평#2 T/L GIS 정밀점검","서부산S/S 서부산-신평#2 T/L GIS 정밀점검 (서부산-신평#2T/L 1DS(6A1) 정밀점검)","2017-05-15 08:00","2017-05-16 20:00","2017-05-15 08:00","2017-05-16 20:00","연속",null,null,null,201703090534]
[406,"부산울산","서부산","서부산S/S 154kV #65 BUS","서부산S/S 서부산-신평#2 T/L GIS 정밀점검","서부산S/S 서부산-신평#2 T/L GIS 정밀점검 (서부산-신평#2T/L CB(6A7) + 2DS(6A2) 정밀점검)","2017-05-17 08:00","2017-05-17 20:00","2017-05-17 08:00","2017-05-17 20:00","당일",null,null,null,201703090533]
[407,"부산울산","서부산","서부산S/S 154kV #65 BUS","서부산S/S 서부산-신평#1 T/L GIS 정밀점검","서부산S/S 서부산-신평#1 T/L GIS 정밀점검 (서부산-신평#1T/L CB(6B7) + 2DS(6B2) 정밀점검)","2017-05-24 08:00","2017-05-24 20:00","2017-05-24 08:00","2017-05-24 20:00","당일",null,null,null,201703090532]
[408,"부산울산","울산","동울산효문#2 T/L","2017년 가공송전선로 순시점검 위탁공사(울산전력지사)","154kV 동울산-효문T/L 송전선로 초기점검(22기), 정밀점검(21기)","2017-05-29 09:00","2017-06-01 18:00","2017-05-29 09:00","2017-06-01 18:00","연속",null,null,null,201703080203]
[409,"부산울산","울산","동울산효문#1 T/L","2017년 가공송전선로 순시점검 위탁공사(울산전력지사)","154kV 동울산-효문T/L 송전선로 초기점검(22기), 정밀점검(21기)","2017-05-15 09:00","2017-05-18 18:00","2017-05-15 09:00","2017-05-18 18:00","연속",null,null,null,201703080202]
[410,"부산울산","울산","신울산S/S 154kV #2 BUS TIE CB","'16~17년도 울산전력지사 변전협력회사 총액공사","신울산S/S 6200 GIS 보통점검, 공기조작부 점검","2017-05-17 09:00","2017-05-17 18:00","2017-05-17 09:00","2017-05-17 18:00","당일",null,null,null,201703100339]
[411,"부산울산","울산","신울산S/S 154kV #1 BUS TIE CB","'16~17년도 울산전력지사 변전협력회사 총액공사","신울산S/S 6100 GIS 보통점검, 공기조작부 점검","2017-05-16 09:00","2017-05-16 18:00","2017-05-16 09:00","2017-05-16 18:00","당일",null,null,null,201703100338]
[412,"부산울산","울산","용연울산TP#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 681DS 대체관련 681(미투입) 및 #1BUS 시험가압","2017-05-16 18:00","2017-05-17 18:00","2017-05-16 18:00","2017-05-17 18:00","당일",null,null,null,201703100330]
[413,"부산울산","울산","용연처용#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 687,681,682,686 GIS 대체","2017-05-10 08:00","2017-05-24 18:00","2017-05-10 08:00","2017-05-24 18:00","연속",null,null,null,201703100328]
[414,"부산울산","울산","용연울산TP#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S GIS 대체공사관련 682DS 철거마감부 및 #2BUS 시험가압","2017-05-11 17:00","2017-05-11 18:00","2017-05-11 17:00","2017-05-11 18:00","당일",null,null,null,201703100329]
[415,"부산울산","직할","양정범천 T/L","범천S/S 양정-범천T/L GIS(637) 미동작점검","범천S/S 양정-범천T/L GIS(637) 미동작점검","2017-05-11 10:00","2017-05-11 14:00","2017-05-11 10:00","2017-05-11 14:00","당일",null,null,null,201703080324]
[416,"부산울산","직할","서부산부민#2 T/L","2017년 직할 관내 170kV GIS 정밀점검 공사","부민S/S #3M.Tr (6333) GIS #2DS정밀점검 시험가압선로","2017-05-18 18:00","2017-05-18 19:00","2017-05-18 18:00","2017-05-18 19:00","당일",null,null,null,201703060152]
[417,"부산울산","직할","서부산부민#1 T/L","2017년 직할 관내 170kV GIS 정밀점검 공사","부민S/S #3M.Tr (6333) GIS #1DS,CB 정밀점검 시험가압선로","2017-05-20 17:00","2017-05-20 18:00","2017-05-20 17:00","2017-05-20 18:00","당일",null,null,null,201703060153]
[418,"부산울산","직할","부산영도#1 T/L","154kV 우동 등 3개S/S 지중케이블 선종교체공사","부산S/S 지중케이블 선종교체공사(OF 1200 ---> XLPE 1200 교체) 부산-영도#1,2 : 부산S/S ~ S/J - 0.022km","2017-05-12 09:00","2017-05-26 18:00","2017-05-12 09:00","2017-05-26 18:00","연속",null,null,null,201703090280]
[419,"부산울산","직할","부산영도#2 T/L","154kV 우동 등 3개S/S 지중케이블 선종교체공사","부산S/S 지중케이블 선종교체공사 부산-영도#1,2 : 부산S/S ~ S/J - 0.022km","2017-05-30 09:00","2017-06-13 18:00","2017-05-30 09:00","2017-06-13 18:00","연속",null,null,null,201703090283]
[420,"부산울산","직할","수정범일#2 T/L","수정,범일S/S 수정-범일#2T/L 보호배전반 대체","수정,범일S/S 수정-범일#2T/L 보호배전반 대체(수정S/S:617,범일S/S:627 )","2017-05-15 10:00","2017-05-17 18:00","2017-05-15 10:00","2017-05-17 18:00","연속",null,null,null,201703100071]
[421,"부산울산","직할","수정범일#1 T/L","수정,범일S/S 수정-범일#1T/L 보호배전반 대체","수정,범일S/S 수정-범일#1T/L 보호배전반 대체(수정S/S:627,범일S/S:617)","2017-05-10 10:00","2017-05-12 18:00","2017-05-10 10:00","2017-05-12 18:00","연속",null,null,null,201703100061]
[422,"경남","직할","마천진해#2 T/L","2017년 경남 직할 개폐장치 정밀점검","마천S/S 마천-진해#2T/L GIS 정밀점검","2017-05-15 08:30","2017-05-17 18:00","2017-05-15 08:30","2017-05-17 18:00","연속",null,null,null,201703060054]
[423,"경남","직할","마천진해#1 T/L","2017년 경남 직할 개폐장치 정밀점검","마천S/S 마천-진해#1T/L GIS 정밀점검","2017-05-10 08:30","2017-05-12 18:00","2017-05-10 08:30","2017-05-12 18:00","연속",null,null,null,201703060033]
[424,"경남","직할","신김해진영#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-20 07:00","2017-05-21 18:00","2017-05-20 07:00","2017-05-21 18:00","연속",null,null,null,201703070306]
[425,"경남","직할","신김해진영#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-13 07:00","2017-05-14 18:00","2017-05-13 07:00","2017-05-14 18:00","연속",null,null,null,201703070308]
[426,"경남","직할","신김해주촌#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-03 07:00","2017-05-03 18:00","2017-05-03 07:00","2017-05-03 18:00","당일",null,null,null,201703150045]
[427,"경남","직할","신김해주촌#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-03 07:00","2017-05-03 18:00","2017-05-03 07:00","2017-05-03 18:00","당일",null,null,null,201703150044]
[428,"경남","직할","신김해주촌#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-05 07:00","2017-05-07 18:00","2017-05-05 07:00","2017-05-07 18:00","연속",null,null,null,201703070303]
[429,"경남","직할","신김해진영#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-05 07:00","2017-05-07 18:00","2017-05-05 07:00","2017-05-07 18:00","연속",null,null,null,201703070304]
[430,"경남","직할","신김해진영#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-20 07:00","2017-05-21 18:00","2017-05-20 07:00","2017-05-21 18:00","연속",null,null,null,201703070309]
[431,"경남","직할","신김해진영#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-13 07:00","2017-05-14 18:00","2017-05-13 07:00","2017-05-14 18:00","연속",null,null,null,201703070305]
[432,"경남","직할","신김해주촌#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사 관련 안전거리 확보휴전","2017-05-05 07:00","2017-05-07 18:00","2017-05-05 07:00","2017-05-07 18:00","연속",null,null,null,201703070302]
[433,"경남","직할","차룡창공#1 T/L","2017년 경남 직할 개폐장치 정밀점검","차룡S/S #4M.Tr 1차 GIS 정밀점검(시험가압)","2017-05-01 16:30","2017-05-01 17:30","2017-05-01 16:30","2017-05-01 17:30","당일",null,null,null,201702060230]
[434,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 이도조정(동시휴전)","154kV 하동-개양T/L 이도조정(동시휴전)","2017-05-05 07:00","2017-05-07 18:00","취소","취소","연속",null,null,"신뢰도개선",201703070028]
[435,"경남","진주","가야개양 T/L","154kV 가야-개양T/L 애자련 보강","154kV 가야-개양T/L 48~49, 74~78호 애자련 보강","2017-05-05 07:00","2017-05-07 19:00","2017-05-05 07:00","2017-05-07 19:00","연속",null,null,null,201703070348]
[436,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 이도조정(동시휴전)","154kV 하동-개양T/L 이도조정(동시휴전)","2017-05-03 07:00","2017-05-03 18:00","취소","취소","당일",null,null,"신뢰도개선",201703160062]
[437,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 이도조정(동시휴전)","154kV 하동-개양T/L 이도조정(동시휴전)","2017-05-03 07:00","2017-05-03 18:00","취소","취소","당일",null,null,"신뢰도개선",201703160061]
[438,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 이도조정(동시휴전)","154kV 하동-개양T/L 이도조정(동시휴전)","2017-05-05 07:00","2017-05-07 18:00","취소","취소","연속",null,null,"신뢰도개선",201703070027]
[439,"경남","진주","의령동진주#1 T/L","154kV의령-함양#1T/L SB댐퍼 교체","154kV의령-함양#1T/L SB댐퍼 교체(1~132호) 안전이격 확보용","2017-05-01 07:00","2017-05-01 18:00","2017-05-01 07:00","2017-05-01 18:00","매일",null,null,null,201702070267]
[440,"경남","진주","의령동진주#2 T/L","154kV산청-함양, 의령-산청T/L SB댐퍼 교체","154kV산청-함양, 의령-산청T/L SB댐퍼 교체(153기) 안전이격 확보용","2017-05-13 07:00","2017-05-13 18:00","2017-05-14 07:00","2017-05-14 18:00","매일",null,null,"신뢰도개선",201702070291]
[441,"경남","진주","의령동진주#1 T/L","154kV산청-함양, 의령-산청T/L SB댐퍼 교체","154kV산청-함양, 의령-산청T/L SB댐퍼 교체(153기) 안전이격 확보용","2017-05-13 07:00","2017-05-13 18:00","2017-05-14 07:00","2017-05-14 18:00","매일",null,null,"신뢰도개선",201703160017]
[442,"경남","진주","의령산청 T/L","154kV산청-함양, 의령-산청T/L SB댐퍼 교체","154kV산청-함양, 의령-산청T/L SB댐퍼 교체(153기)","2017-05-13 07:00","2017-05-14 18:00","2017-05-13 07:00","2017-05-14 18:00","매일",null,null,null,201702070298]
[443,"경남","진주","산청함양 T/L","154kV 쌍림-합천 등 10개T/L 전선교체 등 보강공사","154kV 산청-함양T/L 전선교체공사 85~89, 92~93, 95~98호","2017-05-01 07:00","2017-05-04 13:00","2017-05-01 07:00","2017-05-04 13:00","연속",null,null,null,201702070325]
[444,"경남","진주","의령함양 T/L","154kV 쌍림-합천 등 10개T/L 전선교체 등 보강공사","154kV 의령-함양T/L 전선교체공사 85~89, 92~93, 95~98호","2017-05-04 13:00","2017-05-07 19:00","2017-05-04 13:00","2017-05-07 19:00","연속",null,null,null,201702070330]
[445,"경남","진주","합천수력#1 T/L","154kV 쌍림-합천 등 10개T/L 전선교체 등 보강공사","154kV 쌍림-합천#2T/L 51~54,55~56호 154kV 합천수력T/L 4회선철탑 안전이격확보용 휴전","2017-05-21 07:00","2017-05-22 19:00","2017-05-21 07:00","2017-05-22 19:00","연속",null,null,null,201703060237]
[446,"경남","진주","합천수력#2 T/L","154kV 쌍림-합천 등 10개T/L 전선교체 등 보강공사","154kV 쌍림-합천#1T/L 51~54,55~56호 154kV 합천수력T/L 4회선철탑 안전이격확보용 휴전","2017-05-19 07:00","2017-05-20 19:00","2017-05-19 07:00","2017-05-20 19:00","연속",null,null,null,201703060228]
[447,"경남","통영","고성통영 T/L","154kV 신고성-통영T/L 안전이격확보공사(철탑상향)","154kV 신고성-통영T/L 안전이격확보공사(철탑상향) No.107~108 (고성-통영T/L 측)","2017-05-21 06:30","2017-05-21 20:00","2017-05-21 06:30","2017-05-21 20:00","매일",null,null,null,201703150158]
[448,"경남","통영","고성통영 T/L","154kV 신고성-통영T/L 안전이격확보공사(철탑상향)","154kV 신고성-통영T/L 안전이격확보공사(철탑상향) No.107~108 (고성-통영T/L 측)","2017-05-28 06:30","2017-05-28 20:00","2017-05-28 06:30","2017-05-28 20:00","매일",null,null,null,201703150159]
[449,"경남","통영","삼천포사천#1 T/L","삼천포S/S 154kV 삼천포-사천#1T/L 휴전(정밀점검 시험가압)","삼천포S/S 154kV 삼천포-사천#1T/L 휴전(정밀점검 시험가압) - 삼천포S/S 154kV BUS TIE GIS(6100) 정밀점검 시험가압","2017-05-23 13:00","2017-05-23 14:00","2017-05-23 13:00","2017-05-23 14:00","당일",null,null,null,201701160161]
[450,"경남","통영","삼천포사천#2 T/L","삼천포S/S 154kV 삼천포-사천#2T/L 휴전(정밀점검 시험가압)","삼천포S/S 154kV 삼천포-사천#2T/L 휴전(정밀점검 시험가압) - 삼천포S/S 154kV BUS TIE GIS(6100) 정밀점검 시험가압","2017-05-24 17:30","2017-05-24 18:30","2017-05-24 17:30","2017-05-24 18:30","당일",null,null,null,201701160163]
[451,"경남","통영","신고성고성 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 철탑 설치 및 전선이설","2017-05-05 07:00","2017-05-05 19:00","2017-05-05 06:00","2017-05-06 13:00","당일",null,null,null,201703200069]
[452,"경남","통영","신고성통영 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 철탑 설치 및 전선이설","2017-05-06 07:00","2017-05-06 19:00","2017-05-06 13:00","2017-05-06 19:00","당일",null,null,null,201703200070]
[453,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 정밀점검","154kV 신고성-거제#1T/L 정밀점검(병가구간 포함)","2017-05-07 08:00","2017-05-07 18:00","2017-05-07 08:00","2017-05-07 18:00","당일",null,null,null,201703200214]
[454,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 정밀점검","154kV 신고성-거제#1T/L 정밀점검(병가구간 포함)","2017-05-13 07:00","2017-05-14 18:00","2017-05-13 07:00","2017-05-14 18:00","매일",null,null,null,201703070330]
[455,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 안전이격확보공사(철탑상향)","154kV 신고성-통영T/L 안전이격확보공사(철탑상향) No.107~108","2017-05-20 06:30","2017-05-20 20:00","2017-05-20 06:30","2017-05-20 20:00","매일",null,null,null,201703150166]
[456,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 안전이격확보공사(철탑상향)","154kV 신고성-통영T/L 안전이격확보공사(철탑상향) No.107~108","2017-05-27 06:30","2017-05-27 20:00","2017-05-27 06:30","2017-05-27 20:00","매일",null,null,null,201703150167]
[457,"경남","통영","통영거제#2 T/L","154kV 신고성-거제#1T/L 정밀점검(병가구간 안전확보)","154kV 신고성-거제#1T/L 정밀점검(병가구간 안전확보)","2017-05-07 07:00","2017-05-07 18:00","2017-05-07 07:00","2017-05-07 18:00","당일",null,null,null,201703150164]
[458,"경남","함안","중리가야#1 T/L","중리-가야#1T/L SB댐퍼 설치공사","중리-가야#1T/L SB댐퍼 설치공사","2017-05-20 08:30","2017-05-21 17:30","2017-05-20 08:30","2017-05-21 17:30","연속",null,null,null,201703030023]
[459,"경남","함안","중리가야#2 T/L","중리-가야#2T/L SB댐퍼 설치공사","중리-가야#2T/L SB댐퍼 설치공사","2017-05-27 08:30","2017-05-28 17:30","2017-05-27 08:30","2017-05-28 17:30","연속",null,null,null,201703030024]
[460,"경남","함안","신마산동읍#2 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 안전이격 확보 (5~7, 11~17, 36~38호)","2017-05-27 07:00","2017-05-28 18:30","2017-05-27 07:00","2017-05-28 18:30","연속",null,null,null,201703070041]
[461,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산#2T/L 정밀점검","154kV 신마산-마산#2T/L 정밀점검","2017-05-20 08:00","2017-05-21 18:00","2017-05-20 08:00","2017-05-21 18:00","연속",null,null,null,201703060048]
[462,"경남","함안","신마산차룡#1 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 (5~7, 11~17, 36~38호)","2017-05-27 07:00","2017-05-28 18:30","2017-05-27 07:00","2017-05-28 18:30","연속",null,null,null,201703070022]
[463,"경남","함안","신마산중리#1 T/L","신마산-중리#1T/L SB댐퍼 설치공사 및 4회선병가구간 안전확보차","신마산-중리#1T/L SB댐퍼 설치공사 및 4회선병가구간 안전확보차 휴전 (중리-가야#2T/L 1~6호 병가구간)","2017-05-27 08:30","2017-05-28 17:30","2017-05-27 08:30","2017-05-28 17:30","연속",null,null,null,201703030025]
[464,"경남","함안","신마산마산#1 T/L","신마산-마산#1T/L 정밀점검","신마산-마산#1T/L 정밀점검","2017-05-13 08:30","2017-05-14 17:30","2017-05-13 08:30","2017-05-14 17:30","연속",null,null,null,201703030022]
[465,"경남","함안","신마산중리#2 T/L","신마산-중리#2T/L SB댐퍼 설치공사 및 4회선병가구간 안전확보차","신마산-중리#2T/L SB댐퍼 설치공사 및 4회선병가구간 안전확보차 휴전 (중리-가야#1T/L 1~6호 병가구간)","2017-05-20 08:30","2017-05-21 17:30","2017-05-20 08:30","2017-05-21 17:30","연속",null,null,null,201703030026]
[466,"경남","함안","진영한림정#2 T/L","154kV 한림정S/S #3M.Tr 증설공사","154kV 한림정S/S #3M.Tr 증설공사(#1DS 시험가압) - 154kV GIS 1CCT 설치","2017-05-27 18:00","2017-05-28 18:00","2017-05-27 18:00","2017-05-28 18:00","연속",null,null,null,201703080212]

{"sheet":"한수원","index":3,"n_rows":8,"n_cols":20,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,19,3,19],[2,12,3,12],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,17,3,17],[2,18,3,18],[0,0,0,7],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2017년도 05월간휴전계획표  -  한국수력원자력㈜"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","1발전소","#1 주변압기","월성 1호기  제25차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7200,7272","- 주변압기/소내용변압기 일반점검\n- 주발전기, 주/소내보조변압기 보호계전기 \n   정기시험(차단기 연동시험 포함)\n- 한전 철탑 이설공사","2017-05-26 09:00","2017-06-10 18:00","2017-05-26 09:00","2017-06-10 18:00","연속","N"]
[2,"한빛본부","한빛2발전소","#4 주변압기","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7A00, 7A71 ","○ OH관련 주변압기, 보조변압기 점검\n○ 보호계전기 개체/연동시험 등","2017-05-18T10:00:00","2017-07-28T22:00:00","2017-05-18T10:00:00","2017-07-28T22:00:00","연속","Y"]
[3,"한빛본부","한빛2발전소","#4 기동변압기 03XN","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7900, 7971 ","○ OH관련 기동변압기 03XN 점검\n○ 보호계전기 개체/연동시험 등","2017-05-29T09:00:00","2017-06-07T18:00:00","2017-05-29T09:00:00","2017-06-07T18:00:00","연속","Y"]
[4,"한빛본부","한빛2발전소","#4 기동변압기 04XN","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7800, 7871 ","○ OH관련 기동변압기 04XN 점검\n○ 보호계전기 개체/연동시험 등","2017-06-14T18:00:00","2017-06-22T17:30:00","2017-06-14T18:00:00","2017-06-22T17:30:00","연속","Y"]

{"sheet":"남부","index":4,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 4월 휴전계획표(한국수력원자력)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"신인천본부","신인천","4MT001 주변압기","갑종 보호계전기 정기시험 등","갑종 보호계전기 정기시험 등","2017-05-12T09:00:00","2017-05-16T18:00:00","2017-05-12T09:00:00","2017-05-16T18:00:00","연속"]
[2,"신인천본부","신인천","4MT201 주변압기","갑종 보호계전기 정기시험 등","갑종 보호계전기 정기시험 등","2017-05-12T09:00:00","2017-05-20T18:00:00","2017-05-12T09:00:00","2017-05-20T18:00:00","연속"]

{"sheet":"중부","index":5,"n_rows":8,"n_cols":21,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,20,3,20],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2017년도 05월 휴전계획표(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전소\n연계","사업소\n간","사업소\n내","발전소 정지\n계획(OH) 연계"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령화력","3발전소","345kV 청양-보령화력 #2T/L\n(CB 7771)","항공장애표시구\n설치공사","#7, 8 항공장애표시구 설치공사","2017-05-22T09:00:00","2017-05-28T17:00:00","2017-05-22T09:00:00","2017-05-28T17:00:00","연속"]
[2,"보령화력","3발전소","보령 7,8호기 #1BUS\n(CB7771, 7871)","갑종보호계전기 시험\nGIS 77Bay 보통점검","갑종보호계전기(모선보호반) 시험\nGIS 77Bay 보통점검","2017-05-22T09:00:00","2017-05-26T17:00:00","2017-05-22T09:00:00","2017-05-26T17:00:00","연속"]
[3,"인천복합","1CC","GT #1, 2 주변압기\n(CB7500, CB7572)","간이점검, 정기검사","간이점검, 정기검사(갑종보호계전기 시험 포함)","2017-05-07T09:00:00","2017-05-10T13:00:00","2017-05-07T09:00:00","2017-05-10T13:00:00","연속",{"$nulls":9},"Y"]
[4,"인천복합","1CC","ST #1 주변압기\n(CB7600, CB7672)","간이점검, 정기검사","간이점검, 정기검사(갑종보호계전기 시험 포함)","2017-05-10T14:00:00","2017-05-12T14:00:00","2017-05-10T14:00:00","2017-05-12T14:00:00","연속",{"$nulls":9},"Y"]