{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":14,"n_cols":16,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #3 M.Tr A-1","신가평S/S 345kV 장경간 GIB 구조개선 공사","신가평S/S 345kV 장경간 GIB 구조개선 공사","2017-06-26 09:00","2017-07-31 18:00","2017-06-26 09:00","2017-07-31 18:00","연속",null,null,null,201704180041]
[2,"경기","성남","신안성S/S 765kV #1 BUS","765kV GIS 정밀점검","7851 DS 정밀점검","2017-06-12 09:00","2017-06-18 18:00","2017-06-12 09:00","2017-06-18 18:00","연속",null,null,null,201704140174]
[3,"경기","성남","신안성S/S 765kV #2 BUS","765kV GIS 정밀점검","7852 DS 정밀점검","2017-06-19 09:00","2017-06-25 18:00","2017-06-19 09:00","2017-06-25 18:00","연속",null,null,null,201704140175]
[4,"강원","태백","신태백신한울#1 T/L","2017년 신태백S/S 800kV GIS 정밀점검 공사","신태백-신한울#1T/L GIS 정밀점검 (8471CB, 8461,8421,8401DS)","2017-06-19 09:00","2017-07-16 18:00","2017-06-19 09:00","2017-07-16 18:00","연속",null,null,null,201704100616]
[5,"대전충남","서산","당진T/P 신서산-당진TP#1T/L CB","'17년 서산P/O 765kV GIS 보통점검 공사","당진화력 765kV 신서산-당진T/P #1T/L GIS(8371) 보통점검","2017-06-19 09:00","2017-06-20 18:00","2017-06-19 09:00","2017-06-20 18:00","당일",null,null,null,201704180140]
[6,"대전충남","서산","당진T/P 신서산-당진TP#2T/L CB","'17년 서산P/O 765kV GIS 보통점검 공사","당진화력 765kV 신서산-당진T/P #2T/L GIS(8471) 보통점검","2017-06-21 09:00","2017-06-22 18:00","2017-06-21 09:00","2017-06-22 18:00","당일",null,null,null,201704180142]
[7,"대전충남","서산","신서산S/S 신서산-당진TP#1T/L CB","'17년 서산P/O 765kV GIS 보통점검 공사","신서산S/S 765kV 신서산-당진T/P #1T/L GIS(8471) 보통점검","2017-06-26 09:00","2017-06-27 18:00","2017-06-26 09:00","2017-06-27 18:00","당일",null,null,null,201704180141]
[8,"대전충남","서산","신서산S/S 신서산-당진TP#2T/L CB","'17년 서산P/O 765kV GIS 보통점검 공사","신서산S/S 765kV 신서산-당진T/P #2T/L GIS(8371) 보통점검","2017-06-28 09:00","2017-06-29 18:00","2017-06-28 09:00","2017-06-29 18:00","당일",null,null,null,201704180143]
[9,"경남","함안","북경남신고리NP#1 T/L","765kV 북경남-신고리NPT/L 착설방지링 설치","765kV 북경남-신고리NP#1T/L 착설방지링 설치","2017-06-17 08:00","2017-06-23 18:00","2017-06-17 08:00","2017-06-23 18:00","연속",null,null,null,201704050033]
[10,"경남","함안","북경남신고리NP#2 T/L","765kV 북경남-신고리NPT/L 착설방지링 설치","765kV 북경남-신고리NP#2T/L 착설방지링 설치","2017-06-24 08:00","2017-06-30 18:00","2017-06-24 08:00","2017-06-30 18:00","연속",null,null,null,201704050015]

{"sheet":"345송부","index":1,"n_rows":235,"n_cols":16,"rows_kept":235,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #3 M.Tr A","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #3M.Tr 2차)","2017-06-22 09:20","2017-06-23 18:00","2017-06-22 09:20","2017-06-23 18:00","연속",null,null,null,201704120225]
[2,"서울","성동","성동S/S #4 M.Tr A","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #4M.Tr 2차)","2017-06-24 09:20","2017-06-25 18:00","2017-06-24 09:20","2017-06-25 18:00","연속",null,null,null,201704120222]
[3,"서울","중부","중부S/S #3 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 74 BAY (7472) 모자익반 교체","2017-06-22 10:00","2017-06-26 18:00","2017-06-22 10:00","2017-06-26 18:00","연속",null,null,null,201704130054]
[4,"남서울","동서울","동서울S/S #1 M.Tr A","170kV GCB 보통점검","170kV GCB 보통점검, 냉각설비 점검","2017-06-12 10:00","2017-06-12 18:00","2017-06-12 10:00","2017-06-12 18:00","당일",null,null,null,201704170370]
[5,"남서울","동서울","동서울S/S #2 M.Tr A","170kV GCB 보통점검","170kV GCB 보통점검, 냉각설비 점검","2017-06-13 10:00","2017-06-13 18:00","2017-06-13 10:00","2017-06-13 18:00","당일",null,null,null,201704170371]
[6,"남서울","동서울","동서울S/S #3 M.Tr A","170kV GCB 보통점검","170kV GCB 보통점검, 냉각설비 점검, 소내전원 회로보완","2017-06-14 10:00","2017-06-14 18:00","2017-06-14 10:00","2017-06-14 18:00","당일",null,null,null,201704170373]
[7,"남서울","영등포","영서S/S #1 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-12 09:00","2017-06-13 18:00","2017-06-12 09:00","2017-06-13 18:00","연속",null,null,null,201704170185]
[8,"남서울","영등포","영서S/S #2 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-16 09:00","2017-06-16 18:00","2017-06-16 09:00","2017-06-16 18:00","연속",null,null,null,201704170186]
[9,"남서울","영등포","영서S/S 영서-영등포#2T/L CB (7672)","345kV 장기 미동작 차단기 조작시험","영서S/S 345kV 영서-영등포#2T/L CB(7672) 조작시험","2017-06-02 11:00","2017-06-02 12:00","2017-06-02 11:00","2017-06-02 12:00","당일",null,null,null,201704270104]
[10,"남서울","영등포","영서S/S TIE-영서-영등포#2T/L CB (7600)","345kV 장기 미동작 차단기 조작시험","영서S/S 345kV 영등포#2T/L TIE CB(7600) 조작시험","2017-06-02 10:00","2017-06-02 11:00","2017-06-02 10:00","2017-06-02 11:00","당일",null,null,null,201704270103]
[11,"남서울","직할","영등포S/S 345kV #1 Sh.R","'16~'17년도 남서울직할 변전협력회사 총액공사","345kV #1Sh.R 보통점검","2017-06-20 09:00","2017-06-20 18:00","2017-06-20 09:00","2017-06-20 18:00","당일",null,null,null,201704200080]
[12,"남서울","직할","영등포S/S 345kV #3Sh.R","'16~'17년도 남서울직할 변전협력회사 총액공사","345kV #3Sh.R 및 #3Sh.R GIS 하자점검","2017-06-19 09:00","2017-06-19 18:00","2017-06-19 09:00","2017-06-19 18:00","당일",null,null,null,201704200081]
[13,"남서울","직할","영등포S/S 345kV 70 BUS","영등포S/S 345kV 모선보호반(#70BUS) 교체공사","영등포S/S 345kV 모선보호반(#70BUS) 교체공사","2017-06-05 09:30","2017-06-09 18:00","2017-06-05 09:30","2017-06-09 18:00","연속",null,null,"신뢰도개선",201704050016]
[14,"남서울","직할","영등포S/S 345kV 75 BUS","영등포S/S 345kV 모선보호반(#75BUS) 교체공사","영등포S/S 345kV 모선보호반(#75BUS) 교체공사","2017-06-12 09:30","2017-06-16 18:00","2017-06-12 09:30","2017-06-16 18:00","연속",null,null,"신뢰도개선",201704050017]
[15,"인천","김포","345kV신김포S/S 신김포 - 서인천#T/L CB (7572)","신김포S/S 345kV 신김포-서인천T/L 7572CB 기기점검","신김포S/S 345kV 신김포-서인천T/L 7572CB 기기점검","2017-06-26 10:00","2017-06-26 18:00","2017-06-26 10:00","2017-06-26 18:00","당일",null,null,null,201704130278]
[16,"인천","김포","345kV신김포S/S 신김포 - 신인천#T/L CB (7471)","신김포S/S 345kV 신김포-신인천T/L 7471CB 기기점검","신김포S/S 345kV 신김포-신인천T/L 7471CB 기기점검","2017-06-27 10:00","2017-06-27 18:00","2017-06-27 10:00","2017-06-27 18:00","당일",null,null,null,201704130279]
[17,"인천","김포","신김포S/S 345KV #2Sh.R - TIE CB(7200)","신김포S/S 345kV #2Sh.R TIE 7200CB 기기점검","신김포S/S 345kV #2Sh.R TIE 7200CB 기기점검","2017-06-22 10:00","2017-06-22 18:00","2017-06-22 10:00","2017-06-22 18:00","당일",null,null,null,201704130282]
[18,"인천","김포","신김포S/S 345KV 신김포-신인천T/L TIE CB(7400)","신김포S/S 345kV 신김포-신인천T/L TIE 7400CB 기기점검","신김포S/S 345kV 신김포-신인천T/L TIE 7400CB 기기점검","2017-06-21 10:00","2017-06-21 18:00","2017-06-21 10:00","2017-06-21 18:00","당일",null,null,null,201704130281]
[19,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥영흥T/L 피뢰기설치 및 전선접속개소 교체공사","345kV 신시흥영흥T/L 피뢰기설치 및 전선접속개소 교체공사 -피뢰기 설치 : No.22~26,55~82(33기) -#3T/L 전선접속개소교체공사 병행, No.54~55","2017-06-24 08:00","2017-06-29 18:00","2017-06-24 08:00","2017-06-29 18:00","연속",null,null,null,201704170063]
[20,"인천","시흥","신시흥영흥TP#1 T/L","신시흥영흥TP #1T/L 보호반 대체공사","신시흥영흥TP #1T/L 보호반 대체공사","2017-06-24 10:00","2017-06-28 18:00","취소","취소","연속",null,null,null,201704150019]
[21,"인천","시흥","신시흥영흥TP#2 T/L","345kV 신시흥영흥T/L 피뢰기설치 공사","345kV 신시흥영흥#4T/L 피뢰기설치 공사 -피뢰기 설치 : No.22~26,55~82(33기)","2017-06-19 08:00","2017-06-23 18:00","2017-06-19 08:00","2017-06-23 18:00","연속",null,null,null,201704170066]
[22,"인천","시흥","신시흥영흥TP#2 T/L","신시흥영흥TP #2T/L 보호반 대체공사","신시흥영흥TP #2T/L 보호반 대체공사","2017-06-19 10:00","2017-06-23 18:00","취소","취소","연속",null,null,null,201704150018]
[23,"인천","시흥","신시흥영흥TP#3 T/L","345kV 신시흥영흥T/L 피뢰기설치 및 전선접속개소 교체공사","345kV 신시흥영흥#1T/L 피뢰기설치 및 전선접속개소 교체공사 -피뢰기 설치 : No.22~26,55~82(33기) -#3T/L 전선접속개소 교체공사, No.54~55","2017-06-24 08:00","2017-06-28 18:00","2017-06-24 08:00","2017-06-28 18:00","연속",null,null,null,201704170072]
[24,"인천","시흥","신시흥영흥TP#4 T/L","345kV 신시흥영흥T/L 피뢰기설치 공사","345kV 신시흥영흥#4T/L 피뢰기설치 공사 -피뢰기 설치 : No.22~26,55~82,183~184(35기)","2017-06-19 08:00","2017-06-23 18:00","2017-06-19 08:00","2017-06-23 18:00","연속",null,null,null,201704170082]
[25,"인천","시흥","영흥1TP-영흥2TP#1 T/L","345kV 영흥TP연락#1T/L 정밀점검","345kV 영흥TP연락#1T/L 정밀점검(8기)","2017-06-28 09:00","2017-06-28 18:00","2017-06-28 09:00","2017-06-28 18:00","당일",null,null,null,201704170086]
[26,"인천","시흥","영흥1TP-영흥2TP#2 T/L","345kV 영흥TP연락#2T/L 정밀점검 및 피뢰기설치 공사","345kV 영흥TP연락#2T/L 정밀점검 및 피뢰기설치 공사 -정밀점검 : No.1~8(8기) -피뢰기설치 : 신시흥영흥#1T/L 피뢰기설치공사 병행(6기)","2017-06-29 08:00","2017-06-29 18:00","2017-06-29 08:00","2017-06-29 18:00","당일",null,null,null,201704170091]
[27,"인천","인천","서인천C/C 345kV #3 Sh.R","서인천CC 7B79(#3Sh.R) GIS 초기점검 공사","서인천CC 7B79(#3Sh.R) GIS 초기점검 및 #3Sh.R 물청소","2017-06-22 09:00","2017-06-22 18:00","2017-06-22 09:00","2017-06-22 18:00","당일",null,null,null,201704120188]
[28,"인천","인천","서인천C/C 345kV #4 Sh.R","서인천CC 7A79(#4Sh.R) GIS 초기점검 공사","서인천CC 7A79(#4Sh.R) GIS 초기점검 및 #4Sh.R 물청소","2017-06-23 09:00","2017-06-23 18:00","2017-06-23 09:00","2017-06-23 18:00","당일",null,null,null,201704120189]
[29,"인천","인천","서인천C/C 신부평#2T/L Sh.R(#1 Sh.R) CB","서인천CC 7379(#1Sh.R) GIS 초기점검 및 #1Sh.R 물청소","서인천CC 7379(#1Sh.R) GIS 초기점검 및 #1Sh.R 물청소","2017-06-19 09:00","2017-06-19 18:00","2017-06-19 09:00","2017-06-19 18:00","당일",null,null,null,201704120186]
[30,"인천","인천","서인천C/C 신부평#3T/L Sh.R(#2 Sh.R) CB","서인천CC #2Sh.R 및 GIS 초기점검 공사","서인천CC 7479(#2Sh.R) GIS 및 #2Sh.R 보통점검, 물청소 - 7479(#2Sh.R) GIS 초기점검 - #2Sh.R 보통점검 및 물청소","2017-06-20 09:00","2017-06-21 18:00","2017-06-20 09:00","2017-06-21 18:00","연속",null,null,null,201704120187]
[31,"인천","인천","서인천CC신부평#4 T/L","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 서인천C/C 7A Bay(7A72) CB 및 관련GIS 대체","2017-06-16 10:00","2017-07-12 17:00","2017-06-16 10:00","2017-07-12 17:00","연속",null,null,null,201704170038]
[32,"인천","인천","신가좌S/S #2 M.Tr A","신가좌S/S #2M.Tr 휴전작업","신가좌S/S #2M.Tr 휴전작업 - #2M.Tr 1차(7372) GIS 보통점검 - #2M.Tr 2차(6244) GIS 보통점검","2017-06-27 09:00","2017-06-28 18:00","2017-06-27 09:00","2017-06-28 18:00","연속",null,null,null,201704120192]
[33,"인천","인천","신가좌가정#1TL-신가좌신시흥#1T/L CB (7200)","신가좌S/S 7200 보통점검 공사","신가좌S/S 7200 보통점검 공사","2017-06-26 09:00","2017-06-26 18:00","2017-06-26 09:00","2017-06-26 18:00","당일",null,null,null,201704120191]
[34,"인천","인천","신경서S/S 신경서인천CC#1T/L CB (7271)","신경서S/S 7271 GIS 보통점검 공사","신경서S/S 7271 GIS 보통점검 공사","2017-06-09 09:00","2017-06-09 18:00","2017-06-09 09:00","2017-06-09 18:00","당일",null,null,null,201704120180]
[35,"인천","인천","신경서S/S 신경서인천CC#1T/L-#2M.Tr 1차CB (7200)","신경서S/S 7200 GIS 보통점검 공사","신경서S/S 7200 GIS 보통점검 공사","2017-06-12 09:00","2017-06-12 18:00","2017-06-12 09:00","2017-06-12 18:00","당일",null,null,null,201704120181]
[36,"인천","인천","신인천C/C 71-72-0 SEC CB (71-72-0)","신인천CC 71-72-0 SEC GIS 보통점검 공사","신인천CC 71-72-0 SEC GIS 보통점검 공사","2017-06-13 09:00","2017-06-13 18:00","2017-06-13 09:00","2017-06-13 18:00","당일",null,null,null,201704120182]
[37,"인천","인천","신인천C/C 75-76-0 SEC CB (75-76-0)","신인천CC 75-76-0 SEC GIS 초기점검 공사","신인천CC 75-76-0 SEC GIS 초기점검 공사","2017-06-14 09:00","2017-06-14 18:00","2017-06-14 09:00","2017-06-14 18:00","당일",null,null,null,201704120183]
[38,"인천","인천","신인천C/C 76-77-0 SEC CB (76-77-0)","신인천CC 76-77-0 SEC GIS 초기점검 공사","신인천CC 76-77-0 SEC GIS 초기점검 공사","2017-06-15 09:00","2017-06-15 18:00","2017-06-15 09:00","2017-06-15 18:00","당일",null,null,null,201704120184]
[39,"인천","인천","인천CC S/Y #2Tie-Tr A","인천CC #2TIE-Tr 2차 GIS 보통점검 공사","인천CC #2TIE-Tr 2차 GIS 보통점검 공사","2017-06-05 09:00","2017-06-05 18:00","2017-06-05 09:00","2017-06-05 18:00","당일",null,null,null,201704120177]
[40,"인천","인천","인천CC S/Y 신경서 인천CC#1T/L CB (7271)","인천CC 7271 GIS 초기점검 공사","인천CC 7271 GIS 초기점검 공사","2017-06-07 09:00","2017-06-07 18:00","2017-06-07 09:00","2017-06-07 18:00","당일",null,null,null,201704120178]
[41,"인천","인천","인천CC S/Y 신경서-인천CC#1T/L-TIE CB (7200)","인천CC 7200 GIS 초기점검 공사","인천CC 7200 GIS 초기점검 공사","2017-06-08 09:00","2017-06-08 18:00","2017-06-08 09:00","2017-06-08 18:00","당일",null,null,null,201704120179]
[42,"인천","인천","포스코S/Y 신경서포스코SY#1T/L-TIE CB (7300)","362kV GIS 정밀점검 공사 (포스코S/Y 7300)","362kV GIS 정밀점검 공사 (포스코S/Y 7300) - GIS 정밀점검 공사","2017-06-26 08:00","2017-06-28 18:00","2017-06-26 08:00","2017-06-28 18:00","연속",null,null,null,201704120175]
[43,"인천","인천","포스코S/Y 포스코#1Step-Up-Tr T/L CB (7172)","362kV GIS 정밀점검 공사 (포스코S/Y 7172)","362kV GIS 정밀점검 공사 (포스코S/Y 7172) - GIS 정밀점검 공사","2017-06-15 08:00","2017-06-17 18:00","2017-06-15 08:00","2017-06-17 18:00","연속",null,null,null,201704120173]
[44,"인천","인천","포스코S/Y 포스코#2Step-Up-Tr T/L CB (7272)","362kV GIS 정밀점검 공사 (포스코S/Y 7272)","362kV GIS 정밀점검 공사 (포스코S/Y 7272) - GIS 정밀점검 공사","2017-06-01 08:00","2017-06-03 18:00","2017-06-01 08:00","2017-06-03 18:00","연속",null,null,null,201704120170]
[45,"인천","인천","포스코S/Y 포스코#3Step-Up-Tr T/L CB (7372)","362kV GIS 정밀점검 공사 (포스코S/Y 7372)","362kV GIS 정밀점검 공사 (포스코S/Y 7372) - GIS 정밀점검 공사","2017-06-29 08:00","2017-07-01 18:00","2017-06-29 08:00","2017-07-01 18:00","연속",null,null,null,201704120176]
[46,"인천","인천","포스코CC인천TP#1 T/L","362kV GIS 정밀점검 공사 (포스코S/Y 7171)","362kV GIS 정밀점검 공사 (포스코S/Y 7171) - GIS 정밀점검 공사 - 가스누기보수 작업","2017-06-07 08:00","2017-06-09 18:00","2017-06-07 08:00","2017-06-09 18:00","연속",null,null,null,201704120171]
[47,"인천","인천","포스코SY인천CC#1T/L-#1GEN STEPUP TIE CB (7100)","362kV GIS 정밀점검 공사 (포스코S/Y 7100)","362kV GIS 정밀점검 공사 (포스코S/Y 7100) - GIS 정밀점검 공사","2017-06-12 08:00","2017-06-14 18:00","2017-06-12 08:00","2017-06-14 18:00","연속",null,null,null,201704120172]
[48,"인천","인천","포스코파워S/Y 신경서포스코SY#1T/L CB (7371)","362kV GIS 정밀점검 공사 (포스코S/Y 7371)","362kV GIS 정밀점검 공사 (포스코S/Y 7371) - GIS 정밀점검 공사","2017-06-20 08:00","2017-06-22 18:00","2017-06-20 08:00","2017-06-22 18:00","연속",null,null,null,201704120174]
[49,"인천","직할","서인천CC신부평#2 T/L","서인천CC-신부평#2T/L OF케이블 절연유 및 가스 보충","서인천CC-신부평#2T/L OF케이블 절연유 및 가스 보충","2017-06-14 09:00","2017-06-14 18:00","2017-06-14 09:00","2017-06-14 18:00","당일",null,null,null,201704140123]
[50,"인천","직할","서인천CC신부평#3 T/L","서인천CC-신부평#3T/L OF케이블 절연유 및 가스 보충","서인천CC-신부평#3T/L OF케이블 절연유 및 가스 보충","2017-06-15 09:00","2017-06-15 18:00","2017-06-15 09:00","2017-06-15 18:00","당일",null,null,null,201704140130]
[51,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 보호반 대체","신부평S/S #2M.Tr 보호반 대체","2017-06-12 09:00","2017-06-16 18:00","2017-06-12 09:00","2017-06-16 18:00","연속",null,null,null,201704180119]
[52,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 보호반 대체","신부평S/S #3M.Tr 보호반 대체","2017-06-19 09:00","2017-06-23 18:00","2017-06-19 09:00","2017-06-23 18:00","연속",null,null,null,201704180120]
[53,"경기북부","구리","미금S/S #3 M.Tr A","미금S/S 345kV #3M.Tr 정밀점검공사","미금S/S 345kV #3M.Tr 정밀점검공사. 3차 GPT 점검, 3차 LA 점검","2017-06-05 09:00","2017-06-16 18:00","2017-06-05 09:00","2017-06-16 18:00","연속",null,null,null,201703090292]
[54,"경기북부","구리","미금S/S 345kV #3 Sh.R","미금S/S #3Sh.R 하자 설비 교체공사","o 공사내용 : 200MVAR Sh.R 교체(1대) o 공사업체 : 효성중공업","2017-06-13 08:00","2017-06-25 17:00","2017-06-21 08:00","2017-07-03 17:00","연속",null,null,null,201703240094]
[55,"경기북부","구리","미금S/S STATCOM M.Tr CB","미금S/S STATCOM M.Tr, AUX M.TR 정밀점검공사","미금S/S 345kV STATCOM M.Tr, AUX M.TR 정밀점검공사","2017-06-26 09:00","2017-07-07 18:00","2017-06-26 09:00","2017-07-07 18:00","연속",null,null,null,201703090301]
[56,"경기북부","구리","신포천S/S 신포천-포천CC#1T/L GIS","신포천S/S 신포천-포천CC#1T/L GIS 보통점검 (7371)","신포천S/S 신포천-포천CC#1T/L GIS 보통점검 (7371)","2017-06-13 10:00","2017-06-13 18:00","2017-06-13 10:00","2017-06-13 18:00","당일",null,null,null,201704070307]
[57,"경기북부","구리","신포천S/S 신포천-포천CC#1T/L GIS","신포천S/S 신포천-포천CC#1T/L GIS 보통점검 (7300)","신포천S/S 신포천-포천CC#1T/L GIS 보통점검 (7300)","2017-06-14 10:00","2017-06-14 18:00","2017-06-14 10:00","2017-06-14 18:00","당일",null,null,null,201704070311]
[58,"경기북부","구리","신포천S/S 신포천-포천CC#2T/L GIS","신포천S/S 신포천-포천CC#2T/L GIS 보통점검 (7471)","신포천S/S 신포천-포천CC#2T/L GIS 보통점검 (7471)","2017-06-15 10:00","2017-06-15 18:00","2017-06-15 10:00","2017-06-15 18:00","당일",null,null,null,201704070318]
[59,"경기북부","구리","신포천S/S 신포천-포천LNGCC#1T/L GIS","신포천S/S 신포천-포천LNGCC#1T/L GIS 보통점검 (7171)","신포천S/S 신포천-포천LNGCC#1T/L GIS 보통점검 (7171)","2017-06-20 10:00","2017-06-20 18:00","2017-06-20 10:00","2017-06-20 18:00","당일",null,null,null,201704070331]
[60,"경기북부","구리","신포천S/S 신포천-포천LNGCC#2 T/L GIS","신포천S/S 신포천-포천LNGCC#2T/L GIS 보통점검 (7271)","신포천S/S 신포천-포천LNGCC#2T/L GIS 보통점검 (7271)","2017-06-21 10:00","2017-06-21 18:00","2017-06-21 10:00","2017-06-21 18:00","당일",null,null,null,201704070332]
[61,"경기북부","구리","포천C/C 신포천-포천CC #1T/L GIS","포천C/C 신포천-포천CC #1T/L GIS (7171) 제작사 하자점검","포천C/C 신포천-포천CC #1T/L GIS (7171) 제작사 하자점검 - 유압누유 관련 제작사 합동점검","2017-06-08 10:00","2017-06-08 18:00","2017-06-08 10:00","2017-06-08 18:00","당일",null,null,null,201704070298]
[62,"경기북부","직할","신가평신의정부#2 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","345kV 신가평-신의정부#2T/L 피뢰기 설치공사 시행 - No.98~138호 41기(154kV 신의정부내촌#2T/L 하단병가)","2017-06-17 08:00","2017-06-23 18:00","2017-06-17 08:00","2017-06-23 18:00","연속",null,null,null,201704110147]
[63,"경기북부","직할","신의정부양주#2 T/L","17년 362kV GIS 정밀점검 공사","362kV GIS 정밀점검","2017-06-13 09:00","2017-06-16 18:00","2017-06-13 09:00","2017-06-16 18:00","연속",null,null,null,201704130085]
[64,"경기북부","직할","양주S/S #1 M.Tr A","경기북부 직할 345kV M.Tr 정밀점검","경기북부 직할 345kV M.Tr 정밀점검","2017-06-12 09:00","2017-06-16 18:00","2017-06-12 09:00","2017-06-16 18:00","연속",null,null,null,201704130001]
[65,"경기북부","직할","양주S/S #2 M.Tr A","17년 362kV GIS 정밀점검 공사","362kV GIS 정밀점검","2017-06-19 09:00","2017-06-23 18:00","2017-06-19 09:00","2017-06-23 18:00","연속",null,null,null,201704130086]
[66,"경기북부","직할","양주S/S #4 M.Tr A","17년 GIS 정밀점검공사","GIS 정밀점검","2017-06-01 09:00","2017-06-02 18:00","2017-06-01 09:00","2017-06-02 18:00","연속",null,null,null,201704130109]
[67,"경기북부","직할","양주S/S SVC M.Tr CB","17년 362kV GIS 정밀점검 공사","362kV GIS 정밀점검","2017-06-26 09:00","2017-06-30 18:00","2017-06-26 09:00","2017-06-30 18:00","연속",null,null,null,201704130087]
[68,"경기북부","직할","양주중부#1 T/L","345kV 양주-중부#1T/L 전선교체공사","345kV 양주-중부#1T/L No.22-26 접속개소 전선교체공사","2017-06-24 07:00","2017-06-26 18:00","2017-06-24 07:00","2017-06-26 18:00","연속",null,null,null,201704130267]
[69,"경기북부","직할","양주중부#2 T/L","345kV 양주-중부#2T/L 전선교체공사","345kV 양주-중부#2T/L No.3-5, 22-26 접속개소 전선교체공사","2017-06-27 07:00","2017-06-30 18:00","2017-06-27 07:00","2017-06-30 18:00","연속",null,null,null,201704130268]
[70,"경기북부","파주","신김포신파주#2 T/L","신파주S/S CLR 설치공사","1. 362kV GIB 일부철거 및 설치 2. 345kV CLR 설치","2017-06-01 09:00","2017-06-15 18:00","2017-06-01 09:00","2017-06-15 18:00","연속",null,null,"신뢰도개선",201704060052]
[71,"경기북부","파주","신덕은S/S 345kV #1 BUS","신덕은S/S 345kV SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 설치 ㅇ 기타 부대공사 1식 * LG Display 전력공급 송전선로 신설","2017-06-19 09:00","2017-06-27 18:00","2017-06-19 09:00","2017-06-27 18:00","연속",null,null,null,201704130151]
[72,"경기북부","파주","신파주S/S #1SVC Tr CB","345kV 신파주S/S SVC 투수블럭 포장공사","SVC FC5 투수블럭 포장","2017-06-12 09:30","2017-06-18 18:00","2017-06-21 09:30","2017-06-27 18:00","연속",null,null,null,201704040093]
[73,"경기북부","파주","신파주S/S #3 M.Tr A","17년 파주전력지사 362kV GIS 정밀점검공사","신파주S/S CLR 설치 및 GIS 정밀점검관련 공용 7400 CB 휴전","2017-06-02 09:00","2017-06-02 18:00","2017-06-02 09:00","2017-06-02 18:00","당일",null,null,null,201704170382]
[74,"경기북부","파주","신파주S/S 345kV #76 BUS","신파주S/S #75-76 SEC GIS 정밀점검공사","신파주S/S #75-76SEC CB 및 관련DS 정밀점검","2017-06-01 08:00","2017-06-02 18:00","2017-06-01 08:00","2017-06-02 18:00","연속",null,null,null,201702280192]
[75,"경기북부","파주","신파주신덕은#1 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","신덕은-원흥T/L No.62-68 장기사용전력선 교체 4회선 병가구간","2017-06-16 08:00","2017-06-20 18:00","2017-06-16 08:00","2017-06-20 18:00","연속",null,null,null,201704100203]
[76,"경기북부","파주","신파주신덕은#2 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","신덕은-수색T/L No.62-68 장기사용전력선 교체 4회선 병가구간","2017-06-21 08:00","2017-06-26 18:00","2017-06-21 08:00","2017-06-26 18:00","연속",null,null,null,201704100209]
[77,"경기북부","파주","신파주양주#1 T/L","신파주S/S CLR 설치공사","1.신파주-신김포 #2T/L 3상 GIB 설치(3층 ~지상 1층)- 설치시 근접작업 2. CLR 설치 - 장비사용시 근접선로 안전작업위한 3. 신김포-신파주#2 T/L 붓싱철거 4. 기타 부대공사","2017-06-07 09:00","2017-06-12 18:00","2017-06-07 09:00","2017-06-12 18:00","연속",null,null,null,201704060054]
[78,"경기북부","파주","신파주양주#2 T/L","신파주S/S CLR 설치공사","1.신파주-신김포 #2T/L A상 WALL BUSHING 철거","2017-06-02 09:00","2017-06-03 18:00","2017-06-02 09:00","2017-06-03 18:00","연속",null,null,null,201704060053]
[79,"경기북부","파주","신김포신파주#1 T/L","신파주S/S 345kV CLR 설치공사","* 신김포-신파주#1T/L CLR 24시간 무부하 가압 ( CLR 건전성 확인)","2017-06-16 09:30","2017-06-17 09:30","2017-06-16 09:30","2017-06-17 09:30","연속",null,null,null,201704210023]
[80,"경기","군포","신시흥신안산 T/L","345kV 신시흥영흥T/L 피뢰기설치 공사","345kV 신시흥영흥#4T/L 피뢰기설치 공사 -피뢰기 설치 : No.183(1기)","2017-06-18 08:00","2017-06-18 12:00","2017-06-18 08:00","2017-06-18 12:00","당일",null,null,"신뢰도개선",201704170084]
[81,"경기","성남","신수원S/S #1 M.Tr A","17년 성남변전협력회사 총액공사","96P 전선관 개선, 6144 GIS 타임측정","2017-06-10 09:00","2017-06-10 18:00","2017-06-10 09:00","2017-06-10 18:00","당일",null,null,null,201704140170]
[82,"경기","성남","신수원S/S 신수원삼성#1T/L GIS","17년 성남변전협력회사 총액공사","7372 GIS 보통점검","2017-06-16 10:00","2017-06-16 18:00","2017-06-16 10:00","2017-06-16 18:00","당일",null,null,null,201704140062]
[83,"경기","성남","신수원S/S 신수원삼성#1T/L-TIE GIS","17년 성남변전협력회사 총액공사","7300 GIS 보통점검","2017-06-02 10:00","2017-06-02 18:00","2017-06-02 10:00","2017-06-02 18:00","당일",null,null,null,201704140061]
[84,"경기","성남","신수원S/S 신수원삼성#2T/L GIS","17년 성남변전협력회사 총액공사","7472 GIS 보통점검","2017-06-12 10:00","2017-06-12 18:00","2017-06-12 10:00","2017-06-12 18:00","당일",null,null,null,201704140065]
[85,"경기","성남","신시흥신성남#1 T/L","345kV 신시흥영흥T/L 피뢰기설치 공사","345kV 신시흥영흥#4T/L 피뢰기설치 공사 -피뢰기 설치 : No.184(1기)","2017-06-18 13:00","2017-06-18 17:00","2017-06-18 13:00","2017-06-18 17:00","당일",null,null,null,201704170085]
[86,"경기","성남","신안성서안성#2 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","- 345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69) 시 No.2~11 병가선로 안전이격확보","2017-06-06 08:00","2017-06-06 18:00","2017-06-06 08:00","2017-06-06 18:00","당일",null,null,null,201704120106]
[87,"경기","성남","신안성신수원#1 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","- 345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","2017-06-04 08:00","2017-06-10 18:00","2017-06-04 08:00","2017-06-10 18:00","연속",null,null,null,201704190068]
[88,"경기","성남","신용인S/S #2 M.Tr A","17년 성남변전협력회사 총액공사","2차LA 하자점검, 6244타임측정 ,PCT NCT이설","2017-06-01 10:00","2017-06-01 18:00","2017-06-01 10:00","2017-06-01 18:00","당일",null,null,null,201704140059]
[89,"경기","성남","동서울신용인#1 T/L","345kV 신용인-동서울T/L 태전지구 지중화사업","○ 설치 : ACSR480㎟×2B×2C×0.2km. C/H2기 ○ 철거 : ACSR480㎟×2B×2C×2.5km. 철탑8기","2017-06-30 08:00","2017-07-07 18:00","2017-06-30 08:00","2017-07-07 18:00","연속",null,null,null,201704100486]
[90,"경기","성남","신용인신수원 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)시 안전이격확보차 병가선로 휴전시행","2017-06-04 08:00","2017-06-04 18:00","2017-06-04 08:00","2017-06-04 18:00","당일",null,null,null,201704190079]
[91,"경기","직할","화성서서울#2 T/L","345kV 화성서서울#2T/L GIS 보통 및 LA교체","345kV 화성서서울#2T/L GIS 보통(7400,7471) 및 LA교체","2017-06-20 10:00","2017-06-20 18:00","2017-06-20 10:00","2017-06-20 18:00","당일",null,null,null,201704110305]
[92,"경기","직할","화성S/S #3M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-06-21 09:00","2017-06-27 18:00","2017-06-21 09:00","2017-06-27 18:00","당일",null,null,null,201703140424]
[93,"경기","직할","화성S/S #4M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-06-28 09:00","2017-07-04 18:00","2017-06-28 09:00","2017-07-04 18:00","당일",null,null,null,201703140423]
[94,"경기","직할","화성S/S #1M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-06-12 09:00","2017-06-18 18:00","2017-06-12 09:00","2017-06-18 18:00","당일",null,null,null,201703140421]
[95,"강원","강릉","신양양_양양PP T/L","2016~17년 송전정비협력회사 총액공사","○ 송전선로용 피뢰기 설치(신양양-양양PP T/L No.1 등 5기, 15SET)","2017-06-12 07:30","2017-06-13 18:00","2017-06-12 07:30","2017-06-13 18:00","매일",null,null,null,201704090062]
[96,"강원","동해","동해S/S #1 M.Tr 1차 CB (7172)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S #1 M.Tr 1차 CB 정밀점검(7172)","2017-06-14 09:30","2017-06-16 18:00","2017-06-14 09:30","2017-06-16 18:00","연속",null,null,null,201704100248]
[97,"강원","동해","동해S/S #3 M.Tr A","2017년 동해전력지사 변전협력회사 총액공사","1. #3M.Tr 누유 및 과열개소 보수 2. 7600 GIS 보통점검 3. 7672 GIS 보통점검 4. 6344 GIS 초기점검 5. 1차 PT 초기점검","2017-06-19 09:30","2017-06-20 18:00","2017-06-19 09:30","2017-06-20 18:00","연속",null,null,null,201704100284]
[98,"강원","동해","동해S/S 72BAY TIE CB (7200)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 72BAY TIE CB 정밀점검(7200)","2017-06-21 09:30","2017-06-23 18:00","2017-06-21 09:30","2017-06-23 18:00","연속",null,null,null,201704100257]
[99,"강원","동해","동해S/S 73BAY TIE CB (7300)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 73BAY TIE CB 정밀점검(7300)","2017-06-28 09:30","2017-06-30 18:00","2017-06-28 09:30","2017-06-30 18:00","연속",null,null,null,201704100265]
[100,"강원","동해","동해S/S 75BAY TIE CB (7500)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 75BAY TIE CB 보통점검(7500)","2017-06-12 09:30","2017-06-12 18:00","2017-06-12 09:30","2017-06-12 18:00","당일",null,null,null,201704100277]
[101,"강원","동해","동해S/S 동해-삼척GP#1 T/L CB (7571)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-삼척GP#1 T/L GIS 보통점검(7571)","2017-06-08 09:30","2017-06-08 18:00","2017-06-08 09:30","2017-06-08 18:00","당일",null,null,null,201704100274]
[102,"강원","동해","동해S/S 동해-삼척GP#2 T/L CB (7671)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-삼척GP#2 T/L CB 보통점검(7671)","2017-06-15 09:30","2017-06-15 18:00","2017-06-15 09:30","2017-06-15 18:00","당일",null,null,null,201704100279]
[103,"강원","동해","동해S/S 동해-신양양 T/L CB (7371)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 동해-신양양 T/L CB 정밀점검(7371)","2017-06-25 09:30","2017-06-27 18:00","2017-06-25 09:30","2017-06-27 18:00","연속",null,null,null,201704100262]
[104,"강원","동해","동해S/S 신제천-동해#1 T/L-#1M.Tr 1차 CB (7100)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 신제천-동해#1 T/L-#1M.Tr 1차 CB 정밀점검(7100)","2017-06-11 09:30","2017-06-13 18:00","2017-06-11 09:30","2017-06-13 18:00","연속",null,null,null,201704100245]
[105,"강원","동해","동해S/S 신제천-동해#1T/L CB (7171)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 신제천-동해#1T/L GIS 정밀점검(7171)","2017-06-07 09:30","2017-06-09 18:00","2017-06-07 09:30","2017-06-09 18:00","연속",null,null,null,201704100240]
[106,"강원","동해","동해S/S 신제천-동해#2 T/L CB (7271)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 신제천-동해#2 T/L CB 정밀점검(7271)","2017-06-18 09:30","2017-06-20 18:00","2017-06-18 09:30","2017-06-20 18:00","연속",null,null,null,201704100254]
[107,"강원","태백","신태백S/S 345kV #2 Sh.R","16~17 태백전력지사 변전정비 총액공사","신태백S/S 362kV #2Sh.R 7479CB 보통점검(6/8) 신태백S/S 362kV #2Sh.R 7471CB 보통점검(6/9)","2017-06-08 10:00","2017-06-09 18:00","2017-06-08 10:00","2017-06-09 18:00","매일",null,null,null,201704180010]
[108,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV 옥외철구 모선 철거","2017-06-27 08:00","2017-06-27 18:00","2017-06-29 08:00","2017-06-29 18:00","연속",null,null,null,201704070176]
[109,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 모선 접속(옥외철구, GIS 동시휴전)","2017-06-09 08:00","2017-06-11 18:00","2017-06-09 08:00","2017-06-11 18:00","연속",null,null,null,201704070169]
[110,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV 옥외철구 모선 철거","2017-06-18 18:00","2017-06-19 18:00","2017-06-21 18:00","2017-06-22 18:00","연속",null,null,null,201704070174]
[111,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","345kV 옥외철구 모선 철거","2017-06-28 08:00","2017-06-28 18:00","2017-06-30 08:00","2017-06-30 18:00","연속",null,null,null,201704070179]
[112,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","345kV 옥외철구 모선 철거","2017-06-17 08:00","2017-06-18 18:00","2017-06-19 08:00","2017-06-20 18:00","연속",null,null,null,201704070172]
[113,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 모선 접속(GIS 휴전)","2017-06-11 18:00","2017-06-14 18:00","2017-06-11 18:00","2017-06-14 18:00","연속",null,null,null,201704070170]
[114,"충북","직할","신제천동해#1 T/L","345kV 신제천S/S GIS화 공사","신제천-동해#1T/L 옥외철구⇒GIS 이설","2017-06-17 08:00","2017-06-26 18:00","2017-06-19 08:00","2017-06-28 18:00","연속",null,null,null,201704070155]
[115,"충북","직할","신제천신영주#1 T/L","345kV 신제천-신영주T/L 전력선 교체공사","전력선 교체 : 6.471km(No.131-146) 가공지선 교체: 4.863km (No.131-139, 143-146) 스페이서댐퍼교체: 624개(전력선교체구간)","2017-06-03 07:00","2017-06-18 18:00","2017-06-03 07:00","2017-06-18 18:00","연속",null,null,null,201704090008]
[116,"충북","직할","신제천신영주#2 T/L","345kV 신제천S/S GIS화 공사","신제천-신영주#2T/L 옥외철구⇒GIS 이설","2017-06-27 08:00","2017-07-03 18:00","2017-06-29 08:00","2017-07-05 18:00","연속",null,null,null,201704070165]
[117,"충북","직할","신제천신충주#2 T/L","345kV 신제천S/S GIS화 공사","신제천-신충주#2T/L 옥외철구⇒GIS 이설","2017-06-17 08:00","2017-06-26 18:00","2017-06-19 08:00","2017-06-28 18:00","연속",null,null,null,201704070156]
[118,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원TL 안전이격확보공사","No.223~226간 안전이격확보(철탑교체 2기)","2017-06-10 08:00","2017-06-12 19:00","2017-06-10 08:00","2017-06-12 19:00","연속",null,null,null,201704090060]
[119,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원TL 안전이격확보공사","No.223~226간 안전이격확보(철탑교체 2기)","2017-06-28 08:00","2017-06-30 19:00","2017-06-28 08:00","2017-06-30 19:00","연속",null,null,null,201704090061]
[120,"충북","청주","신옥천신남원#2 T/L","345kV 신옥천-신남원TL 안전이격확보공사","No.223~226간 안전이격확보(철탑교체 2기)","2017-06-13 08:00","2017-06-27 19:00","2017-06-13 08:00","2017-06-27 19:00","연속",null,null,null,201704090063]
[121,"충북","충주","신진천S/S #3 M.Tr A","2017년 충주전력지사 154kV GIS 정밀점검공사","#3M.Tr 2차 GIS(차단기 및 #1,2BUS DS)정밀점검","2017-06-07 08:00","2017-06-08 18:00","2017-06-07 08:00","2017-06-08 18:00","연속",null,null,null,201704100155]
[122,"대전충남","서산","신당진S/S #1 M.Tr","'17년 서산P/O 345kV 변압기 정밀점검공사","'17년 서산P/O 345kV 변압기 정밀점검공사","2017-06-12 09:00","2017-06-17 18:00","취소","취소","연속",null,null,null,201704070173]
[123,"대전충남","서산","신당진S/S #2 M.Tr","'17년 서산P/O 345kV 변압기 정밀점검공사","'17년 서산P/O 345kV 변압기 정밀점검공사","2017-06-19 09:00","2017-06-24 18:00","2017-06-12 09:00","2017-06-23 18:00","연속",null,null,null,201704070191]
[124,"대전충남","서산","신당진S/S #3 M.Tr","'17년 변전협력회사 총액공사","신당진S/S 345kV #3M.Tr 하자점검 및 1,2,3차 GIS 보통점검","2017-06-26 09:00","2017-06-28 18:00","2017-06-26 09:00","2017-06-28 18:00","연속",null,null,null,201704100879]
[125,"대전충남","서산","신당진S/S 신당진연락#2T/L CB (7771)","'17년 서산P/O 345kV GIS 정밀점검 공사","신당진S/S 345kV 신당진-연락#2T/L GIS(7771) 정밀점검","2017-06-12 10:00","2017-06-16 18:00","2017-06-07 09:00","2017-06-10 18:00","연속",null,null,null,201704100868]
[126,"대전충남","아산","신온양S/S #4 M.Tr A","신온양S/S 345kV #4M.Tr 2차 6444 GIS 정밀점검","○ 345kV #4M.Tr 2차 6444 GIS 정밀점검","2017-06-08 09:00","2017-06-09 18:00","2017-06-08 09:00","2017-06-09 18:00","당일",null,null,null,201704180024]
[127,"대전충남","아산","청양신온양#1 T/L","[송전] 345kV 청양-신온양T/L 전선교체공사","ㅇ전력선 교체(ACSR 480㎟ × 4B) : 9.490c-km - No.56~64, 68~75, 89~98, 102~109,126~127, 137~142","2017-06-15 07:00","2017-06-23 18:00","2017-06-10 07:00","2017-06-17 18:00","연속",null,null,null,201704060125]
[128,"대전충남","아산","청양신온양#2 T/L","[송전] 345kV 청양-신온양T/L 전선교체공사","ㅇ전력선 교체(ACSR 480㎟ × 4B) : 9.490c-km - No.56~64, 68~75, 89~98, 102~109,126~127, 137~142","2017-06-24 07:00","2017-07-14 18:00","2017-06-18 07:00","2017-06-25 18:00","연속",null,null,null,201704060123]
[129,"대전충남","아산","신탕정S/S 345kV #2 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","○ 7172, 7100Bay 내전압시험","2017-06-22 10:00","2017-06-22 16:00","2017-06-22 10:00","2017-06-22 16:00","당일",null,null,null,201704270151]
[130,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","신탕정S/S 71BAY GIS * 3CB 용량대체","2017-06-01 09:00","2017-06-11 18:00","2017-06-01 09:00","2017-06-11 18:00","매일",null,null,null,201704260119]
[131,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","○ 7171Bay 내전압시험","2017-06-23 10:00","2017-06-23 16:00","2017-06-23 10:00","2017-06-23 16:00","당일",null,null,null,201704270152]
[132,"대전충남","청양","신계룡청양 T/L","345kV 신계룡-청양T/L 전력선교체공사","○ No.156~162(15선), No.219~224(18선) 전선교체 - 병행작업 : 345kV 송전선로 보호배전반 교체 (6.10~14) [변전] 345kV 신계룡-청양T/L 피뢰기설치공사 (6.12) [송전]","2017-06-10 07:00","2017-06-14 18:00","2017-06-26 07:00","2017-06-30 18:00","연속",null,null,null,201704060018]
[133,"대전충남","청양","아산보령화력#1 T/L","보령화력 GIS 건물 내진성능보강 및 도장공사","○ 보령화력 345kV GIS 건물 내진성능보강 및 도장","2017-06-03 09:00","2017-06-04 18:00","2017-06-03 09:00","2017-06-04 18:00","연속",null,null,null,201704070243]
[134,"대전충남","청양","청양S/S 345kV #76 BUS","청양S/S #76BUS 보호반 교체","#76BUS 보호반 교체","2017-06-19 09:00","2017-06-21 18:00","2017-06-26 09:00","2017-06-28 18:00","연속",null,null,null,201703080398]
[135,"대전충남","청양","보령TP보령CC#2 T/L","보령화력 항공장애표시구 설치공사(#7, 8)","보령화력 항공장애표시구 설치공사(#7, 8)","2017-06-23 09:00","2017-06-25 17:00","2017-06-23 09:00","2017-06-25 17:00","연속",null,null,null,201704250084]
[136,"대전충남","청양","청양보령TP#2 T/L","보령화력 송전선로 항공장애표시구 설치공사","보령화력 송전선로 항공장애표시구 설치공사(#7, 8호기)","2017-06-09 09:00","2017-06-15 17:00","2017-06-09 09:00","2017-06-15 17:00","연속",null,null,null,201704250083]
[137,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","2017년 군산P/O 170kV 차단기 정밀점검 공사 2017년 군산P/O 345kV 차단기 정밀점검 공사","2017-06-19 09:00","2017-06-30 18:00","2017-06-19 09:00","2017-06-30 18:00","연속",null,null,"신뢰도 개선",201704110007]
[138,"전북","군산","군산새만금#1 T/L","군산새만금#1 T/L","2017년 군산P/O 345kV 차단기 정밀점검 공사","2017-06-19 09:00","2017-06-30 18:00","2017-06-19 09:00","2017-06-30 18:00","연속",null,null,null,201704110018]
[139,"전북","군산","군산새만금#2 T/L","군산-새만금#2T/L","군산P/O 차단기 보통점검공사","2017-06-07 09:00","2017-06-09 18:00","2017-06-07 09:00","2017-06-09 18:00","연속",null,null,null,201704140197]
[140,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L 하자접속함 교체공사","LS제 하자 중간접속함 교체공사","2017-06-26 08:00","2017-07-14 18:00","2017-06-26 08:00","2017-07-14 18:00","연속",null,null,null,201704180154]
[141,"전북","김제","신김제S/S #3 M.Tr A","관내S/S 노후배전반 교체공사","변압기 보호반 및 B/F반 교체","2017-06-05 09:00","2017-06-16 18:00","2017-06-05 09:00","2017-06-16 18:00","연속",null,null,null,201704180109]
[142,"전북","김제","신김제S/S #3 M.Tr A","김제P/O 154KV GIS정밀점검","345KV #3M.TR 2차 GIS 정밀점검","2017-06-19 09:00","2017-06-21 18:00","2017-06-19 09:00","2017-06-21 18:00","연속",null,null,null,201704170264]
[143,"전북","김제","신김제S/S #4 M.Tr A","김제P/O 170KV GIS 정밀점검","#4M.TR 2차 GIS 정밀점검","2017-06-29 09:00","2017-07-01 18:00","2017-06-29 09:00","2017-07-01 18:00","연속",null,null,null,201704170269]
[144,"전북","직할","신남원S/S 신남원-신광주#2 - TIE GIS","신남원S/S 345kV 차단기 정밀점검공사(7800)","- GIS(차단기) 정밀점검","2017-06-19 09:30","2017-06-22 18:00","2017-06-19 09:30","2017-06-22 18:00","연속",null,null,null,201703160053]
[145,"전북","직할","신남원S/S 신남원-신광주#2 T/L GIS","신남원S/S 345kV 차단기 정밀점검공사(7871)","- GIS(차단기) 정밀점검","2017-06-12 09:30","2017-06-15 18:00","2017-06-12 09:30","2017-06-15 18:00","연속",null,null,null,201703160052]
[146,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양T/L 전력선교체공사","○ 전선접속개소 전력선 교체 ( 2.266C-km) - 대상구간 : No.235~238 ○ 스페이서 댐퍼 설치/철거 : 90개/120개 ○ 항공장애표시구 설치/철거 : 10개/8개 ○ 아마롯드 설치 및 기타 부대공사","2017-06-17 07:00","2017-06-21 18:00","취소","취소","연속",null,null,null,201704170367]
[147,"전북","직할","신남원신광주#1 T/L","신남원S/S 345kV 차단기 정밀점검공사(7700) 시험가압","- GIS(차단기) 정밀점검","2017-06-01 13:30","2017-06-01 16:00","2017-06-01 13:30","2017-06-01 16:00","연속",null,null,null,201703170083]
[148,"전북","직할","신남원신광주#2 T/L","신남원S/S 345kV 차단기 정밀점검공사(7871) 시험가압","- GIS(차단기) 정밀점검","2017-06-15 13:30","2017-06-15 16:00","2017-06-15 13:30","2017-06-15 16:00","연속",null,null,null,201703170086]
[149,"전북","직할","신남원신광주#2 T/L","신남원S/S 345kV 차단기 정밀점검공사(7800) 시험가압","- GIS(차단기) 정밀점검","2017-06-22 13:30","2017-06-22 16:00","2017-06-22 13:30","2017-06-22 16:00","연속",null,null,null,201703170087]
[150,"전북","직할","신남원한빛NP#2 T/L","345kV 신남원-한빛#2T/L 전력선 교체공사","No.20~24호 등 8개 내장-내장 구간 6.314C-km 전선교체 34~36호 등 3개 내장-내장구간 154kV 고창-홍농T/L과 병행선로내 작업","2017-06-14 07:00","2017-07-10 18:00","2017-06-14 07:00","2017-07-10 18:00","연속",null,null,"신뢰도 개선",201703070337]
[151,"광주전남","강진","신화순신강진#1 T/L","345kV 신화순-신강진T/L 접속개소 해소공사","접속개소 전선교체 - 구간 : No.132~133 emd 9구간 -전선교체 : acsr 480, 16.666km","2017-06-16 07:00","2017-07-07 18:00","2017-06-23 07:00","2017-07-17 18:00","연속",null,null,null,201704060227]
[152,"광주전남","광주","신광주S/S #2 M.Tr A","신광주S/S #2 M.Tr (인출변경 및 인출GIS연결","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-06-09 07:00","2017-06-20 18:00","2017-06-09 07:00","2017-06-20 18:00","연속",null,null,null,201701250019]
[153,"광주전남","광주","신광주한빛NP#1 T/L","345kV 신광주-한빛NPT/L 전선접속개소해소공사","345kV 신광주-한빛NPT/L 전선접속개소해소 공사구간 : No.112~118호","2017-06-01 07:00","2017-06-05 18:00","2017-06-01 07:00","2017-06-05 18:00","연속",null,null,"신뢰도 개선",201704050070]
[154,"광주전남","광주","신광주한빛NP#2 T/L","345kV 신광주-한빛NPT/L 전선접속개소해소공사","345kV 신광주-한빛NPT/L 전선접속개소해소 공사구간 : No.112~118호","2017-06-06 07:00","2017-06-10 18:00","2017-06-06 07:00","2017-06-10 18:00","연속",null,null,"신뢰도 개선",201704050071]
[155,"광주전남","광주","신화순S/S #1 M.Tr A","신화순S/S #1 M.Tr(변전협력회사공사)","#1S.Tr 대체 관련 M.Tr 보호반 정정 및 시험(시험팀)","2017-06-26 09:00","2017-06-26 18:00","취소","취소","연속",null,null,null,201704060083]
[156,"광주전남","광주","신화순S/S #2 M.Tr A","2017년 광주전력지사 170KV GIS 정밀점검 공사","- 신화순S/S 345KV #2M.Tr 2차 GIS 정밀점검","2017-06-28 09:00","2017-06-30 18:00","2017-06-20 09:00","2017-06-22 18:00","연속",null,null,null,201704140196]
[157,"광주전남","목포","한빛2NP-한빛3NP#4 T/L","한빛-연락#4T/L(LS산전제 유사고장)","- LS산전제 유사고장 공사 - 한빛-연락#4T/L CVT 대체공사","2017-06-12 09:00","2017-06-23 18:00","2017-06-12 09:00","2017-06-23 18:00","연속",null,null,null,201703080018]
[158,"광주전남","순천","광양S/S #1 M.Tr A","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2017-06-20 10:00","2017-09-22 14:00","2017-06-20 10:00","2017-09-22 14:00","연속",null,null,null,201704060063]
[159,"광주전남","순천","광양S/S #3 M.Tr A","345kV 광양S/S #3 M.Tr(1,2차 LA 보통점검)","17년 순천전력 변전협력회사 총액공사 - 345kV 광양S/S #3 M.Tr(1,2차 LA 보통점검)","2017-06-01 09:00","2017-06-01 18:00","2017-06-01 09:00","2017-06-01 18:00","당일",null,null,null,201704100858]
[160,"광주전남","순천","광양율촌CC T/L","345kV 광양-율촌CC T/L(전력선 교체)","345kV 신남원-광양 등 4개T/L 전선접속개소 해소공사 - 광양-율촌CC T/L 103~136호간 전력선 교체","2017-06-13 07:00","2017-06-30 18:00","2017-06-20 07:00","2017-07-08 18:00","연속",null,null,null,201704100731]
[161,"광주전남","순천","신남원광양#2 T/L","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2017-06-20 10:00","2017-09-22 14:00","2017-06-20 10:00","2017-09-22 14:00","연속",null,null,null,201704060062]
[162,"광주전남","순천","여수T/P #1 Tie-Tr","345kV 여수T/P #1M.Tr(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - 2차 GIS 보조계전기 교체","2017-06-14 10:00","2017-06-14 18:00","2017-06-14 10:00","2017-06-14 18:00","당일",null,null,null,201704070133]
[163,"광주전남","순천","여수T/P #2 Tie-Tr","345kV 여수T/P #2M.Tr(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - 2차 GIS 보조계전기 교체","2017-06-15 10:00","2017-06-15 18:00","2017-06-15 10:00","2017-06-15 18:00","당일",null,null,null,201704070136]
[164,"광주전남","순천","율촌CC여수TP T/L","2017년 가공송전 순시점검 위탁공사 (정밀점검)","- 정밀점검 (68호~여수TP, 131기)","2017-06-05 08:00","2017-06-07 18:00","2017-06-05 08:00","2017-06-07 18:00","매일",null,null,null,201703200163]
[165,"대구경북","경산","신경산대구#1 T/L","345kV 울주-신경산 등 3개 T/L 전선교체공사","154kV 경산-자인T/L 전선교체공사 안전확보 (#2T/L No.16-24)","2017-06-20 08:00","2017-06-28 18:00","2017-06-17 08:00","2017-06-25 18:00","연속",null,null,null,201704050012]
[166,"대구경북","경산","신경산대구#2 T/L","345kV 울주-신경산 등 3개 T/L 전선교체공사","154kV 경산-자인T/L 전선교체공사 안전확보 (#1T/L No.16-24)","2017-06-11 08:00","2017-06-19 18:00","2017-06-08 08:00","2017-06-16 18:00","연속",null,null,null,201704050010]
[167,"대구경북","구미","선산S/S #1 M.Tr A","선산S/S 154kV 옥외철구설비 GIS화 공사","T-BUS 철거","2017-06-07 09:00","2017-06-08 18:00","취소","취소","연속",null,null,null,201704090034]
[168,"대구경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구설비 GIS화 공사","파일시공 관련 안전확보","2017-06-22 09:00","2017-06-26 18:00","2017-06-28 09:00","2017-06-29 18:00","연속",null,null,null,201704090043]
[169,"대구경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구설비 GIS화 공사","파일시공 관련 안전확보","2017-06-15 09:00","2017-06-18 18:00","취소","취소","연속",null,null,null,201704090039]
[170,"대구경북","달성","대구S/S #3 M.Tr 1차 CB (7372)","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-16 15:00","2017-06-16 18:00","2017-06-16 09:30","2017-06-16 12:00","당일",null,null,null,201704070140]
[171,"대구경북","달성","대구S/S 북경남-대구#2T/L CB (7371)","2017년 달성변전협력 총액공사","장기미동작타임측정(7371)","2017-06-16 09:30","2017-06-16 11:30","취소","취소","당일",null,null,null,201704070134]
[172,"대구경북","달성","대구S/S 북경남-대구#2T/L-#3M.Tr 1차 CB (7300)","2017년 달성변전협력 총액공사","장기미동작타임측정(7300)","2017-06-16 11:30","2017-06-16 15:00","취소","취소","당일",null,null,null,201704070138]
[173,"대구경북","안동","신영주안동CC T/L","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS *3 CB 170kV GIS * 5CCT","2017-06-24 15:00","2017-06-26 15:00","취소","취소","연속",null,null,null,201702090230,"○"]
[174,"대구경북","안동","안동복합S/Y 345kV #2 BUS","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS * 3CB 170kV GIS * 5CCT.","2017-06-15 10:00","2017-06-28 09:30","2017-06-15 10:00","2017-06-28 09:30","연속",null,null,null,201704170403,"○"]
[175,"대구경북","영주","신영주S/S #1 M.Tr A","공기압 조작방식 차단기 동작특성시험","공기압 조작방식 차단기 동작특성시험","2017-06-07 09:30","2017-06-07 17:00","2017-06-07 09:30","2017-06-07 17:00","당일",null,null,null,201704130342]
[176,"대구경북","영주","신영주S/S #2 M.Tr A","공기압 조작방식 차단기 동작특성시험","공기압 조작방식 차단기 동작특성시험","2017-06-08 08:30","2017-06-08 19:00","2017-06-08 08:30","2017-06-08 19:00","당일",null,null,null,201704130343]
[177,"대구경북","칠곡","서대구S/S #1M.Tr A","서대구S/S #1M.Tr 휴전","서대구S/S #1M.Tr 2차 6144 CB 장기미동작 점검, LA(1,2,3차), 3차 PT 보통점검, 1차 CVT 초기점검, 4179 보통점검","2017-06-21 09:30","2017-06-22 18:00","2017-06-21 09:30","2017-06-22 18:00","연속",null,null,null,201704100873]
[178,"대구경북","칠곡","서대구S/S #2 M.Tr A","서대구S/S #2M.Tr 휴전","서대구S/S #2M.Tr 2차 6244 CB 장기미동작 점검, 3차 LA교체","2017-06-15 09:30","2017-06-15 18:00","2017-06-15 09:30","2017-06-15 18:00","당일",null,null,null,201704110119]
[179,"대구경북","칠곡","서대구S/S #3 M.Tr 1차 CB (7671)","서대구S/S #3M.Tr 1차 CB 휴전","서대구S/S #3M.Tr 1차 CB 장기미동작 점검","2017-06-01 09:30","2017-06-01 14:00","2017-06-01 09:30","2017-06-01 14:00","당일",null,null,null,201704100789]
[180,"대구경북","칠곡","서대구S/S #3 M.Tr 1차-TIE CB (7600)","서대구S/S #3M.Tr 1차-TIE CB 휴전","서대구S/S #3M.Tr 1차-TIE CB 장기미동작 점검","2017-06-01 14:00","2017-06-01 18:00","2017-06-01 14:00","2017-06-01 18:00","당일",null,null,null,201704100790]
[181,"대구경북","칠곡","서대구S/S 북대구서대구#2T/L CB (7772)","서대구S/S 북대구서대구#2T/L CB 휴전","서대구S/S 북대구서대구#2T/L CB 장기미동작 점검","2017-06-05 14:00","2017-06-05 18:00","취소","취소","당일",null,null,null,201704100828]
[182,"대구경북","칠곡","서대구S/S 서대구-고령#1T/L CB (7172)","서대구S/S 서대구-고령#1T/L CB 휴전","서대구S/S 서대구-고령#1T/L CB 장기미동작 점검","2017-06-13 09:30","2017-06-13 18:00","2017-06-13 09:30","2017-06-13 18:00","당일",null,null,null,201704100813]
[183,"대구경북","칠곡","서대구S/S 서대구-고령#2T/L CB (7271)","서대구S/S 서대구-고령#2T/L CB 휴전","서대구S/S 서대구-고령#2T/L CB 장기미동작 점검","2017-06-08 09:30","2017-06-08 14:00","2017-06-08 09:30","2017-06-08 14:00","당일",null,null,null,201704100791]
[184,"대구경북","칠곡","서대구S/S 서대구-고령#2T/L-TIE CB (7200)","서대구S/S 서대구-고령#2T/L-TIE CB 휴전","서대구S/S 서대구-고령#2T/L-TIE CB 장기미동작 점검","2017-06-08 14:00","2017-06-08 18:00","2017-06-08 14:00","2017-06-08 18:00","당일",null,null,null,201704100796]
[185,"대구경북","칠곡","서대구S/S 서대구-선산#1T/L CB (7472)","서대구S/S 서대구-선산#1T/L CB 휴전","서대구S/S 서대구-선산#1T/L CB 장기미동작 점검","2017-06-05 09:30","2017-06-05 14:00","2017-06-05 09:30","2017-06-05 14:00","당일",null,null,null,201704100805]
[186,"대구경북","칠곡","서대구S/S 신옥천/서대구/선산#1T/L-TIE CB (7400)","서대구S/S 북경남-서대구#1-서-선#1T/L-TIE CB 휴전","서대구S/S 북경남-서대구#1-서-선#1T/L-TIE CB 장기미동작 점검","2017-06-14 14:00","2017-06-14 18:00","2017-06-14 14:00","2017-06-14 18:00","당일",null,null,null,201704100807]
[187,"대구경북","칠곡","서대구S/S 신옥천-서대구T/L CB (7471)","서대구S/S 북경남-서대구1T/L CB 휴전","서대구S/S 북경남-서대구1T/L CB 장기미동작 점검","2017-06-14 09:30","2017-06-14 14:00","2017-06-14 09:30","2017-06-14 14:00","당일",null,null,null,201704100804]
[188,"대구경북","포항","동울산월성NP#1 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","철탑 1기 철거/설치, 철탑보강 3기, 전력선교체","2017-06-08 08:00","2017-06-17 18:00","2017-06-08 08:00","2017-06-17 18:00","연속",null,null,null,201703100069,"○"]
[189,"대구경북","포항","신영일S/S #3 M.Tr A","신영일S/S RTU교체에 따른 SCADA 정비공사","신영일S/S RTU교체에 따른 SCADA 정비공사","2017-06-21 09:00","2017-06-21 14:00","취소","취소","당일",null,null,null,201704100400]
[190,"대구경북","포항","신영일S/S #4 M.Tr A","신영일S/S RTU교체에 따른 SCADA 정비공사","신영일S/S RTU교체에 따른 SCADA 정비공사","2017-06-21 14:00","2017-06-21 18:00","취소","취소","당일",null,null,null,201704100406]
[191,"대구경북","포항","신포항S/S #1 M.Tr A","신포항S/S #1M.Tr 1,2차 차단기 동작시험","신포항S/S #1M.Tr 1,2차 차단기 동작시험","2017-06-05 09:00","2017-06-05 18:00","2017-06-05 09:00","2017-06-05 18:00","당일",null,null,null,201704100668,"○"]
[192,"대구경북","포항","신포항S/S #2 M.Tr A","신포항S/S #2 M.Tr 보통점검","신포항S/S #2 M.Tr 보통점검","2017-06-07 09:00","2017-06-08 18:00","2017-06-07 09:00","2017-06-08 18:00","연속",null,null,null,201704120018]
[193,"대구경북","포항","신포항S/S #3 M.Tr A","신포항S/S #3 M.Tr C상 방열기 누유보수","신포항S/S #3 M.Tr C상 방열기 누유보수","2017-06-12 09:00","2017-06-14 18:00","2017-06-12 09:00","2017-06-14 18:00","연속",null,null,null,201704100620]
[194,"대구경북","포항","신포항S/S #4 M.Tr A","신포항S/S #4 M.Tr 1,2차 차단기 동작시험","신포항S/S #4 M.Tr 1,2차 차단기 동작시험","2017-06-09 09:00","2017-06-09 18:00","2017-06-09 09:00","2017-06-09 18:00","당일",null,null,null,201704100626]
[195,"부산울산","동부산","고리N/P S/Y 신울산-고리#1T/L CB (7371)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 7371 GIS 보통점검","2017-06-28 09:00","2017-06-28 18:00","취소","취소","당일",null,null,null,201704100777]
[196,"부산울산","동부산","신양산S/S #1 M.Tr A","신양산S/S 345kV M.Tr 정밀점검공사","신양산S/S #1M.Tr 본체 및 OLTC 정밀점검","2017-06-19 09:00","2017-07-01 18:00","2017-06-19 09:00","2017-07-01 18:00","연속",null,null,null,201704100775]
[197,"부산울산","동부산","신울산고리NP#2 T/L","고리NP S/Y 362kV GIS 조작불량 보수","1.고리NP S/Y 7261 조작불량 보수 2.7271GIS 보통점검 3.7271,7200GIS 실리콘히터 설치","2017-06-29 09:00","2017-06-29 18:00","2017-06-29 09:00","2017-06-29 18:00","당일",null,null,null,201704100776]
[198,"부산울산","북부산","북부산S/S #4 M.Tr A","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(리드 분리 및 리드 연결) 2. PNL 이설 3. 시험가압 및 사용전검사","2017-06-23 09:00","2017-06-30 18:00","2017-06-30 09:00","2017-07-07 18:00","연속",null,null,null,201704070390]
[199,"부산울산","북부산","북부산S/S #4M.Tr 1차 CB(신) ((신)7872)","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(구 76BAY → 신 78BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-06-25 09:00","2017-06-30 18:00","취소","취소","연속",null,null,null,201704110008]
[200,"부산울산","북부산","북부산S/S 345kV #4 Sh.R","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 이설(Reactor 및 CB) 2. PNL 이설 3. 시험가압 및 사용전검사","2017-06-23 09:00","2017-07-21 18:00","2017-06-30 09:00","2017-07-28 18:00","연속",null,null,null,201704070394]
[201,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 모선 연결 리드 분리 및 붓싱(GIB) 철거","2017-06-23 09:00","2017-06-24 18:00","2017-06-30 09:00","2017-07-01 18:00","연속",null,null,null,201704070397]
[202,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","시험가압(1. 서부산-북부산#2T/L 과 #2Sh.R 연결 GIB 설치분 2. #2Sh.R CB 대체분)","2017-06-20 10:00","2017-06-21 10:00","2017-06-27 10:00","2017-06-28 10:00","연속",null,null,null,201704070374]
[203,"부산울산","북부산","북부산S/S 서부산#3T/L-#4M.Tr 1차 CB(신) ((신)7800)","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(구 76BAY → 신 78BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-06-25 09:00","2017-06-30 18:00","취소","취소","연속",null,null,null,201704110009]
[204,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산T/L 전선교체 및 피뢰기 설치공사","-전선교체:8호-9호, 22호-27호,28호-36호 -피뢰기설치:1호-110호","2017-06-26 07:00","2017-07-05 18:00","2017-06-26 07:00","2017-07-05 18:00","연속",null,null,null,201704040045,"○"]
[205,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","시험가압(1. 서부산-북부산#2T/L 과 #2Sh.R 연결 GIB 설치분 2. #2Sh.R CB 대체분)","2017-06-20 10:00","2017-06-21 10:00","2017-06-27 10:00","2017-06-28 10:00","연속",null,null,null,201704070378,"○"]
[206,"부산울산","북부산","북부산울산TP T/L","345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사","345kV 북부산-울산TP T/L 전선접속개소 전선교체 No.49~82호","2017-06-19 07:00","2017-07-03 18:00","2017-06-19 07:00","2017-07-03 18:00","연속",null,null,null,201704030199]
[207,"부산울산","북부산","서부산북부산#2 T/L","345kV 북부산S/S 차단기용량대체공사","1. 서부산-북부산#2T/L 과 #2Sh.R 연결 GIB 설치 2. #2Sh.R CB 대체 시험가압 및 사용전 검사","2017-06-15 09:00","2017-06-22 18:00","2017-06-22 09:00","2017-06-29 18:00","연속",null,null,null,201704070363]
[208,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사","345kV 신김해-북부산#1T/L 전선교체공사 No.10∼22호","2017-06-09 07:00","2017-06-14 18:00","취소","취소","연속",null,null,null,201704030210]
[209,"부산울산","북부산","신김해북부산#2 T/L","345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사","345kV 신김해-북부산#2T/L 전선교체공사 No.10∼22호","2017-06-03 07:00","2017-06-08 18:00","취소","취소","연속",null,null,null,201704030212]
[210,"부산울산","서부산","서부산북부산#1 T/L","#1 Sh.R용 차단기 7177 설치","#1 Sh.R용 차단기 7177 설치","2017-06-24 09:00","2017-06-27 18:00","2017-06-24 09:00","2017-06-27 18:00","연속",null,null,null,201704110090]
[211,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산분기T/L 항공장애표지 설치공사","345kV 동울산분기T/L 항공장애표지 설치","2017-06-02 08:00","2017-06-05 18:00","2017-06-02 08:00","2017-06-05 18:00","연속",null,null,null,201704030255,"○"]
[212,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산분기T/L 항공장애표지 설치공사","345kV 동울산분기T/L 항공장애표지 설치","2017-06-08 08:00","2017-06-11 18:00","2017-06-08 08:00","2017-06-11 18:00","연속",null,null,null,201704030257]
[213,"부산울산","울산","신온산S/S #3 M.Tr A","345kV 신온산S/S S-OIL SW 증설공사","345kV S-OIL #6T/L(7571) 증설 - 75Bay B/F반 대체공사","2017-06-09 09:00","2017-06-16 18:00","2017-06-09 09:00","2017-06-16 18:00","연속",null,null,null,201704070058]
[214,"부산울산","울산","신온산S/S 345kV #1 BUS","345kV 신온산S/S S-OIL SW 증설공사","S-OIL #6T/L (7571) 예비가압","2017-06-17 18:00","2017-06-18 18:00","2017-06-17 18:00","2017-06-18 18:00","연속",null,null,null,201704070053]
[215,"부산울산","울산","신울산신온산#2 T/L","345kV 신온산S/S S-OIL SW 증설공사","신온산S/S 75Bay 신설 #1BUS (63kA) 예비가압","2017-06-05 18:00","2017-06-06 18:00","2017-06-05 18:00","2017-06-06 18:00","연속",null,null,null,201703100117]
[216,"부산울산","울산","신울산신온산#2 T/L","345kV 신온산S/S S-OIL SW 증설공사","신온산S/S 7571CB 예비가압","2017-06-17 18:00","2017-06-18 18:00","2017-06-17 18:00","2017-06-18 18:00","연속",null,null,null,201703100118]
[217,"부산울산","울산","울주S/S #4 M.Tr","2016-17년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV #4M.Tr 및 2차 GIS(6444) 보통점검","2017-06-12 09:00","2017-06-13 18:00","2017-06-12 09:00","2017-06-13 18:00","연속",null,null,null,201704100322]
[218,"부산울산","울산","울주고리NP#2 T/L","유호제 345kV T/L보호반 내부통신회로 개선","1.유호제 345울주-고리NP#2T/L 보호반 내부통신회로 개선 2.고리NP 7C71 GIS 보통점검","2017-06-01 09:00","2017-06-01 18:00","2017-06-01 09:00","2017-06-01 18:00","당일",null,null,null,201704100774]
[219,"경남","진주","광양하동화력#1 T/L","하동화력 345kV 광양-하동화력#1T/L PNL 대체","하동화력 345kV 광양-하동화력#1T/L PNL 대체 광양-하동화력#1(A,B,C) PT하자점검[병행작업]","2017-06-26 09:30","2017-07-03 18:30","2017-06-26 09:30","2017-07-03 18:30","연속",null,null,null,201703060296]
[220,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","안전이격 거리확보 전선교체(39~43, 129~136호)","2017-06-10 07:00","2017-06-20 20:00","취소","취소","연속",null,null,null,201703090136]
[221,"경남","진주","의령산청양수#1 T/L","345kV 의령-산청양수#1T/L 보호반 교체","345kV 의령-산청양수#1T/L 보호반 교체 - 참고사항 : 시송전선로","2017-06-05 09:00","2017-06-30 18:00","2017-06-05 09:00","2017-06-30 18:00","연속",null,null,null,201704050155]
[222,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 6-8호 지장이설공사(요청자시행)","#1T/L측 부적합사항 조치","2017-06-21 07:00","2017-06-21 19:00","2017-06-21 07:00","2017-06-21 19:00","당일",null,null,null,201704180117]
[223,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력#2T/L 정밀점검","345kV 의령-하동화력 #2T/L 정밀점검 - No.50-134","2017-06-22 09:00","2017-06-25 18:00","2017-06-22 09:00","2017-06-25 18:00","매일",null,null,null,201704060011]
[224,"경남","진주","하동T/P #7 M.Tr 1차 CB (7772)","하동T/P #7 M.Tr 1차 CB(7772) 정밀점검","하동T/P #7 M.Tr 1차 CB(7772) 정밀점검","2017-06-29 09:30","2017-07-01 18:30","2017-06-29 09:30","2017-07-01 18:30","연속",null,null,null,201704030217]
[225,"경남","진주","하동T/P #8 M.Tr 1차 CB (7872)","하동T/P #8 M.Tr 1차 CB(7872) 정밀점검","하동T/P #8 M.Tr 1차 CB(7872) 정밀점검","2017-06-07 09:30","2017-06-09 18:30","2017-06-07 09:30","2017-06-09 18:30","연속",null,null,null,201704030213]
[226,"경남","진주","하동T/P TIE-#7 M.Tr 1차 CB (7700)","하동T/P TIE-#7 M.Tr 1차 CB(7700) 정밀점검","하동T/P TIE-#7 M.Tr 1차 CB(7700) 정밀점검","2017-06-26 09:30","2017-06-28 18:30","2017-06-26 09:30","2017-06-28 18:30","연속",null,null,null,201704030215]
[227,"경남","통영","신고성S/S #3 M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","345kV M.Tr 3차측 조류방지커버 설치관련 안전이격","2017-06-13 09:00","2017-06-13 12:00","2017-06-13 09:00","2017-06-13 12:00","당일",null,null,null,201704070224]
[228,"경남","통영","신고성S/S #4M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","345kV M.Tr 3차측 조류방지커버 설치관련 안전이격","2017-06-13 13:00","2017-06-13 18:00","2017-06-13 13:00","2017-06-13 18:00","당일",null,null,null,201704070225]
[229,"경남","통영","신김해삼천포화력#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","345kV 신김해-삼천포화력#1T/L 전선 연선 및 긴선","2017-06-09 07:00","2017-06-15 19:00","2017-06-09 07:00","2017-06-15 19:00","연속",null,null,null,201704050152]
[230,"경남","통영","신김해삼천포화력#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","345kV 신김해-삼천포화력#2T/L 전선 연선 및 긴선","2017-06-16 07:00","2017-06-23 19:00","2017-06-16 07:00","2017-06-23 19:00","연속",null,null,null,201704050153]
[231,"경남","함안","의령신마산#1 T/L","345kV 의령-신마산 #1T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 : 의령-신마산 #1T/L 1~115호 (115기)","2017-06-26 08:00","2017-07-10 18:30","2017-06-26 08:00","2017-07-10 18:30","매일",null,null,null,201704030259]

{"sheet":"154송부","index":2,"n_rows":456,"n_cols":16,"rows_kept":456,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S 154kV #60 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #3M.Tr 2차)","2017-06-22 09:20","2017-06-23 10:00","2017-06-22T09:20:00","2017-06-23T10:00:00","연속",null,null,null,201704120226]
[2,"서울","성동","성동S/S 154kV #61 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #4M.Tr 2차)","2017-06-24 09:20","2017-06-25 10:00","2017-06-24T09:20:00","2017-06-25T10:00:00","연속",null,null,null,201704120223]
[3,"서울","성동","성동S/S 154kV #65 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #3M.Tr 2차)","2017-06-23 10:00","2017-06-23 18:00","2017-06-23T10:00:00","2017-06-23T18:00:00","당일",null,null,null,201704120227]
[4,"서울","성동","성동S/S 154kV #66 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (345kV 성동S/S #4M.Tr 2차)","2017-06-25 10:00","2017-06-25 18:00","2017-06-25T10:00:00","2017-06-25T18:00:00","당일",null,null,null,201704120224]
[5,"서울","성동","성수뚝도#1 T/L","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (성수S/S 154kV 성수뚝도#1T/L)","2017-06-19 09:20","2017-06-20 18:00","2017-06-19T09:20:00","2017-06-20T18:00:00","연속",null,null,null,201704120214]
[6,"서울","성동","성수뚝도#2 T/L","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (성수S/S 154kV 성수뚝도#2T/L)","2017-06-07 09:20","2017-06-08 18:00","2017-06-07T09:20:00","2017-06-08T18:00:00","연속",null,null,null,201704120217]
[7,"서울","성동","창동쌍문#1 T/L","노후 PITR 교체공사","노후 PITR 교체공사 (창동,쌍문S/S 창동쌍문#1T/L)","2017-06-14 10:00","2017-06-14 18:00","2017-06-14T10:00:00","2017-06-14T18:00:00","연속",null,null,null,201704120231]
[8,"서울","성동","창동쌍문#2 T/L","노후 PITR 교체공사","노후 PITR 교체공사 (창동,쌍문S/S 창동쌍문#2T/L)","2017-06-15 10:00","2017-06-15 18:00","2017-06-15T10:00:00","2017-06-15T18:00:00","연속",null,null,null,201704120232]
[9,"서울","성동","화양광장 T/L","노후 PITR 교체공사","노후 PITR 교체공사 (화양, 광장S/S 화양광장T/L)","2017-06-16 10:00","2017-06-16 18:00","2017-06-16T10:00:00","2017-06-16T18:00:00","연속",null,null,null,201704120233]
[10,"서울","성동","화양성수 T/L","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (성수S/S 154kV 화양성수T/L)","2017-06-12 09:20","2017-06-13 18:00","2017-06-12T09:20:00","2017-06-15T18:00:00","연속",null,null,null,201704120219]
[11,"서울","중부","순화동빙고 T/L","PITR 교체공사","순화-동빙고T/L PITR 교체","2017-06-23 09:10","2017-06-23 18:00","2017-06-23T09:10:00","2017-06-23T18:00:00","당일",null,null,null,201704140025]
[12,"서울","중부","중부용산#2 T/L","345kV 중부S/S 모자익배전반 정비공사","중부S/S 중부-용산#2T/L GIS(6G7) 모자익반 교체","2017-06-20 10:00","2017-06-21 18:00","2017-06-20T10:00:00","2017-06-21T18:00:00","연속",null,null,null,201704130052]
[13,"서울","직할","서대문세종로 T/L","17년 직할 170kV GIS 정밀점검","17년 직할 170kV GIS 정밀점검 - 서대문S/S 서대문세종로T/L GIS","2017-06-07 09:30","2017-06-09 17:30","2017-06-07T09:30:00","2017-06-09T17:30:00","연속",null,null,null,201703130058]
[14,"서울","직할","서소문S/S 154kV #1 BUS","17년 직할 변전협력 총액공사","170kV GIS 초기점검","2017-06-19 10:00","2017-06-19 14:00","2017-06-19T10:00:00","2017-06-19T14:00:00","당일",null,null,null,201703100207]
[15,"서울","직할","서소문S/S 154kV #2 BUS","17년 직할 변전협력 총액공사","170kV GIS 초기점검","2017-06-19 14:00","2017-06-19 17:00","2017-06-19T14:00:00","2017-06-19T17:00:00","당일",null,null,null,201703100208]
[16,"서울","직할","운니S/S 154kV #1 BUS","17년 직할 170kV GIS 정밀점검","17년 직할 170kV GIS 정밀점검 - 운니S/S #1M.Tr 1차 GIS","2017-06-26 09:30","2017-06-27 11:00","2017-06-26T09:30:00","2017-06-27T11:00:00","연속",null,null,null,201704130013]
[17,"서울","직할","운니S/S 154kV #1 BUS","17년 직할 170kV GIS 정밀점검","17년 직할 170kV GIS 정밀점검 - 운니S/S #2M.Tr 1차 GIS","2017-06-29 09:30","2017-06-30 11:00","2017-06-29T09:30:00","2017-06-30T11:00:00","연속",null,null,null,201704130015]
[18,"서울","직할","운니S/S 154kV #2 BUS","17년 직할 170kV GIS 정밀점검","17년 직할 170kV GIS 정밀점검 - 운니S/S #2M.Tr 1차 GIS","2017-06-30 11:00","2017-07-01 17:00","2017-06-30T11:00:00","2017-07-01T17:00:00","연속",null,null,null,201704130017]
[19,"서울","직할","운니S/S 154kV #2 BUS","17년 직할 170kV GIS 정밀점검","17년 직할 170kV GIS 정밀점검 - 운니S/S #1M.Tr 1차 GIS","2017-06-27 11:00","2017-06-28 17:00","2017-06-27T11:00:00","2017-06-28T17:00:00","연속",null,null,null,201704130014]
[20,"남서울","강남","역삼대치#1 T/L","154kV 논일-역삼, 논현-대치 지중T/L 건설공사","1. 구간 : 154kV 논일S/S, 논현S/S~기설 154kV 역삼대치T/L 분기점 2. 선종/회선길이 : XLPE1200, 2C-3.7km(논일-역삼),2C-3km(논현-대치) 3. 공사기간 : 2016.10 ~ 2017. 10 (12개월)","2017-06-19 09:00","2017-07-21 18:00","취소","취소","연속",null,null,"신뢰도 개선",201704200021]
[21,"남서울","강남","역삼대치#2 T/L","154kV 논일-역삼, 논현-대치 지중T/L 건설공사","1. 구간 : 154kV 논일S/S, 논현S/S~기설 154kV 역삼대치T/L 분기점 2. 선종/회선길이 : XLPE1200, 2C-3.7km(논일-역삼),2C-3km(논현-대치) 3. 공사기간 : 2016.10 ~ 2017. 10 (12개월)","2017-06-19 09:00","2017-07-21 18:00","취소","취소","연속",null,null,"신뢰도 개선",201704200024]
[22,"남서울","동서울","강동S/S 154kV #1 BUS","170kV GIS 정밀점검(동서울-강동#2T/L)","170kV GIS 정밀점검(동서울-강동#2T/L)","2017-06-01 14:00","2017-06-02 14:00","2017-06-01T14:00:00","2017-06-02T14:00:00","연속",null,null,null,201703210234]
[23,"남서울","동서울","동서울가락#1 T/L","하나감일지구 지장송전선로 가이설 공사","154kV 동서울-가락(송파)T/L No.5, 6, 7 가이설 공사","2017-06-01 08:00","2017-06-07 18:00","2017-06-01T08:00:00","2017-06-07T18:00:00","연속",null,null,null,201704170288,"○"]
[24,"남서울","동서울","동서울가락#2 T/L","하나감일지구 지장송전선로 가이설 공사","154kV 동서울-가락(송파)T/L No.5, 6, 7 가이설 공사","2017-06-08 08:00","2017-06-14 18:00","2017-06-08T08:00:00","2017-06-14T18:00:00","연속",null,null,null,201704170293]
[25,"남서울","동서울","동서울송파#1 T/L","하나감일지구 지장송전선로 가이설 공사","154kV 동서울-가락(송파)T/L No.5, 6, 7 가이설 공사","2017-06-01 08:00","2017-06-07 18:00","2017-06-01T08:00:00","2017-06-07T18:00:00","연속",null,null,null,201704170289]
[26,"남서울","동서울","동서울송파#2 T/L","하나감일지구 지장송전선로 가이설 공사","154kV 동서울-가락(송파)T/L No.5, 6, 7 가이설 공사","2017-06-08 08:00","2017-06-14 18:00","2017-06-08T08:00:00","2017-06-14T18:00:00","연속",null,null,null,201704170294]
[27,"남서울","동서울","동서울신장#1 T/L","170kV GCB 정밀점검","170kV GCB 정밀점검","2017-06-08 09:00","2017-06-09 18:00","2017-06-08T09:00:00","2017-06-09T18:00:00","연속",null,null,null,201704170275]
[28,"남서울","영등포","영서광명#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-13 09:00","2017-06-13 18:00","2017-06-13T09:00:00","2017-06-13T18:00:00","연속",null,null,null,201704170182]
[29,"남서울","영등포","영서광명#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-14 09:00","2017-06-14 18:00","2017-06-14T09:00:00","2017-06-14T18:00:00","연속",null,null,null,201704170183]
[30,"남서울","영등포","영서시흥#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-08 09:00","2017-06-08 18:00","2017-06-08T09:00:00","2017-06-08T18:00:00","연속",null,null,null,201704170179]
[31,"남서울","영등포","영서시흥#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-10 09:00","2017-06-10 18:00","2017-06-10T09:00:00","2017-06-10T18:00:00","연속",null,null,null,201704170180]
[32,"남서울","영등포","영서천왕#3 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사 전력구 기초시공","전력구 기초시공","2017-06-15 09:00","2017-06-15 18:00","2017-06-15T09:00:00","2017-06-15T18:00:00","연속",null,null,null,201704170184]
[33,"남서울","영등포","마곡화곡#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2017-06-30 09:00","2017-06-30 18:00","2017-06-30T09:00:00","2017-06-30T18:00:00","당일",null,null,null,201703200127]
[34,"남서울","영등포","마곡화곡#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2017-06-30 09:00","2017-06-30 18:00","2017-06-30T09:00:00","2017-06-30T18:00:00","당일",null,null,null,201703200128]
[35,"인천","김포","경서양촌#1 T/L","154kV 경서-양촌#1T/L EBA 절연유 채유","○ 종단접속(EBA) 절연유 분석 - 내용 : 내부 절연유(실리콘유) 채취 후 성분분석을 통한 열화상태 진단 - 적용대상 : 철구형 또는 수평배치형 C/H에 설치된 EBA - 시행방법 : 시료채취(위탁전문회사) 후 설비진단처 분석 의뢰","2017-06-19 09:00","2017-06-20 18:00","2017-05-29T09:00:00","2017-05-30T18:00:00","연속",null,null,null,201704100200]
[36,"인천","김포","경서양촌#2 T/L","154kV 경서-양촌#2T/L EBA 절연유 채유","○ 종단접속(EBA) 절연유 분석 - 내용 : 내부 절연유(실리콘유) 채취 후 성분분석을 통한 열화상태 진단 - 적용대상 : 철구형 또는 수평배치형 C/H에 설치된 EBA - 시행방법 : 시료채취(위탁전문회사) 후 설비진단처 분석 의뢰","2017-06-21 09:00","2017-06-22 18:00","2017-05-31T09:00:00","2017-06-01T18:00:00","연속",null,null,null,201704100205]
[37,"인천","김포","신경서경서#1 T/L","170kV 신경서-경서#1T/L GIS 정밀점검","170kV 신경서-경서#1T/L GIS 정밀점검","2017-06-26 09:00","2017-06-28 18:00","2017-06-26T09:00:00","2017-06-28T18:00:00","연속",null,null,null,201704170173]
[38,"인천","김포","신경서경서#2 T/L","170kV 신경서-경서#2T/L GIS 정밀점검","170kV 신경서-경서#2T/L GIS 정밀점검","2017-06-29 09:00","2017-07-01 18:00","2017-06-29T09:00:00","2017-07-01T18:00:00","연속",null,null,null,201704170174]
[39,"인천","김포","신김포양곡#1 T/L","신김포S/S 154kV 신김포-양곡#1T/L 기기점검","신김포S/S 154kV 신김포-양곡#1T/L GIS (637CB) 기기점검","2017-06-16 10:00","2017-06-16 18:00","2017-06-02T10:00:00","2017-06-02T18:00:00","당일",null,null,null,201704130283]
[40,"인천","김포","신김포양곡#2 T/L","신김포S/S 154kV 신김포-양곡#2T/L 기기점검","신김포S/S 154kV 신김포-양곡#2T/L GIS (647CB) 기기점검","2017-06-23 10:00","2017-06-23 18:00","2017-06-05T10:00:00","2017-06-05T18:00:00","당일",null,null,null,201704130284]
[41,"인천","시흥","소래S/S 154kV #1 BUS","소래S/S 영서소래 T/L GIS 정밀점검","소래S/S 영서소래 T/L GIS 정밀점검","2017-06-08 14:00","2017-06-09 18:00","2017-06-08T14:00:00","2017-06-09T18:00:00","연속",null,null,null,201704140293]
[42,"인천","시흥","소래S/S 154kV #1 BUS","소래S/S #3M.Tr 1차 GIS 정밀점검","소래S/S #3M.Tr 1차 GIS 정밀점검","2017-06-02 14:00","2017-06-03 18:00","취소","취소","연속",null,null,null,201704150024]
[43,"인천","시흥","소래S/S 154kV #1 BUS","소래S/S 서안양소래T/L GIS 정밀점검","소래S/S 서안양소래T/L GIS 정밀점검","2017-06-12 14:00","2017-06-13 18:00","2017-06-12T14:00:00","2017-06-13T18:00:00","연속",null,null,null,201704140290]
[44,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #3M.Tr 1차 GIS 정밀점검","소래S/S #3M.Tr 1차 GIS 정밀점검","2017-06-01 08:00","2017-06-02 14:00","취소","취소","연속",null,null,null,201704150023]
[45,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S 서안양소래T/L GIS 정밀점검","소래S/S 서안양소래T/L GIS 정밀점검","2017-06-11 08:00","2017-06-12 14:00","2017-06-11T08:00:00","2017-06-12T14:00:00","연속",null,null,null,201704140289]
[46,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S 영서소래 T/L GIS 정밀점검","소래S/S 영서소래 T/L GIS 정밀점검","2017-06-07 08:00","2017-06-08 14:00","2017-06-07T08:00:00","2017-06-08T14:00:00","연속",null,null,null,201704140292]
[47,"인천","시흥","영서소래 T/L","소래S/S 영서소래 T/L GIS 정밀점검","소래S/S 영서소래 T/L GIS 정밀점검","2017-06-07 08:00","2017-06-09 18:00","2017-06-07T08:00:00","2017-06-09T18:00:00","연속",null,null,null,201704140291]
[48,"인천","인천","관교만수 T/L","154kV 만수S/S 인출구간 OF케이블 선종교체공사","단일계통 옥내형GIS변전소 내 OF케이블 선종교체를 통한 화재 및 정전고장 예방","2017-06-27 09:00","2017-07-14 18:00","2017-06-27T09:00:00","2017-07-14T18:00:00","연속",null,null,null,201704120015]
[49,"인천","인천","서인천CC신경서 T/L","신경서S/S 신경서서인천CC T/L GIS 조작시험(양단)","신경서S/S 신경서서인천CC T/L GIS 조작시험(양단)","2017-06-16 09:00","2017-06-16 14:00","2017-06-16T09:00:00","2017-06-16T14:00:00","당일",null,null,null,201704120185]
[50,"인천","인천","송현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-06-07 10:00","2017-06-08 10:00","취소","취소","연속",null,null,null,201703150163]
[51,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-06-07 10:00","2017-06-08 10:00","취소","취소","연속",null,null,null,201703150156]
[52,"인천","인천","주안만수 T/L","154kV 만수S/S 인출구간 OF케이블 선종교체공사","단일계통 옥내형GIS변전소 내 OF케이블 선종교체를 통한 화재 및 정전고장 예방","2017-06-09 09:00","2017-06-26 18:00","2017-06-09T09:00:00","2017-06-26T18:00:00","연속",null,null,null,201704120016]
[53,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 6100 TIE 170kV GIS 정밀점검","부개S/S 6100 TIE 170kV GIS 정밀점검","2017-06-15 08:00","2017-06-16 14:00","취소","취소","연속",null,null,null,201704140067]
[54,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 부흥부개 #1T/L 170kV GIS 정밀점검","부개S/S 부흥부개 #1T/L 170kV GIS 정밀점검","2017-06-01 08:00","2017-06-02 14:00","취소","취소","연속",null,null,null,201704190072]
[55,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","2017-06-05 08:00","2017-06-06 14:00","취소","취소","연속",null,null,null,201704140082]
[56,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 신가좌부개#1T/L 170kV GIS 정밀점검","부개S/S 신가좌부개#1T/L 170kV GIS 정밀점검","2017-06-08 08:00","2017-06-09 14:00","취소","취소","연속",null,null,null,201704140070]
[57,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 신가좌부개#2T/L 170kV GIS 정밀점검","부개S/S 신가좌부개#2T/L 170kV GIS 정밀점검","2017-06-12 08:00","2017-06-13 14:00","취소","취소","연속",null,null,null,201704140073]
[58,"인천","직할","부개S/S 154kV #1 BUS TIE CB","부개S/S 6100 TIE 170kV GIS 정밀점검","부개S/S 6100 TIE 170kV GIS 정밀점검","2017-06-15 08:00","2017-06-17 18:00","취소","취소","연속",null,null,null,201704140066]
[59,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 부흥부개 #1T/L 170kV GIS 정밀점검","부개S/S 부흥부개 #1T/L 170kV GIS 정밀점검","2017-06-02 14:00","2017-06-03 18:00","취소","취소","연속",null,null,null,201704190073]
[60,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","2017-06-06 14:00","2017-06-07 18:00","취소","취소","연속",null,null,null,201704140083]
[61,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 신가좌부개#1T/L 170kV GIS 정밀점검","부개S/S 신가좌부개#1T/L 170kV GIS 정밀점검","2017-06-09 14:00","2017-06-10 18:00","취소","취소","연속",null,null,null,201704140071]
[62,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 6100 TIE 170kV GIS 정밀점검","부개S/S 6100 TIE 170kV GIS 정밀점검","2017-06-16 14:00","2017-06-17 18:00","취소","취소","연속",null,null,null,201704140068]
[63,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 신가좌부개#2T/L 170kV GIS 정밀점검","부개S/S 신가좌부개#2T/L 170kV GIS 정밀점검","2017-06-13 14:00","2017-06-14 18:00","취소","취소","연속",null,null,null,201704140074]
[64,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","2017-06-05 08:00","2017-06-06 14:00","2017-06-05T08:00:00","2017-06-06T14:00:00","연속",null,null,null,201704140088]
[65,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 6100TIE 170kV GIS 정밀점검","부천S/S 6100TIE 170kV GIS 정밀점검","2017-06-12 08:00","2017-06-13 14:00","2017-06-12T08:00:00","2017-06-13T14:00:00","연속",null,null,null,201704140095]
[66,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","2017-06-08 08:00","2017-06-09 14:00","2017-06-08T08:00:00","2017-06-09T14:00:00","연속",null,null,null,201704140091]
[67,"인천","직할","부천S/S 154kV #1 BUS TIE CB","부천S/S 6100TIE 170kV GIS 정밀점검","부천S/S 6100TIE 170kV GIS 정밀점검","2017-06-12 08:00","2017-06-14 18:00","2017-06-12T08:00:00","2017-06-14T18:00:00","연속",null,null,null,201704140093]
[68,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","2017-06-06 14:00","2017-06-07 18:00","2017-06-06T14:00:00","2017-06-07T18:00:00","연속",null,null,null,201704140086]
[69,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 6100TIE 170kV GIS 정밀점검","부천S/S 6100TIE 170kV GIS 정밀점검","2017-06-13 14:00","2017-06-14 18:00","2017-06-13T14:00:00","2017-06-14T18:00:00","연속",null,null,null,201704140096]
[70,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","2017-06-09 14:00","2017-06-10 18:00","2017-06-09T14:00:00","2017-06-10T18:00:00","연속",null,null,null,201704140092]
[71,"인천","직할","부천신정#1 T/L","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","부천S/S 부천신정#1T/L 170kV GIS 정밀점검","2017-06-05 08:00","2017-06-07 18:00","2017-06-05T08:00:00","2017-06-07T18:00:00","연속",null,null,null,201704140085]
[72,"인천","직할","부천신정#2 T/L","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","부천S/S 부천신정#2T/L 170kV GIS 정밀점검","2017-06-08 08:00","2017-06-10 18:00","2017-06-08T08:00:00","2017-06-10T18:00:00","연속",null,null,null,201704140090]
[73,"인천","직할","부천원미#1 T/L","부천-원미#1T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-26 09:00","2017-06-27 18:00","2017-06-26T09:00:00","2017-06-27T18:00:00","매일",null,null,null,201704140126]
[74,"인천","직할","부천원미#2 T/L","부천-원미#2T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-28 09:00","2017-06-29 18:00","2017-06-28T09:00:00","2017-06-29T18:00:00","매일",null,null,null,201704140128]
[75,"인천","직할","부흥부개#1 T/L","부개S/S 부흥부개 #1T/L 170kV GIS 정밀점검","부개S/S 부흥부개 #1T/L 170kV GIS 정밀점검","2017-06-01 08:00","2017-06-03 18:00","취소","취소","연속",null,null,null,201704190071]
[76,"인천","직할","부흥부개#2 T/L","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","부개S/S 부흥부개#2T/L 170kV GIS 정밀점검","2017-06-05 08:00","2017-06-07 18:00","취소","취소","연속",null,null,null,201704140081]
[77,"인천","직할","신가좌부개#1 T/L","부개S/S 신가좌부개#1T/L 170kV GIS 정밀점검","부개S/S 신가좌부개#1T/L 170kV GIS 정밀점검","2017-06-08 08:00","2017-06-10 18:00","취소","취소","연속",null,null,null,201704140069]
[78,"인천","직할","신가좌부개#2 T/L","부개S/S 신가좌부개#2T/L 170kV GIS 정밀점검","부개S/S 신가좌부개#2T/L 170kV GIS 정밀점검","2017-06-12 08:00","2017-06-14 18:00","취소","취소","연속",null,null,null,201704140072]
[79,"인천","직할","신부평S/S 154kV #1 BUS TIE CB","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-06-01 08:00","2017-06-02 20:00","취소","취소","연속",null,null,null,201704190089]
[80,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-06-02 10:00","2017-06-02 20:00","취소","취소","연속",null,null,null,201704190091]
[81,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S #62M.Tr 1차 170kV GIS 정밀점검","신부평S/S #62M.Tr 1차 170kV GIS 정밀점검","2017-06-05 08:00","2017-06-06 10:00","취소","취소","연속",null,null,null,201704140149]
[82,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-06-07 08:00","2017-06-08 10:00","취소","취소","연속",null,null,null,201704140099]
[83,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-06-01 08:00","2017-06-02 10:00","취소","취소","연속",null,null,null,201704190090]
[84,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-06-14 08:00","2017-06-15 10:00","취소","취소","연속",null,null,null,201704140143]
[85,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-06-12 08:00","2017-06-13 10:00","취소","취소","연속",null,null,null,201704140107]
[86,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-06-09 08:00","2017-06-10 10:00","취소","취소","연속",null,null,null,201704140102]
[87,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-06-15 10:00","2017-06-15 20:00","취소","취소","연속",null,null,null,201704140144]
[88,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S #62M.Tr 1차 170kV GIS 정밀점검","신부평S/S #62M.Tr 1차 170kV GIS 정밀점검","2017-06-06 10:00","2017-06-06 20:00","취소","취소","연속",null,null,null,201704140150]
[89,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-06-16 08:00","2017-06-17 10:00","취소","취소","연속",null,null,null,201704140146]
[90,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-06-13 10:00","2017-06-13 20:00","취소","취소","연속",null,null,null,201704140108]
[91,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-06-10 10:00","2017-06-10 20:00","취소","취소","연속",null,null,null,201704140103]
[92,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-06-08 10:00","2017-06-08 20:00","취소","취소","연속",null,null,null,201704140100]
[93,"인천","직할","신부평S/S 154kV #66 BUS","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-06-17 10:00","2017-06-17 20:00","취소","취소","연속",null,null,null,201704140147]
[94,"인천","직할","신부평S/S 60-61-0 SEC CB","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-06-14 08:00","2017-06-15 20:00","취소","취소","연속",null,null,null,201704140142]
[95,"인천","직할","신부평S/S 65-66-0 SEC CB","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-06-16 08:00","2017-06-17 20:00","취소","취소","연속",null,null,null,201704140145]
[96,"인천","직할","신부평고강#2 T/L","신부평-고강#2T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-21 09:00","2017-06-23 18:00","2017-06-21T09:00:00","2017-06-23T18:00:00","매일",null,null,null,201704140125]
[97,"인천","직할","신부평부천#1 T/L","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-06-07 08:00","2017-06-08 20:00","취소","취소","연속",null,null,null,201704140098]
[98,"인천","직할","신부평부천#2 T/L","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-06-09 08:00","2017-06-10 20:00","취소","취소","연속",null,null,null,201704140101]
[99,"인천","직할","신부평부흥#1 T/L","신부평-부흥#1T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-24 09:00","2017-06-25 18:00","2017-06-24T09:00:00","2017-06-25T18:00:00","매일",null,null,null,201704140119]
[100,"인천","직할","신부평부흥#2 T/L","신부평-부흥#2T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-19 09:00","2017-06-20 18:00","2017-06-19T09:00:00","2017-06-20T18:00:00","매일",null,null,null,201704140121]
[101,"인천","직할","신부평임학#1 T/L","신부평-임학#1T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-14 09:00","2017-06-15 18:00","2017-06-14T09:00:00","2017-06-15T18:00:00","매일",null,null,null,201704140122]
[102,"인천","직할","신부평임학#2 T/L","신부평-임학#2T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-12 09:00","2017-06-13 18:00","2017-06-12T09:00:00","2017-06-13T18:00:00","매일",null,null,null,201704140124]
[103,"인천","직할","신부평중동#1 T/L","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-06-12 08:00","2017-06-13 20:00","2017-06-16T08:00:00","2017-06-16T20:00:00","연속",null,null,null,201704140105]
[104,"인천","직할","신부평중동#2 T/L","신부평-중동#2T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-18 09:00","2017-06-18 18:00","2017-06-02T09:00:00","2017-06-02T18:00:00","당일",null,null,null,201704140117]
[105,"인천","직할","신부평중동#3 T/L","신부평-중동#3T/L 접지선 정비","맨홀, 전력구내 접지선 정비(150mm2→240mm2)","2017-06-30 09:00","2017-06-30 18:00","2017-06-30T09:00:00","2017-06-30T18:00:00","당일",null,null,null,201704140118]
[106,"경기북부","구리","구리신내#2 T/L","구형 시스전압제한기(SVL) 교체공사","1. 대상 : 154kV 구리-신내#2T/L 구리S/S EBG 1개소(3상) 2. 내용 : 구형 시스전압제한기 철거 및 신형 설치","2017-06-09 09:00","2017-06-09 18:00","2017-06-09T09:00:00","2017-06-09T18:00:00","당일",null,null,null,201704130162]
[107,"경기북부","구리","덕소마석#1 T/L","자기제 기중종단접속함(EB-A) 애관 교체공사","대상 : 154kV 덕소-마석#1T/L 덕소C/H 1개소(3상) 내용 : 구형 자기제 애관 철거 및 신형 대체용 폴리머애관 설치","2017-06-19 08:00","2017-06-22 18:00","2017-06-19T08:00:00","2017-06-22T18:00:00","연속",null,null,null,201704060070]
[108,"경기북부","구리","덕소마석#2 T/L","자기제 기중종단접속함(EB-A) 애관 교체공사","대상 : 154kV 덕소-마석#2T/L 덕소C/H 1개소(3상) 내용 : 구형 자기제 애관 철거 및 신형 대체용 폴리머애관 설치","2017-06-23 08:00","2017-06-26 18:00","2017-06-23T08:00:00","2017-06-26T18:00:00","연속",null,null,null,201704060071]
[109,"경기북부","구리","덕소별내#2 T/L","154kV 덕소별내#2 T/L 정밀점검","154kV 덕소별내#2 T/L 송전선로 정밀점검(철탑 및 충전부 등)","2017-06-26 08:00","2017-06-28 18:00","2017-06-26T08:00:00","2017-06-28T18:00:00","연속",null,null,null,201704130249]
[110,"경기북부","구리","덕소팔당HP청평HP T/L","자기제 기중종단접속함(EB-A) 애관 교체공사","대상 : 154kV 덕소-팔당HP-청평HP T/L 팔당C/H 1개소(3상) 내용 : 구형 자기제 애관 철거 및 신형 대체용 폴리머애관 설치","2017-06-12 08:00","2017-06-15 18:00","2017-06-12T08:00:00","2017-06-15T18:00:00","연속",null,null,null,201704060069]
[111,"경기북부","구리","미금광장 T/L","미금-광장T/L 보호반 교체공사","미금-광장T/L 보호반 교체공사","2017-06-26 09:00","2017-06-28 18:00","2017-06-26T09:00:00","2017-06-28T18:00:00","연속",null,null,null,201704120139]
[112,"경기북부","구리","미금구리#1 T/L","미금-구리#1T/L 보호반 교체공사","미금-구리#1T/L 보호반 교체공사","2017-06-19 09:00","2017-06-21 18:00","2017-06-19T09:00:00","2017-06-21T18:00:00","연속",null,null,null,201704120134]
[113,"경기북부","구리","미금구리#2 T/L","구리S/S 미금구리#2T/L GIS 정밀점검공사","구리S/S 미금구리#2T/L GIS 정밀점검공사","2017-06-22 08:00","2017-06-24 18:00","2017-06-22T08:00:00","2017-06-24T18:00:00","연속",null,null,null,201703140068]
[114,"경기북부","구리","미금덕소#1 T/L","154kV 미금-덕소#1T/L 정밀점검","154kV 미금-덕소#1T/L 정밀점검","2017-06-16 08:00","2017-06-16 18:00","2017-06-16T08:00:00","2017-06-16T18:00:00","당일",null,null,null,201702140021]
[115,"경기북부","구리","별내진접 T/L","일진제 조립식접속함(PMJ) 교체공사","대상 : 154kV 별내-진접T/L J/B#1~#3 총 3개소(9상) 내용 : 구형 중간접속함 전량 교체(R-Type→Flat-Type)","2017-06-19 08:00","2017-06-25 18:00","2017-06-19T08:00:00","2017-06-25T18:00:00","연속",null,null,null,201704060073]
[116,"경기북부","구리","서종청평PP#2 T/L","154kV 서종-청평PPT/L 전선접속개소 전선교체공사","154kv 서종-청평PP T/L No.12~13등 5개구간","2017-06-14 08:00","2017-06-30 18:00","취소","취소","연속",null,null,"신뢰도 개선",201703140396]
[117,"경기북부","구리","신포천덕계#2 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","154kV 백석-덕계#2T/L 피뢰기 설치공사 시행 - No.22~27호 6기(신포천덕계#2T/L 상단병가선로)","2017-06-25 07:00","2017-06-25 18:00","2017-06-25T07:00:00","2017-06-25T18:00:00","당일",null,null,null,201704130237]
[118,"경기북부","구리","진접S/S 도봉-진접T/L GIS","154kV GIS 보통점검","154kV GIS 보통점검","2017-06-07 10:00","2017-06-07 18:00","2017-06-07T10:00:00","2017-06-07T18:00:00","당일",null,null,null,201704170026]
[119,"경기북부","구리","청평HP의암HP T/L","154kV 청평HP-의암HP T/L 정밀점검","154kV 청평HP-의암HP T/L 정밀점검","2017-06-12 08:00","2017-06-15 18:00","2017-06-12T08:00:00","2017-06-15T18:00:00","연속",null,null,null,201702140020]
[120,"경기북부","구리","청평P/P 남춘천-청평PPT/L GIS","154kV GIS 보통점검","154kV GIS 보통점검","2017-06-08 10:00","2017-06-08 18:00","2017-06-08T10:00:00","2017-06-08T18:00:00","당일",null,null,null,201704170027]
[121,"경기북부","직할","녹양백석#1 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","154kV 녹양-백석#2T/L 피뢰기 설치공사 시행 - No.33~40호 8기(No.37~40호 수평배열로 인한 #1,2T/L 동시휴전)","2017-06-24 07:00","2017-06-24 13:00","2017-06-24T07:00:00","2017-06-24T13:00:00","당일",null,null,null,201704130228]
[122,"경기북부","직할","녹양백석#2 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","154kV 녹양-백석#2T/L 피뢰기 설치공사 시행 - No.33~40호 8기(No.37~40호 수평배열로 인한 #1,2T/L 동시휴전)","2017-06-24 07:00","2017-06-24 18:00","2017-06-24T07:00:00","2017-06-24T18:00:00","매일",null,null,null,201704130229]
[123,"경기북부","직할","백석덕계#1 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","154kV 녹양-백석#2T/L 피뢰기 설치공사 시행 - No.33~40호 8기(백석덕계#1T/L 상단병가선로)","2017-06-24 13:00","2017-06-24 18:00","2017-06-24T13:00:00","2017-06-24T18:00:00","당일",null,null,null,201704130230]
[124,"경기북부","직할","백석덕계#2 T/L","'16-17년 직할 가공송전정비 협력회사 총액공사","154kV 백석-덕계#2T/L 피뢰기 설치공사 시행 - No.22~27호 6기(신포천덕계#2T/L 상단병가선로)","2017-06-25 07:00","2017-06-25 18:00","2017-06-25T07:00:00","2017-06-25T18:00:00","당일",null,null,null,201704130236]
[125,"경기북부","파주","능곡S/S 지도-능곡#2T/L CB","2017년 파주전력지사 170kV GIS 정밀점검공사","능곡S/S 지도-능곡#2T/L GIS 정밀점검","2017-06-19 09:00","2017-06-21 18:00","2017-06-19T09:00:00","2017-06-21T18:00:00","연속",null,null,null,201704120052]
[126,"경기북부","파주","문산S/S 문산-선유#1T/L CB","2017년 파주전력지사 170kV GIS 정밀점검공사","문산S/S 문산-선유#1T/Lr GIS 정밀점검","2017-06-12 09:00","2017-06-14 18:00","2017-06-12T09:00:00","2017-06-14T18:00:00","연속",null,null,null,201704120050]
[127,"경기북부","파주","문산S/S 문산-선유#2T/L CB","2017년 파주전력지사 170kV GIS 정밀점검공사","문산S/S 문산-선유#2T/L GIS 정밀점검","2017-06-15 09:00","2017-06-17 18:00","2017-06-15T09:00:00","2017-06-17T18:00:00","연속",null,null,null,201704120051]
[128,"경기북부","파주","문산월롱#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2017-06-30 08:00","2017-07-04 18:00","2017-06-30T08:00:00","2017-07-04T18:00:00","연속",null,null,null,201704070059]
[129,"경기북부","파주","신덕은문산#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사 (병가선로)","2017-06-30 08:00","2017-07-04 18:00","2017-06-30T08:00:00","2017-07-04T18:00:00","연속",null,null,null,201704070060]
[130,"경기북부","파주","신덕은원흥#1 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","전력선교체 : 4.319km","2017-06-19 08:00","2017-06-23 18:00","2017-06-19T08:00:00","2017-06-23T18:00:00","연속",null,null,"신뢰도 개선",201704100207]
[131,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-수색T/L 송전용량증대 전선교체공사","전력선교체 : 4.319km","2017-06-24 08:00","2017-06-29 18:00","2017-06-24T08:00:00","2017-06-29T18:00:00","연속",null,null,"신뢰도 개선",201704100212]
[132,"경기북부","파주","양주금촌#1 T/L","154kV 양주-금촌#1T/L 전선교체공사 등","154kV 양주-금촌#1T/L No.9-14 전선교체공사 345kV 양주-중부#2T/L 전선교체공사 병가선로 안전확보","2017-06-27 07:00","2017-06-30 18:00","2017-06-27T07:00:00","2017-06-30T18:00:00","연속",null,null,null,201704130270]
[133,"경기북부","파주","원흥수색#1 T/L","154kV 원흥-수색T/L 송전용량증대 전선교체공사","No.9~12, No.14~16","2017-06-11 08:00","2017-06-14 18:00","2017-06-11T08:00:00","2017-06-14T18:00:00","연속",null,null,"신뢰도 개선",201704100214]
[134,"경기북부","파주","원흥수색#2 T/L","154kV 원흥-수색T/L 송전용량증대 전선교체공사","No.9~12, No.14~16","2017-06-15 08:00","2017-06-18 18:00","2017-06-15T08:00:00","2017-06-18T18:00:00","연속",null,null,"신뢰도 개선",201704100223]
[135,"경기북부","파주","일산S/S #1S/T GIS","16~17 파주전력지사 변전협력회사 총액공사","일산S/S #1S/T T/L(6113) GIS 하자점검","2017-06-21 09:00","2017-06-21 18:00","2017-06-21T09:00:00","2017-06-21T18:00:00","당일",null,null,null,201704120057]
[136,"경기북부","파주","일산S/S 154kV #66 BUS","일산S/S 170kV GIS 교체공사","170kV GIS 교체공사 - #2S/T, #5G/T, #4M.Tr 1차 GIS 철거, 설치 - 기타부대공사","2017-06-01 08:30","2017-06-07 08:00","2017-06-01T08:30:00","2017-06-07T08:00:00","연속",null,null,null,201703140134]
[137,"경기북부","파주","일산S/S 일산-지도#1T/L GIS","16~17 파주전력지사 변전협력회사 총액공사","일산S/S 일산-지도#1T/L GIS 초기점검","2017-06-14 09:00","2017-06-14 18:00","2017-06-14T09:00:00","2017-06-14T18:00:00","당일",null,null,null,201704130026]
[138,"경기북부","파주","일산S/S 일산-지도#2T/L GIS","16~17 파주전력지사 변전협력회사 총액공사","일산S/S 일산-지도#2T/L GIS 초기점검","2017-06-12 09:00","2017-06-12 18:00","2017-06-12T09:00:00","2017-06-12T18:00:00","당일",null,null,null,201704130028]
[139,"경기","군포","관양평촌#2 T/L","154kV 평촌S/S S.W 증설 관련 GIS 설치공사","- 기기설치 후 무부하 가압","2017-06-15 15:00","2017-06-16 15:00","2017-06-15T15:00:00","2017-06-16T15:00:00","연속",null,null,null,201704130041]
[140,"경기","군포","관양평촌#2 T/L","154kV 평촌S/S S.W 증설 관련 GIS 설치공사","- 기기설치 후 무부하 가압","2017-06-08 14:00","2017-06-09 14:00","2017-06-08T14:00:00","2017-06-09T14:00:00","연속",null,null,null,201704130040]
[141,"경기","군포","서서울일동#1 T/L","345kV 신군포변전소 건설공사","서서울-일동 #1T/L 1회선 이설 기존 서서울 SS, 변경 서서울2 SS","2017-06-12 07:00","2017-06-17 18:00","2017-06-12T07:00:00","2017-06-17T18:00:00","연속",null,null,null,201704110180]
[142,"경기","군포","서서울일동#2 T/L","345kV 신군포변전소 건설공사","서서울-일동 #2T/L 1회선 이설 기존 서서울 SS, 변경 서서울2 SS","2017-06-19 07:00","2017-06-24 18:00","2017-06-19T07:00:00","2017-06-24T18:00:00","연속",null,null,null,201704110181]
[143,"경기","군포","서안양소래 T/L","154kV 서서울-서안양 등 4개T/L 자기애관 교체공사","자기제 애관을 폴리머제 애관으로 교체","2017-06-10 09:00","2017-06-13 18:00","2017-06-10T09:00:00","2017-06-13T18:00:00","연속",null,null,null,201704140077]
[144,"경기","군포","시화중시화 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 중시화S/S 시화중시화T/L","2017-06-01 09:00","2017-06-03 18:00","2017-06-01T09:00:00","2017-06-03T18:00:00","연속",null,null,null,201703080332]
[145,"경기","군포","신안산S/S 154kV #1 BUS TIE GIS","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 신안산S/S #1BUS-TIE GIS","2017-06-19 09:00","2017-06-21 18:00","2017-06-19T09:00:00","2017-06-21T18:00:00","연속",null,null,null,201704060193]
[146,"경기","군포","신안산S/S 154kV #2 BUS TIE GIS","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 신안산S/S #2BUS-TIE GIS","2017-06-22 09:00","2017-06-24 18:00","2017-06-22T09:00:00","2017-06-24T18:00:00","연속",null,null,null,201704060199]
[147,"경기","군포","신안산남안산#1 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 신안산S/S 신안산-남안산#1T/L GIS","2017-06-12 09:00","2017-06-14 18:00","2017-06-12T09:00:00","2017-06-14T18:00:00","연속",null,null,null,201704060169]
[148,"경기","군포","신안산남안산#2 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 신안산S/S 신안산-남안산#2T/L GIS","2017-06-15 09:00","2017-06-17 18:00","2017-06-15T09:00:00","2017-06-17T18:00:00","연속",null,null,null,201704060191]
[149,"경기","군포","신안산성포#3 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 신안산S/S 신안산-성포#3T/L GIS","2017-06-07 09:00","2017-06-09 18:00","2017-06-07T09:00:00","2017-06-09T18:00:00","연속",null,null,null,201704060166]
[150,"경기","동부","곤지암초월#1 T/L","17년 동부 주기도래 점검","곤지암S/S 곤지암-초월 GIS (보통)","2017-06-30 09:30","2017-06-30 18:00","2017-06-30T09:30:00","2017-06-30T18:00:00","당일",null,null,null,201704130310]
[151,"경기","동부","곤지암초월#2 T/L","GIS 정밀점검 공사","초월S/S 곤지암-초월#2 GIS (정밀)/병행:곤지암S/S 곤지암-초월#2 GIS(보통)","2017-06-22 09:00","2017-06-24 18:00","2017-06-22T09:00:00","2017-06-24T18:00:00","연속",null,null,null,201704130292]
[152,"경기","동부","동판교야탑 T/L","17년 동부 주기도래 점검","동판교S/S 동판교-야탑 GIS (보통)","2017-06-16 09:30","2017-06-16 18:00","2017-06-16T09:30:00","2017-06-16T18:00:00","당일",null,null,null,201704130309]
[153,"경기","동부","분당S/S 154kV #1 BUS TIE GIS","GIS 정밀점검 공사","분당S/S 6100 TIE GIS (정밀)","2017-06-19 09:00","2017-06-21 18:00","2017-06-19T09:00:00","2017-06-21T18:00:00","연속",null,null,null,201704130291]
[154,"경기","동부","분당S/S 60-61 SEC GIS","GIS 정밀점검 공사","분당S/S 60-61 SEC GIS (정밀)","2017-06-12 09:00","2017-06-14 18:00","2017-06-12T09:00:00","2017-06-14T18:00:00","연속",null,null,null,201704130289]
[155,"경기","동부","분당S/S 65-66 SEC GIS","GIS 정밀점검 공사","분당S/S 65-66 SEC GIS (정밀)","2017-06-15 09:00","2017-06-17 18:00","2017-06-15T09:00:00","2017-06-17T18:00:00","연속",null,null,null,201704130290]
[156,"경기","동부","오포모현#1 T/L","154kV 오포-모현#1T/L 낙뢰소산장치 철거공사","154kV 오포-모현#1T/L 4~18호 구간 낙뢰소산장치 철거","2017-06-19 07:00","2017-06-26 18:00","2017-06-19T07:00:00","2017-06-26T18:00:00","연속",null,null,null,201704110138]
[157,"경기","성남","동탄C/C S/T#1 GIS","17년 성남변전협력회사 총액공사","6233 GIS 초기점검","2017-06-12 10:00","2017-06-12 18:00","2017-06-12T10:00:00","2017-06-12T18:00:00","당일",null,null,null,201704140087]
[158,"경기","성남","동탄C/C S/T#2 GIS","17년 성남변전협력회사 총액공사","6333 GIS 초기점검","2017-06-16 10:00","2017-06-16 18:00","2017-06-16T10:00:00","2017-06-16T18:00:00","당일",null,null,null,201704140173]
[159,"경기","성남","모현용인#1 T/L","154kV 모현-용인#1T/L 소도체 이도조정 및 애자련 교체 공사","154kV 모현-용인#1T/L 13~15호 소도체 이도조정 154kV 모현-용인#1T/L 38호 애자련 교체","2017-06-27 08:00","2017-06-28 13:00","2017-06-27T08:00:00","2017-06-28T13:00:00","연속",null,null,null,201704070274]
[160,"경기","성남","모현용인#2 T/L","154kV 모현-용인#2T/L 소도체 이도조정 및 애자련 교체 공사","154kV 모현-용인#2T/L 13~15호 소도체 이도조정 154kV 모현-용인#2T/L 38호 애자련 교체","2017-06-28 13:00","2017-06-29 18:00","2017-06-28T13:00:00","2017-06-29T18:00:00","연속",null,null,null,201704070276]
[161,"경기","성남","서안성남사#2 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","- 345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69) 시 No.26 병가선로 안전이격확보","2017-06-09 08:00","2017-06-09 18:00","2017-06-09T08:00:00","2017-06-09T18:00:00","당일",null,null,null,201704190070]
[162,"경기","성남","신용인S/S 154kV #2 BUS-TIE(6200) GIS","17년 성남변전협력회사 총액공사","GIS 보통점검","2017-06-09 10:00","2017-06-09 18:00","2017-06-09T10:00:00","2017-06-09T18:00:00","당일",null,null,null,201704140169]
[163,"경기","성남","신용인용인#1 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","- 345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69) 시 No.46-48 병가선로 안전이격확보","2017-06-07 08:00","2017-06-07 18:00","2017-06-07T08:00:00","2017-06-07T18:00:00","당일",null,null,null,201704120112]
[164,"경기","성남","신용인용인#2 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","- 345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69) 시 No.46-48 병가선로 안전이격확보","2017-06-08 08:00","2017-06-08 18:00","2017-06-08T08:00:00","2017-06-08T18:00:00","당일",null,null,null,201704130107]
[165,"경기","성남","용인남사#1 T/L","345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69)","- 345kV 신안성신수원T/L 피뢰기 설치공사(No.1~69) 시 No.26 병가선로 안전이격확보","2017-06-09 08:00","2017-06-09 18:00","2017-06-09T08:00:00","2017-06-09T18:00:00","당일",null,null,null,201704190069]
[166,"경기","직할","관양동안양#1 T/L","동안양S/S 154kV 관양동안양#1T/L 차단기 조작시험","동안양S/S 154kV 관양동안양#1T/L 차단기 조작시험","2017-06-05 10:00","2017-06-05 14:00","2017-06-05T10:00:00","2017-06-05T14:00:00","당일",null,null,null,201704130007]
[167,"경기","직할","관양동안양#2 T/L","동안양S/S 154kV 관양동안양#2T/L 차단기 조작시험","동안양S/S 154kV 관양동안양#2T/L 차단기 조작시험","2017-06-05 14:00","2017-06-05 18:00","2017-06-05T14:00:00","2017-06-05T18:00:00","당일",null,null,null,201704130008]
[168,"경기","직할","발안향남#1 T/L","154kV 남수원-발안T/L No.7-8 등 4개구간 전선 교체공사","-154kV 남수원-발안T/L No.7-8 등 3개구간 전선접속개소 교체공사 전선교체시병가선로 안전이격확보","2017-06-16 08:00","2017-06-18 18:00","2017-06-16T08:00:00","2017-06-18T18:00:00","연속",null,null,null,201704130098]
[169,"경기","직할","발안향남#2 T/L","154kV 남수원-발안T/L No.7-8 등 4개구간 전선 교체공사","-154kV 남수원-발안T/L No.7-8 등 3개구간 전선접속개소 교체공사 전선교체시 병가선로 안전이격확보","2017-06-21 08:00","2017-06-23 18:00","2017-06-21T08:00:00","2017-06-23T18:00:00","연속",null,null,null,201704130099]
[170,"경기","직할","병점세교#1 T/L","세교S/S 154kV 병점세교#1T/L 차단기 조작시험","세교S/S 154kV 병점세교#1T/L 차단기 조작시험","2017-06-09 10:00","2017-06-09 14:00","2017-06-09T10:00:00","2017-06-09T14:00:00","당일",null,null,null,201704130010]
[171,"경기","직할","병점세교#2 T/L","세교S/S 154kV 병점세교#2T/L 차단기 조작시험","세교S/S 154kV 병점세교#2T/L 차단기 조작시험","2017-06-09 14:00","2017-06-09 18:00","2017-06-09T14:00:00","2017-06-09T18:00:00","당일",null,null,null,201704130011]
[172,"경기","직할","서서울남수원#1 T/L","154kV 남수원-발안T/L No.7-8 등 4개구간 전선 교체공사","-154kV 남수원-발안T/L No.55-56 전선접속개소 교체공사 전선교체시 병가선로 안전이격확보","2017-06-20 08:00","2017-06-20 18:00","2017-06-20T08:00:00","2017-06-20T18:00:00","당일",null,null,null,201704120120]
[173,"경기","직할","서서울남수원#2 T/L","154kV 남수원-발안T/L No.7-8 등 4개구간 전선 교체공사","-154kV 남수원-발안T/L No.55-56 전선접속개소 교체공사 전선교체시 병가선로 안전이격확보","2017-06-19 08:00","2017-06-19 18:00","2017-06-19T08:00:00","2017-06-19T18:00:00","당일",null,null,null,201704120119]
[174,"경기","평택","서안성안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측(#1BUS-SEC, 안성-남안성#1T/L BAY 설치) 무부하가압","2017-06-05 09:30","2017-06-06 18:00","2017-06-05T09:30:00","2017-06-06T18:00:00","연속",null,null,null,201703170178]
[175,"경기","평택","서안성안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측(#1BUS-SEC, 안성-남안성#1T/L BAY 설치) 무부하가압","2017-06-19 09:30","2017-06-20 18:00","2017-06-19T09:30:00","2017-06-20T18:00:00","연속",null,null,null,201703170194]
[176,"경기","평택","서안성안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측(#1BUS-SEC, 안성-남안성#1T/L BAY 설치) 무부하가압","2017-06-12 09:30","2017-06-13 18:00","2017-06-12T09:30:00","2017-06-13T18:00:00","연속",null,null,null,201703170198]
[177,"경기","평택","서안성안성#2 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측(#2BUS-SEC, 안성-남안성#1T/L BAY 설치)안전이격거리확보","2017-06-01 09:30","2017-06-03 18:00","2017-06-01T09:30:00","2017-06-03T18:00:00","연속",null,null,null,201703140546]
[178,"경기","평택","서운안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측(#61BUS PT, 6200 B/T,안성-남안성#2T/L BAY 설치) 안전이격거리확보","2017-06-08 09:30","2017-06-09 18:00","2017-06-08T09:30:00","2017-06-09T18:00:00","연속",null,null,null,201704180148,"○"]
[179,"경기","평택","서운안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측(#2BUS-SEC, 안성-남안성#1T/L BAY 설치)안전이격거리확보","2017-06-01 09:30","2017-06-03 18:00","2017-06-01T09:30:00","2017-06-03T18:00:00","연속",null,null,null,201703140540,"○"]
[180,"경기","평택","서운안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS(#66BUS PT, 6200B/T, 안성-남안성#2T/L)BAY 설치 안전이격거리확보","2017-06-15 09:30","2017-06-16 18:00","2017-06-15T09:30:00","2017-06-16T18:00:00","연속",null,null,null,201703140543,"○"]
[181,"경기","평택","서운안성#2 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측(#61BUS PT, 6200 B/T,안성-남안성#2T/L BAY 설치) 안전이격거리확보","2017-06-10 09:30","2017-06-10 18:00","2017-06-10T09:30:00","2017-06-10T18:00:00","연속",null,null,null,201704180149]
[182,"경기","평택","서운안성#2 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS(#66BUS PT, 6200B/T, 안성-남안성#2T/L)BAY 설치 안전이격거리확보","2017-06-17 09:30","2017-06-17 18:00","2017-06-17T09:30:00","2017-06-17T18:00:00","연속",null,null,null,201703140547]
[183,"경기","평택","안성S/S 154kV #1 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS측 GIS와 모선보호반간 인터록 시험","2017-06-21 09:30","2017-06-22 18:00","2017-06-21T09:30:00","2017-06-22T18:00:00","연속",null,null,null,201704130255,"○"]
[184,"경기","평택","안성S/S 154kV #1 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS(#61BUS PT, 6200B/T, 안성-남안성#2T/L)BAY 설치","2017-06-07 09:30","2017-06-13 18:00","2017-06-07T09:30:00","2017-06-13T18:00:00","연속",null,null,null,201703140549,"○"]
[185,"경기","평택","안성S/S 154kV #2 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS(#66BUS PT, 6200B/T, 안성-남안성#2T/L)BAY 설치","2017-06-14 09:30","2017-06-20 18:00","2017-06-14T09:30:00","2017-06-20T18:00:00","연속",null,null,null,201703140538]
[186,"경기","평택","안성S/S 154kV #2 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측 GIS와 모선보호반간 인터록 시험","2017-06-23 09:30","2017-06-24 18:00","2017-06-23T09:30:00","2017-06-24T18:00:00","연속",null,null,null,201704130256]
[187,"경기","평택","오산평택#1 T/L","154kV 오산평택T/L 지중화공사(구간 No.6~9)","정남산업단지조성관련 지중화공사(6~9호, 전력구 0.58km) 임시선로 구성 휴전작업 (임시철탑 2기), 오산향남T/L 병가선로","2017-06-04 08:00","2017-06-07 18:00","2017-06-04T08:00:00","2017-06-07T18:00:00","연속",null,null,null,201704140012]
[188,"경기","평택","오산평택#2 T/L","154kV 오산평택T/L 지중화공사(구간 6~9)","화성정남산업단지조성관련 선로지중화(오산평택 6~9, 0.58km) 임시선로구성 휴전작업(오산평택 #2, 철탑 2기)","2017-06-01 07:00","2017-06-03 18:00","2017-06-01T07:00:00","2017-06-03T18:00:00","연속",null,null,null,201704140014]
[189,"경기","평택","오산평택#2 T/L","154kV 오산-평택T/L 안전이격거리 확보공사 등 3개공사","○ 공사규모 : 철탑 3기 교체, 전력선 1.28km교체(안전이격공사) ○ 공사구간 : No.53~58(안전이격공사) ○ 이외공사 : 전력선교체 3개소, 피뢰기설치 73기","2017-06-08 07:00","2017-06-09 18:00","2017-06-08T07:00:00","2017-06-09T18:00:00","연속",null,null,null,201704140265]
[190,"경기","평택","오산향남#1 T/L","154kV 오산향남T/L 지중화공사(구간 No.14~17)","정남산업단지조성관련 지중화공사(14~17호, 전력구 0.58km) 임시선로 구성 휴전작업 (임시철탑 2기)","2017-06-04 08:00","2017-06-07 18:00","2017-06-04T08:00:00","2017-06-07T18:00:00","연속",null,null,null,201704140011]
[191,"경기","평택","오산향남#2 T/L","154kV 오산향남T/L 지중화공사(구간 No.14~17)","정남산업단지조성관련 지중화공사(14~17호, 전력구 0.58km) 임시선로 구성 휴전작업 (임시철탑 2기)","2017-06-01 08:00","2017-06-03 18:00","2017-06-01T08:00:00","2017-06-03T18:00:00","연속",null,null,null,201704140006]
[192,"경기","평택","청북평택#2 T/L","154kV 청북-평택T/L 송전용 피뢰기설치공사","○ 공사규모 : 피뢰기 14기 설치 ○ 공사구간 : No.10~26","2017-06-15 08:00","2017-06-17 18:00","2017-06-15T08:00:00","2017-06-17T18:00:00","매일",null,null,null,201704140266]
[193,"강원","강릉","북평영동TP#1 T/L","2017년 변전협력회사 총액공사","영동화력S/Y 154kV GIS 점검, 피뢰기 점검","2017-06-07 10:00","2017-06-07 18:00","2017-06-07 10:00","2017-06-07 18:00","당일",null,null,null,201704070248]
[194,"강원","강릉","북평영동TP#2 T/L","2017년 변전협력회사 총액공사","영동화력S/Y 154kV GIS 점검, 피뢰기 점검","2017-06-08 10:00","2017-06-08 18:00","2017-06-08 10:00","2017-06-08 18:00","당일",null,null,null,201704070250]
[195,"강원","강릉","신양양_양양#1 T/L","154kV 주문진양양 #2T/L 피뢰기 설치공사(병가철탑구간)","○ 송전선로용 피뢰기 설치공사 병가철탑(주문진양양#2 작업, 25일)","2017-06-25 07:30","2017-06-25 18:00","2017-06-25 07:30","2017-06-25 18:00","당일",null,null,null,201704100199]
[196,"강원","동해","이원도계 T/L","2017년 가공송전선로 순시점검위탁공사(동해)","154kV 이원-도계T/L 송전선로 정밀점검 -No.31~이원S/S (94기) -66년산 애자발취","2017-06-19 09:00","2017-06-27 18:00","2017-06-19 09:00","2017-06-27 18:00","매일",null,null,null,201704100001]
[197,"강원","동해","이원태백 T/L","2017년 가공송전선로 순시점검위탁공사(동해)","154kV 이원-태백T/L 송전선로 정밀점검 -No.31~이원S/S (94기)","2017-06-12 09:00","2017-06-16 18:00","2017-06-12 09:00","2017-06-16 18:00","매일",null,null,null,201704100002]
[198,"강원","원주","횡성홍천#1 T/L","154kV 횡성-홍천T/L No.69-74 안전이격 확보공사","철거 : 5기, 신설 5기 보강 1기 전력선교체 : 2.304km","2017-06-12 09:00","2017-06-19 18:00","2017-06-12 09:00","2017-06-19 18:00","연속",null,null,null,201704060084]
[199,"강원","원주","횡성홍천#2 T/L","154kV 횡성-홍천T/L No.69-74 안전이격 확보공사","철거 5기, 신설 5기 보강 1기 전력선 교체 ; 2.034km","2017-06-12 09:00","2017-06-19 18:00","2017-06-12 09:00","2017-06-19 18:00","연속",null,null,null,201704060085]
[200,"강원","직할","가평춘천HP T/L","16-17년 직할 변전정비 협력회사 총액공사","춘천HP 가평-춘천HP T/L DS B 북춘천-춘천HP T/L DS B 154kV #1BUS PT 하자점검","2017-06-12 09:00","2017-06-12 18:00","2017-06-12 09:00","2017-06-12 18:00","당일",null,null,null,201704070392]
[201,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑설치/철거 : 4기 (No.46,47,48,49) ○ 전력선교체 : No.46~50간 (2c-1.64km)","2017-06-19 08:00","2017-06-22 18:00","2017-06-19 08:00","2017-06-22 18:00","연속",null,null,null,201704100417]
[202,"강원","직할","북춘천춘천HP T/L","16-17년 직할 변전정비 협력회사 총액공사","춘천HP 가평-춘천HP T/L DS B 북춘천-춘천HP T/L DS B 154kV #1BUS PT 하자점검","2017-06-12 09:00","2017-06-12 18:00","2017-06-12 09:00","2017-06-12 18:00","당일",null,null,null,201704070393]
[203,"강원","직할","북춘천화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑설치/철거 : 4기 (No.46,47,48,49) ○ 전력선교체 : No.46~50간 (2c-1.64km)","2017-06-23 08:00","2017-06-26 18:00","2017-06-23 08:00","2017-06-26 18:00","연속",null,null,null,201704100421]
[204,"강원","직할","인제양구#1 T/L","2017년도 송전정비 협력회사 총액공사","○ 전력선 교체 - 공사구간 154kV 인제-양구#1T/L No66~양구S/S(25m)","2017-06-02 09:00","2017-06-02 18:00","2017-06-02 09:00","2017-06-02 18:00","당일",null,null,null,201704110093]
[205,"강원","직할","화천화천HP#2 T/L","2017년 가공송전선로 순시점검 위탁공사","○ 정밀점검 : 화천HP~화천S/S (50기)","2017-06-12 08:00","2017-06-14 18:00","2017-06-12 08:00","2017-06-14 18:00","매일",null,null,null,201704110128]
[206,"강원","태백","도계태백 T/L","17년 가공송전 순시점검 위탁공사","154kV 태원T/L 정밀점검","2017-06-08 09:00","2017-06-09 18:00","2017-06-08 09:00","2017-06-09 18:00","매일",null,null,null,201704100594]
[207,"강원","태백","태백고한 T/L","2016~2017 태백전력지사 변전정비 총액공사","태백-고한T/L LA점검 및 고한S/S측 CB 조작시험","2017-06-02 10:00","2017-06-02 18:00","2017-06-02 10:00","2017-06-02 18:00","당일",null,null,null,201703210319]
[208,"충북","직할","신제천남원주#2 T/L","345kV 신제천S/S GIS화 공사","신제천-남원주#2T/L 옥외철구⇒GIS 이설","2017-06-14 08:00","2017-06-16 18:00","2017-06-14 08:00","2017-06-16 18:00","연속",null,null,null,201704070153]
[209,"충북","직할","신제천영월CC#2 T/L","345kV 신제천S/S GIS화 공사","신제천-영월CC#2T/L 옥외철구⇒GIS 이설","2017-06-27 08:00","2017-06-30 18:00","2017-06-27 08:00","2017-06-30 18:00","연속",null,null,null,201704070159]
[210,"충북","직할","신제천제천#2 T/L","345kV 신제천S/S GIS화 공사","신제천-제천#2T/L 옥외철구⇒GIS 이설","2017-06-27 08:00","2017-06-30 18:00","2017-06-27 08:00","2017-06-30 18:00","연속",null,null,null,201704070157]
[211,"충북","직할","신제천주진#1 T/L","345kV 신제천S/S GIS화 공사","신제천-주진#1T/L 옥외철구⇒GIS 이설","2017-06-19 08:00","2017-06-23 18:00","2017-06-19 08:00","2017-06-23 18:00","연속",null,null,null,201704070154]
[212,"충북","청주","옥천보은 T/L","170kV 장기사용 GIS 대체 공사","170kV 장기사용 GIS 대체 공사","2017-06-01 09:30","2017-06-14 18:00","2017-06-01 09:30","2017-06-14 18:00","연속",null,null,null,201704030117]
[213,"충북","청주","옥천영동 T/L","170kV 장기사용 GIS 대체 공사","170kV 장기사용 GIS 대체 공사","2017-06-15 09:30","2017-06-30 18:00","2017-06-15 09:30","2017-06-30 18:00","연속",null,null,null,201704030176]
[214,"충북","충주","신진천S/S 154kV #1 BUS TIE GIS","2017년 충주전력지사 154kV GIS 정밀점검공사","154kV #1BUS-TIE GIS(차단기 및 #1,2BUS DS)정밀점검","2017-06-09 08:00","2017-06-10 18:00","2017-06-09 08:00","2017-06-10 18:00","연속",null,null,null,201704100158]
[215,"충북","충주","신진천S/S 154kV #60 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","154kV #1BUS-TIE GIS(차단기 및 #1BUS DS)정밀점검","2017-06-09 08:00","2017-06-10 09:00","2017-06-09 08:00","2017-06-10 09:00","연속",null,null,null,201704100159]
[216,"충북","충주","신진천S/S 154kV #60 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","#61M.Tr 1차 GIS(차단기 및 #1BUS DS)정밀점검","2017-06-11 08:00","2017-06-12 09:00","2017-06-11 08:00","2017-06-12 09:00","연속",null,null,null,201704100169]
[217,"충북","충주","신진천S/S 154kV #61 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","신진천-오창#1T/L GIS(차단기 및 #1BUS DS)정밀점검","2017-06-03 08:00","2017-06-04 09:00","2017-06-03 08:00","2017-06-04 09:00","연속",null,null,null,201704100143]
[218,"충북","충주","신진천S/S 154kV #61 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","신진천-진천#2T/L GIS(차단기 및 #1BUS DS)정밀점검","2017-06-05 08:00","2017-06-06 09:00","2017-06-05 08:00","2017-06-06 09:00","연속",null,null,null,201704100151]
[219,"충북","충주","신진천S/S 154kV #62 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","#3M.Tr 2차 GIS(차단기 및 #1BUS DS)정밀점검","2017-06-07 08:00","2017-06-08 09:00","2017-06-07 08:00","2017-06-08 09:00","연속",null,null,null,201704100156]
[220,"충북","충주","신진천S/S 154kV #65 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","154kV #1BUS-TIE GIS(차단기 및 #2BUS DS)정밀점검","2017-06-10 09:00","2017-06-10 18:00","2017-06-10 09:00","2017-06-10 18:00","당일",null,null,null,201704100162]
[221,"충북","충주","신진천S/S 154kV #65 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","#61M.Tr 1차 GIS(차단기 및 #2BUS DS)정밀점검","2017-06-12 09:00","2017-06-12 18:00","2017-06-12 09:00","2017-06-12 18:00","당일",null,null,null,201704100177]
[222,"충북","충주","신진천S/S 154kV #66 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","신진천-진천#2T/L GIS(차단기 및 #2BUS DS)정밀점검","2017-06-06 09:00","2017-06-06 18:00","2017-06-06 09:00","2017-06-06 18:00","당일",null,null,null,201704100154]
[223,"충북","충주","신진천S/S 154kV #66 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","신진천-오창#1T/L GIS(차단기 및 #2BUS DS)정밀점검","2017-06-04 09:00","2017-06-04 18:00","2017-06-04 09:00","2017-06-04 18:00","당일",null,null,null,201704100144]
[224,"충북","충주","신진천S/S 154kV #67 BUS","2017년 충주전력지사 154kV GIS 정밀점검공사","#3M.Tr 2차 GIS(차단기 및 #2BUS DS)정밀점검","2017-06-08 09:00","2017-06-08 18:00","2017-06-08 09:00","2017-06-08 18:00","당일",null,null,null,201704100157]
[225,"충북","충주","신진천오창#1 T/L","2017년 충주전력지사 154kV GIS 정밀점검공사","신진천-오창#1T/L GIS(차단기 및 #1,2BUS DS)정밀점검","2017-06-03 08:00","2017-06-04 18:00","2017-06-03 08:00","2017-06-04 18:00","연속",null,null,null,201704100142]
[226,"충북","충주","충주풍동 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.64~75)","2017-06-26 09:00","2017-06-26 18:00","2017-06-26 09:00","2017-06-26 18:00","당일",null,null,null,201704130022,"○"]
[227,"충북","충주","풍동음성#1 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사","154kV 풍동-음성#1T/L 전력선교체","2017-06-13 07:00","2017-06-25 18:00","2017-06-13 07:00","2017-06-25 18:00","연속",null,null,null,201704100493,"○"]
[228,"충북","충주","풍동음성#2 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사","154kV 풍동-음성#2T/L 전력선교체","2017-06-26 07:00","2017-07-05 18:00","2017-06-26 07:00","2017-07-05 18:00","연속",null,null,null,201704100502,"○"]
[229,"대전충남","대전","신계룡S/S #1EM.Tr  CB","신계룡S/S ESS 배터리점검 및 PSS점검","신계룡S/S ESS 배터리점검 및 PSS점검","2017-06-12 09:00","2017-06-16 18:00","2017-06-12T09:00:00","2017-06-16T18:00:00","연속",null,null,null,201704140003]
[230,"대전충남","대전","신계룡두마#1 T/L","(토건)두마S/S 건물내벽(타일) 보강공사","(토건)두마S/S 건물내벽(타일) 보강공사","2017-06-05 09:00","2017-06-08 18:00","2017-06-05T09:00:00","2017-06-08T18:00:00","연속",null,null,null,201704100218]
[231,"대전충남","대전","신계룡두마#2 T/L","(토건)두마S/S 건물내벽(타일) 보강공사","(토건)두마S/S 건물내벽(타일) 보강공사","2017-06-05 09:00","2017-06-08 18:00","2017-06-05T09:00:00","2017-06-08T18:00:00","연속",null,null,null,201704100219]
[232,"대전충남","대전","신옥천남대전#1 T/L","[송전]154kV 조치원-대화 등 7개T/L 노후 피뢰기교체공사","154kV 신옥천남대전#1T/L C/H(No.30)용 피뢰기 교체공사 시행","2017-06-07 09:00","2017-06-07 18:00","2017-06-07T09:00:00","2017-06-07T18:00:00","당일",null,null,null,201704070034]
[233,"대전충남","대전","신옥천남대전#2 T/L","[송전]154kV 조치원-대화 등 7개T/L 노후 피뢰기교체공사","154kV 신옥천남대전#2T/L C/H(No.30)용 피뢰기 교체공사 시행","2017-06-08 09:00","2017-06-08 18:00","2017-06-08T09:00:00","2017-06-08T18:00:00","당일",null,null,null,201704070035]
[234,"대전충남","대전","신옥천남대전#4 T/L","[송전]154kV 조치원-대화 등 7개T/L 노후 피뢰기교체공사","154kV 신옥천남대전#4T/L C/H(No.30)용 피뢰기 교체공사 시행","2017-06-09 09:00","2017-06-09 18:00","2017-06-09T09:00:00","2017-06-09T18:00:00","당일",null,null,null,201704070039]
[235,"대전충남","대전","팔봉두마#1 T/L","(토건)두마S/S 건물내벽(타일) 보강공사","(토건)두마S/S 건물내벽(타일) 보강공사","2017-06-01 09:00","2017-06-04 18:00","2017-06-01T09:00:00","2017-06-04T18:00:00","연속",null,null,null,201704100215]
[236,"대전충남","대전","팔봉두마#2 T/L","(토건)두마S/S 건물내벽(타일) 보강공사","(토건)두마S/S 건물내벽(타일) 보강공사","2017-06-01 09:00","2017-06-04 18:00","2017-06-01T09:00:00","2017-06-04T18:00:00","연속",null,null,null,201704100216]
[237,"대전충남","서산","태안T/P 154kV #1 BUS TIE CB","'17년 변전협력회사 총액공사","태안화력 154kV #1BUS-TIE 차단기 부동작 예방시험","2017-06-05 10:00","2017-06-05 14:00","2017-06-05T10:00:00","2017-06-05T14:00:00","당일",null,null,null,201704100878]
[238,"대전충남","세종","부강월산#1 T/L","[송전] 154kV 부강-월산#1T/L 정밀점검","[송전] #1T/L No.7~43 정밀점검","2017-06-12 07:00","2017-06-14 19:00","2017-06-12T07:00:00","2017-06-14T19:00:00","당일",null,null,null,201704050074]
[239,"대전충남","세종","부강월산#2 T/L","[송전] 154kV 부강-월산#2T/L 정밀점검","[송전] #2T/L No.7~43 정밀점검","2017-06-15 07:00","2017-06-17 19:00","2017-06-15T07:00:00","2017-06-17T19:00:00","당일",null,null,null,201704050075]
[240,"대전충남","세종","부강월산#2 T/L","154kV 월산S/S #3M.Tr 증설공사","○ #3M.TR 1차 GIS 설치 및 #2BUS 가압시험 ○ 인터록케이블 포설 및 결선 등 기타부대공사 * 1식","2017-06-01 18:00","2017-06-02 18:00","취소","취소","연속",null,null,"신뢰도 개선",201704070452]
[241,"대전충남","세종","부강월산#2 T/L","154kV 월산S/S #3M.Tr 증설공사","○ #3M.TR 1차 GIS 설치 및 #1BUS 가압시험 ○ 인터록케이블 포설 및 결선 등 기타부대공사 * 1식","2017-06-03 18:00","2017-06-06 09:30","취소","취소","연속",null,null,"신뢰도 개선",201704100039]
[242,"대전충남","세종","신풍공주#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2017-06-15 09:00","2017-06-15 18:00","2017-06-19T09:00:00","2017-06-19T18:00:00","당일",null,null,null,201704060234]
[243,"대전충남","세종","신풍공주#2 T/L","[송전] 154kV 신풍-공주#2T/L 전선교체공사","[송전] #2T/L No.60~65 전선교체공사","2017-06-19 07:00","2017-06-23 19:00","2017-06-12T07:00:00","2017-06-16T19:00:00","연속",null,null,null,201704050076]
[244,"대전충남","아산","둔포추팔#1 T/L","둔포S/S 154kV 둔포-추팔#1T/L GIS 정밀점검","○ 154kV 둔포-추팔#1T/L GIS 정밀점검","2017-06-29T09:00:00","2017-07-01T18:00:00","취소","취소","연속",null,null,"신뢰도 개선",201704070254]
[245,"대전충남","아산","둔포추팔#2 T/L","둔포S/S 154kV 둔포-추팔#2T/L GIS 정밀점검","○ 154kV 둔포-추팔#2T/L GIS 정밀점검","2017-06-26 09:00","2017-06-28 18:00","취소","취소","연속",null,null,"신뢰도 개선",201704070255]
[246,"대전충남","아산","서천안탕정#1 T/L","서천안S/S 154kV 서천안-탕정#1T/L 보호배전반 교체","○ 154kV 서천안-탕정#1T/L 보호배전반 교체","2017-06-26 09:00","2017-06-29 18:00","2017-06-19T09:00:00","2017-06-22T18:00:00","연속",null,null,null,201704070260]
[247,"대전충남","아산","신온양석곡#1 T/L","신온양S/S 154kV 신온양-석곡#1T/L GIS 정밀점검","○ 154kV 신온양-석곡#1T/L GIS 정밀점검","2017-06-12 09:00","2017-06-13 18:00","2017-06-12T09:00:00","2017-06-13T18:00:00","당일",null,null,null,201704180025]
[248,"대전충남","아산","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L GIS 정밀점검","○ 154kV 신온양-석곡#2T/L GIS 정밀점검","2017-06-14 09:00","2017-06-15 18:00","2017-06-14T09:00:00","2017-06-15T18:00:00","당일",null,null,null,201704180026]
[249,"대전충남","아산","아산예산#1 T/L","[송전] 154kV 아산-예산T/L 안전이격확보공사","154kV 아산-예산T/L 15호 안전이격확보공사 및 기타 부대공사","2017-06-04 07:00","2017-06-07 18:00","2017-06-04T07:00:00","2017-06-08T18:00:00","연속",null,null,null,201703080127]
[250,"대전충남","아산","아산예산#2 T/L","[송전] 154kV 아산-예산T/L 안전이격확보공사","○ 154kV 아산-예산T/L 15호 안전이격확보공사 및 기타 부대공사","2017-06-04 07:00","2017-06-07 18:00","2017-06-04T07:00:00","2017-06-08T18:00:00","연속",null,null,null,201703080128]
[251,"대전충남","아산","온양풍세#2 T/L","154kV 온양-풍세 #2T/L 정밀점검","154kV 온양-풍세 #2T/L 정밀점검","2017-06-17 07:00","2017-06-18 18:00","2017-06-17T07:00:00","2017-06-18T18:00:00","매일",null,null,null,201704060226]
[252,"대전충남","아산","서천안탕정#2 T/L","서천안S/S 154kV 서천안-탕정#2T/L 보호배전반 교체","○ 154kV 서천안-탕정#2T/L 보호배전반 교체","2017-06-19 09:00","2017-06-22 18:00","2017-06-07T09:00:00","2017-06-10T18:00:00","연속",null,null,null,201703080128]
[253,"대전충남","아산","둔포한샘#2 T/L","한샘S/S 154kV 한샘-둔포#2T/L 보호배전반 교체","○ 154kV 한샘-둔포#2T/L 보호배전반 교체","2017-06-12 09:00","2017-06-15 18:00","취소","취소","연속",null,null,null,201704060226]
[254,"대전충남","청양","관창보령복합 T/L","170kV GIS 정밀점검공사","617 점검","2017-06-15 09:30","2017-06-17 18:00","2017-06-19T09:30:00","2017-06-20T18:00:00","연속",null,null,null,201704050223]
[255,"대전충남","청양","보령C/C 154kV #1 BUS TIE CB","170kV GIS 정밀점검공사","6100 점검","2017-06-12 09:30","2017-06-14 18:00","2017-06-12T09:00:00","2017-06-13T18:00:00","연속",null,null,null,201704050221]
[256,"대전충남","청양","보령TP보령CC T/L","170kV GIS 정밀점검공사","617 점검","2017-06-12 09:30","2017-06-14 18:00","2017-06-14T09:00:00","2017-06-15T18:00:00","연속",null,null,null,201704050222]
[257,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산S/S 154kV #1 BUS TIE CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-07 09:00","2017-06-09 18:00","2017-06-07 09:00","2017-06-09 18:00","연속",null,null,null,201704110025]
[258,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산S/S 154kV #1 BUS TIE CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-15 09:00","2017-06-17 18:00","2017-06-15 09:00","2017-06-17 18:00","연속",null,null,null,201704110026]
[259,"전북","군산","군산S/S 154kV #3 BUS TIE CB","군산S/S 154kV #3 BUS TIE CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-19 09:00","2017-06-21 18:00","2017-06-19 09:00","2017-06-21 18:00","연속",null,null,null,201704110049]
[260,"전북","군산","군산S/S 154kV #60 BUS","군산S/S 154kV #60 BUS","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-07 09:00","2017-06-08 11:00","2017-06-07 09:00","2017-06-08 11:00","연속",null,null,null,201704110019]
[261,"전북","군산","군산S/S 154kV #60 BUS","군산S/S 154kV #60 BUS","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-15 09:00","2017-06-16 11:00","2017-06-15 09:00","2017-06-16 11:00","연속",null,null,null,201704110020]
[262,"전북","군산","군산S/S 154kV #62 BUS","군산S/S 154kV #62 BUS","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-19 09:00","2017-06-20 11:00","2017-06-19 09:00","2017-06-20 11:00","연속",null,null,null,201704110011]
[263,"전북","군산","군산S/S 154kV #65 BUS","군산S/S 154kV #65 BUS","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-08 11:00","2017-06-09 18:00","2017-06-08 11:00","2017-06-09 18:00","연속",null,null,null,201704110021]
[264,"전북","군산","군산S/S 154kV #65 BUS","군산S/S 154kV #65 BUS","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-16 11:00","2017-06-17 18:00","2017-06-16 11:00","2017-06-17 18:00","연속",null,null,null,201704110023]
[265,"전북","군산","군산S/S 154kV #67 BUS","군산S/S 154kV #67 BUS","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-20 11:00","2017-06-21 18:00","2017-06-20 11:00","2017-06-21 18:00","연속",null,null,null,201704110012]
[266,"전북","군산","군산S/S 60-61-0 SEC CB","군산S/S 60-61-0 SEC CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-07 09:00","2017-06-08 11:00","2017-06-07 09:00","2017-06-08 11:00","연속",null,null,null,201704110029]
[267,"전북","군산","군산S/S 60-61-0 SEC CB","군산S/S 60-61-0 SEC CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-15 09:00","2017-06-16 11:00","2017-06-15 09:00","2017-06-16 11:00","연속",null,null,null,201704110030]
[268,"전북","군산","군산S/S 61-62-0 SEC CB","군산S/S 61-62-0 SEC CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-19 09:00","2017-06-20 11:00","2017-06-19 09:00","2017-06-20 11:00","연속",null,null,null,201704110046]
[269,"전북","군산","군산S/S 65-66-0 SEC CB","군산S/S 65-66-0 SEC CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-16 11:00","2017-06-17 18:00","2017-06-16 11:00","2017-06-17 18:00","연속",null,null,null,201704110033]
[270,"전북","군산","군산S/S 65-66-0 SEC CB","군산S/S 65-66-0 SEC CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-08 11:00","2017-06-09 18:00","2017-06-08 11:00","2017-06-09 18:00","연속",null,null,null,201704110034]
[271,"전북","군산","군산S/S 66-67-0 SEC CB","군산S/S 66-67-0 SEC CB","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-20 11:00","2017-06-21 18:00","2017-06-20 11:00","2017-06-21 18:00","연속",null,null,null,201704110047]
[272,"전북","군산","군산동군산#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - 군산-동군산#1T/L - 동군산-군산복합#1T/L - #1M.Tr 1차측","2017-06-03 08:00","2017-07-02 18:00","2017-06-03 08:00","2017-07-02 18:00","연속",null,null,null,201704150025]
[273,"전북","군산","군산서군산#1 T/L","군산-서군산#1T/L","서군산S/S 군산-서군산#1T/L 인출ES 조작함 교체","2017-06-02 09:00","2017-06-02 18:00","2017-06-02 09:00","2017-06-02 18:00","당일",null,null,null,201704140203]
[274,"전북","군산","군산서군산#2 T/L","군산서군산#2 T/L","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-20 10:00","2017-06-20 11:00","2017-06-20 10:00","2017-06-20 11:00","연속",null,null,null,201704110013]
[275,"전북","군산","군산서군산#2 T/L","군산서군산#2 T/L","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-21 10:00","2017-06-21 11:00","2017-06-21 10:00","2017-06-21 11:00","연속",null,null,null,201704110014]
[276,"전북","군산","군산영등#1 T/L","영등S/S 군산-영등#1T/L 차단기 보통점검","군산P/O 차단기 보통점검","2017-06-12 13:30","2017-06-12 18:00","2017-06-11 13:30","2017-06-11 18:00","당일",null,null,"신뢰도개선",201703170094]
[277,"전북","군산","군산이리#1 T/L","군산이리#1 T/L","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-08 10:00","2017-06-08 11:00","2017-06-08 10:00","2017-06-08 11:00","당일",null,null,null,201704140199]
[278,"전북","군산","군산이리#1 T/L","군산이리#1 T/L","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-09 10:00","2017-06-09 11:00","2017-06-09 10:00","2017-06-09 11:00","당일",null,null,null,201704140200]
[279,"전북","군산","군산이리#1 T/L","군산이리#1 T/L","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-16 10:00","2017-06-16 11:00","2017-06-16 10:00","2017-06-16 11:00","당일",null,null,null,201704110042]
[280,"전북","군산","군산이리#1 T/L","군산이리#1 T/L","2017년 군산P/O 170kV 차단기 정밀점검 공사","2017-06-17 10:00","2017-06-17 11:00","2017-06-17 10:00","2017-06-17 11:00","당일",null,null,null,201704110043]
[281,"전북","군산","동군산군산CC#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - 군산-동군산#1T/L - 동군산-군산복합#1T/L - #1M.Tr 1차측","2017-06-03 08:00","2017-07-02 18:00","2017-06-03 08:00","2017-07-02 18:00","연속",null,null,null,201704150026]
[282,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #1BUS 시험가압","2017-06-18 08:00","2017-06-21 08:00","취소","취소","연속",null,null,"신뢰도개선",201704150017]
[283,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #1M.Tr 근접작업으로 안전 이격거리 확보","2017-06-03 08:00","2017-06-05 19:00","취소","취소","연속",null,null,"신뢰도개선",201704150014]
[284,"전북","군산","팔봉영등#2 T/L","영등S/S 팔봉-영등#2T/L 차단기 보통점검","군산P/O 차단기 보통점검","2017-06-13 09:00","2017-06-13 14:00","2017-06-11 09:00","2017-06-11 14:00","당일",null,null,"신뢰도개선",201703170095]
[285,"전북","김제","고창영광 T/L","154kV 영고T/L 정밀점검","154kV 영고T/L 정밀점검(No.46~155)","2017-06-07 09:00","2017-06-11 18:00","2017-07-05 09:00","2017-07-09 18:00","매일",null,null,null,201703200129]
[286,"전북","김제","고창홍농 T/L","154kV 고창-홍농T/L 전력선 교체공사","공사명 : 154kV 고창-홍농T/L 전력선 교체공사 공사구간 : No.61~65, No. 67~72 (ACSR/AW 330㎟ x S : 3.126C-km) 345kV 신남원-한빛#2T/L과 병행선로내 작업","2017-06-14 07:00","2017-07-04 18:00","2017-06-15 07:00","2017-07-05 18:00","연속",null,null,null,201703090031]
[287,"전북","김제","신김제S/S #61D.Tr CB","신김제S/S ESS 정기점검","ESS PCS 및 밧데리 제작사 정기점검","2017-06-26 09:00","2017-06-30 18:00","2017-06-26 09:00","2017-06-30 18:00","연속",null,null,null,201704180107]
[288,"전북","김제","신김제S/S 60-61-0 SEC CB","모선보호반 교체공사","#60,65 모선보호반 교체공사","2017-06-12 09:00","2017-06-16 18:00","취소","취소","연속",null,null,null,201704190114]
[289,"전북","김제","신김제S/S 65-66-0 SEC CB","모선보호반 교체공사","#60,65 모선보호반 교체공사","2017-06-12 09:00","2017-06-16 18:00","취소","취소","연속",null,null,null,201704190115]
[290,"전북","김제","신김제남전주#1 T/L","김제P/O 154KV GIS정밀점검","신김제-남전주#1T/L GIS 정밀점검","2017-06-26 09:00","2017-06-28 18:00","2017-06-24 09:00","2017-06-25 18:00","연속",null,null,null,201704170231]
[291,"전북","김제","신김제남전주#2 T/L","김제P/O 154KV GIS정밀점검","신김제-남전주#2T/L GIS 정밀점검","2017-06-22 09:00","2017-06-24 18:00","2017-06-17 09:00","2017-06-18 18:00","연속",null,null,null,201704170225]
[292,"전북","김제","신김제전주#1 T/L","김제P/O 154KV GIS정밀점검","신김제-남전주#1T/L GIS 정밀점검","2017-06-27 13:00","2017-06-28 18:00","2017-06-27 13:00","2017-06-28 18:00","매일",null,null,null,201704170237]
[293,"전북","김제","신김제전주#2 T/L","김제P/O 154KV GIS정밀점검","신김제-남전주#1T/L GIS 정밀점검","2017-06-23 13:00","2017-06-24 18:00","2017-06-23 13:00","2017-06-24 18:00","매일",null,null,null,201704190130]
[294,"전북","김제","신김제정공#1 T/L","154kV 정공S/S #4M.Tr 증설공사","154kV M.Tr x 1BANK 170kV GIS x 1CCT 25.8kV GIS x 3CCT","2017-06-05 17:30","2017-06-05 18:00","2017-06-05 17:30","2017-06-05 18:00","당일",null,null,null,201704170359]
[295,"전북","김제","신김제정공#2 T/L","관내S/S 노후배전반 교체공사","신김제 및 정공S/S 보호반 교체","2017-06-26 09:00","2017-06-29 18:00","2017-06-26 09:00","2017-06-29 18:00","연속",null,null,null,201704190113]
[296,"전북","김제","신김제정공#2 T/L","154kV 정공S/S #4M.Tr 증설공사","154kV M.Tr x 1BANK 170kV GIS x 1CCT 25.8kV GIS x 3CCT","2017-06-09 17:30","2017-06-09 18:00","2017-06-09 17:30","2017-06-09 18:00","당일",null,null,null,201704170384]
[297,"전북","김제","정공S/S 154kV #1 BUS TIE CB","154kV 정공S/S #4M.Tr 증설공사","154kV M.Tr x 1BANK 170kV GIS x 1CCT 25.8kV GIS x 3CCT","2017-06-04 09:00","2017-06-08 09:00","2017-06-04 09:00","2017-06-08 09:00","연속",null,null,null,201704170429,"○"]
[298,"전북","김제","정공담양 T/L","김제P/O 154KV GIS정밀점검","정공 - 담양T/L 154KV GIS 정밀점검","2017-06-01 09:00","2017-06-03 18:00","2017-06-04 09:00","2017-06-06 18:00","연속",null,null,null,201704170178,"○"]
[299,"전북","김제","정공담양 T/L","154kV 정공-담양T/L 정밀점검","154kV 정공-담양T/L 정밀점검(No.1~43호)","2017-06-07 09:00","2017-06-09 18:00","2017-06-07 09:00","2017-06-09 18:00","매일",null,null,null,201703200156,"○"]
[300,"전북","김제","정공섬진강수력 T/L","김제P/O 154KV GIS정밀점검","154KV #2 SC GIS 정밀점검","2017-06-13 13:00","2017-06-14 18:00","2017-06-13 13:00","2017-06-14 18:00","매일",null,null,null,201704170204,"○"]
[301,"전북","김제","정공섬진강수력 T/L","김제P/O 154KV GIS정밀점검","정공 - 담양T/L 154KV GIS 정밀점검","2017-06-02 13:00","2017-06-03 18:00","2017-06-02 13:00","2017-06-03 18:00","매일",null,null,null,201704170188,"○"]
[302,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강수력T/L 점퍼지지애자 교체공사","154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 병행","2017-06-12 07:00","2017-06-13 18:00","2017-06-12 07:00","2017-06-13 18:00","매일",null,null,null,201704170043,"○"]
[303,"전북","김제","정공섬진강수력 T/L","김제P/O 154KV GIS정밀점검","정공 - 섬진강T/L 154KV GIS 정밀점검","2017-06-15 09:00","2017-06-17 18:00","2017-06-15 09:00","2017-06-17 18:00","연속",null,null,null,201704170189,"○"]
[304,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 점퍼지지애자 교체공사","154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 병행","2017-06-12 07:00","2017-06-13 18:00","2017-06-17 09:00","2017-06-18 18:00","매일",null,null,null,201704170042]
[305,"전북","김제","정공정주#2 T/L","154kV 정공S/S #4M.Tr 증설공사","154kV M.Tr x 1BANK 170kV GIS x 1CCT 25.8kV GIS x 3CCT","2017-06-04 09:00","2017-06-07 18:00","2017-06-24 09:00","2017-06-25 18:00","매일",null,null,null,201704170349]
[306,"전북","김제","정공정주#2 T/L","154kV 정공-담양T/L 정밀점검(병가구간)","154kV 정공-담양T/L 정밀점검(No.1~43호)","2017-06-07 09:00","2017-06-07 18:00","2017-06-24 09:00","2017-06-25 18:00","당일",null,null,null,201703200157]
[307,"전북","김제","정주고창#1 T/L","154kV 영고T/L 정밀점검(병가구간)","154kV 영고T/L 정밀점검 No.46~155","2017-06-11 09:00","2017-06-11 18:00","2017-07-09 09:00","2017-07-09 18:00","당일",null,null,null,201703200132]
[308,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 점퍼지지애자 교체공사","No.86,94호 2기 점퍼지지애자 교체 154kV 고창-홍농T/L 병행 구간","2017-06-14 07:00","2017-06-14 18:00","2017-06-14 07:00","2017-06-14 18:00","당일",null,null,null,201704170046]
[309,"전북","직할","북전주진안 T/L","진안S/S 154kV 북전주-진안T/L 차단기 보통점검","154kV 북전주-진안T/L 투입저항교체 및 개폐타임 측정","2017-06-05 10:00","2017-06-05 18:00","2017-06-05 10:00","2017-06-05 18:00","당일",null,null,null,201704140127]
[310,"광주전남","강진","남창해남CS#1 T/L","강진전력지사 170kV GIS 정밀점검공사","-170kV 남창-해남C/S#1T/L 정밀점검","2017-06-19 09:00","2017-06-23 18:00","2017-06-19 09:00","2017-06-23 18:00","연속",null,null,null,201704060072]
[311,"광주전남","강진","남창해남CS#2 T/L","강진전력지사 170kV GIS 정밀점검공사","-남창-해남C/S#2T/L GIS 정밀점검","2017-06-26 09:00","2017-06-30 18:00","2017-06-26 09:00","2017-06-30 18:00","연속",null,null,null,201704060076]
[312,"광주전남","강진","진도C/S #2Pole C.Tr CB","'16~'17년 #2HVDC 변환설비 위탁정비공사","#2HVDC 변환설비 연차점검(#2Pole)","2017-06-03 09:00","2017-06-11 18:00","2017-06-03 09:00","2017-06-11 18:00","연속",null,null,null,201703230059]
[313,"광주전남","강진","진도진도CS#1 T/L","154kV 진도-진도C/S #1T/L(강진 변전협력회사 총액공사)","GIS 보통점검","2017-06-02 09:00","2017-06-02 18:00","2017-06-02 09:00","2017-06-02 18:00","당일",null,null,null,201704110245]
[314,"광주전남","강진","진도진도CS#2 T/L","154kV 진도-진도C/S #2T/L(강진 변전협력회사 총액공사)","GIS 보통점검","2017-06-08 09:00","2017-06-08 18:00","2017-06-08 09:00","2017-06-08 18:00","당일",null,null,null,201704110256]
[315,"광주전남","강진","해남진도#1 T/L","154kV 해남-진도 #1T/L(강진 변전협력회사 총액공사)","송전선로 보호반 대체","2017-06-26 09:00","2017-06-28 18:00","2017-06-26 09:00","2017-06-28 18:00","연속",null,null,null,201704110259]
[316,"광주전남","강진","신강진대불#1 T/L","154kV 대불-남악 등 3개T/L 접속개소 해소공사","가. 구 간 ○ 154kV 대불-남악 T/L No.7∼10 등 2구간 ○ 154kV 신강진-대불 T/L No.8∼11 등 9구간 나. 전선교체 : ACSR/AW 410㎟ × 2B, 26.464㎞","2017-06-03 07:00","2017-06-03 18:00","2017-06-03 07:00","2017-06-03 18:00","당일",null,null,null,201704260084]
[317,"광주전남","광주","곡성남원#1 T/L","곡성S/S 170kV 장기사용 GIS 교체공사","곡성S/S 신광주-곡성#2T/L GIS 교체공사 무부하가압선로","2017-06-01 09:00","2017-06-01 10:00","2017-06-08 09:00","2017-06-08 10:00","당일",null,null,null,201704140115]
[318,"광주전남","광주","곡성남원#1 T/L","곡성S/S 170kV 장기사용 GIS 교체공사","곡성S/S 신광주-곡성#2T/L GIS 교체공사 무부하가압선로","2017-06-28 18:00","2017-06-29 18:00","2017-07-06 18:00","2017-07-07 18:00","당일",null,null,null,201704140116]
[319,"광주전남","광주","담양S/S 154kV #1 BUS TIE CB","담양S/S 154kV Bus Tie(6100)(170 GIS 보통점검)","담양S/S 154kV Bus Tie(6100)170 GIS 보통점검","2017-06-09 09:00","2017-06-09 18:00","2017-06-09 09:00","2017-06-09 18:00","당일",null,null,null,201704110136]
[320,"광주전남","광주","북광주계림#1 T/L","2017년 광주전력지사 170KV GIS 정밀점검 공사","- 북광주S/S 154KV 북광주-계림#1T/L GIS 정밀점검","2017-06-15 09:00","2017-06-17 18:00","2017-06-22 09:00","2017-06-24 18:00","연속",null,null,null,201704140194]
[321,"광주전남","광주","북광주계림#2 T/L","2017년 광주전력지사 170KV GIS 정밀점검 공사","- 북광주S/S 154KV 북광주-계림#2T/L GIS 정밀점검","2017-06-19 09:00","2017-06-21 18:00","2017-06-26 09:00","2017-06-28 18:00","연속",null,null,null,201704140195]
[322,"광주전남","광주","북광주일곡#1 T/L","2017년 광주전력지사 170KV GIS 정밀점검 공사","- 북광주S/S 154KV 북광주-일곡#1T/L GIS 정밀점검","2017-06-07 09:00","2017-06-09 18:00","2017-06-14 09:00","2017-06-16 18:00","연속",null,null,null,201704140192]
[323,"광주전남","광주","북광주일곡#1 T/L","154kV 북광주-일곡#1T/L('17~18년 지중송전설비 위탁정비공사)","상반기 맨홀점검에 따른 가압","2017-06-02 09:00","2017-06-02 18:00","2017-06-09 09:00","2017-06-09 18:00","당일",null,null,null,201703170076]
[324,"광주전남","광주","북광주일곡#2 T/L","154kV 북광주-일곡#2T/L('17~18년 지중송전설비 위탁정비공사)","상반기 맨홀점검에 따른 가압","2017-06-02 09:00","2017-06-02 18:00","2017-06-09 09:00","2017-06-09 18:00","당일",null,null,null,201703170077]
[325,"광주전남","광주","북광주일곡#2 T/L","2017년 광주전력지사 170KV GIS 정밀점검 공사","- 북광주S/S 154KV 북광주-일곡#2T/L GIS 정밀점검","2017-06-12 09:00","2017-06-14 18:00","2017-06-19 09:00","2017-06-21 18:00","연속",null,null,null,201704140193]
[326,"광주전남","광주","신광주S/S 154kV #1 BUS TIE CB(신)","신광주S/S 154kV 60-65BUS 모선보호반 이설","-인출변경및 인출GIS연결 - 제어케이불 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시첨","2017-06-26 07:00","2017-06-30 18:00","2017-06-26 07:00","2017-06-30 18:00","연속",null,null,null,201703140391]
[327,"광주전남","광주","신광주S/S 154kV #2 BUS TIE CB(신)","신광주S/S 154kV 60-65BUS 모선보호반 이설","- 154kV 60-65BUS 모선보호반 이설 - 보호용 Panel 시첨","2017-06-26 07:00","2017-06-30 18:00","2017-06-26 07:00","2017-06-30 18:00","연속",null,null,null,201703170066]
[328,"광주전남","광주","신광주계림#2 T/L","신광주계림#2 T/L( #2MTr 2차 내장모선철거 안전거리 확보)","#2M.Tr 2차 내장모선철거에 따른 안전거리확보","2017-06-21 07:00","2017-06-21 18:00","2017-06-21 07:00","2017-06-21 18:00","당일",null,null,null,201702280165,"○"]
[329,"광주전남","광주","신광주곡성#1 T/L","곡성S/S 170kV 장기사용 GIS 교체공사","곡성S/S 신광주-곡성#1T/L GIS 교체공사","2017-06-29 09:00","2017-07-28 18:00","2017-06-29 09:00","2017-07-10 18:00","연속",null,null,null,201704140109]
[330,"광주전남","광주","신광주일곡#1 T/L","신광주일곡#1T/L(인출변경 및 인출GIS연결)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-06-04 07:00","2017-06-08 18:00","2017-06-04 07:00","2017-06-08 18:00","연속",null,null,null,201701250016]
[331,"광주전남","광주","신광주장성#1 T/L","신광주장성#1 T/L( 인출변경 및 인출GIS연결)","- 인출변경 및 인출 GIS연결 - 제어케이블 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시험","2017-06-09 07:00","2017-06-18 18:00","2017-06-09 07:00","2017-06-18 18:00","당일",null,null,null,201701250020]
[332,"광주전남","광주","신광주장성#1 T/L","신광주S/S 취약설비 GIS화 관련 인출정비공사","154kV 신광주-계림 등 3개T/L 인출정비공사","2017-06-04 07:00","2017-06-04 18:00","2017-06-04 07:00","2017-06-04 18:00","당일",null,null,null,201704140212]
[333,"광주전남","광주","신광주장성#2 T/L","신광주장성#2 T/L( #2MTr 2차 내장모선연결 안전거리 확보)","-#2M.Tr 2차 내장모선 연결 안전거리확보","2017-06-19 07:00","2017-06-20 18:00","2017-06-19 07:00","2017-06-20 18:00","당일",null,null,null,201702280168]
[334,"광주전남","목포","고창영광 T/L","154kV 장성-영광T/L전선접속개소전선교체공사","장성-영광 전선교체공사 관련 4회선 구간 안전이격거리 확보차","2017-06-08 07:00","2017-06-14 18:00","취소","취소","연속",null,null,null,201704100285]
[335,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다T/L OPGW 증설공사","154kV 나주-엄다#1T/L(엄다-목포#2T/L) NO.91호 ~ 엄다S/S OPGW 증설 : 8Km","2017-06-14 09:00","2017-06-21 18:00","2017-06-14 09:00","2017-06-21 18:00","연속",null,null,null,201704140274]
[336,"광주전남","목포","엄다목포#2 T/L","154kV 나주-엄다T/L OPGW 증설공사","154kV 나주-엄다#1T/L(엄다-목포#2T/L) NO.91호 ~ 엄다S/S OPGW 증설 : 8Km","2017-06-14 09:00","2017-06-21 18:00","2017-06-14 09:00","2017-06-21 18:00","연속",null,null,null,201704190095]
[337,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농T/L(송전선로보호반 대체)","송전선로 보호반 대체 2면","2017-06-01 09:00","2017-06-07 18:00","취소","취소","연속",null,null,null,201704060211]
[338,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.69~160","2017-06-08 07:00","2017-06-14 18:00","2017-06-08 07:00","2017-06-14 18:00","연속",null,null,null,201704100270]
[339,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.69~160","2017-06-01 07:00","2017-06-07 18:00","2017-06-01 07:00","2017-06-07 18:00","연속",null,null,null,201704100264]
[340,"광주전남","순천","광양순천#1 T/L","154kV 순천옥내화 건설공사","순천옥내화 건설공사 - #2M.Tr 무부하 가압","2017-06-23 15:00","2017-06-24 15:00","2017-06-23 15:00","2017-06-24 15:00","연속",null,null,null,201704050095]
[341,"광주전남","순천","서순천주암HP T/L","154kV 서순천주암HP T/L(전력선 교체)","345kV 신남원-광양 등 4개T/L 전선접속개소 해소공사 - 주암분기(서순천-주암HP) T/L 4~5호간 전력선 교체","2017-06-20 07:00","2017-06-21 18:00","2017-06-20 07:00","2017-06-21 18:00","연속",null,null,null,201704100743]
[342,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주#2T/L(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보조계전기 교체","2017-06-07 10:00","2017-06-07 18:00","2017-06-07 10:00","2017-06-07 18:00","당일",null,null,null,201704070127]
[343,"광주전남","순천","여수T/P 60-61 SEC GIS","154kV 여수T/P #60-61SEC(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보조계전기 교체","2017-06-12 10:00","2017-06-12 18:00","2017-06-12 10:00","2017-06-12 18:00","당일",null,null,null,201704070131]
[344,"광주전남","순천","여수T/P 65-66 SEC GIS","154kV 여수T/P #65-66SEC(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보조계전기 교체","2017-06-13 10:00","2017-06-13 18:00","2017-06-13 10:00","2017-06-13 18:00","당일",null,null,null,201704070132]
[345,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천#2T/L(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보조계전기 교체","2017-06-16 10:00","2017-06-16 18:00","2017-06-16 10:00","2017-06-16 18:00","당일",null,null,null,201704070139]
[346,"광주전남","순천","여수TP여천#2 T/L","154kV 여천S/S 여수TP-여천#2 T/L","17년 순천전력 변전협력 총액공사 - CB 동작시험","2017-06-21 13:00","2017-06-21 18:00","2017-06-21 13:00","2017-06-21 18:00","당일",null,null,null,201704110204]
[347,"광주전남","순천","여수TP화치#1 T/L","154kV 여수TP-화치#1T/L(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보조계전기 교체","2017-06-08 10:00","2017-06-08 18:00","2017-06-08 10:00","2017-06-08 18:00","당일",null,null,null,201704070128]
[348,"광주전남","순천","여수TP화치#2 T/L","154kV 여수TP-화치#2T/L(GIS 보조계전기 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보조계전기 교체","2017-06-09 10:00","2017-06-09 18:00","2017-06-09 10:00","2017-06-09 18:00","당일",null,null,null,201704070129]
[349,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수#1 T/L(CB 동작시험)","17년 순천전력 변전협력 총액공사 - CB 동작시험","2017-06-22 09:00","2017-06-22 13:00","2017-06-22 09:00","2017-06-22 13:00","당일",null,null,null,201704110183]
[350,"광주전남","순천","여천여수#2 T/L","154kV 여천-여수#2 T/L(CB 동작시험)","17년 순천전력 변전협력 총액공사 - CB 동작시험","2017-06-22 13:00","2017-06-22 18:00","2017-06-22 13:00","2017-06-22 18:00","당일",null,null,null,201704110184]
[351,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP#1 T/L(CB 동작시험)","17년 순천전력 변전협력 총액공사 - CB 동작시험","2017-06-19 09:00","2017-06-19 13:00","2017-06-19 09:00","2017-06-19 13:00","당일",null,null,null,201704110176]
[352,"광주전남","순천","여천호남TP#2 T/L","154kV 여천-호남TP#2 T/L(CB 동작시험)","17년 순천전력 변전협력 총액공사 - CB 동작시험","2017-06-19 13:00","2017-06-19 18:00","2017-06-19 13:00","2017-06-19 18:00","당일",null,null,null,201704110178]
[353,"광주전남","순천","율촌화치#1 T/L","154kV 율촌-화치#1 T/L(LA 보통점검, CB 동작시험)","17년 순천전력 변전협력 총액공사 - LA 보통점검 - CB 동작시험","2017-06-08 09:00","2017-06-08 18:00","2017-06-08 09:00","2017-06-08 18:00","당일",null,null,null,201704110172]
[354,"광주전남","순천","율촌화치#2 T/L","154kV 율촌-화치#2 T/L(LA 보통점검, CB 동작시험)","17년 순천전력 변전협력 총액공사 - LA 보통점검 - CB 동작시험","2017-06-09 09:00","2017-06-09 18:00","2017-06-09 09:00","2017-06-09 18:00","당일",null,null,null,201704110175]
[355,"대구경북","경산","대구청도#1 T/L","345kV 울주-신경산 등 3개 T/L 전선교체공사","154kV 청도-밀양T/L 전선교체 안전확보","2017-06-07 08:00","2017-06-10 18:00","2017-06-05 08:00","2017-06-07 18:00","연속",null,null,null,201704140272]
[356,"대구경북","경산","대구청도#2 T/L","345kV 울주-신경산 등 3개 T/L 전선교체공사","154kV 청도-밀양T/L 전선교체 안전확보","2017-06-03 08:00","2017-06-06 18:00","2017-06-03 08:00","2017-06-04 18:00","연속",null,null,null,201704140270]
[357,"대구경북","구미","남인동인동#1 T/L","남인동S/S 154kV남인동-인동#1T/L 변전설비 점검","- 남인동, 인동S/S GIS 조작시험 - LA 보통점검 - PT 초기점검","2017-06-19 09:00","2017-06-19 18:00","2017-06-19 09:00","2017-06-19 18:00","당일",null,null,null,201704100213]
[358,"대구경북","구미","남인동인동#2 T/L","남인동S/S 154kV 남인동-인동#2T/L 변전설비 점검","- 남인동, 인동S/S GIS 조작시험 - LA 보통점검 - PT 초기점검","2017-06-20 09:00","2017-06-20 18:00","2017-06-20 09:00","2017-06-20 18:00","당일",null,null,null,201704100217]
[359,"대구경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구설비 GIS화 공사","파일시공 관련 안전확보","2017-06-22 09:00","2017-06-28 18:00","취소","취소","연속",null,null,null,201704090041]
[360,"대구경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구설비 GIS화 공사","파일시공 관련 안전확보","2017-06-15 09:00","2017-06-21 18:00","취소","취소","연속",null,null,null,201704090040]
[361,"대구경북","달성","강창성서#1 T/L","154kV 강창-성서#1T/L 전력선 교체 및 피뢰기 설치","-154kV 강창-성서#1T/L No4~5호 구간 전력선 교체 -154kV 강창-성서#1T/L 피뢰기 설치","2017-06-23 08:00","2017-06-23 18:00","2017-06-24 08:00","2017-06-24 18:00","당일",null,null,null,201704060103]
[362,"대구경북","달성","고령다산#1 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-12 09:30","2017-06-12 18:00","2017-06-12 09:30","2017-06-12 18:00","당일",null,null,null,201704070180]
[363,"대구경북","달성","고령다산#2 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-13 09:30","2017-06-13 18:00","2017-06-13 09:30","2017-06-13 18:00","당일",null,null,null,201704070181]
[364,"대구경북","달성","내당두류#1 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-27 09:30","2017-06-27 11:00","2017-06-27 09:30","2017-06-27 11:00","당일",null,null,null,201704180073]
[365,"대구경북","달성","내당두류#2 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-27 11:00","2017-06-27 15:00","2017-06-27 11:00","2017-06-27 15:00","당일",null,null,null,201704180074]
[366,"대구경북","달성","다산강창#1 T/L","154kV 강창-성서#1T/L 전력선 교체공사 관련 안전이격","-154kV 강창-성서#1T/L 전력선 교체공사 관련 안전 이격 - 강창-성서#1T/L 4~5호 구간 전력선 교체","2017-06-23 08:00","2017-06-23 18:00","2017-06-24 08:00","2017-06-24 18:00","당일",null,null,null,201704060104]
[367,"대구경북","달성","다산강창#2 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-15 09:30","2017-06-15 18:00","2017-06-14 09:30","2017-06-16 18:00","당일",null,null,null,201704070184]
[368,"대구경북","달성","대구봉덕#1 T/L","154kV 대구봉덕#1T/L 정밀점검","No.1-33","2017-06-12 09:00","2017-06-14 18:00","2017-06-12 09:00","2017-06-14 18:00","연속",null,null,null,201704060035]
[369,"대구경북","달성","대구봉덕#2 T/L","154kV 대구봉덕#2T/L 정밀점검","No.1-33","2017-06-15 09:00","2017-06-17 18:00","2017-06-15 09:00","2017-06-17 18:00","연속",null,null,null,201704060039]
[370,"대구경북","달성","두류봉덕#1 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-07 13:00","2017-06-07 18:00","2017-06-07 13:00","2017-06-07 18:00","당일",null,null,null,201704180072]
[371,"대구경북","달성","두류봉덕#2 T/L","2017년 달성변전협력 총액공사","장기미동작타임측정","2017-06-07 09:30","2017-06-07 13:00","2017-06-07 09:30","2017-06-07 13:00","당일",null,null,null,201704070175]
[372,"대구경북","안동","동안동임하HP T/L","동안동S/S 장기 미동작차단기 연동시험","동안동S/S 장기 미동작차단기 연동시험","2017-06-07 14:00","2017-06-07 18:00","2017-06-07 14:00","2017-06-07 18:00","당일",null,null,null,201704130067]
[373,"대구경북","안동","신영주안동#1 T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay 나. 제어 및 전력케이블 철거·설치 × 1식 다. 철구 및 기기기초 철거·설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2017-06-19 09:00","2017-06-21 18:00","2017-06-19 09:00","2017-06-21 18:00","연속",null,null,null,201704100522]
[374,"대구경북","안동","신영주안동#2 T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay 나. 제어 및 전력케이블 철거·설치 × 1식 다. 철구 및 기기기초 철거·설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2017-06-22 09:00","2017-06-24 18:00","2017-06-22 09:00","2017-06-24 18:00","연속",null,null,null,201704100528]
[375,"대구경북","영주","신영주안동#1 T/L","154kV신영주-안동#1T/L 전선접속개소 정비공사","No.2-6, 11-13 전선접속개소 정비공사","2017-06-02 08:00","2017-06-08 18:00","2017-06-01 08:00","2017-06-07 18:00","연속",null,null,null,201704170436]
[376,"대구경북","영주","신영주안동#2 T/L","154kV신영주-안동#2T/L 전선접속개소 정비공사","No.2-6, 11-13 전선접속개소 정비공사","2017-06-09 08:00","2017-06-14 18:00","2017-06-08 08:00","2017-06-08 18:00","연속",null,null,null,201704170437]
[377,"대구경북","영주","영주봉화#2 T/L","154kV영주-봉화#2T/L 전선접속개소 정비공사, 지장철탑이설","No.2-76 전선접속교체, 지장철탑이설공사","2017-06-15 08:00","2017-06-28 18:00","2017-06-14 08:00","2017-06-26 18:00","연속",null,null,null,201704170438]
[378,"대구경북","영주","점촌문경 T/L","문경S/S 점촌-문경T/L 617 GIS 정밀점검","문경S/S 점촌-문경T/L 617 GIS 정밀점검","2017-06-12 08:00","2017-06-17 18:00","취소","취소","연속",null,null,null,201704130316]
[379,"대구경북","직할","남대구동인#2 T/L","OF케이블 선종교체공사","동인S/S 인출 OF케이블 선종교체공사","2017-06-08 08:00","2017-08-04 20:00","2017-06-08 08:00","2017-08-04 20:00","연속",null,null,null,201704080002]
[380,"대구경북","직할","동인내당#2 T/L","OF케이블 선종교체공사","동인S/S 인출 OF케이블 선종교체공사","2017-06-08 09:00","2017-07-07 18:00","2017-06-08 09:00","2017-07-07 18:00","연속",null,null,null,201704080001]
[381,"대구경북","칠곡","관음구암#1 T/L","관음구암#1 T/L 휴전","관음S/S 관음구암#1 T/L CB 장기미동작 점검","2017-06-16 09:30","2017-06-16 18:00","2017-06-16 09:30","2017-06-16 18:00","당일",null,null,null,201704100867]
[382,"대구경북","칠곡","관음구암#2 T/L","관음구암#2 T/L 휴전","관음S/S 관음구암#2 T/L CB 장기미동작 점검, LA 교체","2017-06-16 09:30","2017-06-16 18:00","2017-06-16 09:30","2017-06-16 18:00","당일",null,null,null,201704100869]
[383,"대구경북","포항","신포항상정#2 T/L","154kV 상정-양북T/L 건설공사","목적 : 포항 블루밸리산업단지 전력수요 대비 및 상정S/S 단일계통 해소 구간 : 기설 154kV 영일-양북T/L No.29,31~기설 154kV 상정S/S 개요 : 철탑 39기, 14.725km","2017-06-22 08:00","2017-07-02 18:00","2017-06-22 08:00","2017-07-02 18:00","연속",null,null,null,201704070228]
[384,"대구경북","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.28-32)","2017-06-19 08:00","2017-06-27 18:00","취소","취소","연속",null,null,null,201704050006]
[385,"대구경북","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.28-32)","2017-06-19 08:00","2017-06-27 18:00","취소","취소","연속",null,null,null,201704050007]
[386,"대구경북","포항","영일입실 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","154kV 송전선로 횡단개소 안전확보","2017-06-15 08:00","2017-06-17 18:00","2017-06-15 08:00","2017-06-17 18:00","연속",null,null,null,201703100085]
[387,"대구경북","포항","옥동외동#2 T/L","외동옥동#2 T/L 보호반 교체","외동옥동#2 T/L 보호반 교체","2017-06-14 09:00","2017-06-16 18:00","2017-06-14 09:00","2017-06-16 18:00","연속",null,null,null,201704100007]
[388,"대구경북","포항","입실양북 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","154kV 송전선로 횡단개소 안전확보","2017-06-15 08:00","2017-06-17 18:00","2017-06-15 08:00","2017-06-17 18:00","연속",null,null,null,201703100084]
[389,"대구경북","포항","청하영덕#1 T/L","154kV 청하-영덕 T/L 접속개소 전력선교체공사","154kV 청하-영덕T/L 33~116호 전력선교체 : 33~116호 ACSR 410㎟*2B*2C, 21C_km 가공지선교체 : 39~78호 ACSR 97㎟, 3.998C_km","2017-06-07 08:00","2017-06-21 18:00","2017-06-07 08:00","2017-06-21 18:00","연속",null,null,null,201704100372]
[390,"대구경북","포항","청하영덕#2 T/L","154kV 청하-영덕 T/L 접속개소 전력선교체공사","154kV 청하-영덕T/L 33~116호 전력선교체 : 33~116호 ACSR 410㎟*2B*2C, 21C_km 가공지선교체 : 39~78호 ACSR 97㎟, 3.998C_km","2017-06-22 08:00","2017-07-06 18:00","2017-06-22 08:00","2017-07-06 18:00","연속",null,null,null,201704100379]
[391,"부산울산","동부산","명례정관 T/L","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 681DS 시험가압선로","2017-06-02 16:00","2017-06-03 16:00","2017-06-02 16:00","2017-06-03 16:00","연속",null,null,null,201703100018]
[392,"부산울산","동부산","명례정관 T/L","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 정관S/S 정관에너지T/L GIS(687) ~ 부산정관에너지측 GIS 시험가압선로","2017-06-27 14:00","2017-06-28 14:00","2017-06-27 14:00","2017-06-28 14:00","연속",null,null,null,201704200054]
[393,"부산울산","동부산","명례정관 T/L","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 682DS, 687CB, 686DS 시험가압선로","2017-06-08 14:00","2017-06-09 14:00","2017-06-08 14:00","2017-06-09 14:00","연속",null,null,null,201704110166]
[394,"부산울산","동부산","웅촌서창#1 T/L","154kV 서창-산막 등 2개 T/L EB-A 자기애관 교체공사","지중송전 케이블헤드용 애관교체공사(자기애관 → 폴리머애관)","2017-06-05 09:00","2017-06-09 18:00","2017-06-05 09:00","2017-06-09 18:00","연속",null,null,null,201704100654]
[395,"부산울산","동부산","웅촌서창#2 T/L","154kV 서창-산막 등 2개 T/L EB-A 자기애관 교체공사","지중송전 케이블헤드용 애관교체공사(자기애관 → 폴리머애관)","2017-06-19 09:00","2017-06-23 18:00","2017-06-19 09:00","2017-06-23 18:00","연속",null,null,null,201704100664]
[396,"부산울산","북부산","물금S/S 154KV #1 BUS TIE CB","154kV 물금분기T/L SW 증설공사(시험가압)","o 154kV GIS * 2CCT 설치 (#2BUS~C/H 시험가압)","2017-06-16 19:00","2017-06-17 18:00","2017-06-16 19:00","2017-06-17 18:00","연속",null,null,null,201704170132]
[397,"부산울산","북부산","물금S/S 154KV #1 BUS TIE CB","154kV 물금분기T/L SW 증설공사(시험가압)","o 154kV GIS * 2CCT 설치 (#1BUS 시험가압)","2017-06-09 19:00","2017-06-10 18:00","2017-06-09 19:00","2017-06-10 18:00","연속",null,null,null,201704170131]
[398,"부산울산","북부산","북부산구포#1 T/L","2017년 북부산 170kV GIS 정밀점검 공사","구포S/S 북부산-구포#1T/L (617) GIS 정밀점검","2017-06-12 08:00","2017-06-14 19:00","2017-06-12 08:00","2017-06-14 19:00","연속",null,null,null,201704100538,"○"]
[399,"부산울산","북부산","북부산삼랑진PP#2 T/L","2017년 가공송전 협력업체 공사","NO.13~17호 이도불평형조정","2017-06-03 08:00","2017-06-06 18:00","2017-06-03 08:00","2017-06-06 18:00","연속",null,null,null,201704100627]
[400,"부산울산","북부산","북부산호포 T/L","2017년 가공송전 협력업체 공사","북부산-삼랑진#2 13~17호 이도불평형조정 안전이격확보","2017-06-03 08:00","2017-06-06 18:00","2017-06-03 08:00","2017-06-06 18:00","매일",null,null,null,201704100631]
[401,"부산울산","북부산","북부산호포 T/L","2017년 북부산 170kV GIS 정밀점검 공사","호포S/S 북부산-호포T/L (687) GIS 정밀점검","2017-06-20 08:00","2017-06-22 19:00","2017-06-20 08:00","2017-06-22 19:00","연속",null,null,null,201704100547]
[402,"부산울산","북부산","매리호포#1 T/L","2017년 북부산 170kV GIS 정밀점검 공사","호포S/S 호포-매리#1T/L (617) GIS 정밀점검","2017-06-26 08:00","2017-06-28 19:00","2017-06-26 08:00","2017-06-28 19:00","연속",null,null,null,201704100561]
[403,"부산울산","북부산","매리호포#2 T/L","2017년 북부산 170kV GIS 정밀점검 공사","호포S/S 호포-매리#2T/L (637) GIS 정밀점검","2017-06-29 08:00","2017-07-01 19:00","2017-06-29 08:00","2017-07-01 19:00","연속",null,null,null,201704100564]
[404,"부산울산","북부산","호포물금 T/L","154kV 물금분기T/L SW 증설공사(시험가압)","o 154kV GIS * 2CCT 설치 (#1BUS 시험가압 선로)","2017-06-09 18:00","2017-06-09 19:00","2017-06-09 18:00","2017-06-09 19:00","당일",null,null,null,201704100540]
[405,"부산울산","북부산","호포물금 T/L","154kV 물금분기T/L SW 증설공사(시험가압)","o 154kV GIS * 2CCT 설치 (#2BUS,652,657,662,667 시험가압 선로)","2017-06-16 18:00","2017-06-16 19:00","2017-06-16 18:00","2017-06-16 19:00","당일",null,null,null,201704100542]
[406,"부산울산","서부산","서부산신평#1 T/L","154kV 서부산C/H 지장송전선로 이설공사","서부산C/H 1기 설치 및 철거","2017-06-08 08:00","2017-07-02 18:00","2017-06-08 08:00","2017-07-02 18:00","연속",null,null,null,201704040142]
[407,"부산울산","서부산","서부산신평#2 T/L","154kV 서부산C/H 지장송전선로 이설공사","서부산C/H 1기 설치 및 철거 - 154kV 서부산-신평#1,2T/L 및 154kV YKT/L 이설","2017-06-18 06:00","2017-06-18 18:00","2017-06-18 06:00","2017-06-18 18:00","당일",null,null,null,201704050029]
[408,"부산울산","울산","동울산방어진 T/L","2017년 울산P/O 170kV 개폐장치 정밀점검공사","방어진S/S 154kV 6431 GIS 정밀점검관련 시험가압","2017-06-07 17:00","2017-06-07 18:00","2017-06-07 17:00","2017-06-07 18:00","당일",null,null,null,201704100307]
[409,"부산울산","울산","동울산방어진 T/L","2017년 울산P/O 170kV 개폐장치 정밀점검공사","방어진S/S 154kV 6442,6433 GIS 정밀점검관련 시험가압","2017-06-09 17:00","2017-06-09 18:00","2017-06-09 17:00","2017-06-09 18:00","당일",null,null,null,201704100309]
[410,"부산울산","울산","동울산방어진 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","방어진S/S 170kV 617 GIS 보통점검","2017-06-24 08:00","2017-06-24 18:00","2017-06-24 08:00","2017-06-24 18:00","당일",null,null,null,201704100331]
[411,"부산울산","울산","신온산온산#1 T/L","2017년 관내 노후배전반 대체공사","신온산,온산S/S 양측 송전선로 보호반 대체","2017-06-26 08:00","2017-06-27 18:00","2017-06-26 08:00","2017-06-27 18:00","연속",null,null,null,201704100341]
[412,"부산울산","울산","신온산온산#2 T/L","2017년 관내 노후배전반 대체공사","신온산,온산S/S 양측 송전선로 보호반 대체","2017-06-28 08:00","2017-06-29 18:00","2017-06-28 08:00","2017-06-29 18:00","연속",null,null,null,201704100342]
[413,"부산울산","울산","신울산S/S 62-63-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV #62-67B/P PNL 대체","2017-06-23 08:00","2017-06-26 18:00","2017-06-23 08:00","2017-06-26 18:00","연속",null,null,null,201704100327]
[414,"부산울산","울산","신울산언양#1 T/L","2017년 울산P/O 170kV 개폐장치 정밀점검공사","언양S/S 170kV 677 GIS 정밀점검","2017-06-12 08:00","2017-06-14 18:00","2017-06-12 08:00","2017-06-14 18:00","연속",null,null,null,201704100363]
[415,"부산울산","울산","신울산언양#2 T/L","2017년 울산P/O 170kV 개폐장치 정밀점검공사","언양S/S 170kV 687 GIS 정밀점검","2017-06-15 08:00","2017-06-17 18:00","2017-06-15 08:00","2017-06-17 18:00","연속",null,null,null,201704100366]
[416,"부산울산","울산","옥동외동#1 T/L","154KV 외동-옥동#1T/L 송전선로용 피뢰기 설치공사","ㅁ 피뢰기 설치 : 59(기) [No.1~62(8~10 제외)]","2017-06-25 07:00","2017-06-30 18:00","2017-06-25 07:00","2017-06-30 18:00","연속",null,null,null,201704070304]
[417,"부산울산","울산","용연울산TP#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 170kV 622 GIS 철거 및 마감부 시험가압","2017-06-07 17:00","2017-06-07 18:00","2017-06-07 17:00","2017-06-07 18:00","당일",null,null,null,201704100301]
[418,"부산울산","울산","용연울산TP#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 170kV 621 GIS(1DS개방상태) 시험가압","2017-06-14 12:00","2017-06-15 12:00","2017-06-14 12:00","2017-06-15 12:00","연속",null,null,null,201704100303]
[419,"부산울산","울산","용연울산TP#3 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","용연,울산T/P 양측 송전선로 보호반 대체","2017-06-24 08:00","2017-06-25 18:00","2017-06-24 08:00","2017-06-25 18:00","연속",null,null,null,201704100336]
[420,"부산울산","울산","용연처용#1 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 170kV 621,622,626,667 GIS대체","2017-06-07 08:00","2017-06-21 18:00","2017-06-07 08:00","2017-06-21 18:00","연속",null,null,null,201704100297]
[421,"부산울산","울산","울산T/P 154kV #2 BUS TIE CB","2016-17년 울산전력지사 변전협력회사 총액공사","울산T/P 154kV 6200 GIS 보통점검","2017-06-10 09:00","2017-06-10 18:00","2017-06-10 09:00","2017-06-10 18:00","당일",null,null,null,201704100314]
[422,"부산울산","울산","효문방어진 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","방어진S/S 154kV 657 GIS 보통점검","2017-06-17 09:00","2017-06-17 18:00","2017-06-17 09:00","2017-06-17 18:00","당일",null,null,null,201704100310]
[423,"부산울산","직할","부민부산 T/L","부민S/S 부민-부산T/L GIS(627) 미동작점검","부민S/S 부민-부산T/L GIS(627) 미동작점검","2017-06-01 10:00","2017-06-01 12:00","2017-06-01 10:00","2017-06-01 12:00","당일",null,null,null,201704100708]
[424,"부산울산","직할","부산영도#1 T/L","154kV 우동 등 3개S/S 지중케이블 선종교체공사","부산S/S 지중케이블 선종교체공사(OF 1200 ---> XLPE 1200 교체) 부산-영도#1,2 : 부산S/S ~ S/J - 0.022km","2017-06-01 09:00","2017-06-15 18:00","2017-06-01 09:00","2017-06-15 18:00","연속",null,null,null,201704060060]
[425,"부산울산","직할","부산영도#2 T/L","154kV 우동 등 3개S/S 지중케이블 선종교체공사","부산S/S 지중케이블 선종교체공사 부산-영도#1,2 : 부산S/S ~ S/J - 0.022km","2017-06-16 09:00","2017-06-30 18:00","2017-06-16 09:00","2017-06-30 18:00","연속",null,null,null,201704060061]
[426,"부산울산","직할","서부산부민#1 T/L","부민S/S 서부산-부민#1T/L GIS(6J7) 미동작점검","부민S/S 서부산-부민#1T/L GIS(6J7) 미동작점검","2017-06-01 13:00","2017-06-01 15:00","2017-06-01 13:00","2017-06-01 15:00","당일",null,null,null,201704100709]
[427,"부산울산","직할","신대연양정#1 T/L","양정S/S 신대연-양정#1T/L GIS(617) 미동작점검","양정S/S 신대연-양정#1T/L GIS(617) 미동작점검","2017-06-02 10:00","2017-06-02 12:00","2017-06-02 10:00","2017-06-02 12:00","당일",null,null,null,201704100711]
[428,"부산울산","직할","신대연양정#2 T/L","양정S/S 신대연-양정#2T/L GIS(627) 미동작점검","양정S/S 신대연-양정#2T/L GIS(627) 미동작점검","2017-06-02 13:00","2017-06-02 15:00","2017-06-02 13:00","2017-06-02 15:00","당일",null,null,null,201704100712]
[429,"경남","직할","마천진해#1 T/L","154kV 마천-진해 등 3개 T/L 케이블헤드 용접부분 안전도 검토","케이블헤드 용접 부분 안전도 검토(154kV 마천-진해T/L 1호 철탑)","2017-06-06 09:00","2017-06-06 11:00","2017-06-06 09:00","2017-06-06 11:00","당일",null,null,null,201704050036]
[430,"경남","직할","마천진해#2 T/L","154kV 마천-진해 등 3개 T/L 케이블헤드 용접부분 안전도 검토","케이블헤드 용접 부분 안전도 검토(154kV 마천-진해T/L 1호 철탑)","2017-06-06 09:00","2017-06-06 11:00","2017-06-06 09:00","2017-06-06 11:00","당일",null,null,null,201704050037]
[431,"경남","직할","안민진해#1 T/L","154kV 마천-진해 등 3개 T/L 케이블헤드 용접부분 안전도 검토","케이블헤드 용접 부분 안전도 검토(154kV 마천-진해T/L 1호 철탑)","2017-06-06 11:00","2017-06-06 13:00","2017-06-06 11:00","2017-06-06 13:00","당일",null,null,null,201704050038]
[432,"경남","직할","안민진해#2 T/L","154kV 마천-진해 등 3개 T/L 케이블헤드 용접부분 안전도 검토","케이블헤드 용접 부분 안전도 검토(154kV 마천-진해T/L 1호 철탑)","2017-06-06 11:00","2017-06-06 13:00","2017-06-06 11:00","2017-06-06 13:00","당일",null,null,null,201704050039]
[433,"경남","진주","동진주진주#1 T/L","동진주진주#1 T/L CB(647)보통점검","동진주진주#1 T/L CB(647)보통점검 - 병행작업: PT하자점검 - 참고사항: 시송전선로","2017-06-17 09:30","2017-06-17 18:30","2017-06-18 09:30","2017-06-18 18:30","당일",null,null,null,201704030364]
[434,"경남","진주","사천개양#1 T/L","154kV 사천-개양T/L 암교체 공사","154kV 사천-개양T/L 암교체 공사","2017-06-24 07:00","2017-06-25 19:00","2017-06-24 07:00","2017-06-25 19:00","연속",null,null,null,201704050072]
[435,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L 암교체 공사","154kV 사천-개양T/L 암교체 공사","2017-06-24 07:00","2017-06-27 19:00","2017-06-24 07:00","2017-06-27 19:00","연속",null,null,null,201704050073]
[436,"경남","진주","산청함양 T/L","산청함양 T/L CB(617) 정밀점검","산청함양 T/L CB(617) 정밀점검","2017-06-02 09:30","2017-06-04 18:30","2017-06-02 09:30","2017-06-04 18:30","연속",null,null,null,201704030182]
[437,"경남","진주","하동하동화력#1 T/L","154kV 하동-하동화력T/L 전선교체공사","154kV 하동-하동화력T/L 전선교체공사 - 154kV 하동-하동화력 #1,2T/L - 3~7, 10~12, 13~14, 21~22, 26~28, 30~34, 49~53호","2017-06-24 07:00","2017-06-29 19:00","2017-06-24 07:00","2017-06-29 19:00","연속",null,null,null,201703060251]
[438,"경남","통영","고성통영 T/L","고성S/S 154kV 고성-통영T/L GIS 초기점검","고성S/S 154kV 고성-통영T/L GIS 초기점검,LA보통점검","2017-06-06 09:30","2017-06-06 18:30","2017-06-06 09:30","2017-06-06 18:30","당일",null,null,null,201704050196]
[439,"경남","통영","신고성고성 T/L","고성S/S 154kV 신고성-고성T/L GIS 초기점검","고성S/S 154kV 신고성-고성T/L GIS 초기점검,LA 보통점검","2017-06-24 09:30","2017-06-24 18:30","2017-06-24 09:30","2017-06-24 18:30","당일",null,null,null,201704050197]
[440,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 정밀점검","154kV 통영-거제#1T/L 정밀점검 No.1~72","2017-06-03 08:30","2017-06-04 18:00","2017-06-03 08:30","2017-06-04 18:00","매일",null,null,null,201704100760]
[441,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 정밀점검","154kV 통영-거제#1T/L 정밀점검 No.1~72","2017-06-10 08:30","2017-06-11 18:00","2017-06-10 08:30","2017-06-11 18:00","매일",null,null,null,201704050214]
[442,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 정밀점검","154kV 통영-거제#1T/L 정밀점검 No.1~72","2017-06-17 08:30","2017-06-18 18:00","2017-06-17 08:30","2017-06-18 18:00","매일",null,null,null,201704050217]
[443,"경남","함안","신마산S/S 154kV #2 BUS TIE CB","신마산S/S 154kV #2BUSTIE GCB 보통점검","신마산S/S 154kV #2BUSTIE GCB 보통점검 신마산S/S 154kV #2BUSTIE GCB 공기조작부 점검","2017-06-04 08:00","2017-06-04 18:00","2017-06-04 08:00","2017-06-04 18:00","당일",null,null,null,201704050129]
[444,"경남","함안","신마산S/S 65-66-0 SEC CB","신마산S/S 154kV 65-66-0 GCB 보통점검","신마산S/S 154kV 65-66-0 GCB 보통점검 신마산S/S 154kV 65-66-0 GCB 공기조작부 점검","2017-06-06 08:00","2017-06-06 18:00","2017-06-06 08:00","2017-06-06 18:00","당일",null,null,null,201704050195]
[445,"경남","함안","신마산차룡#1 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 (5~7, 11~17, 36~38호)","2017-06-03 07:30","2017-06-04 18:30","2017-06-03 07:30","2017-06-04 18:30","연속",null,null,null,201704030256]
[446,"경남","함안","신마산차룡#1 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 (5~7, 11~17, 36~38호)","2017-06-10 07:30","2017-06-11 18:30","2017-06-10 07:30","2017-06-11 18:30","연속",null,null,null,201704030260]
[447,"경남","함안","신마산차룡#2 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 (5~7, 11~17, 36~38호)","2017-06-24 07:30","2017-06-25 18:30","2017-06-24 07:30","2017-06-25 18:30","연속",null,null,null,201704030265]
[448,"경남","함안","신마산차룡#2 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 (5~7, 11~17, 36~38호)","2017-06-17 07:30","2017-06-18 18:30","2017-06-17 07:30","2017-06-18 18:30","연속",null,null,null,201704030262]
[449,"경남","함안","진영한림정#1 T/L","진영S/S 154kV 진영-한림정#1T/L GIS 정밀점검","진영S/S 154kV 진영-한림정#1T/L GIS 정밀점검","2017-06-10 08:00","2017-06-11 19:30","2017-06-10 08:00","2017-06-11 19:30","연속",null,null,null,201704050104]
[450,"경남","함안","진영한림정#2 T/L","진영S/S 154kV 진영-한림정#2T/L GIS 정밀점검","진영S/S 154kV 진영-한림정#2T/L GIS 정밀점검","2017-06-17 08:00","2017-06-18 19:30","2017-06-17 08:00","2017-06-18 19:30","연속",null,null,null,201704050103]
[451,"경남","함안","진영한림정#2 T/L","154kV 한림정S/S #3M.Tr 증설공사","154kV 한림정S/S #3M.Tr 증설공사(#2DS 시험가압) - 154kV GIS 1CCT 설치","2017-06-03 18:00","2017-06-04 18:00","2017-06-03 18:00","2017-06-04 18:00","연속",null,null,null,201703150017]
[452,"경남","함안","진영한림정#2 T/L","154kV 한림정S/S #3M.Tr 증설공사","154kV 한림정S/S #3M.Tr 증설공사(최초가압)","2017-06-24 14:00","2017-06-25 14:00","2017-06-24 14:00","2017-06-25 14:00","연속",null,null,null,201704060233]

{"sheet":"한수원","index":3,"n_rows":8,"n_cols":20,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,17,3,17],[2,18,3,18],[2,19,3,19],[2,13,3,13],[2,14,3,14],[2,16,3,16],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,15,3,15],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2017년도 06월 월간휴전계획표  -  한국수력원자력㈜"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","2발전소","고리4호기 기동변압기#1","공사명 : 기동변압기#1 휴전\n조작차단기 : 7C00, 7C72","○ 부싱 및 애자 점검\n○ 변압기 냉각팬 점검\n○ 변압기 패널 점검\n○ 변압기 외함 누유 점검","2017-05-30 07:00","2017-06-05 24:00","2017-05-30 07:00","2017-06-05 24:00","연속",null,null,null," "]
[2,"고리본부","2발전소","고리4호기 기동변압기#2","공사명 : 기동변압기#2 휴전\n조작차단기 : 7600, 7672","○ 변압기 휴전 후 절연유 완전 배유\n○ 저압부싱 밀봉가스켓 정비 공사\n○ 변압기 진공형성 및 유지\n○ 절연유 여과 후 충유\n○ 변압기 가압\n○ 우천 시 공사 시작일 순연 가능","2017-06-13 07:00","2017-06-19 24:00","2017-06-13 07:00","2017-06-19 24:00","연속",null,null,null," "]
[3,"월성본부","1발전소","#1 기동용변압기","월성 1호기 제25차 계획예방정비관련 기동용변압기 점검\n*조작차단기 : CB7600, CB7671","- 기동용변압기 일반점검\n- 기동용변압기 보호계전기 정기시험\n   (차단기 연동시험 포함)","2017-06-13 09:00","2017-06-20 18:00","2017-06-13 09:00","2017-06-20 18:00","연속","N",null,null," "]
[4,"한빛본부","한빛2발전소","#4 기동변압기 04XN","한빛4호기 16차 계획예방정비\n- 조작차단기 : PCB 7800, 7871 ","○ OH관련 기동변압기 04XN 점검\n○ 보호계전기 개체/연동시험 등","2017-06-14T09:00:00","2017-06-22T18:00:00","2017-06-14T09:00:00","2017-06-22T18:00:00","연속","Y"]

{"sheet":"중부","index":4,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19]]}
["2017년도 6월 월간휴전계획표(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령","3발전소","345kV 청양-보령화력 #2T/L\n(CB 7771, 7700)","7,8호기 항공장애표시구\n 설치공사","항공장애표시구 설치공사","2017-06-09  \n09:00:00","2017-06-15 \n 17:00:00","2017-06-09  \n09:00:00","2017-06-15 \n 17:00:00","연속"]
[2,"보령","3발전소","345kV 보령화력-보령복합\n(연락) #2T/L","7,8호기 항공장애표시구\n 설치공사","항공장애표시구 설치공사","2017-06-23  \n09:00:00","2017-06-25 \n 17:00:00","2017-06-23  \n09:00:00","2017-06-25 \n 17:00:00","연속"]