{"text_format":"2","workbook":"xlsx","n_sheets":6,"sheets":["765송부","345송부","154송부","중부발전","한수원","수자원공사"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":12,"n_cols":16,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"\"2017년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2017년도 10월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S 765kV #2 BUS","신가평S/S 765kV GIS 정밀점검공사","- 8352DS 정밀점검 - 8352DS #2BUS모선 가스누기 보수","2017-10-09 09:00","2017-10-20 18:00","2017-10-09 09:00","2017-10-20 18:00","연속",null,null,null,201707110048]
[2,"경기","성남","신안성S/S 765kV #2 BUS","신안성S/S 765kV GIS 정밀점검","신안성S/S 8772, 8752 GIS 정밀점검","2017-10-10 09:00","2017-10-21 18:00","2017-10-10 09:00","2017-10-21 18:00","연속",null,null,null,201708100026]
[3,"강원","태백","신태백S/S 765kV #2 BUS","○ 2017년 신태백S/S 800kV GIS 정밀점검 공사","○ 신태백-신한울#1T/L GIS 정밀점검 공사","2017-10-21 10:01","2017-10-27 18:01","2017-10-21 10:01","2017-10-27 18:01","연속",null,null,null,201708290128]
[4,"강원","태백","신태백S/S 765kV #1 BUS","○ 2017년 신태백S/S 800kV GIS 정밀점검 공사","○ 신태백-신한울#1T/L GIS 정밀점검 공사","2017-10-28 10:02","2017-11-03 18:02","2017-10-28 10:02","2017-11-03 18:02","연속",null,null,null,201708290120]
[5,"대전충남","서산","당진T/P 7호기 1차 CB","'17년 서산P/O 765kV GIS 보통점검 공사","당진화력 765kV 7호기 1차 GIS(8772) 보통점검","2017-10-20 09:00","2017-10-21 18:00","2017-10-20 09:00","2017-10-21 18:00","당일",null,null,null,201707070349]
[6,"대전충남","서산","신서산S/S 신서산당진TP#1T/L-TIE CB","'17년 서산P/O 765kV GIS 보통점검 공사","신서산S/S 765kV 신서산당진T/P#1T/L-TIE GIS(8400) 보통점검","2017-10-27 09:00","2017-10-28 18:00","2017-10-27 09:00","2017-10-28 18:00","당일",null,null,null,201707070315]
[7,"경북","영주","신한울S/S #1 M.Tr A-1","362kV LS제 GIS 차단기 재발방지 대책","362kV LS제 GIS 차단기 페퍼실린더 강도보강","2017-10-11 09:00","2017-10-17 18:00","취소","취소","연속",null,null,null,201708230130]
[8,"경북","영주","신한울S/S #2 M.Tr A-1","362kV LS제 GIS 차단기 재발방지 대책","362kV LS제 GIS 차단기 페퍼실린더 강도보강","2017-10-18 09:00","2017-10-24 18:00","취소","취소","연속",null,null,null,201708230131]

{"sheet":"345송부","index":1,"n_rows":327,"n_cols":16,"rows_kept":327,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"\"2017년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2017년도 10월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr A","17년 성동P/O 변전협력회사 총액공사","주변압기 보통점검 (성동S/S 345kV #1M.Tr)","2017-10-23 10:00","2017-10-24 17:00","2017-10-23 10:00","2017-10-24 17:00","연속",null,null,null,201708060007,"-"]
[2,"서울","중부","중부S/S 345kV #1 Sh.R","345kV 중부S/S #1Sh.R 교체공사","345kV 중부S/S #1Sh.R 교체공사","2017-10-10 10:00","2017-12-08 18:00","2017-10-10 10:00","2017-12-08 18:00","연속",null,null,null,201708090023,"-"]
[3,"서울","중부","중부S/S #3 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 모자익반 교체 (TCC PNL)","2017-10-16 10:00","2017-10-20 18:00","2017-10-16 10:00","2017-10-20 18:00","연속",null,null,null,201707100422,"-"]
[4,"서울","중부","중부S/S #2 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 모자익반 교체 (TCC PNL)","2017-10-23 10:00","2017-10-27 18:00","2017-10-23 10:00","2017-10-27 18:00","연속",null,null,null,201707100066,"-"]
[5,"서울","중부","중부S/S #1 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 모자익반 교체 (TCC PNL)","2017-10-30 10:00","2017-11-03 18:00","2017-10-30 10:00","2017-11-03 18:00","연속",null,null,null,201707100067,"-"]
[6,"남서울","강남","신양재S/S 345kV #1 Sh.R","362kV GIS 조작시험 및 개폐타임측정 - 변전협력","362kV GIS 조작시험 및 개폐타임측정","2017-10-12 10:00","2017-10-12 14:00","2017-10-12 10:00","2017-10-12 14:00","당일",null,null,null,201708180222,"-"]
[7,"남서울","강남","신양재S/S 345kV #2 Sh.R","362kV GIS 조작시험 및 개폐타임측정 - 변전협력","362kV GIS 조작시험 및 개폐타임측정","2017-10-12 14:00","2017-10-12 18:00","2017-10-12 14:00","2017-10-12 18:00","당일",null,null,null,201708180223,"-"]
[8,"남서울","강남","신양재S/S 345kV #3 Sh.R","362kV GIS 조작시험 및 개폐타임측정 - 변전협력","362kV GIS 조작시험 및 개폐타임측정","2017-10-19 10:00","2017-10-19 14:00","2017-10-19 10:00","2017-10-19 14:00","당일",null,null,null,201708180224,"-"]
[9,"남서울","강남","신양재S/S 345kV #4 Sh.R","362kV GIS 조작시험 및 개폐타임측정 - 변전협력","362kV GIS 조작시험 및 개폐타임측정","2017-10-19 14:00","2017-10-19 18:00","2017-10-19 14:00","2017-10-19 18:00","당일",null,null,null,201708180225,"-"]
[10,"남서울","강남","신양재S/S #1 M.Tr A","362,170kV GIS 조작시험 및 개폐타임측정 - 변전협력","362,170kV GIS 조작시험 및 개폐타임측정 : 7100,7172,6164 GIS","2017-10-20 10:00","2017-10-20 18:00","2017-10-20 10:00","2017-10-20 18:00","당일",null,null,null,201708180226,"-"]
[11,"남서울","강남","신양재S/S #2 M.Tr A","362,170kV GIS 조작시험 및 개폐타임측정 - 변전협력","362,170kV GIS 조작시험 및 개폐타임측정 : 7200,7272,6264 GIS","2017-10-23 10:00","2017-10-23 18:00","2017-10-23 10:00","2017-10-23 18:00","당일",null,null,null,201708180227,"-"]
[12,"남서울","강남","신양재S/S #3 M.Tr A","362,170kV GIS 조작시험 및 개폐타임측정 - 변전협력","362,170kV GIS 조작시험 및 개폐타임측정 : 7300,7372,6364 GIS","2017-10-24 10:00","2017-10-24 18:00","2017-10-24 10:00","2017-10-24 18:00","당일",null,null,null,201708180228,"-"]
[13,"남서울","강남","신양재S/S 신성남-신양재#1T/L CB (7171)","362kV GIS 조작시험 및 개폐타임측정 - 변전협력","362,170kV GIS 조작시험 및 개폐타임측정 : 7171,7271 GIS","2017-10-25 10:00","2017-10-25 14:00","2017-10-25 10:00","2017-10-25 14:00","당일",null,null,null,201708180229,"-"]
[14,"남서울","강남","신양재S/S 신성남-신양재#2T/L CB (7271)","362kV GIS 조작시험 및 개폐타임측정 - 변전협력","362,170kV GIS 조작시험 및 개폐타임측정 : 7171,7271 GIS","2017-10-25 14:00","2017-10-25 18:00","2017-10-25 14:00","2017-10-25 18:00","당일",null,null,null,201708180230,"-"]
[15,"남서울","동서울","동서울미금#1 T/L","345kV 동서울-미금T/L 지중화공사(하남시 현안지구)","하남시 지역현안1지구 개발관련 요청자 부담 지중화공사 - 기설 가공송전선로 철거 : No.15~No.17(C/H) - 지중송전선로 신설 : 신설C/H ~ J/B#3","2017-10-10 08:00","2017-11-01 18:00","2017-10-10 08:00","2017-11-01 18:00","연속",null,null,null,201708100202,"-"]
[16,"남서울","동서울","동서울S/S SVC M.Tr A","동서울S/S SVC 울타리 설치","동서울S/S SVC 울타리 설치, 조작시험","2017-10-10 09:00","2017-10-11 18:00","2017-10-10 09:00","2017-10-11 18:00","연속",null,null,null,201708280092,"-"]
[17,"남서울","동서울","동서울S/S #2 M.Tr A","345kV 주변압기 정밀점검","345kV 주변압기 정밀점검","2017-10-12 09:00","2017-10-20 18:00","2017-10-12 09:00","2017-10-20 18:00","연속",null,null,null,201708210195,"-"]
[18,"남서울","동서울","동서울S/S 345kV #71 BUS","345kV GIS 정밀점검","345kV GIS 정밀점검(7551DS)","2017-10-16 09:00","2017-10-17 18:00","2017-10-16 09:00","2017-10-17 18:00","연속",null,null,null,201708210171,"-"]
[19,"남서울","동서울","신성남동서울#1 T/L","345kV GIS 정밀점검","345kV GIS 정밀점검(7571CB, 7500CB)","2017-10-16 09:00","2017-10-22 18:00","2017-10-16 09:00","2017-10-22 18:00","연속",null,null,null,201708220050,"-"]
[20,"남서울","동서울","동서울S/S #3 M.Tr A","345kV GIS 정밀점검","345kV GIS 정밀점검(7572CB)","2017-10-23 09:00","2017-10-27 18:00","2017-10-23 09:00","2017-10-27 18:00","연속",null,null,null,201708210185,"-"]
[21,"남서울","동서울","동서울S/S 345kV #76 BUS","345kV GIS 정밀점검","345kV GIS 정밀점검(7552, 7652DS)","2017-10-28 09:00","2017-10-29 18:00","2017-10-28 09:00","2017-10-29 18:00","연속",null,null,null,201708220058,"-"]
[22,"남서울","동서울","동서울S/S #4 M.Tr A","345kV GIS 정밀점검","345kV GIS 정밀점검(7672CB)","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708220054,"-"]
[23,"남서울","영등포","영서S/S 영서#1T/L-신영서#1T/L CB (7100)","영서S/S 영서#1T/L-신영서#1T/L CB(7100) 조작시험","영서S/S 영서#1T/L-신영서#1T/L CB(7100) 조작시험","2017-10-10 09:00","2017-10-10 11:00","2017-10-10 09:00","2017-10-10 11:00","당일",null,null,null,201708180108,"-"]
[24,"남서울","영등포","영서S/S 서서울-영서#1T/L CB (7171)","영서S/S 영서S/S 서서울-영서#1T/L CB(7171) 조작시험","영서S/S 영서S/S 서서울-영서#1T/L CB(7171) 조작시험","2017-10-10 11:00","2017-10-10 13:00","2017-10-10 11:00","2017-10-10 13:00","당일",null,null,null,201708180110,"-"]
[25,"남서울","영등포","영서S/S 345kV 70-71 SEC CB (70-71-0)","영서S/S 345kV 70-71 SEC CB 조작시험","영서S/S 345kV 70-71 SEC CB 조작시험","2017-10-10 13:00","2017-10-10 15:00","2017-10-10 13:00","2017-10-10 15:00","당일",null,null,null,201708180116,"-"]
[26,"남서울","영등포","영서S/S #2 M.Tr 1차-영서#2T/L CB (7200)","영서S/S #2 M.Tr 1차-영서#2T/L(7200) 조작시험","영서S/S #2 M.Tr 1차-영서#2T/L(7200) 조작시험","2017-10-11 09:00","2017-10-11 12:00","2017-10-11 09:00","2017-10-11 12:00","당일",null,null,null,201708180124,"-"]
[27,"남서울","영등포","영서S/S #2 M.Tr A","영서S/S #2 M.Tr 1차 GCB 조작시험","영서S/S #2M.Tr 1차 GCB 조작시험 영서S/S #2 M.Tr 3차 23kV VCB 보통점검 영서S/S 23kV #2-1, #2-2 Sh.R VCB 보통점검 영서S/S 23kV #2-1, #2-2 Sh.R 보통점검","2017-10-11 09:00","2017-10-11 18:00","2017-10-11 09:00","2017-10-11 18:00","당일",null,null,null,201708180097,"-"]
[28,"남서울","영등포","영서S/S 345kV 75-76 SEC CB (75-76-0)","영서S/S 345kV 75-76 SEC CB 조작시험","영서S/S 345kV 75-76 SEC CB 조작시험","2017-10-12 10:00","2017-10-12 12:00","2017-10-12 10:00","2017-10-12 12:00","당일",null,null,null,201708180113,"-"]
[29,"남서울","영등포","영서S/S 신시흥-영서#1T/L CB (7172)","영서S/S 신시흥-영서#1T/L CB(7172) 조작시험","영서S/S 신시흥-영서#1T/L CB(7172) 조작시험","2017-10-12 13:00","2017-10-12 15:00","2017-10-12 13:00","2017-10-12 15:00","당일",null,null,null,201708180122,"-"]
[30,"남서울","영등포","영서S/S #4 M.Tr 1차-신시흥-영서#2T/L CB (7400)","영서S/S #4 M.Tr 1차-신시흥-영서#2T/L(7400) 조작시험","영서S/S #4 M.Tr 1차-신시흥-영서#2T/L (7400) 조작시험","2017-10-13 09:00","2017-10-13 12:00","2017-10-13 09:00","2017-10-13 12:00","당일",null,null,null,201708180133,"-"]
[31,"남서울","영등포","영서S/S #4 M.Tr A","영서S/S #4 M.Tr 1차 GCB 조작시험","영서S/S #4M.Tr 1차 GCB 조작시험 영서S/S #4 M.Tr 3차 23kV VCB 보통점검 영서S/S #4 S.Tr VCB 보통점검 영서S/S 23kV #4-1, #4-2 Sh.R VCB 보통점검","2017-10-13 09:00","2017-10-13 18:00","2017-10-13 09:00","2017-10-13 18:00","당일",null,null,null,201708180104,"-"]
[32,"남서울","영등포","영서S/S 345kV #71 BUS","영서S/S 345kV CVT 보통점검(#71 BUS)","영서S/S 345kV CVT 보통점검(#71 BUS)","2017-10-17 09:30","2017-10-17 14:00","2017-10-17 09:30","2017-10-17 14:00","당일",null,null,null,201708180070,"-"]
[33,"남서울","영등포","영서S/S 345kV #76 BUS","영서S/S 345kV CVT 보통점검(#76 BUS)","영서S/S 345kV CVT 보통점검(#76 BUS)","2017-10-17 14:00","2017-10-17 18:00","2017-10-17 14:00","2017-10-17 18:00","당일",null,null,null,201708180071,"-"]
[34,"남서울","영등포","영서S/S 서서울-영서#2T/L CB (7272)","영서S/S 345kV 서서울-영서#2T/L CB(7272) 조작시험","영서S/S 345kV 서서울-영서#2T/L CB(7272) 조작시험","2017-10-17 14:00","2017-10-17 16:00","2017-10-17 14:00","2017-10-17 16:00","당일",null,null,null,201708180129,"-"]
[35,"남서울","영등포","영서S/S 신시흥-영서#2T/L CB (7472)","영서S/S 345kV 신시흥-영서#2T/L CB(7472) 조작시험","영서S/S 345kV 신시흥-영서#2T/L CB(7472) 조작시험","2017-10-17 16:00","2017-10-17 18:00","2017-10-17 16:00","2017-10-17 18:00","당일",null,null,null,201708180132,"-"]
[36,"남서울","영등포","영서S/S 345kV #75 BUS","영서S/S 345kV GIS 정밀점검 공사(#75BUS)","- 345kV 40kA 4000A GIS 내부점검(5CB) - #75BUS CVT 보통점검","2017-10-20 08:00","2017-10-20 18:00","2017-10-20 08:00","2017-10-20 18:00","당일",null,null,null,201708180046,"-"]
[37,"남서울","영등포","영서S/S 영서-영등포#1T/L CB (7572)","영서S/S 345kV GIS 정밀점검 공사(7572CB)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-10-20 08:00","2017-10-22 10:00","2017-10-20 08:00","2017-10-22 10:00","연속",null,null,null,201708180047,"-"]
[38,"남서울","영등포","영서S/S #3 M.Tr A","영서S/S #3 M.Tr 1차, 2차 GCB 조작시험","영서S/S #3M.Tr 1차, 2차 GCB 조작시험 영서S/S #3 M.Tr 2차 LA 보통점검 영서S/S #3 M.Tr 3차 23kV VCB 보통점검 영서S/S 23kV #3 S.Tr VCB 보통점검","2017-10-20 09:00","2017-10-20 18:00","2017-10-20 09:00","2017-10-20 18:00","당일",null,null,null,201708180075,"-"]
[39,"남서울","영등포","영서S/S TIE-#3M.Tr 1차 CB (7300)","영서S/S TIE-#3M.Tr 1차 CB(7300) 조작시험","영서S/S TIE-#3M.Tr 1차 CB(7300) 조작시험","2017-10-20 09:00","2017-10-20 12:00","2017-10-20 09:00","2017-10-20 12:00","당일",null,null,null,201708180125,"-"]
[40,"남서울","영등포","영서S/S #1M.Tr 1차-영서-영등포#1T/L CB (7500)","영서S/S 345kV GIS 정밀점검 공사(7500 CB)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-10-21 08:00","2017-10-23 18:00","2017-10-21 08:00","2017-10-23 18:00","연속",null,null,null,201708180048,"-"]
[41,"남서울","영등포","영서영등포#1 T/L","영서S/S 345kV GIS 정밀점검 공사(영서-영등포#1T/L)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-10-21 08:00","2017-10-22 10:00","2017-10-21 08:00","2017-10-22 10:00","연속",null,null,null,201708180049,"-"]
[42,"남서울","영등포","영서S/S #1 M.Tr A","영서S/S #1 M.Tr 정밀점검","영서S/S #1 M.Tr 정밀점검 영서S/S #1M.Tr 2차 GCB 개폐타임 측정","2017-10-22 08:00","2017-10-27 08:00","2017-10-22 08:00","2017-10-27 08:00","연속",null,null,null,201708180088,"-"]
[43,"남서울","영등포","영서S/S #1M.Tr 1차 CB (7571)","영서S/S 345kV GIS 정밀점검 공사(7571 CB)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-10-22 08:00","2017-10-27 08:00","2017-10-22 08:00","2017-10-27 08:00","연속",null,null,null,201708180050,"-"]
[44,"남서울","영등포","영서S/S 345kV #70 BUS","영서S/S 345kV GIS 정밀점검 공사(70BUS)","- 345kV 40kA 4000A GIS 내부점검(5CB) - 345kV #70 CVT 점검","2017-10-20 08:00","2017-10-20 18:00","2017-10-20 08:00","2017-10-20 18:00","연속",null,null,null,201708180054,"-"]
[45,"남서울","영등포","영서S/S 345kV #75 BUS","영서S/S 345kV GIS 정밀점검 공사(#75BUS)","- 345kV 40kA 4000A GIS 내부점검(5CB) - #75BUS CVT 보통점검","2017-10-27 08:00","2017-10-27 18:00","2017-10-27 08:00","2017-10-27 18:00","당일",null,null,null,201708180063,"-"]
[46,"남서울","영등포","영서S/S 영서-영등포#2T/L CB (7672)","영서S/S 345kV GIS 정밀점검 공사(7672CB)","- 345kV 40kA 4000A GIS 내부점검","2017-10-27 08:00","2017-10-29 10:00","2017-10-27 08:00","2017-10-29 10:00","연속",null,null,null,201708180064,"-"]
[47,"남서울","영등포","영서S/S TIE-영서-영등포#2T/L CB (7600)","영서S/S 345kV GIS 정밀점검 공사(7600 CB)","- 345kV 40kA 4000A GIS 내부점검","2017-10-28 08:00","2017-10-29 18:00","2017-10-28 08:00","2017-10-29 18:00","연속",null,null,null,201708180067,"-"]
[48,"남서울","영등포","영서영등포#2 T/L","영서S/S 345kV GIS 정밀점검 공사(영서-영등포#2T/L)","- 345kV 40kA 4000A GIS 내부점검","2017-10-28 08:00","2017-10-29 10:00","2017-10-28 08:00","2017-10-29 10:00","연속",null,null,null,201708180066,"-"]
[49,"남서울","영등포","영서S/S 345kV #70 BUS","영서S/S 345kV GIS 정밀점검 공사(70BUS)","- 345kV 40kA 4000A GIS 내부점검","2017-10-29 08:00","2017-10-29 18:00","2017-10-29 08:00","2017-10-29 18:00","연속",null,null,null,201708180069,"-"]
[50,"남서울","직할","영등포S/S 345kV 70 BUS","영등포S/S 345kV 모선보호반 교체공사","영등포S/S 345kV 모선보호반 교체공사 - #70BUS","2017-10-10 09:00","2017-10-13 18:00","2017-10-10 09:00","2017-10-13 18:00","연속",null,null,null,201708180042,"-"]
[51,"남서울","직할","영등포S/S 영서-영등포#1T/L CB (7171)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-10 09:00","2017-10-10 18:00","2017-10-10 09:00","2017-10-10 18:00","당일",null,null,null,201708210336,"-"]
[52,"남서울","직할","영등포S/S 영서-영등포#2T/L CB (7271)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-10 09:00","2017-10-10 18:00","2017-10-10 09:00","2017-10-10 18:00","당일",null,null,null,201708210338,"-"]
[53,"남서울","직할","영등포S/S #1 M.Tr 1차 CB (7172)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708210349,"-"]
[54,"남서울","직할","영등포S/S #2 M.Tr 1차 CB (7272)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708210351,"-"]
[55,"남서울","직할","영등포S/S #3 M.Tr 1차 CB (7372)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708210353,"-"]
[56,"남서울","직할","영등포S/S 345kV 75 BUS","영등포S/S 345kV 모선보호반 교체공사","영등포S/S 345kV 모선보호반 교체공사 - #75BUS","2017-10-16 09:00","2017-10-19 18:00","2017-10-16 09:00","2017-10-19 18:00","연속",null,null,null,201708180043,"-"]
[57,"남서울","직할","영서-영등포#1T/L-#1M.Tr 1차 CB (7100)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-20 09:00","2017-10-20 18:00","2017-10-20 09:00","2017-10-20 18:00","당일",null,null,null,201708210359,"-"]
[58,"남서울","직할","영서-영등포#2T/L-#2 M.Tr 1차 CB (7200)","345kV 차단기 조작시험","345kV 차단기 조작시험 및 개폐타임 측정","2017-10-27 09:00","2017-10-27 18:00","2017-10-27 09:00","2017-10-27 18:00","당일",null,null,null,201708210364,"-"]
[59,"인천","시흥","신시흥#1S/S 신시흥영흥TP#4T/L-#3 M.Tr 1 (7800)","신시흥#1S/S 345kV 7800 CB 정밀점검","신시흥#1S/S 345kV 7800 CB 정밀점검","2017-10-11 08:00","2017-10-13 18:00","2017-10-11 08:00","2017-10-13 18:00","연속",null,null,null,201708160247,"-"]
[60,"인천","시흥","영흥T/P #1G/T 1차 CB (7172)","영흥T/P #1G/T 1차 CB (7172) 구조개선공사","영흥T/P #1G/T 1차 CB (7172) 구조개선공사","2017-10-11 08:00","2017-10-13 18:00","2017-10-11 08:00","2017-10-13 18:00","연속",null,null,null,201708160240,"-"]
[61,"인천","시흥","신시흥#1S/S #2 M.Tr 1차 CB (7A72)","신시흥#1S/S 345kV 7A72 CB 정밀점검","신시흥#1S/S 345kV 7A72 CB 정밀점검","2017-10-15 08:00","2017-10-17 18:00","2017-10-15 08:00","2017-10-17 18:00","연속",null,null,null,201708160248,"-"]
[62,"인천","시흥","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB (7100)","영흥T/P 연락#1T/L-#1 G/T 1차 CB (7100) 구조개선공사","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB (7100) 구조개선공사","2017-10-16 08:00","2017-10-18 18:00","2017-10-16 08:00","2017-10-18 18:00","연속",null,null,null,201708160241,"-"]
[63,"인천","시흥","신시흥영서#1 T/L","345kV신시흥-영서#1T/L 과열개소정비","345kV신시흥-영서#1T/L 과열개소정비","2017-10-18 08:00","2017-10-18 13:00","2017-10-18 08:00","2017-10-18 13:00","당일",null,null,null,201708170012,"-"]
[64,"인천","시흥","신시흥영서#2 T/L","345kV신시흥-영서#2T/L 과열개소정비","345kV신시흥-영서#2T/L 과열개소정비","2017-10-18 13:00","2017-10-18 18:00","2017-10-18 13:00","2017-10-18 18:00","당일",null,null,null,201708170013,"-"]
[65,"인천","시흥","신시흥#1S/S 신시흥영서#2T/L CB (7A71)","신시흥#1S/S 345kV 7A71 CB 정밀점검","신시흥#1S/S 345kV 7A71 CB 정밀점검","2017-10-19 08:00","2017-10-22 18:00","2017-10-19 08:00","2017-10-22 18:00","연속",null,null,null,201708160249,"-"]
[66,"인천","시흥","영흥T/P 영흥TP연락#1T/L CB (7171)","영흥T/P 영흥TP연락#1T/L CB (7171) 구조개선공사","영흥T/P 영흥TP연락#1T/L CB (7171) 구조개선공사","2017-10-19 08:00","2017-10-21 18:00","2017-10-19 08:00","2017-10-21 18:00","연속",null,null,null,201708160242,"-"]
[67,"인천","시흥","영흥T/P 영흥TP연락#2T/L CB (7271)","영흥T/P 영흥TP연락#2T/L CB (7271) 구조개선공사","영흥T/P 영흥TP연락#2T/L CB (7271) 구조개선공사","2017-10-23 08:00","2017-10-25 18:00","2017-10-23 08:00","2017-10-25 18:00","연속",null,null,null,201708160243,"-"]
[68,"인천","시흥","신시흥#1S/S 신가좌신시흥#2T/L-TIE CB (7C00)","신시흥#1S/S 345kV 7C00 CB 정밀점검","신시흥#1S/S 345kV 7C00 CB 정밀점검","2017-10-24 08:00","2017-10-27 18:00","2017-10-24 08:00","2017-10-27 18:00","연속",null,null,null,201708160250,"-"]
[69,"인천","시흥","영흥T/P 신시흥영흥TP#4T/L CB (7571)","영흥T/P 신시흥영흥TP#4T/L CB (7571) 구조개선공사","영흥T/P 신시흥영흥TP#4T/L CB (7571) 구조개선공사","2017-10-26 08:00","2017-10-28 18:00","2017-10-26 08:00","2017-10-28 18:00","연속",null,null,null,201708160244,"-"]
[70,"인천","시흥","영흥T/P #2 TIE Tr 1차 CB (7372)","영흥T/P #2 TIE Tr 1차 CB (7372) 구조개선공사","영흥T/P #2 TIE Tr 1차 CB (7372) 구조개선공사","2017-10-30 08:00","2017-11-01 18:00","2017-10-30 08:00","2017-11-01 18:00","연속",null,null,null,201708160245,"-"]
[71,"인천","인천","서인천C/C #2 M.Tr","서인천복합S/Y #2M.Tr 345kV 주변압기 정밀점검 공사","서인천복합S/Y #2M.Tr 345kV 주변압기 정밀점검 공사","2017-10-10 09:00","2017-10-14 18:00","2017-10-10 09:00","2017-10-14 18:00","연속",null,null,null,201708220137,"-"]
[72,"인천","인천","신가좌S/S TIE-#4 M.Tr 1차 CB (신) (7600 A)","신가좌S/S 7600 GIS 초기점검 공사","신가좌S/S 7600 GIS 초기점검 공사","2017-10-10 09:00","2017-10-10 18:00","2017-10-10 09:00","2017-10-10 18:00","당일",null,null,null,201708090253,"-"]
[73,"인천","인천","신가좌S/S #2 M.Tr A","신가좌S/S #2M.Tr 1,2차 GIS 보통점검 등 휴전작업","신가좌S/S #2M.Tr 휴전작업 - 1차(7372) GIS 보통점검 - 6244 GIS 보통점검 - GPT 점검 - 신가좌S/S 345,154kV 옥외분전반 대체공사(#2M.Tr)","2017-10-11 09:00","2017-10-13 18:00","2017-10-11 09:00","2017-10-13 18:00","연속",null,null,null,201708020181,"-"]
[74,"인천","인천","신가좌S/S 신가좌신시흥#2T/L CB (7471)","신가좌S/S 362kV GIS 정밀점검 공사(7471)","신가좌S/S 362kV GIS 정밀점검 공사(7471)","2017-10-11 09:00","2017-10-13 18:00","2017-10-11 09:00","2017-10-13 18:00","연속",null,null,null,201708090254,"-"]
[75,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","* 서인천C/C 345kV #70BUS 현장개조 * 345kV #70BUS 관련 DS교체","2017-10-11 10:00","2017-11-14 17:00","취소","취소","연속",null,null,null,201708180044,"-"]
[76,"인천","인천","신가좌S/S #3 M.Tr A","인천전력지사 345kV 주변압기 정밀점검 공사(신가좌S/S #3M.Tr)","- 주변압기 정밀점검 - OLTC 정밀점검 - 누유개소 보수 - 기계적 보호장치 및 각종 계기 교체","2017-10-16 09:00","2017-10-31 18:00","2017-10-16 09:00","2017-10-29 18:00","연속",null,null,null,201708010038,"-"]
[77,"인천","인천","신가좌S/S #4 M.Tr 1차 CB (신) (7672 A)","신가좌S/S 7672 GIS 초기점검 공사","신가좌S/S 7672 GIS 초기점검 공사","2017-10-17 09:00","2017-10-17 18:00","취소","취소","당일",null,null,null,201708090255,"-"]
[78,"인천","인천","신가좌가정#1 T/L","345kV신가좌-가정#1T/L 과열개소정비","345kV신가좌-가정#1T/L 과열개소정비","2017-10-19 08:00","2017-10-19 18:00","2017-10-30 08:00","2017-10-30 13:00","당일",null,null,null,201708170016,"-"]
[79,"인천","인천","인천CC S/Y #2Tie-Tr A","인천CC #2Tie-Tr 휴전작업","인천CC #2Tie-Tr 휴전작업 - 2차 GIS 보통점검(6144)","2017-10-19 09:00","2017-10-19 18:00","2017-10-19 09:00","2017-10-19 18:00","연속",null,null,null,201708090256,"-"]
[80,"인천","인천","포스코파워S/Y 포스코SY-인천CC#1T/L CB (7171)","LS제 362kV 차단기 하자처리 대체공사(포스코S/Y 7171)","LS제 362kV 차단기 하자처리 대체공사(포스코S/Y 7171)","2017-10-23 09:00","2017-10-30 18:00","2017-10-23 09:00","2017-10-30 18:00","연속",null,null,null,201708090257,"-"]
[81,"인천","인천","신인천C/C 345kV #72 BUS","345kV 서(신)인천C/C 모선용CLR 설치공사","* #72BUS 모선측CLR용 GIS 설치","2017-10-24 10:00","2017-10-31 17:00","2017-10-24 10:00","2017-10-31 17:00","연속",null,null,null,201708180045,"-"]
[82,"인천","인천","인천CC S/Y 신경서-인천CC#1T/L-TIE CB (7200)","인천CC 7200 대시포트 누유보수 공사","인천CC 7200 대시포트 누유보수 공사(성우전기 시행)","2017-10-26 09:00","2017-10-26 18:00","2017-10-26 09:00","2017-10-26 18:00","당일",null,null,null,201708090266,"-"]
[83,"인천","인천","서인천C/C #4 M.Tr","서인천복합S/Y #4M.Tr 345kV 주변압기 정밀점검 공사","서인천복합S/Y #4M.Tr 345kV 주변압기 정밀점검 공사 - #4M.Tr 변압기 정밀점검 및 각종시험 등 - 170kV GIS 정밀점검(#4M.Tr 2차 GIS) 병행 등","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708160001,"-"]
[84,"인천","인천","인천CC S/Y #1Tie-Tr A","인천CC #1Tie-Tr 휴전작업","인천CC #1Tie-Tr 휴전작업 - M.Tr, LA 보통점검 - 2차 GIS 보통점검","2017-10-30 09:00","2017-10-31 18:00","2017-10-30 09:00","2017-10-31 18:00","연속",null,null,null,201708090268,"-"]
[85,"인천","인천","포스코SY인천CC#1T/L-#1GEN STEPUP TIE CB (7100)","LS제 362kV 차단기 하자처리 대체공사(포스코S/Y 7100)","LS제 362kV 차단기 하자처리 대체공사(포스코S/Y 7100)","2017-10-31 09:00","2017-11-07 18:00","2017-10-31 09:00","2017-11-07 18:00","연속",null,null,null,201708090258,"-"]
[86,"인천","직할","신부평S/S #1 M.Tr A","신부평S/S #1M.Tr 345kV 주변압기 정밀점검","신부평S/S #1M.Tr 345kV 주변압기 정밀점검","2017-10-16 08:00","2017-10-21 18:00","2017-10-16 08:00","2017-10-21 18:00","연속",null,null,null,201708140097,"-"]
[87,"인천","직할","신부평S/S #4 M.Tr A","신부평S/S #4M.Tr 345kV 주변압기 정밀점검","신부평S/S #4M.Tr 345kV 주변압기 정밀점검","2017-10-23 08:00","2017-10-28 18:00","2017-10-23 08:00","2017-10-28 18:00","연속",null,null,null,201708140098,"-"]
[88,"인천","직할","신부평S/S 345kV #3 Sh.R","신부평S/S #3Sh.R 345kV 주변압기 정밀점검","신부평S/S #3Sh.R 345kV 주변압기 정밀점검","2017-10-30 08:00","2017-11-04 18:00","2017-10-30 08:00","2017-11-04 18:00","연속",null,null,null,201708140100,"-"]
[89,"인천","직할","신부평S/S 서인천CC-신부평#1T/L CB (7171)","신부평S/S 서인천-신부평#1T/L(7171) 362kV GIS 정밀점검","신부평S/S 서인천-신부평#1T/L(7171) 362kV GIS 정밀점검","2017-10-30 08:00","2017-11-01 18:00","2017-10-30 08:00","2017-11-01 18:00","연속",null,null,null,201708180179,"-"]
[90,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN CB (7079)","7279 개폐제어형 다빈도 차단기 시범적용","7279 개폐제어형 다빈도차단기 시범적용 -분기모선에 따른 #1,2,5 Sh.R 동시휴전","2017-10-12 09:00","2017-10-12 18:00","2017-10-12 09:00","2017-10-12 18:00","당일",null,null,null,201708180008,"-"]
[91,"경기북부","구리","미금S/S 345kV #1 BUS","345kV 79Bay GIS 정밀점검","345kV 79Bay GIS 정밀점검 - 7951DS 정밀점검","2017-10-14 09:00","2017-10-15 18:00","2017-10-14 09:00","2017-10-15 18:00","당일",null,null,null,201708180001,"-"]
[92,"경기북부","구리","신포천포천CC#1 T/L","신포천-포천CC #1T/L 3상 접지BAR 설치","신포천-포천CC #1T/L 3상 접지BAR 설치 -A,B,C상 공통접지","2017-10-16 09:00","2017-10-17 18:00","2017-10-16 09:00","2017-10-17 18:00","연속",null,null,null,201707030116,"○"]
[93,"경기북부","구리","미금S/S #1 M.Tr A","17년 154kV GIS 보통점검","17년 154kV GIS 보통점검","2017-10-16 13:00","2017-10-16 18:00","2017-10-16 13:00","2017-10-16 18:00","당일",null,null,null,201708100176,"-"]
[94,"경기북부","구리","신포천포천CC#2 T/L","신포천-포천CC #2T/L 3상 접지BAR 설치","신포천-포천CC #2T/L 3상 접지BAR 설치 -A,B,C상 공통접지","2017-10-18 09:00","2017-10-19 18:00","2017-10-16 09:00","2017-10-17 18:00","연속",null,null,null,201707030117,"-"]
[95,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN CB (7079)","7279 개폐제어형 다빈도 차단기 시범적용","7279 개폐제어형 다빈도차단기 시범적용 -분기모선에 따른 #1,2,5 Sh.R 동시휴전","2017-10-19 09:00","2017-10-20 18:00","2017-10-19 09:00","2017-10-20 18:00","연속",null,null,null,201708180009,"-"]
[96,"경기북부","구리","미금S/S 345kV #2 BUS","345kV 79Bay GIS 정밀점검","345kV 79Bay GIS 정밀점검 - 7952DS 정밀점검","2017-10-21 09:00","2017-10-22 18:00","2017-10-21 09:00","2017-10-22 18:00","당일",null,null,null,201708180002,"-"]
[97,"경기북부","구리","미금S/S #2 M.Tr A","17년 154kV GIS 보통점검","17년 154kV GIS 보통점검","2017-10-23 13:00","2017-10-23 18:00","2017-10-23 13:00","2017-10-23 18:00","당일",null,null,null,201708100178,"-"]
[98,"경기북부","구리","미금S/S 345kV #3 Sh.R","미금S/S 345kV #3 Sh.R 개폐제어용 다빈도차단기 시적용","○ 345kV 개폐제어용 다빈도차단기 시적용 - 제어기 설치, 시험","2017-10-30 08:00","2017-11-03 18:00","2017-10-30 08:00","2017-11-03 18:00","연속",null,null,null,201707180055,"-"]
[99,"경기북부","구리","미금S/S 345kV #4 Sh.R","미금S/S 345kV #3 Sh.R 개폐제어용 다빈도차단기 시적용","○ 345kV 개폐제어용 다빈도차단기 시적용 - 제어기 설치, 시험 ○ #3Sh.R 인접설비 Trip 회로 공유.","2017-10-30 08:00","2017-11-03 18:00","2017-10-30 08:00","2017-11-03 18:00","매일",null,null,null,201707180058,"-"]
[100,"경기북부","직할","양주중부#2 T/L","345kV 양주-중부#2T/L 접속개소 전선교체공사","ㅇ 내용 : 접속개소전선교체공사 ㅇ 구간 : 345kV 양주-중부#2T/L No.3-5, 22-26","2017-10-08 08:00","2017-10-11 18:00","2017-10-08 08:00","2017-10-11 18:00","연속",null,null,null,201708180178,"-"]
[101,"경기북부","직할","신의정부양주#1 T/L","345kV 신의정부-양주T/L 전선접속개소 전선교체공사","345kV 신의정부-양주#1,2T/L 21.334km 전력선 교체 및 가공지선 10.090km 교체","2017-10-11 09:00","2017-11-09 18:00","2017-10-13 09:00","2017-11-11 18:00","연속",null,null,null,201705160113,"-"]
[102,"경기북부","직할","양주중부#2 T/L","양주S/S 345kV #6 Sh.R 1차 GIS 개조공사","양주S/S 345kV #6 Sh.R 1차 GIS 균압콘덴서 교체","2017-10-18 09:00","2017-10-20 18:00","2017-10-17 07:00","2017-10-21 18:00","연속",null,null,null,201708160184,"-"]
[103,"경기북부","직할","신의정부미금#2 T/L","16~17년 직할 가공송전정비 협력회사 총액공사(병가)","154kV 신의정부-송우#1T/L 피뢰기설치공사 - 8기 24SET 피뢰기설치 - 345kV 신의정부-미금#2T/L 상단병가선로 휴전 시행","2017-10-22 07:00","2017-10-22 18:00","2017-10-22 07:00","2017-10-22 18:00","당일",null,null,null,201707100349,"-"]
[104,"경기북부","직할","양주S/S 345kV #5 Sh.R","양주S/S 345kV #5 Sh.R 1차 GIS 개조공사","양주S/S 345kV #5 Sh.R 1차 GIS 균압콘덴서 교체","2017-10-24 09:00","2017-11-30 18:00","2017-10-24 09:00","2017-11-30 18:00","연속",null,null,null,201708160181,"-"]
[105,"경기북부","직할","양주중부#1 T/L","양주S/S 345kV #5 Sh.R 1차 GIS 개조공사","양주S/S 345kV #5 Sh.R 1차 GIS 균압콘덴서 교체","2017-10-24 09:00","2017-10-26 18:00","2017-10-23 07:00","2017-10-27 18:00","연속",null,null,null,201708160182,"-"]
[106,"경기북부","파주","파주문산C/C 파주문산-발전단#4T/L GIS","7400, 7472 투입회로개선","7400, 7472 투입회로개선","2017-10-07 09:00","2017-10-07 18:00","2017-10-07 09:00","2017-10-07 18:00","당일",null,null,null,201708180121,"-"]
[107,"경기북부","파주","파주문산C/C 파주문산-발전단#3T/L GIS","7300, 7372 투입회로개선","7300, 7372 투입회로개선","2017-10-08 09:00","2017-10-08 18:00","2017-10-08 09:00","2017-10-08 18:00","당일",null,null,null,201708180120,"-"]
[108,"경기북부","파주","신덕은S/S 345kV #2 BUS","345kV 신덕은S/S SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 설치 ㅇ 기타 부대공사 1식 * LG Display 전력공급 송전선로 신설","2017-10-11 09:00","2017-10-15 18:00","2017-10-11 09:00","2017-10-15 18:00","연속",null,null,null,201707100285,"-"]
[109,"경기북부","파주","신덕은파주문산CC#1 T/L","GIS 고주파 써지 측정장치 설치","신덕은-파주문산#1T/L CC 고주파 측정장치 설치 후 개폐 써지 측정","2017-10-11 09:30","2017-10-15 18:00","2017-10-11 09:30","2017-10-15 18:00","연속",null,null,null,201708110406,"-"]
[110,"경기북부","파주","신파주신덕은#1 T/L","154kV 신덕은-수색T/L 송전용량증대 전력선교체공사","154kV 신덕은-원흥T/L No.60~68 전력선교체 * 신덕은-원흥T/L 4회선구간 병행휴전","2017-10-14 08:00","2017-10-18 12:00","2017-10-14 08:00","2017-10-18 12:00","연속",null,null,null,201708090170,"-"]
[111,"경기북부","파주","신파주신덕은#2 T/L","154kV 신덕은-수색T/L 송전용량증대 전력선교체공사","154kV 신덕은-원흥T/L No.60~68 전력선교체 * 신덕은-원흥T/L 4회선구간 병행휴전","2017-10-18 12:00","2017-10-22 18:00","2017-10-18 12:00","2017-10-22 18:00","연속",null,null,null,201708090171,"-"]
[112,"경기북부","파주","신파주양주#2 T/L","345kV 신파주-양주#2T/L 접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 대상 : No.21-22, 26-27,42-43,47-48","2017-10-23 07:00","2017-10-27 18:00","2017-10-23 07:00","2017-10-27 18:00","연속",null,null,null,201707070110,"-"]
[113,"경기북부","파주","파주문산C/C 파주문산-발전단#1T/L GIS","7100,7172 투입회로개선","7100,7172 투입회로개선","2017-10-28 09:00","2017-10-28 18:00","2017-10-28 09:00","2017-10-28 18:00","당일",null,null,null,201708180117,"-"]
[114,"경기북부","파주","파주문산C/C 파주문산-발전단#2T/L GIS","7200, 7272 투입회로개선","7200, 7272 투입회로개선","2017-10-29 09:00","2017-10-29 18:00","2017-10-29 09:00","2017-10-29 18:00","당일",null,null,null,201708180119,"-"]
[115,"경기","군포","서서울#2신성남 #2T/L","군포송정지구 송전선로 지중화 사업","ㅇ 구간 : 345kV 서서울#2S/S~345kV 서서울#2-신성남T/L No.51 ㅇ 규모 : 345kV XLPE 2500㎟, 2회선(D)-1.3km","2017-10-30 09:00","2017-11-26 18:00","2017-10-30 09:00","2017-11-26 18:00","연속",null,null,null,201708210011,"-"]
[116,"경기","군포","서서울S/S #4 M.Tr A","서서울S/S #4M.Tr 3차측 모선 지지애자 교체작업","서서울S/S #4M.Tr 3차측 모선 지지애자 절연보강관련 전량 교체작업 시행","2017-10-16 09:00","2017-10-20 18:00","2017-10-16 09:00","2017-10-20 18:00","연속",null,null,null,201708160025,"-"]
[117,"경기","군포","서서울S/S #1 M.Tr A","서서울S/S #1M.Tr 3차측 모선 지지애자 교체작업","서서울S/S #1M.Tr 3차측 모선 지지애자 절연보강관련 전량 교체작업 및 1차 피뢰기 교체","2017-10-23 09:00","2017-10-27 18:00","2017-10-23 09:00","2017-10-27 18:00","연속",null,null,null,201708160027,"-"]
[118,"경기","군포","화성신안산 T/L","345kV 화성-신안산T/L 가공송전선로 정밀점검","345kV 화성-신안산T/L 가공송전선로 정밀점검(1~56.1호, 57기)","2017-10-27 09:00","2017-10-30 18:00","2017-10-27 09:00","2017-10-30 18:00","매일",null,null,null,201708160166,"-"]
[119,"경기","군포","서서울S/S #2 M.Tr A","서서울S/S #2M.Tr 3차측 모선 지지애자 교체작업","서서울S/S #2M.Tr 3차측 모선 지지애자 절연보강관련 전량 교체작업","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708160028,"-"]
[120,"경기","군포","신시흥신안산 T/L","345kV 신시흥-신안산T/L 가공송전선로 정밀점검","345kV 신시흥-신안산T/L 가공송전선로 정밀점검(56.1~101호, 47기)","2017-10-31 09:00","2017-11-02 18:00","2017-10-31 09:00","2017-11-02 18:00","매일",null,null,null,201708160161,"-"]
[121,"경기","동부","곤지암신충주#1 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사(#1T/L)","0 전선교체 : No.4~6 등 13개소, 38경간 0 가공지선 교체 : No.25~32등 2개소 14경간 0 금구류 교체 등","2017-10-12 07:30","2017-10-31 18:00","2017-10-12 07:30","2017-10-31 18:00","연속",null,null,null,201708070117,"-"]
[122,"경기","동부","곤지암S/S #1 M.Tr A","동부 변전 총액공사","곤지암SS #1M.Tr(보통)/7172/6144GIS(보통)","2017-10-14 09:00","2017-10-15 18:00","2017-10-14 09:00","2017-10-15 18:00","연속",null,null,null,201708160289,"-"]
[123,"경기","동부","곤지암S/S #2 M.Tr A","동부 변전 총액공사","곤지암SS #2M.Tr(보통)/7372/6244GIS(보통)","2017-10-21 09:00","2017-10-22 18:00","2017-10-21 09:00","2017-10-22 18:00","연속",null,null,null,201708160291,"-"]
[124,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #64D.Tr용 GIS 설치공사","154kV #61BUS 무부하 가압","2017-10-28 09:00","2017-10-29 09:00","2017-10-28 09:00","2017-10-29 09:00","연속",null,null,null,201708210107,"-"]
[125,"경기","성남","서안성신진천#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.93 ~ 서안성S/S OPGW 증설(7기)","2017-10-01 07:00","2017-10-04 18:00","취소","취소","연속",null,null,null,201708070282,"-"]
[126,"경기","성남","신안성서안성#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.14 ~ 서안성S/S OPGW 증설(7기)","2017-10-01 07:00","2017-10-03 18:00","취소","취소","연속",null,null,null,201708070283,"-"]
[127,"경기","성남","신안성서안성#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.13 ~ 14 OPGW 증설(2기)","2017-10-04 07:00","2017-10-06 18:00","취소","취소","연속",null,null,null,201708070284,"-"]
[128,"경기","성남","서안성신진천#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.93 ~ 98 항공장애표시구 설치(6기)","2017-10-05 07:00","2017-10-06 18:00","취소","취소","연속",null,null,null,201708070285,"-"]
[129,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울#1T/L 정밀점검","345kV 신용인-동서울#1T/L 정밀점검","2017-10-10 09:00","2017-10-13 18:00","2017-10-10 09:00","2017-10-13 18:00","연속",null,null,null,201708160179,"-"]
[130,"경기","성남","신안성신수원#1 T/L","17년 성남변전협력회사 총액공사","신수원S/S 7271, 7200 GIS 보통점검 및 LA 보통점검 신안성S/S 7902 DS B상 가스누기개소 보수","2017-10-11 10:00","2017-10-12 18:00","2017-10-11 10:00","2017-10-12 18:00","연속",null,null,null,201708100052,"-"]
[131,"경기","성남","신성남S/S #4M.Tr A","17년 성남변전협력회사 총액공사","75BAY BF 대체 및 7571, 7500, 6444 GIS 조작시험","2017-10-16 09:00","2017-10-19 18:00","2017-10-16 09:00","2017-10-19 18:00","연속",null,null,null,201708100040,"-"]
[132,"경기","성남","신안성신성남#2 T/L","17년 성남변전협력회사 총액공사","75BAY BF 대체 및 7500, 7571 GIS 조작시험","2017-10-16 09:00","2017-10-19 18:00","2017-10-16 09:00","2017-10-19 18:00","연속",null,null,null,201708100041,"-"]
[133,"경기","성남","신용인S/S #3 M.Tr A","17년 성남변전협력회사 총액공사","M.Tr 정밀점검, 3차 PT 및 LA보통점검, 6344 조작시험","2017-10-16 09:00","2017-10-30 18:00","2017-10-16 09:00","2017-10-30 18:00","연속",null,null,null,201708100078,"-"]
[134,"경기","성남","신안성신수원#2 T/L","17년 성남변전협력회사 총액공사","신수원S/S 7300, 7371 GIS 조작시험 및 LA 보통점검 신안성S/S 7A02 DS C상 가스누기개소 보수","2017-10-18 10:00","2017-10-20 18:00","2017-10-18 10:00","2017-10-20 18:00","연속",null,null,null,201708100051,"-"]
[135,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","신성남-과천#2T/L GIS 대체 공사관련 무부하 가압","2017-10-20 09:00","2017-10-20 21:00","2017-10-20 09:00","2017-10-20 21:00","당일",null,null,null,201708100038,"-"]
[136,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","신성남-과천#2T/L GIS 대체 공사관련 무부하 가압","2017-10-23 09:00","2017-10-24 21:00","2017-10-23 09:00","2017-10-24 21:00","연속",null,null,null,201708100039,"-"]
[137,"경기","성남","신성남S/S #5 M.Tr A","17년 성남변전협력회사 총액공사","77BAY BF 대체","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708100043,"-"]
[138,"경기","성남","신성남신양재#2 T/L","17년 성남변전협력회사 총액공사","77BAY BF 대체","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708100042,"-"]
[139,"경기","성남","신수원S/S #3 M.Tr A","17년 성남변전협력회사 총액공사","M.Tr 정밀점검, 7572,7500,6344,LA보통점검 및 7572 가스 누기보수","2017-10-31 09:00","2017-11-15 18:00","2017-10-31 09:00","2017-11-15 18:00","연속",null,null,null,201708100084,"-"]
[140,"경기","직할","화성S/S #1M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-10-10 09:00","2017-10-12 18:00","2017-10-10 09:00","2017-10-12 18:00","연속",null,null,null,201708170048,"-"]
[141,"경기","직할","화성S/S #3M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-10-13 09:00","2017-10-15 18:00","2017-10-13 09:00","2017-10-15 18:00","연속",null,null,null,201708170050,"-"]
[142,"경기","직할","화성S/S 70-71 SEC GIS","화성S/S 70-71 SEC GIS 조작시험","화성S/S 70-71 SEC GIS 조작시험","2017-10-19 10:00","2017-10-19 13:00","2017-10-19 10:00","2017-10-19 13:00","당일",null,null,null,201708170036,"-"]
[143,"경기","직할","화성S/S 75-76 SEC GIS","화성S/S 75-76 SEC GIS 조작시험","화성S/S 75-76 SEC GIS 조작시험","2017-10-19 13:00","2017-10-19 15:00","2017-10-19 13:00","2017-10-19 15:00","당일",null,null,null,201708170037,"-"]
[144,"경기","직할","화성신시흥 T/L","345kV 화성-신시흥T/L 가공송전선로 정밀점검","345kV 화성-신시흥T/L 가공송전선로 정밀점검(1~101호, 104기)","2017-10-20 09:00","2017-10-26 18:00","2017-10-20 09:00","2017-10-26 18:00","매일",null,null,null,201708160156,"-"]
[145,"경기","평택","화성평택T/P#2 T/L","154kV 포승-평택TPT/L 안전이격거리 확보공사(안전확보)","○ 공사구간 : 154kV 포승-평택TPT/L No.6~8 ○ 공사규모 : 관형주 1기설치, 사각철탑 1기철거, 전력선 0.402km교체","2017-10-14 07:00","2017-10-16 18:00","2017-10-14 07:00","2017-10-16 18:00","매일",null,null,null,201708140338,"-"]
[146,"경기","평택","화성평택T/P#1 T/L","154kV 포승-평택TPT/L 안전이격거리 확보공사(안전확보)","○ 공사구간 : 154kV 포승-평택TPT/L No.6~8 ○ 공사규모 : 관형주 1기설치, 사각철탑 1기철거, 전력선 0.402km교체","2017-10-20 07:00","2017-10-22 18:00","2017-10-20 07:00","2017-10-22 18:00","매일",null,null,null,201708140339,"-"]
[147,"강원","강릉","양양P/P #4 M.Tr 1차 CB (7372)","양양양수S/Y 345kV GIS 정밀점검공사","7372 CB 정밀점검","2017-10-16 09:00","2017-10-20 18:00","2017-10-16 09:00","2017-10-20 18:00","연속",null,null,null,201708030001,"-"]
[148,"강원","강릉","양양P/P #2 M.Tr 1차 CB (7271)","양양양수S/Y 345kV GIS 정밀점검공사","7271 CB 정밀점검","2017-10-23 09:00","2017-10-28 18:00","2017-10-23 09:00","2017-10-28 18:00","연속",null,null,null,201708030002,"-"]
[149,"강원","강릉","양양P/P #2 M.Tr 1차-#3 M.Tr 1차 CB (7200)","양양양수S/Y 345kV GIS 정밀점검공사","7200 CB 정밀점검","2017-10-23 09:00","2017-10-28 18:00","2017-10-23 09:00","2017-10-28 18:00","연속",null,null,null,201708030003,"-"]
[150,"강원","강릉","동해양양PP T/L","2016~17년 송전정비협력회사 총액공사","○ 345kV 동해-양양PP T/L No.191, 192호 불량애자교체 ○ 345kV 동해-양양PP T/L No.217, 218 사선애자청소","2017-10-30 07:00","2017-10-31 18:00","2017-10-30 07:00","2017-10-31 18:00","매일",null,null,null,201708090198,"-"]
[151,"강원","강릉","양양P/P #3 M.Tr 1차 CB (7272)","양양양수S/Y 345kV GIS 정밀점검공사","7272 CB 정밀점검","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708030004,"-"]
[152,"강원","동해","동해S/S 동해-삼척GP#1 T/L CB (7571)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-삼척GP#1 T/L GIS 보통점검(7571)","2017-10-11 09:30","2017-10-11 18:00","2017-10-11 09:30","2017-10-11 18:00","당일",null,null,null,201708080220,"-"]
[153,"강원","동해","동해S/S #2 M.Tr A","2017년 동해전력지사 변전협력회사 총액공사","1. #2M.Tr 과열개소 보수(B상 3차측 모선연결 클램프) 2. #2M.Tr 2차 GIS 초기점검(6244)","2017-10-12 09:00","2017-10-12 18:00","2017-10-12 09:00","2017-10-12 18:00","당일",null,null,null,201708160357,"-"]
[154,"강원","동해","동해S/S 75BAY TIE CB (7500)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-삼척GP#2 T/L CB 보통점검(7500)","2017-10-12 09:30","2017-10-12 18:00","2017-10-12 09:30","2017-10-12 18:00","당일",null,null,null,201708080224,"-"]
[155,"강원","동해","동해S/S 동해-삼척GP#2 T/L CB (7671)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-삼척GP#2 T/L CB 보통점검(7671)","2017-10-13 09:30","2017-10-13 18:00","2017-10-13 09:30","2017-10-13 18:00","당일",null,null,null,201708080222,"-"]
[156,"강원","동해","삼척GP #2기동 Tr CB (7572)","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP #2기동 Tr CB 하자점검(7572)","2017-10-16 09:30","2017-10-16 18:00","2017-10-16 09:30","2017-10-16 18:00","당일",null,null,null,201708090097,"-"]
[157,"강원","동해","북평T/P #2STEP-UP Tr 1차 CB (7272)","2017년 동해전력지사 변전협력회사 총액공사","1. 북평TP #2STEP-UP Tr CB 하자점검(7272)","2017-10-17 09:30","2017-10-17 18:00","2017-10-17 09:30","2017-10-17 18:00","당일",null,null,null,201708090101,"-"]
[158,"충북","직할","신충주S/S 345kV #1 BUS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-11 10:00","2017-10-16 10:00","2017-10-18 10:00","2017-10-23 10:00","연속",null,null,null,201708160372,"-"]
[159,"충북","직할","신제천신충주#2 T/L","2016~17년 직할 송전정비 협력회사 총액공사","조류착지방지장치설치(No.5~158) 및 전력선교체(No.175~176)","2017-10-12 07:30","2017-10-15 18:00","2017-10-12 07:30","2017-10-15 18:00","연속",null,null,null,201708140024,"-"]
[160,"충북","직할","신제천S/S #2 M.Tr A","#2M.Tr 3차 PT 제작사 하자 점검","M.Tr 3차측 공진현상 원인규명 및 3차 PT 제작사 공장 점검","2017-10-16 10:00","2017-11-03 18:00","취소","취소","연속",null,null,null,201708170132,"-"]
[161,"충북","직할","신충주S/S 신제천-신충주 #2 T/L CB (7471)","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-16 10:00","2017-10-17 10:00","2017-10-23 10:00","2017-10-24 10:00","연속",null,null,null,201708160373,"-"]
[162,"충북","직할","신충주S/S 신제천-신충주 #2 T/L-TIE CB (7400)","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-16 10:00","2017-10-17 10:00","2017-10-23 10:00","2017-10-24 10:00","연속",null,null,null,201708160374,"-"]
[163,"충북","직할","신충주S/S 345kV #2 BUS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-17 10:00","2017-10-22 10:00","2017-10-24 10:00","2017-10-29 10:00","연속",null,null,null,201708230083,"-"]
[164,"충북","직할","신충주S/S #3 M.Tr A","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-22 10:00","2017-10-23 10:00","2017-10-29 10:00","2017-10-30 10:00","연속",null,null,null,201708230085,"-"]
[165,"충북","직할","신충주S/S 신제천-신충주#2 T/L GIS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-22 10:00","2017-10-23 10:00","2017-10-29 10:00","2017-10-30 10:00","연속",null,null,null,201708230084,"-"]
[166,"충북","직할","신충주S/S 신제천-신충주#2T/L-TIE GIS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-10-22 10:00","2017-10-23 10:00","2017-10-29 10:00","2017-10-30 10:00","연속",null,null,null,201708230086,"-"]
[167,"충북","청주","세종청원#2 T/L","2017년 청주전력 변전협력회사 총액공사","세종청원#2T/L 피뢰기 누설전류 불량조치","2017-10-10 09:30","2017-10-10 18:00","2017-10-10 09:30","2017-10-10 18:00","당일",null,null,null,201708170080,"-"]
[168,"충북","청주","청원S/S #3 M.Tr A","청원S/S 옥외분전반 대체작업시 안전이격거리 확보","청원S/S 옥외분전반 대체작업시 안전이격거리 확보","2017-10-11 13:00","2017-10-11 16:00","2017-10-11 13:00","2017-10-11 16:00","당일",null,null,null,201708140316,"-"]
[169,"충북","청주","청원S/S #4 M.Tr A","17년 청주전력지사 170kV GIS 정밀점검공사","청원S/S #4 M.Tr 1차 GIS CB 정밀점검","2017-10-12 09:30","2017-10-13 18:00","2017-10-12 09:30","2017-10-13 18:00","연속",null,null,null,201708140071,"-"]
[170,"충북","청주","신옥천세종#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","불량애자교체 28-1호 (1개) 항공구설치 1~8호 (4개)","2017-10-15 08:00","2017-10-21 19:00","2017-10-23 08:00","2017-10-29 19:00","연속",null,null,null,201708140314,"-"]
[171,"충북","청주","신옥천S/S 345kV #1 BUS","신옥천S/S 345kV 용량부족차단기 대체공사","1.부분방전 이상 개소 내부점검 2.리미트 SW 회로보완","2017-10-15 09:00","2017-10-21 18:00","2017-10-15 09:00","2017-10-21 18:00","연속",null,null,null,201708180068,"-"]
[172,"충북","청주","신옥천세종#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","불량애자교체 1, 2, 27호 (3개) 항공구설치 1~8호 (6개)","2017-10-22 08:00","2017-10-22 19:00","2017-10-22 08:00","2017-10-22 19:00","당일",null,null,null,201708140312,"-"]
[173,"충북","청주","청원S/S #1 M.Tr A","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2017-10-23 09:00","2017-12-31 18:00","2017-10-30 09:00","2018-01-07 18:00","연속",null,null,null,201708170139,"-"]
[174,"충북","청주","청원S/S 청원-신진천#2T/L-#1 M.Tr 1차 CB (7200)","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2017-10-23 09:00","2017-12-31 18:00","2017-10-30 09:00","2018-01-07 18:00","연속",null,null,null,201708170145,"-"]
[175,"충북","청주","신옥천북경남 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","불량애자교체 325호 (1개) 항공구설치 333~334호 (2개)","2017-10-24 08:00","2017-10-24 12:00","2017-10-24 08:00","2017-10-24 12:00","당일",null,null,null,201708140328,"-"]
[176,"충북","청주","신옥천무주양수 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공구설치 8~9, 333~334호 (4개)","2017-10-24 13:00","2017-10-25 19:00","2017-10-24 13:00","2017-10-25 19:00","당일",null,null,null,201708170120,"-"]
[177,"충북","청주","신옥천S/S #1 M.Tr A","2017년 청주전력 변전협력회사 총액공사","#1M.Tr 2차 CB 공기조작부 분해 점검","2017-10-26 09:30","2017-10-26 18:00","2017-10-26 09:30","2017-10-26 18:00","당일",null,null,null,201708140154,"-"]
[178,"충북","청주","신옥천S/S #2 M.Tr A","2017년 청주전력 변전협력회사 총액공사","#2M.Tr 2차 CB 공기조작부 분해 점검","2017-10-27 09:30","2017-10-27 18:00","2017-10-27 09:30","2017-10-27 18:00","당일",null,null,null,201708140155,"-"]
[179,"대전충남","대전","신옥천신계룡 T/L","신계룡S/S 신옥천-신계룡T/L GIS 보통점검","신계룡S/S 신옥천-신계룡T/L GIS 보통점검 등 병행작업","2017-10-14 09:00","2017-10-14 18:00","2017-10-14 09:00","2017-10-14 18:00","당일",null,null,null,201708080130,"-"]
[180,"대전충남","서산","당진T/P #71 Tie-Tr A","'17년 변전협력회사 총액공사","당진화력 345kV #71Tie-Tr 보통점검","2017-10-10 09:00","2017-10-13 18:00","2017-10-16 09:00","2017-10-18 18:00","연속",null,null,null,201708140092,"-"]
[181,"대전충남","서산","신당진S/S 신당진연락#1T/L CB (7471)","'17년 서산P/O 345kV GIS 정밀점검공사","신당진S/S 345kV 신당진-연락#1T/L GIS(7471) 정밀점검","2017-10-10 09:00","2017-10-13 18:00","2017-10-23 09:00","2017-10-27 18:00","연속",null,null,null,201708140091,"-"]
[182,"대전충남","서산","당진T/P #72 Tie-Tr A","'17년 변전협력회사 총액공사","당진화력 345kV #72Tie-Tr 보통점검","2017-10-16 09:00","2017-10-19 18:00","2017-10-10 09:00","2017-10-13 18:00","연속",null,null,null,201708140095,"-"]
[183,"대전충남","서산","신당진S/S 신당진연락#2T/L CB (7771)","'17년 서산P/O 345kV GIS 정밀점검 공사","신당진S/S 345kV 신당진-연락 #2T/L GIS(7771) 정밀점검","2017-10-16 09:00","2017-10-19 18:00","2017-10-16 09:00","2017-10-19 18:00","당일",null,null,null,201707070354,"-"]
[184,"대전충남","서산","신서산S/S 신서산-태안TP#2T/L CB (7572)","'17년 변전협력회사 총액공사","신서산S/S 345kV 신서산-태안화력#2T/L GIS(7572) 보통점검","2017-10-20 09:00","2017-10-20 18:00","2017-10-20 09:00","2017-10-20 18:00","당일",null,null,null,201708230041,"-"]
[185,"대전충남","서산","신서산S/S #3M.Tr2차-신서산태안TP#1T/L CB (7600)","'17년 변전협력회사 총액공사","신서산S/S 345kV #3M.Tr 2차-신서산태안화력#1T/L GIS(7600) 보통점검","2017-10-23 09:00","2017-10-23 18:00","2017-10-23 09:00","2017-10-23 18:00","당일",null,null,null,201708230035,"-"]
[186,"대전충남","서산","신서산S/S #4 Sh.R-신서산신당진#2T/L CB (7700)","'17년 변전협력회사 총액공사","신서산S/S 345kV #4Sh.R-신서산신당진#2T/L GIS(7700) 보통점검","2017-10-24 09:00","2017-10-24 18:00","2017-10-24 09:00","2017-10-24 18:00","당일",null,null,null,201708230036,"-"]
[187,"대전충남","서산","신서산S/S 345kV #3 Sh.R","'17년 변전협력회사 총액공사","신서산S/S 345kV #3Sh.R GIS(7571), #3Sh.R CB(7579) 보통점검","2017-10-25 09:00","2017-10-26 18:00","2017-10-25 09:00","2017-10-26 18:00","매일",null,null,null,201708140107,"-"]
[188,"대전충남","서산","신서산S/S TIE-신서산아산#2T/L CB (7A00)","'17년 변전협력회사 총액공사","신서산S/S 345kV TIE-신서산아산#2T/L GIS(7A00) 보통점검","2017-10-25 09:00","2017-10-25 18:00","2017-10-25 09:00","2017-10-25 18:00","당일",null,null,null,201708230042,"-"]
[189,"대전충남","서산","태안T/P 개폐소-태안TP#2-9호기 1차 CB (7900)","'17년 변전협력회사 총액공사","태안화력 345kV 개폐소태안화력#2T/L-9호기 1차 GIS(7900) 하자점검","2017-10-26 09:00","2017-10-26 18:00","2017-10-26 09:00","2017-10-26 18:00","당일",null,null,null,201708140111,"-"]
[190,"대전충남","서산","태안T/P 9호기 1차 CB (7972)","'17년 변전협력회사 총액공사","태안화력 345kV 9호기 1차 GIS(7972) 하자점검","2017-10-27 09:00","2017-10-27 18:00","2017-10-27 09:00","2017-10-27 18:00","당일",null,null,null,201708140113,"-"]
[191,"대전충남","서산","신서산S/S 신서산-아산#2T/L CB (7A72)","'17년 변전협력회사 총액공사","신서산S/S 345kV 신서산-아산#2T/L GIS(7A72) 보통점검","2017-10-30 09:00","2017-10-30 18:00","2017-10-30 09:00","2017-10-30 18:00","당일",null,null,null,201708230037,"-"]
[192,"대전충남","서산","태안T/P 345kV #70 BUS","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","1.기존 40KA, 4000A CB 4대 철거(7300, 7372, 70710, 75760) 2 대체 63KA, 6300A CB 4대 철거(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 : 7300, 7372 GIS 대체계속(#70모선 73bay 구간 및 관련DS 대체)","2017-10-30 10:00","2017-12-06 14:00","2017-10-30 10:00","2017-12-06 14:00","연속",null,null,null,201708110197,"-"]
[193,"대전충남","서산","신서산S/S 신서산-태안TP#1T/L CB (7672)","'17년 변전협력회사 총액공사","신서산S/S 345kV 신서산-태안화력#1T/L GIS(7672) 보통점검","2017-10-31 09:00","2017-10-31 18:00","2017-10-31 09:00","2017-10-31 18:00","당일",null,null,null,201708230040,"-"]
[194,"대전충남","아산","청양신온양#2 T/L","[송전]345kV 청양-신온양T/L 안전이격확보공사","ㅇ 전선교체 : 127~130호가(4가닥) ㅇ 연,긴선작업 : 113~120, 127~130호간 ㅇ OPGW 이설 : 전자제어파트 시행 ㅇ 기타 부대공사","2017-10-07 08:00","2017-10-13 18:00","2017-10-07 08:00","2017-10-13 18:00","연속",null,null,null,201708100015,"-"]
[195,"대전충남","아산","청양신온양#2 T/L","[송전]345kV 청양-신온양T/L 지장송전선로 이설공사","ㅇ 2기설치, 2기 철거","2017-10-07 08:00","2017-10-13 18:00","취소","취소","연속",null,null,null,201708100293,"-"]
[196,"대전충남","아산","아산S/S 아산-보령화력#2T/L CB (7172)","아산S/S 345kV 7172 GIS 정밀점검","○ 345kV 7172 GIS 정밀점검","2017-10-11 09:00","2017-10-13 18:00","2017-10-11 09:00","2017-10-13 18:00","연속",null,null,null,201708100258,"-"]
[197,"대전충남","아산","아산S/S 아산-화성#2T/L CB (7271)","아산S/S 345kV 7271 GIS 정밀점검","○ 345kV 7271 GIS 정밀점검","2017-10-16 09:00","2017-10-18 18:00","2017-10-16 09:00","2017-10-18 18:00","연속",null,null,null,201708100265,"-"]
[198,"대전충남","아산","아산S/S 아산-화성#1T/L-TIE CB (7400)","아산S/S 345kV 7400 GIS 정밀점검","○ 345kV 7400 GIS 정밀점검","2017-10-19 09:00","2017-10-21 18:00","2017-10-19 09:00","2017-10-21 18:00","연속",null,null,null,201708100266,"-"]
[199,"대전충남","아산","아산S/S TIE-#2 M.Tr 1차 CB (7500)","아산S/S 345kV 7500 GIS 정밀점검","○ 345kV 7500 GIS 정밀점검","2017-10-23 09:00","2017-10-25 18:00","2017-10-23 09:00","2017-10-25 18:00","연속",null,null,null,201708100269,"-"]
[200,"대전충남","아산","아산S/S #1 M.Tr A ","아산S/S 345kV #1M.Tr 부싱 긴급점검"," ○ 345kV #1M.Tr 부싱 긴급점검 - 부싱 절연열화 측정 - 부싱 절연유 채유 ","2017-10-10 09:00","2017-10-10 18:00","2017-10-10 09:00","2017-10-10 18:00","당일",null,null,null,201708300010,"-"]
[201,"대전충남","아산","아산S/S TIE-#4 M.Tr 1차 CB (7800)","아산S/S 345kV 7800 GIS 정밀점검","○ 345kV 7800 GIS 정밀점검","2017-10-30 09:00","2017-11-01 18:00","2017-10-30 09:00","2017-11-01 18:00","연속",null,null,null,201708100275,"-"]
[202,"대전충남","청양","보령T/P #6 M.Tr 1차 CB (7671)","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2017-10-09 09:00","2017-11-22 18:00","취소","취소","연속",null,null,null,201708070143,"-"]
[203,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2017-10-09 09:00","2017-10-09 18:00","취소","취소","당일",null,null,null,201708070145,"-"]
[204,"대전충남","청양","청양보령화력#1 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2017-10-09 09:00","2017-11-22 18:00","취소","취소","연속",null,null,null,201708070140,"-"]
[205,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2017-10-10 09:00","2017-10-10 18:00","취소","취소","당일",null,null,null,201708070146,"-"]
[206,"대전충남","청양","보령C/C #4 M.Tr 1차 CB (7472)","345kV 차단기 부동작 예방조작시험","345kV 차단기 부동작 예방조작시험","2017-10-11 09:00","2017-10-11 13:00","2017-10-11 09:00","2017-10-11 13:00","당일",null,null,null,201708100001,"-"]
[207,"대전충남","청양","보령C/C #4 M.Tr 1차-신보령연락T/L CB (7400)","345kV 차단기 부동작 예방조작시험","345kV 차단기 부동작 예방조작시험","2017-10-11 14:00","2017-10-11 18:00","2017-10-11 14:00","2017-10-11 18:00","당일",null,null,null,201708100002,"-"]
[208,"대전충남","청양","보령C/C 보령연락#1T/L CB (7171)","345kV 차단기 부동작 예방조작시험","345kV 차단기 부동작 예방조작시험","2017-10-12 09:00","2017-10-12 13:00","2017-10-12 09:00","2017-10-12 13:00","당일",null,null,null,201708100003,"-"]
[209,"대전충남","청양","보령T/P 보령연락#1T/L CB (7271)","345kV 차단기 부동작 예방조작시험","345kV 차단기 부동작 예방조작시험","2017-10-12 14:00","2017-10-12 18:00","2017-10-12 14:00","2017-10-12 18:00","당일",null,null,null,201708100004,"-"]
[210,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708070147,"-"]
[211,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2017-10-17 09:00","2017-10-17 18:00","2017-10-17 09:00","2017-10-17 18:00","당일",null,null,null,201708070148,"-"]
[212,"대전충남","청양","보령C/C 청양보령복합T/L CB (7371)","보령C/C 362kV GIS 정밀점검 공사","-7371, 7200, 7272 CB 정밀점검","2017-10-18 09:00","2017-10-20 18:00","2017-10-18 09:00","2017-10-20 18:00","연속",null,null,null,201708070131,"-"]
[213,"대전충남","청양","보령C/C #3 M.Tr 1차 CB (7372)","보령C/C 73Bay B/F 보호반 교체","B/F 보호반 교체","2017-10-18 09:30","2017-10-23 18:00","2017-10-18 09:30","2017-10-23 18:00","연속",null,null,null,201708030072,"-"]
[214,"대전충남","청양","청양보령복합 T/L","보령C/C 73Bay B/F 보호반 교체","B/F 보호반 교체","2017-10-18 09:30","2017-10-23 18:00","2017-10-18 09:30","2017-10-23 18:00","연속",null,null,null,201708030071,"-"]
[215,"대전충남","청양","보령C/C 보령연락#2T/L-#2 M.Tr 1차 CB (7200)","보령C/C 362kV GIS 정밀점검 공사","-7371, 7200, 7272 CB 정밀점검","2017-10-23 09:00","2017-10-25 18:00","2017-10-23 09:00","2017-10-25 18:00","연속",null,null,null,201708070132,"-"]
[216,"대전충남","청양","보령C/C #2 M.Tr 1차 CB (7272)","보령C/C 362kV GIS 정밀점검 공사","-7371, 7200, 7272 CB 정밀점검","2017-10-26 09:00","2017-10-28 18:00","2017-10-26 09:00","2017-10-28 18:00","연속",null,null,null,201708070133,"-"]
[217,"전북","군산","군산신김제#1 T/L","군산-신김제#1T/L","차단기 조작시험","2017-10-10 09:00","2017-10-10 14:00","2017-10-23 09:00","2017-10-23 11:00","당일",null,null,null,201708160284,"-"]
[218,"전북","군산","군산S/S #1 M.Tr A","군산S/S #1M.Tr","1,2차 차단기 조작시험","2017-10-10 14:00","2017-10-10 18:00","2017-10-23 11:00","2017-10-23 14:00","당일",null,null,null,201708160280,"-"]
[219,"전북","군산","군산신김제#2 T/L","군산-신김제#2T/L","차단기 조작시험","2017-10-11 09:00","2017-10-11 14:00","취소","취소","당일",null,null,null,201708160287,"-"]
[220,"전북","군산","군산S/S #3 M.Tr A","군산S/S #3M.Tr","1,2차 차단기 조작시험","2017-10-11 14:00","2017-10-11 18:00","2017-10-23 16:00","2017-10-23 18:00","당일",null,null,null,201708160295,"-"]
[221,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2M.Tr","1,2차 차단기 조작시험","2017-10-12 11:00","2017-10-12 18:00","2017-10-23 14:00","2017-10-23 16:00","당일",null,null,null,201708160290,"-"]
[222,"전북","군산","군산신김제#2 T/L","군산신김제#2 T/L OPGW용 항공장애표시구 설치","군산신김제#2 T/L OPGW용 항공장애표시구 설치 : 154개","2017-10-16 08:00","2017-10-25 18:00","2017-10-24 08:00","2017-11-02 18:00","매일",null,null,null,201708220009,"-"]
[223,"전북","군산","군산새만금#1 T/L","군산-새만금#1T/L","차단기 조작시험","2017-10-16 09:00","2017-10-16 18:00","2017-10-25 09:00","2017-10-25 18:00","당일",null,null,null,201708160304,"-"]
[224,"전북","군산","새만금S/S #2 M.Tr A","새만금S/S #2M.Tr","1,2차 차단기 조작시험","2017-10-16 09:00","2017-10-16 18:00","2017-10-25 09:00","2017-10-25 18:00","당일",null,null,null,201708160299,"-"]
[225,"전북","군산","군산새만금#2 T/L","군산-새만금#2T/L","차단기 조작시험","2017-10-17 09:00","2017-10-17 18:00","2017-10-26 09:00","2017-10-26 18:00","당일",null,null,null,201708160303,"-"]
[226,"전북","군산","새만금S/S #3 M.Tr A","새만금S/S #3M.Tr","1,2차 차단기 조작시험","2017-10-17 09:00","2017-10-17 18:00","2017-10-26 09:00","2017-10-26 18:00","당일",null,null,null,201708160300,"-"]
[227,"전북","직할","무주P/P #2M.Tr 1차 CB (7272)","무주P/P #2M.Tr 1차 CB","1. 무주양수 345kV #2M.Tr 차단기 점검","2017-10-12 09:00","2017-10-12 18:00","2017-10-12 09:00","2017-10-12 18:00","당일",null,null,null,201708160105,"-"]
[228,"전북","직할","무주P/P 72BAY BUS-TIE CB (7200)","무주P/P 72BAY BUS-TIE CB","1. 무주양수 345kV 72Bay BUS-TIE 차단기 점검","2017-10-13 09:00","2017-10-13 18:00","2017-10-13 09:00","2017-10-13 18:00","당일",null,null,null,201708160099,"-"]
[229,"전북","직할","북경남무주양수 T/L","북경남무주양수 T/L","1. 무주양수 345kV 북경남-무주양수T/L 차단기 점검","2017-10-13 09:00","2017-10-13 18:00","2017-10-13 09:00","2017-10-13 18:00","당일",null,null,null,201708160098,"-"]
[230,"전북","직할","무주P/P 71BAY BUS-TIE CB (7100)","무주P/P 71BAY BUS-TIE CB","1. 무주양수 345kV 71Bay BUS-TIE 차단기 점검","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708160102,"-"]
[231,"전북","직할","신옥천무주양수 T/L","신옥천무주양수 T/L","1. 무주양수 345kV 신옥천-무주양수T/L 차단기 점검","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708160101,"-"]
[232,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.108~116)","전력선 교체 : 7.140C-㎞ (ACSR 480㎟×4B) 가공지선 교체 : 3.570㎞ (ACSR 120㎟×S)","2017-10-23 07:00","2017-10-30 18:00","2017-10-23 07:00","2017-10-30 18:00","연속",null,null,null,201708170147,"-"]
[233,"전북","직할","북경남무주양수 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공구설치 8~9호 (2개)","2017-10-25 08:00","2017-10-25 19:00","2017-10-25 08:00","2017-10-25 19:00","당일",null,null,null,201708170121,"-"]
[234,"전북","직할","신남원S/S #1 M.Tr A","345kV 신남원S/S 154kV #61D.Tr 증설공사","154kV 주변압기(15/20MVA×3)×1Bank 설치 170kV GIS(1250A, 50kA)×1CCT증설 25.8kV SIS × 6CCT설치","2017-10-26 10:00","2017-10-28 18:00","2017-10-26 10:00","2017-10-28 18:00","연속",null,null,null,201708170094,"-"]
[235,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.108~116)","전력선 교체 : 7.140C-㎞ (ACSR 480㎟×4B) 가공지선 교체 : 3.570㎞ (ACSR 120㎟×S)","2017-10-31 07:00","2017-11-07 18:00","2017-10-31 07:00","2017-11-07 18:00","연속",null,null,null,201708170149,"-"]
[236,"전북","직할","신남원한빛NP#1 T/L","345kV 신남원-한빛NP#1T/L CVT 대체공사","장기사용 기타설비 대체공사(CVT 교체공사)","2017-10-11 09:30","2017-10-11 18:00","2017-10-11 09:30","2017-10-11 18:00","당일",null,null,null,201708170094,"-"]
[237,"전북","직할","신남원한빛NP#2 T/L","345kV 신남원-한빛NP#1T/L CVT 대체공사","장기사용 기타설비 대체공사(CVT 교체공사)","2017-10-12 09:30","2017-10-12 18:00","2017-10-12 09:30","2017-10-12 18:00","당일",null,null,null,201708250102,"-"]
[238,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr (96P Trip → 경보 회로변경)","문서번호 광전본(변전)-5632 주변압기 96P 운전형태 변경 알림 - 신강진S/S 345kV #1M.Tr 96P Trip → 경보 회로변경","2017-10-16 09:00","2017-10-16 18:00","2017-10-25 09:00","2017-10-25 18:00","당일",null,null,null,201708070047,"-"]
[239,"광주전남","광주","신화순S/S #2 M.Tr A","2017년 광주전력지사 170kV GIS 정밀점검공사","#2M.Tr 2차 GIS 정밀점검","2017-10-10 09:00","2017-10-11 18:00","2017-10-30 09:00","2017-10-31 18:00","당일",null,null,null,201708250101,"-"]
[240,"광주전남","광주","신화순신강진#2 T/L","2017년 변전협력회사 총액공사","신화순신강진#2 T/L LA, PT교체","2017-10-12 09:00","2017-10-12 18:00","2017-10-26 09:00","2017-10-26 18:00","당일",null,null,null,201708220211,"-"]
[241,"광주전남","광주","신화순신강진#1 T/L","신화순S/S 신화순-신강진#1T/L LA,PT 교체공사","신화순S/S 신화순-신강진#1T/L LA,PT 교체공사","2017-10-13 09:00","2017-10-13 18:00","2017-10-27 09:00","2017-10-27 18:00","당일",null,null,null,201708010064,"-"]
[242,"광주전남","광주","신화순S/S #1 M.Tr A","2017년 변전협력회사 총액공사.","신화순S/S #1M.Tr LA교체","2017-10-17 09:00","2017-10-18 18:00","2017-10-23 09:00","2017-10-24 18:00","당일",null,null,null,201708230124,"-"]
[243,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S #4 M.Tr(345kV M.Tr 정밀점검)","(345kV M.Tr 및 OLTC 정밀점검","2017-10-23 09:00","2017-10-30 18:00","2017-10-25 09:00","2017-10-25 18:00","연속",null,null,null,201708040022,"-"]
[244,"광주전남","목포","신광주한빛NP#1 T/L","345kV 신광주-한빛NPT/L 전선접속개소해소공사","전선교체 : No.112~118호","2017-10-16 07:00","2017-10-20 18:00","2017-10-16 07:00","2017-10-20 18:00","연속",null,null,null,201708160142,"-"]
[245,"광주전남","목포","신광주한빛NP#2 T/L","345kV 신광주-한빛NPT/L 전선접속개소해소공사","전선교체 : No.112~118","2017-10-21 07:00","2017-10-25 18:00","2017-10-21 07:00","2017-10-25 18:00","연속",null,null,null,201708160144,"-"]
[246,"광주전남","순천","광양S/S 345kV #75 BUS","광양S/S 345kV #75BUS GIS 보강공사","- 모선내부정밀점검 및 Bellows측 Moving Cond 교체 - 모선Level 조정작업(Stud Bolt 및 고정Plate 교체) - 기타 부대공사 1식","2017-10-23 09:00","2017-10-29 18:00","2017-10-23 09:00","2017-10-29 18:00","연속",null,null,null,201707180011,"-"]
[247,"광주전남","순천","광양율촌CC T/L","광양S/S 345kV #75BUS GIS 보강공사","- 모선 보강공사후 무부하 가압","2017-10-28 18:00","2017-10-29 18:00","2017-10-28 18:00","2017-10-29 18:00","연속",null,null,null,201708170126,"-"]
[248,"대구","경산","신경산S/S #4 M.Tr A","신경산S/S #4M.Tr 휴전","76BAY B/F PNL 대체공사","2017-10-16 09:00","2017-10-20 18:00","2017-10-16 09:00","2017-10-20 18:00","연속",null,null,null,201708040247,"-"]
[249,"대구","달성","대구S/S #2 M.Tr A","대구S/S 주변압기용 계전기 성능개선","대구S/S 주변압기용 계전기 성능개선","2017-10-11 10:00","2017-10-11 13:00","2017-10-11 10:00","2017-10-11 13:00","당일",null,null,null,201708170127,"-"]
[250,"대구","칠곡","북대구S/S #1 M.Tr A","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사 (7372, 7300 GIS)","2017-10-01 09:30","2017-10-10 18:00","취소","취소","연속",null,null,null,201708080129,"-"]
[251,"대구","칠곡","북대구S/S #3 M.Tr A","345kV 북대구S/S #1Sh.R 설치공사","345kV Sh.R(100MVar) 설치","2017-10-11 09:00","2017-11-01 18:00","2017-10-11 09:00","2017-11-01 18:00","연속",null,null,null,201707170170,"-"]
[252,"대구","칠곡","북대구S/S 345kV #1 BUS","345kV 북대구S/S #1Sh.R 설치공사","345kV Sh.R(100MVar) 설치","2017-10-11 09:00","2017-10-20 18:00","2017-10-11 09:00","2017-10-20 18:00","연속",null,null,null,201707170168,"-"]
[253,"대구","칠곡","북대구서대구#2 T/L","북대구-서대구#2T/L 휴전","서대구S/S 북대구-서대구#2T/L CVT 초기점검","2017-10-13 09:30","2017-10-13 14:00","2017-10-13 09:30","2017-10-13 14:00","당일",null,null,null,201708080132,"-"]
[254,"대구","칠곡","북대구서대구#1 T/L","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사(7371 GIS)","2017-10-16 09:30","2017-10-20 18:00","2017-10-19 09:00","2017-10-20 18:00","연속",null,null,null,201708080141,"-"]
[255,"대구","칠곡","북대구S/S 345kV #1 BUS","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사 (7351, 7451 DS부)","2017-10-23 09:30","2017-10-24 18:00","취소","취소","연속",null,null,null,201708080156,"-"]
[256,"대구","칠곡","북대구S/S 345kV #2 BUS","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사 (7352, 7452 DS부)","2017-10-25 09:30","2017-10-26 18:00","취소","취소","연속",null,null,null,201708080159,"-"]
[257,"대구","칠곡","북대구S/S 345kV #1 BUS","345kV 북대구S/S #1Sh.R 설치공사","345kV Sh.R(100MVar) 설치-무부하 가압","2017-10-31 09:00","2017-11-01 18:00","2017-10-31 09:00","2017-11-01 18:00","연속",null,null,null,201707170169,"-"]
[258,"대구","칠곡","북대구서대구#1 T/L","345kV 북대구S/S #1Sh.R 설치공사","345kV Sh.R(100MVar) 설치- Sh.R 무부하 가압","2017-10-31 09:00","2017-11-01 18:00","2017-10-31 09:00","2017-11-01 18:00","연속",null,null,null,201707170173,"-"]
[259,"대구","포항","신영일S/S #3 M.Tr A","신영일S/S #3 M.Tr 보통점검","신영일S/S #3 M.Tr 보통점검","2017-10-10 09:00","2017-10-11 18:00","2017-10-21 09:00","2017-10-22 18:00","연속",null,null,null,201708030027,"-"]
[260,"대구","포항","신영일S/S #4 M.Tr A","신영일S/S #4 M.Tr 보통점검","신영일S/S #4 M.Tr 보통점검","2017-10-12 09:00","2017-10-13 18:00","2017-10-28 09:00","2017-10-29 18:00","연속",null,null,null,201708030028,"-"]
[261,"대구","포항","신영일안동CC T/L","신영일안동CC T/L 7671,7600CB 보통점검","신영일안동CC T/L 7671,7600CB 보통점검","2017-10-16 09:00","2017-10-16 18:00","2017-10-16 09:00","2017-10-16 18:00","당일",null,null,null,201708030032,"-"]
[262,"대구","포항","신포항신월성NP#4 T/L","신월성S/Y 신포항신월성NP#4 T/L 애자코팅","신월성S/Y 신포항신월성NP#4 T/L 애자코팅","2017-10-19 09:00","2017-10-24 18:00","2017-10-19 09:00","2017-10-24 18:00","연속",null,null,null,201708030034,"-"]
[263,"대구","포항","신월성N/P #2M.Tr 2차 CB (7172)","신월성N/P #2M.Tr 2차 CB 7172CB 보통점검","신월성N/P #2M.Tr 2차 CB 7172CB 보통점검","2017-10-20 09:00","2017-10-20 18:00","2017-10-20 09:00","2017-10-20 18:00","당일",null,null,null,201708030035,"-"]
[264,"대구","포항","신포항신영일 T/L","신포항신영일 T/L 7700CB 보통점검","신포항신영일 T/L 7700CB 보통점검","2017-10-23 09:00","2017-10-23 18:00","2017-10-23 09:00","2017-10-23 18:00","당일",null,null,null,201708030033,"-"]
[265,"경북","영주","(신)신영주S/S 345kV #1 BUS","345kV 신영주S/S STATCOM 설치공사","345kV 신영주S/S STATCOM 설치공사","2017-10-10 10:00","2017-10-14 18:00","2017-10-10 10:00","2017-10-14 18:00","연속",null,null,null,201708110030,"○"]
[266,"경북","영주","신제천신영주#1 T/L","345kV 신영주S/S STATCOM 설치공사","345kV 신영주S/S STATCOM 설치공사","2017-10-10 10:00","2017-10-20 18:00","2017-10-10 10:00","2017-10-20 18:00","연속",null,null,null,201708110029,"○"]
[267,"경북","영주","신한울3_1한울NP#3#1 T/L","362kV LS제 GIS 차단기 재발방지 대책","362kV LS제 GIS 차단기 페퍼실린더 강도보강","2017-10-11 09:00","2017-10-17 18:00","취소","취소","연속",null,null,null,201708230128,"-"]
[268,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","□ 공사구간 : 345kV 신영주-한울NP2T/L 43∼75호 □ 공사내용 : 전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-10-12 07:00","2017-10-26 18:00","취소","취소","연속",null,null,null,201708070129,"○"]
[269,"경북","영주","(신)신영주S/S 345kV #2 BUS","345kV 신영주S/S STATCOM 설치공사","345kV 신영주S/S STATCOM 설치공사","2017-10-16 10:00","2017-10-20 18:00","2017-10-16 10:00","2017-10-20 18:00","연속",null,null,null,201708110031,"○"]
[270,"경북","영주","신한울3_2한울NP#3#2 T/L","362kV LS제 GIS 차단기 재발방지 대책","362kV LS제 GIS 차단기 페퍼실린더 강도보강","2017-10-18 09:00","2017-10-24 18:00","취소","취소","연속",null,null,null,201708230129,"-"]
[271,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선 교체공사","전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-10-27 07:00","2017-11-10 18:00","취소","취소","연속",null,null,null,201708070130,"○"]
[272,"경북","직할","안동복합S/Y 신영일-안동CC T/L CB (7371)","본사지시 LS제 362kV GIS 차단기 교체공사","본사지시 LS제 362kV GIS 차단기 교체공사(7371)","2017-10-30 09:00","2017-11-05 18:00","2017-10-30 09:00","2017-11-05 18:00","연속",null,null,null,201708310043,"○"]
[273,"경북","직할","안동복합S/Y 신영주-안동CC T/L CB (7271)","본사지시 LS제 362kV GIS 차단기 교체공사","본사지시 LS제 362kV GIS 차단기 교체공사(7271)","2017-10-23 09:00","2017-10-29 18:00","2017-10-23 09:00","2017-10-29 18:00","연속",null,null,null,201708310041,"○"]
[274,"경북","직할","안동복합S/Y 신영주-안동CCT/L-TIE CB (7200)","본사지시 LS제 362kV GIS 차단기 교체공사","본사지시 LS제 362kV GIS 차단기 교체공사(7200)","2017-10-16 09:00","2017-10-22 18:00","취소","취소","연속",null,null,null,201708310037,"○"]
[275,"부산울산","북부산","북부산S/S #4Sh.R 1차 CB(신) ((신)7972)","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 인출변경(#70BUS → 신 79BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-10-26 08:00","2017-10-31 18:00","2017-10-26 08:00","2017-10-31 18:00","연속",null,null,null,201707070090,"-"]
[276,"부산울산","북부산","북부산S/S 서부산#2T/L-#4Sh.R 1차 CB(신) ((신)7900)","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 인출변경(#70BUS → 신 79BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-10-26 08:00","2017-10-31 18:00","2017-10-26 08:00","2017-10-31 18:00","연속",null,null,null,201707070091,"-"]
[277,"부산울산","북부산","서부산북부산#2 T/L","345kV 북부산S/S 차단기용량대체공사","#4Sh.R 이설 시험가압 선로","2017-10-28 10:00","2017-10-29 10:00","2017-10-28 10:00","2017-10-29 10:00","연속",null,null,null,201708010087,"-"]
[278,"부산울산","서부산","서부산S/S #2 M.Tr A","서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사","-서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사 및 345kV #1Sh.R GIS(7177) 설치, #2S.Tr 대체, #2M.Tr 3차(4284) 보통점검 병행","2017-10-10 10:00","2017-10-25 18:00","2017-10-10 10:00","2017-10-25 18:00","연속",null,null,null,201707310071,"-"]
[279,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사","서부산S/S 345kV #71BAY B/F(차단실패) PNL 교체 공사","2017-10-10 10:00","2017-10-25 18:00","2017-10-10 10:00","2017-10-25 18:00","연속",null,null,null,201707310072,"-"]
[280,"부산울산","서부산","서부산S/S #1,2 G/T CB (7471)","서부산S/S #1,2G/T CB(7471) 보통점검","서부산S/S #1,2G/T CB(7471) 보통점검","2017-10-20 10:00","2017-10-20 18:00","2017-10-20 10:00","2017-10-20 18:00","당일",null,null,null,201707310074,"-"]
[281,"부산울산","서부산","서부산S/S 345kV #3 Sh.R","서부산S/S 345kV #3Sh.R 열교환기 보수 및 하자점검","서부산S/S 345kV #3Sh.R 열교환기 보수 및 하자점검","2017-10-30 10:00","2017-11-05 18:00","2017-10-30 10:00","2017-11-05 18:00","연속",null,null,null,201707310075,"-"]
[282,"부산울산","울산","울산C/C #2 M.Tr A","2017년도 관내 노후배전반 대체공사","1.울산C/C 345kV #2M.Tr 보호반 대체 2.울산C/C 345kV 7861 가스누기 보수","2017-10-07 09:00","2017-10-10 18:00","2017-10-07 09:00","2017-10-10 18:00","연속",null,null,null,201708110329,"-"]
[283,"부산울산","울산","신온산울산TP T/L","울산C/C 345kV 7861DS 가스누기조치 공사","시험가압(울산C/C 7861가스누기 조치작업관련)","2017-10-09 17:00","2017-10-09 18:00","2017-10-09 17:00","2017-10-09 18:00","당일",null,null,null,201708210244,"-"]
[284,"부산울산","울산","울산C/C 345kV #1 BUS","울산C/C 345kV 7861DS 가스누기조치 공사","시험가압(울산C/C 7861가스누기 조치작업관련)","2017-10-09 17:00","2017-10-09 18:00","2017-10-09 17:00","2017-10-09 18:00","당일",null,null,null,201708210243,"-"]
[285,"부산울산","울산","울산C/C #1 M.Tr A","2017년도 관내 노후배전반 대체공사","울산C/C 345kV #1M.Tr 보호반 대체","2017-10-11 09:00","2017-10-13 18:00","2017-10-11 09:00","2017-10-13 18:00","연속",null,null,null,201708110330,"-"]
[286,"부산울산","울산","신울산S/S #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 345V #2M.Tr 2,3차 GCB 보통점검 및 #2S.Tr 보통점검","2017-10-12 09:00","2017-10-12 18:00","취소","취소","당일",null,null,null,201708110384,"-"]
[287,"부산울산","울산","신울산S/S #4 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 345kV #4M.Tr 2차 GCB 보통점검","2017-10-13 09:00","2017-10-13 18:00","취소","취소","당일",null,null,null,201708110369,"-"]
[288,"부산울산","울산","북부산울산TP T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","노후애자금구류 교체 및 송전용 피뢰기 설치","2017-10-14 08:00","2017-10-27 18:00","2017-10-19 08:00","2017-11-01 18:00","연속",null,null,null,201708070178,"-"]
[289,"부산울산","울산","신울산S/S #5 M.Tr 1차 TIE CB (7700)","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7700 CB 정밀점검","2017-10-16 08:00","2017-10-18 18:00","2017-10-16 08:00","2017-10-18 18:00","연속",null,null,null,201708110349,"-"]
[290,"부산울산","울산","신온산S/S #4 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S 345V #4M.Tr C상 요주의 변압기 내부점검","2017-10-17 09:00","2017-10-20 18:00","취소","취소","연속",null,null,null,201708210050,"-"]
[291,"부산울산","울산","북부산신울산#1 T/L","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7700 CB 정밀점검관련 시험가압","2017-10-18 17:00","2017-10-18 18:00","2017-10-18 17:00","2017-10-18 18:00","당일",null,null,null,201708110351,"-"]
[292,"부산울산","울산","신울산S/S 345kV #70BUS","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7700 CB 정밀점검관련 시험가압","2017-10-18 17:00","2017-10-18 18:00","2017-10-18 17:00","2017-10-18 18:00","당일",null,null,null,201708110350,"-"]
[293,"부산울산","울산","신울산S/S #5 M.Tr 1차 CB (7772)","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7772 CB 정밀점검","2017-10-19 08:00","2017-10-21 18:00","2017-10-19 08:00","2017-10-21 18:00","연속",null,null,null,201708110352,"-"]
[294,"부산울산","울산","북부산신울산#1 T/L","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7772 CB 정밀점검관련 시험가압","2017-10-21 17:00","2017-10-21 18:00","2017-10-21 17:00","2017-10-21 18:00","당일",null,null,null,201708110354,"-"]
[295,"부산울산","울산","신울산S/S 345kV #75BUS","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7772 CB 정밀점검관련 시험가압","2017-10-21 17:00","2017-10-21 18:00","2017-10-21 17:00","2017-10-21 18:00","당일",null,null,null,201708110353,"○"]
[296,"부산울산","울산","울주S/S 345kV #1 BUS","울주S/S #2M.Tr 증설공사","- #2M.Tr 1차 GIS (7400,7472) 설치관련 #1BUS 도킹작업","2017-10-22 09:00","2017-10-26 18:00","2017-10-22 09:00","2017-10-26 18:00","연속",null,null,null,201708110274,"-"]
[297,"부산울산","울산","신울산S/S 북부산-신울산#1T/L CB (7471)","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7471 CB 정밀점검","2017-10-25 08:00","2017-10-27 18:00","2017-10-25 08:00","2017-10-27 18:00","연속",null,null,null,201708110360,"-"]
[298,"부산울산","울산","울주고리NP#2 T/L","울주S/S #2M.Tr 증설공사","- 울주S/S #2M.Tr 1차 GIS (7400,7472) 설치관련 #1BUS 시험가압","2017-10-25 18:00","2017-10-26 18:00","2017-10-25 18:00","2017-10-26 18:00","연속",null,null,null,201708110271,"-"]
[299,"부산울산","울산","울주S/S 345kV #2 BUS","울주S/S #2M.Tr 증설공사","- #2M.Tr 1차 GIS (7400,7472) 설치관련 #2BUS 도킹작업","2017-10-27 09:00","2017-10-31 18:00","2017-10-27 09:00","2017-10-31 18:00","연속",null,null,null,201708110275,"-"]
[300,"부산울산","울산","북부산신울산#1 T/L","2017년 362kV 개폐장치 정밀점검공사","신울산S/S 362kV 7471 CB 정밀점검관련 시험가압","2017-10-27 17:00","2017-10-27 18:00","2017-10-27 17:00","2017-10-27 18:00","당일",null,null,null,201708110357,"-"]
[301,"부산울산","울산","신온산울산TP T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","노후애자금구류 교체 및 송전용 피뢰기 설치","2017-10-28 08:00","2017-11-10 18:00","취소","취소","연속",null,null,null,201708070181,"-"]
[302,"부산울산","울산","신울산S/S #3 M.Tr A","2017년 울산P/O 345kV 주변압기 누유개소 보수공사","신울산S/S 345V #3M.Tr 라디에이터 누유보수","2017-10-30 09:00","2017-11-03 18:00","2017-10-30 09:00","2017-11-03 18:00","연속",null,null,null,201708110389,"○"]
[303,"부산울산","울산","울주고리NP#2 T/L","울주S/S #2M.Tr 증설공사","- 울주S/S #2M.Tr 1차 GIS (7400,7472) 설치관련 #2BUS 시험가압","2017-10-30 18:00","2017-10-31 18:00","2017-10-30 18:00","2017-10-31 18:00","연속",null,null,null,201708110273,"-"]
[304,"경남","직할","신마산신김해#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-10-10 07:00","2017-10-11 18:00","2017-10-10 07:00","2017-10-11 18:00","연속",null,null,null,201708020052,"-"]
[305,"경남","직할","신김해S/S #2 M.Tr A","신김해S/S #2M.Tr OLTC 조작함 계전기 점검 및 교체","신김해S/S #2M.Tr OLTC 조작함 계전기 점검 및 교체","2017-10-11 09:30","2017-10-11 17:30","2017-10-11 09:30","2017-10-11 17:30","당일",null,null,null,201708010024,"-"]
[306,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선교체(신김해-북부산T/L 59~62호 등 7개 구간)","2017-10-12 07:00","2017-10-23 18:00","2017-10-12 07:00","2017-10-23 18:00","연속",null,null,null,201707060125,"-"]
[307,"경남","직할","신김해S/S #1 M.Tr A","신김해S/S #1M.Tr OLTC 조작함 계전기 점검 및 교체","신김해S/S #1M.Tr OLTC 조작함 계전기 점검 및 교체","2017-10-16 09:30","2017-10-16 17:30","2017-10-16 09:30","2017-10-16 17:30","당일",null,null,null,201708010020,"-"]
[308,"경남","직할","신김해S/S #3 M.Tr A","신김해S/S 23kV Sh.R 교체공사 관련 안전이격거리 확보차","신김해S/S 23kV Sh.R 교체공사 관련 안전이격거리 확보차 병행작업 : #3M.Tr OLTC 조작함 계전기 점검 및 교체","2017-10-17 09:30","2017-10-20 17:30","2017-10-17 09:30","2017-10-20 17:30","연속",null,null,null,201708010026,"-"]
[309,"경남","직할","신마산신김해#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보 휴전)","2017-10-23 07:00","2017-10-23 18:00","2017-10-23 07:00","2017-10-23 18:00","당일",null,null,null,201707060128,"-"]
[310,"경남","직할","신김해S/S 예비 M.Tr","신김해S/S 예비TR 하자점검","신김해S/S 예비TR 하자점검","2017-10-23 09:30","2017-10-24 17:30","2017-10-23 09:30","2017-10-24 17:30","연속",null,null,null,201708010081,"-"]
[311,"경남","진주","의령산청양수#2 T/L","345kV 의령-산청양수#2T/L 보호반 대체","345kV 의령-산청양수#2T/L 보호반 대체 - CB(7200)A,B,C상 러버히터 설치[병행]","2017-10-23 09:00","2017-11-03 18:00","2017-10-23 09:00","2017-11-03 18:00","연속",null,null,null,201707310035,"-"]
[312,"경남","진주","하동T/P 광양-하동TP#1T/L-#3 M.Tr 1차 CB (7300)","광양-하동TP#1T/L-#3 M.Tr 1차 GIS(7300) 보통점검","광양-하동TP#1T/L-#3 M.Tr 1차 GIS(7300) 보통점검","2017-10-25 09:30","2017-10-25 18:00","2017-10-25 09:30","2017-10-25 18:00","당일",null,null,null,201707310041,"-"]
[313,"경남","진주","하동T/P #3 M.Tr 1차 CB (7372)","#3M.Tr 1차 GIS(7372) 보통점검","#3M.Tr 1차 GIS(7372) 보통점검","2017-10-26 09:30","2017-10-26 18:00","2017-10-26 09:30","2017-10-26 18:00","당일",null,null,null,201707310042,"-"]
[314,"경남","진주","의령신마산#2 T/L","의령-신마산#2(A,B,C) LA초기,PT보통점검","의령-신마산#2(A,B,C) LA초기,PT보통점검","2017-10-31 09:30","2017-10-31 18:00","2017-10-31 09:30","2017-10-31 18:00","당일",null,null,null,201707310043,"-"]
[315,"경남","통영","신김해삼천포화력#1 T/L","345kV 신김해-삼천포화력#1T/L 노후 스페이서댐퍼 교체공사","345kV 신김해-삼천포화력T/L S/T~102호 구간 노후스페이서 교체","2017-10-10 07:00","2017-10-19 18:00","2017-10-10 07:00","2017-10-19 18:00","연속",null,null,null,201708010089,"-"]
[316,"경남","통영","신김해삼천포화력#2 T/L","345kV 신김해-삼천포화력#2T/L 노후 스페이서댐퍼 교체공사","345kV 신김해-삼천포화력T/L S/T~102호 구간 노후스페이서 교체 (병행)삼천포T/P 신김해-삼천포화력#2T/L 과열개소 보수(통영 변전)","2017-10-20 07:00","2017-10-29 18:00","2017-10-20 07:00","2017-10-29 18:00","연속",null,null,null,201708010090,"-"]
[317,"경남","통영","신고성S/S #3 M.Tr A","신고성S/S 345kV #3M.Tr A상 누유개소 보수","신고성S/S 345kV #3M.Tr A상 누유개소 보수","2017-10-26 09:30","2017-10-27 18:30","2017-10-26 09:30","2017-10-27 18:30","연속",null,null,null,201708020043,"-"]
[318,"경남","통영","신마산삼천포화력#1 T/L","삼천포T/P 345kV 신마산-삼천포화력#1T/L CB 보통점검","삼천포T/P 345kV 신마산-삼천포화력#1T/L CB 보통점검 삼천포T/P 345kV 신마산-삼천포화력#1T/L LA,PT 보통점검","2017-10-30 09:30","2017-10-30 18:30","2017-10-30 09:30","2017-10-30 18:30","당일",null,null,null,201707280055,"-"]
[319,"경남","함안","신마산S/S 345kV #1 BUS","신마산S/S 용량부족차단기 대체공사","전력구 시공 - 345kV #1, #2BUS 하단부 주변압기 1차측 전력케이블 구성관련 전력구 시공","2017-10-10 08:00","2017-10-19 18:00","2017-10-10 08:00","2017-10-19 18:00","당일",null,null,null,201708090079,"-"]
[320,"경남","함안","북경남S/S 북경남-고령 #1 T/L GIS (7872)","북경남S/S 북경남-고령#1T/L(7872) 장기미동작 CB 점검","북경남S/S 북경남-고령#1T/L(7872) 장기미동작 CB 점검","2017-10-10 09:30","2017-10-10 13:30","2017-10-10 09:30","2017-10-10 13:30","당일",null,null,null,201708020091,"-"]
[321,"경남","함안","신마산S/S 345kV #2 BUS","신마산S/S 용량부족차단기 대체공사","전력구 시공 - 345kV #1, #2BUS 하단부 주변압기 1차측 전력케이블 구성관련 전력구 시공","2017-10-20 08:00","2017-10-29 18:00","2017-10-20 08:00","2017-10-29 18:00","당일",null,null,null,201708090080,"-"]
[322,"경남","함안","신마산S/S #5 M.Tr A","신마산S/S #5M.Tr 6544 GCB 특별점검","신마산S/S #5M.Tr 6544 GCB 특별점검","2017-10-30 09:30","2017-10-30 17:30","2017-10-30 09:30","2017-10-30 17:30","당일",null,null,null,201708020140,"-"]
[323,"경남","함안","신마산S/S #3 M.Tr A","신마산S/S #3M.Tr 6344 GCB 특별점검","신마산S/S #3M.Tr 6344 GCB 특별점검 신마산S/S #3-1Sh.R 초기점검","2017-10-31 09:30","2017-10-31 17:30","2017-10-31 09:30","2017-10-31 17:30","당일",null,null,null,201708020135,"-"]

{"sheet":"154송부","index":2,"n_rows":447,"n_cols":16,"rows_kept":447,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"\"2017년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2017년도 10월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동왕십리 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (왕십리S/S 성동왕십리T/L)","2017-10-10 10:00","2017-10-10 17:00","2017-10-10T10:00:00","2017-10-10T17:00:00","당일",null,null,null,201708060004,"-"]
[2,"서울","성동","왕십리S/S 154kV BUS TIE CB","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (왕십리S/S 154kV BUSTIE)","2017-10-13 10:00","2017-10-13 17:00","2017-10-13T10:00:00","2017-10-13T17:00:00","당일",null,null,null,201708060003,"-"]
[3,"서울","중부","당인리S/S 154kV #60 BUS","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요","2017-10-10 09:20","2018-02-28 18:00","2017-10-10T09:00:00","2018-02-28T18:00:00","연속",null,null,null,201708020153,"-"]
[4,"서울","중부","당인리S/S 154kV #61 BUS","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2017-11-30 18:00","2017-10-10T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201708020155,"-"]
[5,"서울","중부","당인리S/S 154kV #65 BUS","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2018-02-28 18:00","2017-10-10T09:00:00","2018-02-28T18:00:00","연속",null,null,null,201708020154,"-"]
[6,"서울","중부","당인리S/S 154kV #66 BUS","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2017-11-30 18:00","2017-10-10T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201708020156,"-"]
[7,"서울","중부","당인리목동#1 T/L","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2017-11-30 18:00","2017-10-10T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201708020159,"-"]
[8,"서울","중부","당인리목동#2 T/L","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2017-11-30 18:00","2017-10-10T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201708020160,"-"]
[9,"서울","중부","당인리여의 T/L","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2017-11-30 18:00","2017-10-10T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201708020163,"-"]
[10,"서울","중부","의사당당인리 T/L","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요 - 주변압기 구내이설(별도 가수전설비 설치) 공급 예정","2017-10-10 09:20","2017-11-30 18:00","2017-10-10T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201708020161,"-"]
[11,"서울","중부","중부당인리#1 T/L","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요","2017-10-10 09:20","2018-02-28 18:00","2017-10-10T09:00:00","2018-02-28T18:00:00","연속",null,null,null,201708020157,"-"]
[12,"서울","중부","중부당인리#2 T/L","당인리S/S 옥내화 공사","당인리S/S 옥내화공사 건축물 설치 - 기설설비 존치상태 건축물 공사로 안전확보 필요","2017-10-10 09:20","2018-02-28 18:00","2017-10-10T09:00:00","2018-02-28T18:00:00","연속",null,null,null,201708020158,"-"]
[13,"서울","중부","중부용산#1 T/L","345kV 중부S/S 모자익배전반 정비공사","중부S/S 154kV 중부용산#1 T/L (647) 모자익반 교체","2017-10-10 10:00","2017-10-13 18:00","2017-10-10T10:00:00","2017-10-13T18:00:00","연속",null,null,null,201707100060,"-"]
[14,"서울","중부","상암등촌#1 T/L","154kV 상암등촌#1T/L EBA 자기애관 교체공사","154kV 상암등촌#1T/L EBA 자기애관 교체공사","2017-10-23 09:20","2017-10-25 18:00","2017-10-23T09:00:00","2017-10-25T18:00:00","연속",null,null,null,201708210004,"-"]
[15,"서울","중부","상암등촌#2 T/L","154kV 상암등촌#2T/L EBA 자기애관 교체공사","154kV 상암등촌#2T/L EBA 자기애관 교체공사","2017-10-23 09:20","2017-10-25 18:00","2017-10-23T09:00:00","2017-10-25T18:00:00","연속",null,null,null,201708210005,"-"]
[16,"서울","중부","능곡상암#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 능곡상암#1T/L (617) 보호배전반 교체","2017-10-23 10:00","2017-10-24 18:00","2017-10-23T10:00:00","2017-10-24T18:00:00","연속",null,null,null,201708090068,"-"]
[17,"서울","중부","능곡상암#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 능곡상암#2T/L (627) 보호배전반 교체","2017-10-25 10:00","2017-10-26 18:00","2017-10-25T10:00:00","2017-10-26T18:00:00","연속",null,null,null,201708090069,"-"]
[18,"서울","중부","원흥수색#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 원흥수색#2T/L (617) GCB, LS 보통점검","2017-10-27 10:00","2017-10-28 18:00","2017-10-28T09:00:00","2017-10-29T14:00:00","연속",null,null,null,201708090017,"-"]
[19,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 원흥수색#2T/L (617), #1M.Tr 1차측 LS 보통점검","2017-10-28 08:00","2017-10-28 14:00","2017-10-28T08:00:00","2017-10-28T14:00:00","당일",null,null,null,201708090020,"-"]
[20,"서울","중부","수색S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 원흥수색#2T/L (617), #1M.Tr 1차측, 수색은평#1T/L (627), #3M.Tr 1차측 LS 보통점검","2017-10-28 14:00","2017-10-29 14:00","2017-10-28T14:00:00","2017-10-29T14:00:00","연속",null,null,null,201708090021,"-"]
[21,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 수색은평#1T/L (627), #3M.Tr 1차측 LS 보통점검","2017-10-29 14:00","2017-10-29 18:00","2017-10-29T14:00:00","2017-10-29T18:00:00","당일",null,null,null,201708090022,"-"]
[22,"서울","중부","원흥수색#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 원흥수색#1T/L (687) GCB 조작시험","2017-10-31 10:00","2017-10-31 17:00","2017-10-29T14:00:00","2017-10-29T18:00:00","당일",null,null,null,201708090018,"-"]
[23,"서울","직할","신촌순화 T/L","17년 직할 변전협력 총액공사","장기무동작 차단기 조작시험","2017-10-16 10:00","2017-10-16 18:00","2017-10-16T10:00:00","2017-10-16T18:00:00","당일",null,null,null,201708110323,"-"]
[24,"서울","직할","순화동빙고 T/L","17년 직할 변전협력 총액공사","장기무동작 차단기 조작시험","2017-10-17 10:00","2017-10-17 18:00","2017-10-17T10:00:00","2017-10-17T18:00:00","당일",null,null,null,201708110322,"-"]
[25,"서울","직할","옥인운니#2 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사 업 명 : 154kV 옥인 및 운니S/S 인출T/L 교체공사 2. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 ○ 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XLPE 2000㎟ 4C, XLPE 1200㎟ 4C 총길이1.4㎞","2017-10-19 09:20","2017-11-24 18:00","2017-10-19T09:20:00","2017-11-24T18:00:00","연속",null,null,null,201708080154,"-"]
[26,"남서울","강남","신양재역삼#3 T/L","장기사용 보호배전반 대체공사 - 변전협력","장기사용 보호배전반 대체 170kV GIS 조작시험 및 개폐타임 측정","2017-10-11 10:00","2017-10-13 18:00","2017-10-11T10:00:00","2017-10-13T18:00:00","연속",null,null,null,201708180219,"-"]
[27,"남서울","강남","신양재역삼#2 T/L","장기사용 보호배전반 대체공사 - 변전협력","장기사용 보호배전반 대체 170kV GIS 조작시험 및 개폐타임 측정","2017-10-16 10:00","2017-10-18 14:00","2017-10-16T10:00:00","2017-10-18T14:00:00","연속",null,null,null,201708180220,"-"]
[28,"남서울","강남","신양재역삼#1 T/L","장기사용 보호배전반 대체공사 - 변전협력","장기사용 보호배전반 대체 170kV GIS 조작시험 및 개폐타임 측정","2017-10-18 14:00","2017-10-20 18:00","2017-10-18T14:00:00","2017-10-20T18:00:00","연속",null,null,null,201708180221,"-"]
[29,"남서울","강남","동빙고반포#1 T/L","'17-18 직할 지중송전 위탁정비공사 피뢰기 열화진단","154kV 동빙고-반포T/L 반포C/H 피뢰기 열화진단","2017-10-30 09:00","2017-10-30 18:00","2017-10-30T09:00:00","2017-10-30T18:00:00","당일",null,null,null,201708180105,"-"]
[30,"남서울","강남","동빙고반포#2 T/L","'17-18 직할 지중송전 위탁정비공사 피뢰기 열화진단","154kV 동빙고-반포T/L 반포C/H 피뢰기 열화진단","2017-10-31 09:00","2017-10-31 18:00","2017-10-31T09:00:00","2017-10-31T18:00:00","당일",null,null,null,201708180106,"-"]
[31,"남서울","동서울","동남수서 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2017-10-02 09:00","2017-10-02 18:00","2017-10-02T09:00:00","2017-10-02T18:00:00","당일",null,null,null,201708210140,"-"]
[32,"남서울","동서울","동남위례열병합#1 T/L","170kV GIS 초기점검","170kV GIS 초기점검","2017-10-02 09:00","2017-10-02 14:00","2017-10-02T09:00:00","2017-10-02T14:00:00","당일",null,null,null,201708210135,"-"]
[33,"남서울","동서울","동남위례열병합#2 T/L","170kV GIS 초기점검","170kV GIS 초기점검","2017-10-02 14:00","2017-10-02 18:00","2017-10-02T14:00:00","2017-10-02T18:00:00","당일",null,null,null,201708210137,"-"]
[34,"남서울","동서울","강동상일#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검(강동 : 장홍진), 170kV GIS 조작시험(상일 : 김도현)","2017-10-05 09:00","2017-10-06 18:00","2017-10-05T09:00:00","2017-10-06T18:00:00","연속",null,null,null,201708210146,"-"]
[35,"남서울","동서울","강동상일#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검(강동 : 장홍진), 170kV GIS 조작시험(상일 : 김도현)","2017-10-07 09:00","2017-10-08 18:00","2017-10-07T09:00:00","2017-10-08T18:00:00","연속",null,null,null,201708210148,"-"]
[36,"남서울","동서울","상일하남열병합#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2017-10-08 09:00","2017-10-08 18:00","2017-10-08T09:00:00","2017-10-08T18:00:00","당일",null,null,null,201708210150,"-"]
[37,"남서울","동서울","산성수서#2 T/L","송전철탑 정밀점검","- 대상 : 19기 - 내용 : 기별점검 및 충전부 점검 시행","2017-10-12 09:00","2017-10-13 18:00","2017-10-12T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708180135,"-"]
[38,"남서울","동서울","산성수서#1 T/L","송전철탑 정밀점검","- 대상 : 19기 - 내용 : 기별점검 및 충전부 점검 시행","2017-10-19 09:00","2017-10-20 18:00","2017-10-19T09:00:00","2017-10-20T18:00:00","연속",null,null,null,201708180134,"-"]
[39,"남서울","동서울","산성수서#1 T/L","154kV 산성-수서#1T/L 피뢰기설치공사","154kV 산성-수서#1T/L No.1-23 (9기) 송전선로용 피뢰기설치","2017-10-20 08:00","2017-10-20 18:00","2017-10-20T08:00:00","2017-10-20T18:00:00","당일",null,null,null,201707200092,"-"]
[40,"남서울","동서울","동서울서종#1 T/L","154kV동서울-서종#1t/l정밀점검","철탑 정밀점검","2017-10-23 09:00","2017-10-26 18:00","취소","취소","연속",null,null,null,201707100474,"-"]
[41,"남서울","동서울","강동풍납#1 T/L","170kV GIS 교체공사","170kV GIS 교체공사","2017-10-26 09:00","2017-11-10 18:00","2017-10-26T09:00:00","2017-11-10T18:00:00","연속",null,null,null,201708210199,"-"]
[42,"남서울","동서울","동서울서종#2 T/L","154kV동서울-서종#2t/l정밀점검","철탑 정밀점검","2017-10-27 09:00","2017-10-31 18:00","취소","취소","연속",null,null,null,201707100476,"-"]
[43,"남서울","영등포","봉천S/S 154kV #1 BUS","170kV PT GIS 보통점검(#1BUS)","170kV PT GIS 보통점검(#1BUS)","2017-10-13 10:00","2017-10-13 11:00","2017-10-13T10:00:00","2017-10-13T11:00:00","당일",null,null,null,201708230144,"-"]
[44,"남서울","영등포","봉천S/S 154kV #2 BUS","170kV PT GIS 보통점검(#2BUS)","170kV PT GIS 보통점검(#2BUS)","2017-10-13 11:00","2017-10-13 12:00","2017-10-13T11:00:00","2017-10-13T12:00:00","당일",null,null,null,201708230143,"-"]
[45,"남서울","영등포","독산S/S 154kV #1 BUS","170kV PT GIS 보통점검(#1BUS)","170kV PT GIS 보통점검(#1BUS)","2017-10-13 14:00","2017-10-13 15:00","2017-10-13T14:00:00","2017-10-13T15:00:00","당일",null,null,null,201708230145,"-"]
[46,"남서울","영등포","독산S/S 154kV #2 BUS","170kV PT GIS 보통점검(#2BUS)","170kV PT GIS 보통점검(#2BUS)","2017-10-13 15:00","2017-10-13 16:00","2017-10-13T15:00:00","2017-10-13T16:00:00","당일",null,null,null,201708230146,"-"]
[47,"남서울","영등포","광명구공#1 T/L","광명S/S 154kV 광명구공#1 T/L CB 조작시험","광명S/S 154kV 광명구공#1 T/L CB 조작시험","2017-10-16 09:00","2017-10-16 14:00","2017-10-16T09:00:00","2017-10-16T14:00:00","당일",null,null,null,201708180194,"-"]
[48,"남서울","영등포","중동화곡#1 T/L","2017-2018년 영서전력지사 지중송전설비 위탁정비공사","노후 폴리머피뢰기 교체 및 PD집합반 설치","2017-10-16 09:00","2017-10-17 18:00","취소","취소","연속",null,null,null,201708080094,"-"]
[49,"남서울","영등포","마곡S/S 154kV #1 BUS","마곡S/S #3M.Tr 증설공사","154kV GIS 1CCT 설치","2017-10-16 10:00","2017-10-20 17:00","취소","취소","연속",null,null,null,201707260013,"-"]
[50,"남서울","영등포","신정S/S 154kV #1 BUS","170kV PT GIS 보통점검(#1BUS)","170kV PT GIS 보통점검(#1BUS)","2017-10-16 10:00","2017-10-13 11:00","2017-10-16T10:00:00","2017-10-13T11:00:00","당일",null,null,null,201708230147,"-"]
[51,"남서울","영등포","신정S/S 154kV #2 BUS","170kV PT GIS 보통점검(#2BUS)","170kV PT GIS 보통점검(#2BUS)","2017-10-16 11:00","2017-10-13 12:00","2017-10-16T11:00:00","2017-10-13T12:00:00","당일",null,null,null,201708230148,"-"]
[52,"남서울","영등포","광명구공#2 T/L","광명S/S 154kV 광명구공#2 T/L CB 조작시험","광명S/S 154kV 광명구공#2T/L CB 조작시험","2017-10-16 14:00","2017-10-16 18:00","2017-10-16T14:00:00","2017-10-16T18:00:00","당일",null,null,null,201708180195,"-"]
[53,"남서울","영등포","광명구공#3 T/L","광명S/S 154kV 광명구공#3 T/L CB 조작시험","광명S/S 154kV 광명구공#3T/L CB 조작시험","2017-10-18 09:00","2017-10-18 12:00","2017-10-18T09:00:00","2017-10-18T12:00:00","당일",null,null,null,201708180196,"-"]
[54,"남서울","영등포","중동화곡#2 T/L","2017-2018년 영서전력지사 지중송전설비 위탁정비공사","노후 폴리머피뢰기 교체 및 PD집합반 설치","2017-10-18 09:00","2017-10-19 18:00","취소","취소","연속",null,null,null,201708080096,"-"]
[55,"남서울","영등포","신정목동#1 T/L","신정S/S 154kV 신정목동#1 T/L CB 조작시험","신정S/S 154kV 신정목동#1 T/L CB 조작시험 목동S/S 154kV 신정목동#1 T/L CB 조작시험","2017-10-19 09:00","2017-10-19 18:00","2017-10-19T09:00:00","2017-10-19T18:00:00","당일",null,null,null,201708180197,"-"]
[56,"남서울","영등포","영서소래 T/L","2017-2018년 영서전력지사 지중송전설비 위탁정비공사","노후 폴리머피뢰기 교체","2017-10-20 09:00","2017-10-20 18:00","2017-10-20T09:00:00","2017-10-20T18:00:00","연속",null,null,null,201708080097,"-"]
[57,"남서울","영등포","영서광명#1 T/L","2016-2017년 지중송전 협력회사 총액공사","하안C/H 피뢰기 및 EBA 점검용 안전발판대 설치","2017-10-21 09:00","2017-10-22 18:00","2017-10-21T09:00:00","2017-10-22T18:00:00","연속",null,null,null,201708080085,"-"]
[58,"남서울","영등포","온수소래 T/L","16-17년 지중송전설비 협력회사 총액공사","- 온수ch 피뢰기 및 EBA 설치 및 점검용 안전 발판대 설치공사","2017-10-23 09:00","2017-10-24 18:00","2017-10-23T09:00:00","2017-10-24T18:00:00","당일",null,null,null,201708180163,"-"]
[59,"남서울","영등포","마곡S/S 154kV #2 BUS","마곡S/S #3M.Tr 증설공사","154kV GIS 1CCT 설치","2017-10-23 10:00","2017-10-27 17:00","취소","취소","연속",null,null,null,201707260012,"-"]
[60,"남서울","영등포","신정목동#2 T/L","신정S/S 154kV 신정목동#2 T/L CB 조작시험","신정S/S 154kV 신정목동#2T/L CB 조작시험","2017-10-24 09:00","2017-10-24 18:00","2017-10-24T09:00:00","2017-10-24T18:00:00","당일",null,null,null,201708180199,"-"]
[61,"남서울","영등포","대방신길#1 T/L","대방S/S 대방신길#1 T/L CB 조작시험","대방S/S 대방신길#1 T/L CB 조작시험","2017-10-25 09:00","2017-10-25 13:00","2017-10-25T09:00:00","2017-10-25T13:00:00","당일",null,null,null,201708180201,"-"]
[62,"남서울","영등포","대방신길#2 T/L","대방S/S 대방신길#2 T/L CB 조작시험","대방S/S 대방신길#2 T/L CB 조작시험","2017-10-25 13:00","2017-10-25 18:00","2017-10-25T13:00:00","2017-10-25T18:00:00","당일",null,null,null,201708180202,"-"]
[63,"남서울","영등포","영서시흥#1 T/L","시흥S/S 영서시흥#1 T/L CB 조작시험","시흥S/S 영서시흥#1 T/L CB 조작시험","2017-10-26 09:00","2017-10-26 11:00","2017-10-26T09:00:00","2017-10-26T11:00:00","당일",null,null,null,201708180203,"-"]
[64,"남서울","영등포","영서시흥#2 T/L","시흥S/S 영서시흥#2 T/L CB 조작시험","시흥S/S 영서시흥#2 T/L CB 조작시험","2017-10-26 11:00","2017-10-26 14:00","2017-10-26T11:00:00","2017-10-26T14:00:00","당일",null,null,null,201708180204,"-"]
[65,"남서울","영등포","영서광명#2 T/L","2016-2017년 지중송전 협력회사 총액공사","하안C/H 피뢰기 및 EBA 점검용 안전발판대 설치","2017-10-28 09:00","2017-10-29 18:00","2017-10-28T09:00:00","2017-10-29T18:00:00","연속",null,null,null,201708080086,"-"]
[66,"남서울","직할","신길S/S 154kV #1 BUS TIE CB","154kV 신길S/S CPD PNL 교체, 차단기(6100) 조작시험","154kV 신길S/S CPD PNL 교체, 차단기(6100) 조작시험 및 개폐타임측정","2017-10-23 09:00","2017-10-23 18:00","2017-10-23T09:00:00","2017-10-23T18:00:00","당일",null,null,null,201708160050,"-"]
[67,"인천","김포","신경서경서#1 T/L","경서S/S 170kV 신경서-경서#1T/L GIS 정밀점검","경서S/S 170kV 신경서-경서#1T/L GIS 정밀점검","2017-10-11 09:00","2017-10-13 18:00","2017-10-11T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708160164,"-"]
[68,"인천","김포","신경서경서#2 T/L","경서S/S 170kV 신경서-경서#2T/L GIS 정밀점검","경서S/S 170kV 신경서-경서#2T/L GIS 정밀점검","2017-10-16 09:00","2017-10-18 18:00","2017-10-16T09:00:00","2017-10-18T18:00:00","연속",null,null,null,201708160165,"-"]
[69,"인천","김포","계양김포#1 T/L","154kV 계양-김포#1T/L EBA 절연유 교체","1. 대상 : 154kV 계양-김포#1T/L 계양C/H A상 등 7개소 2. 분석결과 : 7개소 정상범위 초과→절연유 교체","2017-10-23 09:00","2017-10-24 18:00","2017-10-23T09:00:00","2017-10-25T18:00:00","연속",null,null,null,201708080175,"-"]
[70,"인천","김포","계양김포#2 T/L","154kV 계양-김포#2T/L EBA 절연유 교체","1. 대상 : 154kV 계양-김포#2T/L 김포C/H A상 등 7개소 2. 분석결과 : 7개소 정상범위 초과→절연유 교체","2017-10-25 09:00","2017-10-26 18:00","2017-10-26T09:00:00","2017-10-28T18:00:00","연속",null,null,null,201708080181,"-"]
[71,"인천","시흥","도림오봉 T/L","154kV 도림오봉T/L 스페이서 간격조정 및 SB댐퍼 설치 공사","154kV 도림오봉T/L - 남동#2T/L 전력선 교체(No.28-29) 공사관련 휴전(하단) - 스페이서 간격조정 : 도림C/H~오봉C/H - SB댐퍼 설치 : 도림C/H~오봉C/H","2017-10-01 08:00","2017-10-02 18:00","2017-10-01T08:00:00","2017-10-02T18:00:00","연속",null,null,null,201708160155,"-"]
[72,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥남동#2T/L 전력선 교체 및 스페이서 간격조정 공사","154kV 신시흥남동#2T/L - 전력선 교체 : No.28-29 - 스페이서 간격조정 : 신시흥S/S~남동S/S - SB댐퍼 설치 : 신시흥S/S~남동S/S","2017-10-01 08:00","2017-10-05 18:00","2017-10-01T08:00:00","2017-10-05T18:00:00","연속",null,null,null,201708160127,"-"]
[73,"인천","시흥","신시흥도림 T/L","154kV 신시흥도림T/L 스페이서 간격조정 및 SB댐퍼 설치 공사","154kV 신시흥도림T/L - 스페이서 간격조정 : 신시흥S/S~도림C/H - SB댐퍼 설치 : 신시흥S/S~도림C/H","2017-10-03 08:00","2017-10-05 18:00","2017-10-03T08:00:00","2017-10-05T18:00:00","연속",null,null,null,201708160157,"-"]
[74,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥남동#1T/L 피뢰기 설치 및 스페이서 간격조정 공사","154kV 신시흥남동#1T/L - 피뢰기 설치 : 10기 - 스페이서 간격조정 : 신시흥S/S~남동S/S - SB댐퍼 설치 : 신시흥S/S~남동S/S","2017-10-06 08:00","2017-10-09 18:00","2017-10-06T08:00:00","2017-10-09T18:00:00","연속",null,null,null,201708160131,"-"]
[75,"인천","시흥","신시흥오봉 T/L","154kV 신시흥오봉T/L 피뢰기 설치 및스페이서 간격조정 공사","154kV 신시흥오봉T/L - 피뢰기 설치 : 10기 - 스페이서 간격조정 : 신시흥S/S~오봉C/H - SB댐퍼 설치 : 신시흥S/S~오봉C/H","2017-10-06 08:00","2017-10-09 18:00","2017-10-06T08:00:00","2017-10-09T18:00:00","연속",null,null,null,201708160158,"-"]
[76,"인천","시흥","동춘송도#2 T/L","154kV 동송도분기 지중T/L 건설공사","공사목적 : 송도지역 전력계통보강 공사구간 : 154kV 동춘-송도T/L M/H#8~M/H#9(2ㅠ분기) 선종 및 규격 : 154KV XLPE 2000SQ 회선수 및 길이 : 4회선, 2.5KM","2017-10-12 09:30","2017-11-10 18:00","2017-10-11T09:30:00","2017-11-05T18:00:00","연속",null,null,null,201708240075,"-"]
[77,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-10-20 08:00","2017-10-21 15:00","2017-10-20T08:00:00","2017-10-21T15:00:00","연속",null,null,null,201708030083,"-"]
[78,"인천","시흥","신시흥북시화#2 T/L","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-10-20 09:00","2017-11-04 08:00","2017-10-20T09:00:00","2017-11-04T08:00:00","연속",null,null,null,201708030079,"-"]
[79,"인천","시흥","신시흥북시화#2 T/L","154kV 신시흥북시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥북시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","2017-10-21 08:00","2017-10-21 18:00","2017-10-21T08:00:00","2017-10-21T18:00:00","당일",null,null,null,201708210067,"-"]
[80,"인천","시흥","신시흥시화#2 T/L","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","2017-10-21 08:00","2017-10-22 18:00","2017-10-21T08:00:00","2017-10-22T18:00:00","연속",null,null,null,201708210068,"-"]
[81,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-10-21 15:00","2017-10-28 08:00","2017-10-21T15:00:00","2017-10-28T08:00:00","연속",null,null,null,201708030082,"-"]
[82,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-10-27 08:00","2017-10-28 08:00","2017-10-27T08:00:00","2017-10-28T08:00:00","연속",null,null,null,201708030080,"-"]
[83,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-10-28 08:00","2017-11-03 08:00","2017-10-28T08:00:00","2017-11-03T08:00:00","연속",null,null,null,201708030084,"-"]
[84,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 기타 부대공사 1식","2017-10-10 08:00","2017-11-17 18:00","2017-10-10T08:00:00","2017-11-17T18:00:00","연속",null,null,"신뢰도개선",201708160200,"-"]
[85,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 기타 부대공사 1식","2017-10-10 08:00","2017-10-15 18:00","2017-10-10T08:00:00","2017-10-15T18:00:00","연속",null,null,null,201708160205,"-"]
[86,"인천","인천","신현포스코CC#1 T/L","신현S/S 170kV GIS 대체공사","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 기타 부대공사 1식","2017-10-10 08:00","2017-11-17 18:00","2017-10-10T08:00:00","2017-11-17T18:00:00","연속",null,null,"신뢰도개선",201708160198,"-"]
[87,"인천","인천","서인천C/C 154kV #60 BUS","서인천CC #60BUS 철공진 방지장치 설치공사","서인천CC #60BUS 철공진 방지장치 설치공사","2017-10-10 09:00","2017-10-10 14:00","2017-10-10T09:00:00","2017-10-10T14:00:00","당일",null,null,null,201708220155,"-"]
[88,"인천","인천","주안만수 T/L","154kV 만수S/S 인출구간 OF케이블 선종교체공사","단일계통 옥내형GIS변전소 내 OF케이블 선종교체를 통한 화재 및 정전고장 예방","2017-10-10 09:00","2017-10-27 18:00","2017-10-10T09:00:00","2017-10-27T18:00:00","연속",null,null,null,201708010079,"-"]
[89,"인천","인천","서인천C/C 154kV #65 BUS","서인천CC #65BUS 철공진 방지장치 설치공사","서인천CC #65BUS 철공진 방지장치 설치공사","2017-10-10 14:00","2017-10-10 18:00","2017-10-10T14:00:00","2017-10-10T18:00:00","당일",null,null,null,201708220156,"-"]
[90,"인천","인천","신가좌S/S 60-61 SEC GIS","2017년 170kV GIS 정밀점검 공사","2017년 170kV GIS 정밀점검 공사 - 신가좌S/S 60-61-0 SEC 정밀점검","2017-10-11 09:00","2017-10-13 18:00","2017-10-11T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708100093,"-"]
[91,"인천","인천","인천CC북인천#1 T/L","북인천S/S 인천CC북인천#1T/L GIS 보통점검 공사","북인천S/S 인천CC북인천#1T/L GIS 보통점검 공사","2017-10-11 09:00","2017-10-11 18:00","2017-10-11T09:00:00","2017-10-11T18:00:00","당일",null,null,null,201708090247,"-"]
[92,"인천","인천","인천CC북인천#2 T/L","북인천S/S 인천CC북인천#2T/L GIS 보통점검 공사","북인천S/S 인천CC북인천#2T/L GIS 보통점검 공사","2017-10-12 09:00","2017-10-12 18:00","2017-10-12T09:00:00","2017-10-12T18:00:00","당일",null,null,null,201708090249,"-"]
[93,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 기타 부대공사 1식","2017-10-16 08:00","2017-11-05 18:00","2017-10-16T08:00:00","2017-11-05T18:00:00","연속",null,null,null,201708160208,"-"]
[94,"인천","인천","신가좌S/S 65-66 SEC GIS","2017년 170kV GIS 정밀점검 공사","2017년 170kV GIS 정밀점검 공사 - 신가좌S/S 65-66-0 SEC 정밀점검","2017-10-16 09:00","2017-10-18 18:00","2017-10-16T09:00:00","2017-10-18T18:00:00","연속",null,null,null,201708100098,"-"]
[95,"인천","인천","계양북인천 T/L","154kV계양-북인천T/L 과열개소정비","154kV계양-북인천T/L 과열개소정비","2017-10-19 08:00","2017-10-19 18:00","2017-10-30T13:00:00","2017-10-30T18:00:00","당일",null,null,null,201708170020,"-"]
[96,"인천","인천","신가좌S/S 154kV #1 BUS TIE GIS","2017년 170kV GIS 정밀점검 공사","2017년 170kV GIS 정밀점검 공사 - 신가좌S/S 6100GIS 정밀점검","2017-10-19 09:00","2017-10-21 18:00","2017-10-19T09:00:00","2017-10-21T18:00:00","연속",null,null,null,201708100099,"-"]
[97,"인천","인천","인천CC포스코CC#1 T/L","인천CC 인천TP포스코CC#1T/L GIS 보통점검 공사","인천CC 인천TP포스코CC#1T/L GIS 보통점검 공사","2017-10-24 09:00","2017-10-24 18:00","2017-10-24T09:00:00","2017-10-24T18:00:00","당일",null,null,null,201708090261,"-"]
[98,"인천","인천","남동관교#1 T/L","관교S/S 남동-관교#1T/L 보호반대체공사","관교S/S 남동-관교#1T/L 보호반대체공사","2017-10-30 09:00","2017-11-03 18:00","2017-10-30T09:00:00","2017-11-03T18:00:00","연속",null,null,null,201708090263,"-"]
[99,"인천","인천","서인천C/C 154kV #61 BUS","서인천CC #61BUS UHF센서 및 철공진 방지장치 설치공사","서인천CC #61BUS UHF센서 및 철공진 방지장치 설치공사","2017-10-30 09:00","2017-11-03 18:00","2017-10-30T09:00:00","2017-11-03T18:00:00","연속",null,null,null,201708220158,"-"]
[100,"인천","인천","서인천C/C 154kV #66 BUS","서인천CC #66BUS UHF센서 및 철공진 방지장치 설치공사","서인천CC #66BUS UHF센서 및 철공진 방지장치 설치공사","2017-10-30 09:00","2017-11-03 18:00","2017-10-30T09:00:00","2017-11-03T18:00:00","연속",null,null,null,201708220159,"-"]
[101,"인천","직할","신부평S/S 60-61-0 SEC CB","신부평S/S 60-61SEC 170kV GIS 정밀점검","신부평S/S 60-61SEC 170kV GIS 정밀점검","2017-10-10 08:00","2017-10-11 18:00","2017-10-10T08:00:00","2017-10-11T18:00:00","연속",null,null,null,201708140074,"-"]
[102,"인천","직할","신부평S/S 65-66-0 SEC CB","신부평S/S 65-66SEC 170kV GIS 정밀점검","신부평S/S 65-66SEC 170kV GIS 정밀점검","2017-10-12 08:00","2017-10-13 18:00","2017-10-12T08:00:00","2017-10-13T18:00:00","연속",null,null,null,201708140075,"-"]
[103,"인천","직할","신부평고강#2 T/L","154kV 신부평-고강 #2T/L EBA 자기애관 실측","EBA 애관 교체 공사(자기애관 → 폴리머애관) 관련 실측","2017-10-16 09:00","2017-10-16 18:00","2017-10-28T09:00:00","2017-10-28T18:00:00","당일",null,null,null,201708080199,"-"]
[104,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강 #1T/L 절연유 교체","기중종단접속함(EBA) 절연유 교체 시행(A, B, C상)","2017-10-17 09:00","2017-10-19 18:00","취소","취소","연속",null,null,null,201708080200,"-"]
[105,"인천","직할","임학계양#1 T/L","항공장애표시구 설치공사","항공장애표시구 미설치개소 설치공사(오전)","2017-10-20 08:00","2017-10-20 13:00","취소","취소","당일",null,null,null,201708170002,"-"]
[106,"인천","직할","임학계양#2 T/L","항공장애표시구 설치공사","항공장애표시구 미설치개소 설치공사(오후)","2017-10-20 13:00","2017-10-20 18:00","취소","취소","당일",null,null,null,201708170004,"-"]
[107,"경기북부","구리","동서울서종#1 T/L","154kV 동서울-서종 등 2개T/L 전선접속개소 전선교체공사","154kv 동서울-서종 #1 T/L No.37~38등 10개구간 전력선 교체공사","2017-10-11 08:00","2017-10-26 18:00","2017-10-11T08:00:00","2017-10-26T18:00:00","연속",null,null,"신뢰도개선",201706150046,"-"]
[108,"경기북부","구리","미금화양 T/L","154kV 미금-화양T/L 송전선로 정밀점검","154kV 미금-화양T/L 철탑 및 충전부 등 정밀점검","2017-10-11 08:00","2017-10-11 18:00","2017-10-11T08:00:00","2017-10-11T18:00:00","당일",null,null,null,201702140025,"-"]
[109,"경기북부","구리","미금광장 T/L","154kV 미금-광장T/L 송전선로 정밀점검","154kV 미금-광장T/L 철탑 및 충전부 등 정밀점검","2017-10-12 08:00","2017-10-12 18:00","2017-10-12T08:00:00","2017-10-12T18:00:00","당일",null,null,null,201702140026,"-"]
[110,"경기북부","구리","운천철원#2 T/L","16~17년 직할 가공송전정비 협력회사 총액공사","154kV 운천-철원#2T/L 피뢰기설치공사 - 65기 195SET 피뢰기설치","2017-10-23 07:00","2017-10-28 18:00","2017-10-23T07:00:00","2017-10-28T18:00:00","연속",null,null,null,201707100324,"-"]
[111,"경기북부","구리","별내진접 T/L","154kV 별내진접 T/L 송전선로 정밀점검","No.1~9, 1~27 송전선로 철탑 및 충전부 등 정밀점검","2017-10-23 08:00","2017-10-26 18:00","2017-10-23T08:00:00","2017-10-26T18:00:00","연속",null,null,null,201708100237,"-"]
[112,"경기북부","구리","서종S/S 동서울-서종#2T/L GIS","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-10-27 10:00","2017-10-27 18:00","2017-10-27T10:00:00","2017-11-11T18:00:00","당일",null,null,null,201707070271,"-"]
[113,"경기북부","구리","운천철원#1 T/L","운천-철원#1T/L 보호반 교체공사","운천-철원#1T/L 보호반 교체공사","2017-10-30 09:00","2017-11-01 18:00","2017-10-30T09:00:00","2017-11-01T18:00:00","연속",null,null,null,201708090005,"○"]
[114,"경기북부","직할","신의정부금오#1 T/L","경기북부직할 변전총액공사","신의정부금오#1 T/L 보통점검","2017-10-10 08:30","2017-10-10 13:00","2017-10-10T08:30:00","2017-10-10T13:00:00","당일",null,null,null,201708160262,"-"]
[115,"경기북부","직할","신의정부금오#2 T/L","경기북부직할 변전총액공사","신의정부금오#2 T/L 보통점검","2017-10-10 13:00","2017-10-10 18:00","2017-10-10T13:00:00","2017-10-10T18:00:00","당일",null,null,null,201708160263,"-"]
[116,"경기북부","직할","녹양백석#1 T/L","17년도 경기북부직할 170kV GIS 정밀점검공사","녹양백석#1 T/L 정밀점검","2017-10-12 09:00","2017-10-13 18:00","2017-10-12T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708160251,"-"]
[117,"경기북부","직할","녹양백석#2 T/L","154kV 남면, 백석S/S SW 증설공사","○ 백석S/S 170kV GIS 2CCT 설치 (#2 BUS측) ○ 기타 부대공사 1식","2017-10-16 10:00","2017-10-27 18:00","2017-10-16T10:00:00","2017-10-27T18:00:00","연속",null,null,null,201708020090,"-"]
[118,"경기북부","직할","금오상계#1 T/L","16~17년 직할 가공송전정비 협력회사 총액공사","154kV 금오-상계#1T/L 피뢰기설치공사 - 7기 21SET 피뢰기설치","2017-10-18 07:00","2017-10-20 18:00","2017-10-18T07:00:00","2017-10-20T18:00:00","연속",null,null,null,201707100334,"-"]
[119,"경기북부","직할","금오상계#2 T/L","17년도 경기북부직할 170kV GIS 정밀점검공사","금오상계#2 T/L 정밀점검","2017-10-21 09:00","2017-10-22 18:00","2017-10-21T09:00:00","2017-10-22T18:00:00","연속",null,null,null,201708160256,"-"]
[120,"경기북부","직할","양주쌍문#2 T/L","154kV 송전선로 피뢰기 설치공사","154KV 양주-쌍문#2T/L No.1~27 피뢰기 설치공사","2017-10-23 07:00","2017-10-28 18:00","2017-10-23T07:00:00","2017-10-28T18:00:00","연속",null,null,null,201708080170,"-"]
[121,"경기북부","파주","양주고양#1 T/L","154kV 양주-고양#1T/L 접속개소 전선교체공사","ㅇ 공사대상 - 154kV 양주-고양#1T/L No.9-10 등 4개소","2017-10-10 07:00","2017-10-11 18:00","2017-10-08T07:00:00","2017-10-09T18:00:00","연속",null,null,null,201707070176,"○"]
[122,"경기북부","파주","신덕은원흥#1 T/L","154kV 신덕은-수색T/L 송전용량증대 전력선교체공사","154kV 신덕은-원흥T/L No.60~68 전력선교체","2017-10-14 08:00","2017-10-18 12:00","2017-10-14T08:00:00","2017-10-18T12:00:00","연속",null,null,null,201708090168,"-"]
[123,"경기북부","파주","신덕은S/S 154kV #1 BUS TIE GIS","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은S/S #1BUS-TIE GIS 정밀점검","2017-10-16 09:00","2017-10-18 18:00","2017-10-25T09:00:00","2017-10-27T18:00:00","연속",null,null,null,201708030009,"-"]
[124,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-수색T/L 송전용량증대 전력선교체공사","154kV 신덕은-원흥T/L No.60~68 전력선교체","2017-10-18 12:00","2017-10-22 18:00","2017-10-18T12:00:00","2017-10-22T18:00:00","연속",null,null,null,201708090169,"-"]
[125,"경기북부","파주","신덕은S/S 154kV #2 BUS TIE GIS","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은S/S #2BUS-TIE GIS 정밀점검","2017-10-19 09:00","2017-10-21 18:00","2017-10-19T09:00:00","2017-10-21T18:00:00","연속",null,null,null,201708030010,"-"]
[126,"경기북부","파주","신덕은S/S 60-61 SEC GIS","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은S/S 60-61BUS-SEC GIS 정밀점검","2017-10-25 09:00","2017-10-26 18:00","2017-10-10T09:00:00","2017-10-11T18:00:00","연속",null,null,null,201708030011,"-"]
[127,"경기북부","파주","신덕은S/S 65-66 SEC GIS","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은S/S 65-66BUS-SEC GIS 정밀점검","2017-10-27 09:00","2017-10-28 18:00","2017-10-12T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708030012,"-"]
[128,"경기북부","파주","불광서대문#1 T/L","154kV 송전선로 피뢰기 설치공사","154KV 불광-서대문#1T/L No.1~3 피뢰기 설치공사","2017-10-29 07:00","2017-10-29 18:00","2017-10-29T07:00:00","2017-10-29T18:00:00","당일",null,null,null,201708080165,"-"]
[129,"경기북부","파주","신파주금촌#2 T/L","154kV 송전선로 피뢰기 설치공사","154KV 신파주-금촌#2T/L No.1~20 피뢰기 설치공사","2017-10-30 07:00","2017-11-02 18:00","2017-10-30T07:00:00","2017-11-02T18:00:00","연속",null,null,null,201708080166,"-"]
[130,"경기북부","파주","신포천백학#1 T/L","16~17년 파주전력지사 변전협력회사 총액공사","백학S/S 신포천-백학#1T/L GIS 하자점검","2017-10-30 10:00","2017-10-30 18:00","취소","취소","당일",null,null,null,201708110365,"-"]
[131,"경기북부","파주","신포천백학#2 T/L","16~17년 파주전력지사 변전협력회사 총액공사","백학S/S 신포천-백학#2T/L GIS 하자점검","2017-10-31 10:00","2017-10-31 18:00","취소","취소","당일",null,null,null,201708110367,"-"]
[132,"경기","군포","안양평촌#2 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 평촌S/S 안양-평촌#2T/L","2017-10-17 09:00","2017-10-19 18:00","2017-10-17T09:00:00","2017-10-19T18:00:00","연속",null,null,null,201708110291,"-"]
[133,"경기","군포","반월시화#1 T/L","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사 (병가구간, No.18~시화S/S)","2017-10-22 08:00","2017-10-22 18:00","2017-10-22T08:00:00","2017-10-22T18:00:00","당일",null,null,null,201708210069,"-"]
[134,"경기","군포","산본안양#1 T/L","154kV 안양S/S 인출변경 지중T/L 건설공사","선종/회선길이 : 154㎸ XLPE 1,200/2,000㎟, 각 2회선-0.13㎞ - 안양-평촌TL, 안양-산본TL 이설","2017-10-23 10:00","2017-11-09 18:00","2017-10-23T10:00:00","2017-11-09T18:00:00","연속",null,null,null,201708090036,"-"]
[135,"경기","동부","곤지암S/S 154kV #61 BUS","345kV 곤지암S/S #64D.Tr용 GIS 설치공사","○ GIS(170kV 50kA 1250A CHD) x 1CCT 설치","2017-10-23 09:00","2017-10-27 18:00","2017-10-23T09:00:00","2017-10-27T18:00:00","연속",null,null,null,201708110091,"-"]
[136,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #64D.Tr용 GIS 설치공사","○ GIS(170kV 50kA 1250A CHD) x 1CCT 설치","2017-10-29 09:00","2017-11-01 18:00","2017-10-29T09:00:00","2017-11-01T18:00:00","연속",null,null,null,201708110099,"-"]
[137,"경기","성남","신성남S/S 154kV #1 BUS TIE(6100) GIS","신성남S/S 154kV GIS 대체공사","#1BUSTIE GIS 대체","2017-10-10 09:00","2017-10-30 18:00","2017-10-10T09:00:00","2017-10-30T18:00:00","연속",null,null,null,201708100028,"-"]
[138,"경기","성남","신성남과천#2 T/L","신성남S/S 154kV GIS 대체공사","신성남-과천#2T/L GIS 대체","2017-10-10 09:00","2017-10-30 18:00","2017-10-10T09:00:00","2017-10-30T18:00:00","연속",null,null,null,201708100027,"-"]
[139,"경기","성남","서안성안성#1 T/L","154kV 서안성-안성T/L 전선접속개소 교체공사","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 전선교체공사","2017-10-16 08:00","2017-10-21 18:00","2017-10-16T08:00:00","2017-10-21T18:00:00","연속",null,null,null,201708100056,"-"]
[140,"경기","성남","신수원S/S 61-62 SEC(61-62-0) GIS","17년 성남변전협력회사 총액공사","61-62 GIS 보통점검","2017-10-16 10:00","2017-10-16 18:00","2017-10-16T10:00:00","2017-10-16T18:00:00","당일",null,null,null,201708100055,"-"]
[141,"경기","성남","신수원S/S 66-67 SEC(66-67-0) GIS","17년 성남변전협력회사 총액공사","66-67 GIS 보통점검","2017-10-17 10:00","2017-10-17 18:00","2017-10-17T10:00:00","2017-10-17T18:00:00","당일",null,null,null,201708100054,"-"]
[142,"경기","성남","동탄C/C S/T#1 GIS","17년 성남변전협력회사 총액공사","#1S/T 6233 초기점검","2017-10-19 10:00","2017-10-19 18:00","2017-10-19T10:00:00","2017-10-19T18:00:00","당일",null,null,null,201708100050,"-"]
[143,"경기","성남","동탄C/C S/T#2 GIS","17년 성남변전협력회사 총액공사","#2S/T 6333 초기점검","2017-10-20 10:00","2017-10-20 18:00","2017-10-20T10:00:00","2017-10-20T18:00:00","당일",null,null,null,201708100048,"-"]
[144,"경기","성남","서안성안성#2 T/L","154kV 서안성-안성T/L 전선접속개소 교체공사","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 전선교체공사","2017-10-22 08:00","2017-10-27 18:00","2017-10-22T08:00:00","2017-10-27T18:00:00","연속",null,null,null,201708100057,"-"]
[145,"경기","성남","신성남S/S 154kV #60 BUS","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체","2017-10-31 08:00","2017-11-01 18:00","2017-10-31T08:00:00","2017-11-01T18:00:00","연속",null,null,null,201708100035,"-"]
[146,"경기","성남","신성남S/S 60-61 SEC GIS","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체","2017-10-31 08:00","2017-11-15 18:00","2017-10-31T08:00:00","2017-11-15T18:00:00","연속",null,null,null,201708100034,"-"]
[147,"경기","성남","신성남과천#2 T/L","신성남S/S 154kV GIS 대체공사","60-61 GIS 대체관련 안전이격 확보","2017-10-31 09:00","2017-11-16 18:00","2017-10-31T09:00:00","2017-11-16T18:00:00","매일",null,null,null,201708110284,"-"]
[148,"경기","직할","서서울#2남수원 #1T/L","154kV 서서울-남수원T/L 지장철탑 이설공사","No.25호 지장철탑 이설공사(1기 철거, 1기 신설)","2017-10-10 09:00","2017-10-11 18:00","2017-10-10T09:00:00","2017-10-11T18:00:00","연속",null,null,null,201708160276,"-"]
[149,"경기","직할","서서울#2남수원 #2T/L","154kV 서서울-남수원T/L 지장철탑 이설공사","No.25호 지장철탑 이설공사(1기 철거, 1기 신설)","2017-10-12 09:00","2017-10-13 18:00","2017-10-12T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708160277,"-"]
[150,"경기","직할","서수원율전#1 T/L","서수원S/S 154kV 서수원율전#1 T/L 조작시험","서수원S/S 154kV 서수원율전#1 T/L 조작시험","2017-10-13 10:00","2017-10-13 13:00","2017-10-13T10:00:00","2017-10-13T13:00:00","당일",null,null,null,201708170034,"-"]
[151,"경기","직할","서수원율전#2 T/L","서수원S/S 154kV 서수원율전#2 T/L 조작시험","서수원S/S 154kV 서수원율전#2 T/L 조작시험","2017-10-13 13:00","2017-10-13 15:00","2017-10-13T13:00:00","2017-10-13T15:00:00","당일",null,null,null,201708170035,"-"]
[152,"경기","직할","발안구문천#1 T/L","발안S/S 154kV 발안구문천#1T/L 조작시험","발안S/S 154kV 발안구문천#1T/L 조작시험","2017-10-16 10:00","2017-10-16 13:00","2017-10-16T10:00:00","2017-10-16T13:00:00","당일",null,null,null,201708170029,"-"]
[153,"경기","직할","이의광교열병합#1T/L","154kV 이의S/S 이의-열병합#1T/L GIS 보통점검","154kV 이의S/S 이의-열병합#1T/L GIS 보통점검","2017-10-16 10:00","2017-10-16 18:00","2017-10-16T10:00:00","2017-10-16T18:00:00","당일",null,null,null,201708170073,"-"]
[154,"경기","직할","발안구문천#2 T/L","발안S/S 154kV 발안구문천#2T/L 조작시험","발안S/S 154kV 발안구문천#2T/L 조작시험","2017-10-16 13:00","2017-10-16 15:00","2017-10-16T13:00:00","2017-10-16T15:00:00","당일",null,null,null,201708170030,"-"]
[155,"경기","직할","화성S/S 154kV #67 BUS","화성S/S 154kV #68 SC GIS 정밀점검공사","화성S/S 154kV #68 SC GIS 정밀점검공사","2017-10-16 14:00","2017-10-16 18:00","2017-10-16T14:00:00","2017-10-16T18:00:00","연속",null,null,null,201708170056,"-"]
[156,"경기","직할","이의광교열병합#2T/L","154kV 이의S/S 이의-열병합#2T/L GIS 보통점검","154kV 이의S/S 이의-열병합#2T/L GIS 보통점검","2017-10-17 10:00","2017-10-17 18:00","2017-10-17T10:00:00","2017-10-17T18:00:00","당일",null,null,null,201708170074,"-"]
[157,"경기","직할","화성발안#1 T/L","154kV 화성-발안T/L No.10-11 전력선 교체공사","154kV 화성-발안T/L No.10-11 전력선 교체공사","2017-10-19 07:00","2017-10-20 18:00","2017-10-19T07:00:00","2017-10-20T18:00:00","연속",null,null,null,201708160143,"-"]
[158,"경기","직할","화성조암#1 T/L","154kV 화성-발안#1(화성조암)T/LNo.4-12항공구교체(안전이격)","154kV 화성-발안#1(화성조암#1)T/L No.4-12 항공장애표지구 교체공사(안전이격)","2017-10-19 07:00","2017-10-19 18:00","2017-10-19T07:00:00","2017-10-19T18:00:00","당일",null,null,null,201708160172,"-"]
[159,"경기","직할","화성S/S 66-67 SEC GIS","화성S/S 66-67 SEC GIS 조작시험","화성S/S 66-67 SEC GIS 조작시험","2017-10-19 15:00","2017-10-19 18:00","2017-10-19T15:00:00","2017-10-19T18:00:00","당일",null,null,null,201708170038,"-"]
[160,"경기","직할","화성조암#2 T/L","154kV 화성-발안T/L No.10-11 전력선 교체공사(안전이격)","154kV 화성-발안T/L No.10-11 전력선 교체공사(안전이격확보차 휴전)","2017-10-20 07:00","2017-10-20 18:00","2017-10-20T07:00:00","2017-10-20T18:00:00","당일",null,null,null,201708160145,"-"]
[161,"경기","직할","안열#1T/L T/L","154kV 동안양S/S 안열#1T/L 조작시험","154kV 동안양S/S 안열#1T/L 조작시험","2017-10-20 10:00","2017-10-20 15:00","2017-10-20T10:00:00","2017-10-20T15:00:00","당일",null,null,null,201708170075,"-"]
[162,"경기","직할","화성S/S 60-61 SEC GIS","화성S/S 60-61 SEC GIS 조작시험","화성S/S 60-61 SEC GIS 조작시험","2017-10-20 10:00","2017-10-20 13:00","2017-10-20T10:00:00","2017-10-20T13:00:00","당일",null,null,null,201708170039,"-"]
[163,"경기","직할","화성S/S 61-62 SEC GIS","화성S/S 61-62 SEC GIS 조작시험","화성S/S 61-62 SEC GIS 조작시험","2017-10-20 13:00","2017-10-20 15:00","2017-10-20T13:00:00","2017-10-20T15:00:00","당일",null,null,null,201708170040,"-"]
[164,"경기","직할","화성S/S 65-66 SEC GIS","화성S/S 65-66 SEC GIS 조작시험","화성S/S 65-66 SEC GIS 조작시험","2017-10-20 15:00","2017-10-20 18:00","2017-10-20T15:00:00","2017-10-20T18:00:00","당일",null,null,null,201708170041,"-"]
[165,"경기","직할","오산향남#1 T/L","154kV 향남S/S #4M.Tr 증설공사","ㅇ 154kV 향남S/S #4M.Tr 증설공사 - 향남S/S 154kV #1BUS 무부하가압","2017-10-21 10:00","2017-10-22 10:00","2017-10-21T10:00:00","2017-10-22T10:00:00","연속",null,null,null,201708080215,"-"]
[166,"경기","직할","화성발안#2 T/L","154kV 화성-발안T/L No.10-11 전력선 교체공사","154kV 화성-발안T/L No.10-11 전력선 교체공사","2017-10-23 07:00","2017-10-24 18:00","2017-10-23T07:00:00","2017-10-24T18:00:00","연속",null,null,null,201708160141,"-"]
[167,"경기","직할","화성조암#2 T/L","154kV 화성-발안T/L No.10-11 전력선 교체공사(안전이격)","154kV 화성-발안T/L No.10-11 전력선 교체공사(안전이격확보차 휴전)","2017-10-23 07:00","2017-10-24 18:00","2017-10-23T07:00:00","2017-10-24T18:00:00","연속",null,null,null,201708220020,"-"]
[168,"경기","직할","화성S/S 154kV #1 BUS TIE GIS","화성S/S 154kV #1 BUS TIE GIS 조작시험","화성S/S 154kV #1 BUS TIE GIS 조작시험","2017-10-31 10:00","2017-10-31 13:00","2017-10-31T10:00:00","2017-10-31T13:00:00","당일",null,null,null,201708170042,"-"]
[169,"경기","직할","화성S/S 154kV #2 BUS TIE GIS","화성S/S 154kV #2 BUS TIE GIS 조작시험","화성S/S 154kV #2 BUS TIE GIS 조작시험","2017-10-31 13:00","2017-10-31 15:00","2017-10-31T13:00:00","2017-10-31T15:00:00","당일",null,null,null,201708170044,"-"]
[170,"경기","직할","화성S/S 154kV # 3BUS TIE GIS","화성S/S 154kV #3 BUS TIE GIS 조작시험","화성S/S 154kV #3 BUS TIE GIS 조작시험","2017-10-31 15:00","2017-10-31 18:00","2017-10-31T15:00:00","2017-10-31T18:00:00","당일",null,null,null,201708170046,"-"]
[171,"경기","평택","포승평택TP#1 T/L","154kV 포승-평택TPT/L 안전이격거리 확보공사","○ 공사구간 : 154kV 포승-평택TPT/L No.6~8 ○ 공사규모 : 관형주 1기설치, 사각철탑 1기철거, 전력선 0.402km교체","2017-10-12 07:00","2017-10-17 18:00","2017-10-12T07:00:00","2017-10-17T18:00:00","연속",null,null,null,201708140336,"-"]
[172,"경기","평택","서운안성#1 T/L","154kV 서안성-안성T/L 전선교체시 안전이격확보","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 전선교체공사 시 안전이격확보","2017-10-16 08:00","2017-10-18 18:00","2017-10-16T08:00:00","2017-10-18T18:00:00","연속",null,null,null,201708240056,"-"]
[173,"경기","평택","포승평택TP#2 T/L","154kV 포승-평택TPT/L 안전이격거리 확보공사","○ 공사구간 : 154kV 포승-평택TPT/L No.6~8 ○ 공사규모 : 관형주 1기설치, 사각철탑 1기철거, 전력선 0.402km교체","2017-10-20 07:00","2017-10-22 18:00","2017-10-20T07:00:00","2017-10-22T18:00:00","연속",null,null,null,201708140337,"-"]
[174,"경기","평택","서운안성#2 T/L","154kV 서안성-안성T/L 전선교체시 안전이격확보","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 전선교체공사 시 안전이격확보","2017-10-22 08:00","2017-10-24 18:00","2017-10-22T08:00:00","2017-10-24T18:00:00","연속",null,null,null,201708240061,"-"]
[175,"경기","평택","오산평택#1 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.6~9)","6~9 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(8~26)","2017-10-25 08:00","2017-10-29 18:00","2017-10-25T08:00:00","2017-10-29T18:00:00","연속",null,null,null,201708160089,"-"]
[176,"경기","평택","오산향남#1 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.14~17)","14~17호 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(8~26)","2017-10-25 08:00","2017-10-29 18:00","2017-10-25T08:00:00","2017-10-29T18:00:00","연속",null,null,null,201708160088,"-"]
[177,"경기","평택","송탄소사벌 T/L","154kV 소사벌S/S #3M.Tr 증설공사","○ 154kV 소사벌S/S #3M.Tr 증설공사 - 170kV #1BUS 무부하시험","2017-10-28 09:00","2017-10-28 09:00","2017-10-28T09:00:00","2017-10-28T09:00:00","연속",null,null,null,201708090166,"-"]
[178,"경기","평택","오산평택#2 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.6~9)","6~9 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(26~45)","2017-10-30 08:00","2017-11-03 18:00","2017-10-30T08:00:00","2017-11-03T18:00:00","연속",null,null,null,201708160090,"-"]
[179,"경기","평택","오산향남#2 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.14~17)","14~17 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(26~45)","2017-10-30 08:00","2017-11-02 18:00","2017-10-30T08:00:00","2017-11-02T18:00:00","연속",null,null,null,201708160091,"-"]
[180,"강원","강릉","강릉횡계#1 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지중선로 포설 및 접속(No.35~신설 강릉S/S) - No.35~신설CH 전력선 연, 긴선","2017-10-10 09:00","2017-10-25 18:00","2017-10-10T09:00:00","2017-10-25T18:00:00","연속",null,null,null,201708080177,"-"]
[181,"강원","강릉","동해강릉 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지중선로 포설 및 접속(66-2~신설 강릉S/S) - No.66.2~신설CH 전력선 연, 긴선","2017-10-10 09:00","2017-10-25 18:00","2017-10-10T09:00:00","2017-10-25T18:00:00","연속",null,null,null,201708080176,"-"]
[182,"강원","강릉","속초간성#1 T/L","2017년 간성S/S 170kV 장기사용 GIS 대체공사","속초간성#1TL GIS 대체","2017-10-11 08:30","2017-11-01 18:00","2017-10-11T08:30:00","2017-11-01T18:00:00","연속",null,null,null,201707070330,"-"]
[183,"강원","강릉","신제천주진#1 T/L","2017년 강릉전력지사 154kV GIS 정밀점검공사","주진S/S 신제천주진#1T/L GIS 정밀점검","2017-10-16 09:00","2017-10-17 18:00","2017-10-16T09:00:00","2017-10-17T18:00:00","연속",null,null,null,201708030006,"-"]
[184,"강원","강릉","신제천주진#2 T/L","2017년 강릉전력지사 154kV GIS 정밀점검공사","주진S/S 신제천주진#2T/L GIS 정밀점검","2017-10-18 09:00","2017-10-19 18:00","2017-10-18T09:00:00","2017-10-19T18:00:00","연속",null,null,null,201708030007,"-"]
[185,"강원","강릉","주진평창#1 T/L","2017년 강릉전력지사 154kV GIS 정밀점검공사","주진S/S 주진평창#1T/L GIS 정밀점검","2017-10-23 09:00","2017-10-24 18:00","2017-10-23T09:00:00","2017-10-24T18:00:00","연속",null,null,null,201708030067,"-"]
[186,"강원","강릉","주진평창#2 T/L","2017년 강릉전력지사 154kV GIS 정밀점검공사","주진S/S 주진평창#2T/L GIS 정밀점검","2017-10-25 09:00","2017-10-26 18:00","2017-10-25T09:00:00","2017-10-26T18:00:00","연속",null,null,null,201708030069,"-"]
[187,"강원","강릉","강릉횡계#2 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지중선로 포설 및 접속(No.35~신설 강릉S/S) - No.35~신설CH 전력선 연, 긴선","2017-10-26 09:00","2017-11-10 18:00","2017-10-26T09:00:00","2017-11-10T18:00:00","연속",null,null,null,201708080178,"-"]
[188,"강원","강릉","영동TP강릉 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지중선로 포설 및 접속(No.66.2~신설 강릉S/S) - No.66.2~신설CH 전력선 연, 긴선","2017-10-26 09:00","2017-11-10 18:00","2017-10-26T09:00:00","2017-11-10T18:00:00","연속",null,null,null,201708080180,"-"]
[189,"강원","강릉","강릉횡계#2 T/L","154kV 강릉변전소 옥내화 공사 ","154kV 강릉변전소 옥내화 공사 ","2017-10-13 09:00","2017-10-13 18:00","2017-10-13T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708290131,"-"]
[190,"강원","동해","울진삼척GP#2 T/L","○ 154kV 울진T/L 초기점검 및 정밀점검","○ 154kV 울진T/L 초기점검 및 정밀점검","2017-10-16 09:00","2017-10-20 18:00","2017-10-16T09:00:00","2017-10-20T18:00:00","매일",null,null,null,201708080194,"-"]
[191,"강원","동해","동해정선 T/L","2017년 동해전력지사 170kV GIS 정밀점검공사","1. 정선S/S 동해-정선 T/L GIS 정밀점검(657) 2. LA보통점검","2017-10-16 10:00","2017-10-18 18:00","2017-10-16T10:00:00","2017-10-18T18:00:00","연속",null,null,null,201708090130,"-"]
[192,"강원","동해","동해이원#1 T/L","154kV 이원 등 4개T/L 송전선로용 피뢰기설치공사","송전선로용 피뢰기설치 - No.1~28 (28기, 54SET)","2017-10-18 08:00","2017-10-20 18:00","2017-10-18T08:00:00","2017-10-20T18:00:00","매일",null,null,null,201708230107,"-"]
[193,"강원","동해","울진삼척GP#1 T/L","○ 154kV 울진T/L 초기점검 및 정밀점검","○ 154kV 울진T/L 초기점검 및 정밀점검","2017-10-21 09:00","2017-10-28 18:00","2017-10-21T09:00:00","2017-10-28T18:00:00","매일",null,null,null,201708080193,"-"]
[194,"강원","동해","동해영동TP T/L","2016~17년도 동해전력지사 송전정비협력회사 총액공사","○ 2016~17년도 동해전력지사 송전정비협력회사 총액공사 - No.69~72 전선접속개소 전선교체공사 ○ 154KV 이원 등 4개T/L 송전선로용 피뢰기 설치공사","2017-10-23 08:00","2017-10-29 18:00","2017-10-23T08:00:00","2017-10-29T18:00:00","연속",null,null,null,201708080077,"-"]
[195,"강원","동해","북평영동TP#2 T/L","154kV 이원 등 4개T/L 송전선로용 피뢰기설치공사","154kV 동해-영동TPT/L No.87~92 병가구간 작업자 안전확보위한 휴전 (상단 : 동해-영동TP, 하단 : 북평-영동TP#2)","2017-10-26 08:00","2017-10-26 18:00","2017-10-26T08:00:00","2017-10-26T18:00:00","당일",null,null,null,201708180189,"-"]
[196,"강원","동해","정선영월CC T/L","2017년 동해전력지사 170kV GIS 정밀점검공사","1. 정선S/S 정선-영월CC T/L GIS 정밀점검(667) 2. LA보통점검","2017-10-30 10:00","2017-11-01 18:00","2017-10-30T10:00:00","2017-11-01T18:00:00","연속",null,null,null,201708100132,"-"]
[197,"강원","원주","홍천상남#2 T/L","2016~17년 변전협력회사 총액공사","상남S/S 154kV 홍천상남#2T/L GIS 및 LA,CVT 보통점검 홍천S/S 154kV 홍천상남#2T/L LA,CVT 보통점검","2017-10-12 09:00","2017-10-13 18:00","2017-10-12T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708080087,"-"]
[198,"강원","원주","홍천소양강HP T/L","2016~2017년도 송전정비 협력회사 총액공사","○ 작업내용 : 송전선로용 피뢰기 설치","2017-10-16 08:00","2017-10-20 18:00","2017-10-16T08:00:00","2017-10-20T18:00:00","매일",null,null,null,201708070149,"-"]
[199,"강원","직할","철원화천#1 T/L","기계적 인터록 와이어 교체","제작사(현대중공업) 하자보수","2017-10-16 10:00","2017-10-16 14:00","2017-10-16T10:00:00","2017-10-16T14:00:00","당일",null,null,null,201708020132,"-"]
[200,"강원","직할","춘천열병합S/Y #1BUS TIE CB","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-16 10:00","2017-10-16 18:00","2017-10-16T10:00:00","2017-10-16T18:00:00","당일",null,null,null,201708020009,"-"]
[201,"강원","직할","철원화천#2 T/L","기계적 인터록 와이어 교체","제작사(현대중공업) 하자보수","2017-10-16 14:00","2017-10-16 18:00","2017-10-16T14:00:00","2017-10-16T18:00:00","당일",null,null,null,201708020133,"-"]
[202,"강원","직할","청평PP춘천열병합 T/L","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-17 10:00","2017-10-17 18:00","2017-10-17T10:00:00","2017-10-17T18:00:00","당일",null,null,null,201708020012,"-"]
[203,"강원","직할","남춘천춘천열병합#1 T/L","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-18 10:00","2017-10-18 18:00","2017-10-18T10:00:00","2017-10-18T18:00:00","당일",null,null,null,201708020013,"-"]
[204,"강원","직할","남춘천춘천열병합#2 T/L","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-19 10:00","2017-10-19 18:00","2017-10-19T10:00:00","2017-10-19T18:00:00","당일",null,null,null,201708020014,"-"]
[205,"강원","직할","서홍천춘천열병합 T/L","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-20 10:00","2017-10-20 18:00","2017-10-20T10:00:00","2017-10-20T18:00:00","당일",null,null,null,201708020015,"-"]
[206,"강원","직할","춘천열병합S/Y Step-Up TR CB","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-23 10:00","2017-10-23 18:00","2017-10-23T10:00:00","2017-10-23T18:00:00","당일",null,null,null,201708020017,"-"]
[207,"강원","직할","춘천열병합S/Y Station Aux TR CB","17년 직할 변전협력회사 총액공사","춘천열병합S/Y 170kV GIS 초기점검","2017-10-24 10:00","2017-10-24 18:00","2017-10-24T10:00:00","2017-10-24T18:00:00","당일",null,null,null,201708020016,"-"]
[208,"강원","직할","서홍천청평PP T/L","2017년 하반기 장기미동작 차단기 조작시험","2017년 하반기 장기미동작 차단기 조작시험","2017-10-25 10:00","2017-10-25 18:00","2017-10-25T10:00:00","2017-10-25T18:00:00","당일",null,null,null,201708070320,"-"]
[209,"강원","직할","화천화천HP#2 T/L","2017년 하반기 장기미동작 차단기 조작시험","2017년 하반기 장기미동작 차단기 조작시험","2017-10-31 10:00","2017-10-31 18:00","2017-10-31T10:00:00","2017-10-31T18:00:00","당일",null,null,null,201708070321,"-"]
[210,"강원","태백","태백삼척GP#1 T/L","○ 154kV 울진T/L 초기점검 및 정밀점검","○ 154kV 울진T/L 초기점검 및 정밀점검","2017-10-16 09:00","2017-10-20 18:00","2017-10-16T09:00:00","2017-10-20T18:00:00","매일",null,null,null,201708080189,"-"]
[211,"강원","태백","영월_영월CC T/L","○ 16~17 태백전력지사 변전정비 총액공사","○ 17년 장기미동작 차단기조작시험(영월S/S, 영월CC 양단 CB 조작시험)","2017-10-18 10:00","2017-10-18 18:00","2017-10-18T10:00:00","2017-10-18T18:00:00","당일",null,null,null,201708070072,"-"]
[212,"강원","태백","단양영월CC#1 T/L","○ 16~17 태백전력지사 변전정비 총액공사","○ 17년 장기미동작 차단기 조작시험","2017-10-20 10:00","2017-10-20 14:00","2017-10-20T10:00:00","2017-10-20T14:00:00","당일",null,null,null,201708070078,"-"]
[213,"강원","태백","단양영월CC#2 T/L","○ 16~17 태백전력지사 변전정비 총액공사","○ 17년 장기미동작 차단기 조작시험","2017-10-20 14:00","2017-10-20 18:00","2017-10-20T14:00:00","2017-10-20T18:00:00","당일",null,null,null,201708070079,"-"]
[214,"강원","태백","태백삼척GP#2 T/L","○ 154kV 울진T/L 초기점검 및 정밀점검","○ 154kV 울진T/L 초기점검 및 정밀점검","2017-10-21 09:00","2017-10-28 18:00","2017-10-21T09:00:00","2017-10-28T18:00:00","매일",null,null,null,201708080191,"-"]
[215,"강원","태백","태백고한 T/L","○ 16~17 태백전력지사 변전정비 총액공사","○ 17년 장기미동작 차단기 조작시험","2017-10-25 10:00","2017-10-25 14:00","2017-10-25T10:00:00","2017-10-25T14:00:00","당일",null,null,null,201708070139,"-"]
[216,"강원","태백","고한S/S 154kV #1 BUS TIE CB","○ 16~17 태백전력지사 변전정비 총액공사","○ 17년 장기미동작 차단기 조작시험","2017-10-25 14:00","2017-10-25 18:00","2017-10-25T14:00:00","2017-10-25T18:00:00","당일",null,null,null,201708070068,"-"]
[217,"강원","태백","고한영월 T/L","○ 태백T/L 노후취약 지지물 교체공사","○ 태백T/L 노후취약 지지물 교체공사","2017-10-30 09:00","2017-11-07 18:00","2017-10-30T09:00:00","2017-11-07T18:00:00","매일",null,null,null,201708090176,"-"]
[218,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월ccT/L 49호 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 49호 ○ 철탑교체 : 154kV 2회선용 1기 (49호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (0.905km) ○ 가공지선교체 : OPGW 70㎟ × 1조 (전자제어부)","2017-10-11 08:00","2017-10-13 18:00","2017-10-11 08:00","2017-10-13 18:00","연속",null,null,null,201707310073,"-"]
[219,"충북","직할","왕암가남#1 T/L","2017 직할 154kV GIS 정밀점검 공사","2017 직할 154kV GIS 정밀점검 공사","2017-10-11 09:00","2017-10-12 18:00","2017-10-11 09:00","2017-10-12 18:00","연속",null,null,null,201706130034,"-"]
[220,"충북","직할","단양영월CC#1 T/L","154kV 단양-영월ccT/L 49호 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 49호 ○ 철탑교체 : 154kV 2회선용 1기 (49호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (0.905km) ○ 가공지선교체 : OPGW 70㎟ × 1조 (전자제어부)","2017-10-14 08:00","2017-10-17 18:00","2017-10-14 08:00","2017-10-17 18:00","연속",null,null,null,201707310077,"-"]
[221,"충북","직할","왕암가남#2 T/L","2017 직할 154kV GIS 정밀점검 공사","2017 직할 154kV GIS 정밀점검 공사","2017-10-16 09:00","2017-10-17 18:00","2017-10-16 09:00","2017-10-17 18:00","연속",null,null,null,201708040273,"-"]
[222,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월ccT/L 49호 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 49호 ○ 철탑교체 : 154kV 2회선용 1기 (49호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (0.905km) ○ 가공지선교체 : OPGW 70㎟ × 1조 (전자제어부)","2017-10-18 08:00","2017-10-21 18:00","2017-10-18 08:00","2017-10-21 18:00","연속",null,null,null,201707310078,"-"]
[223,"충북","직할","신제천왕암#2 T/L","변전소 누수개소 보수공사","공사현장 안전거리 확보","2017-10-20 10:00","2017-10-20 18:00","2017-10-20 10:00","2017-10-20 18:00","당일",null,null,null,201708170134,"-"]
[224,"충북","직할","제천영월#1 T/L","2016~17년 직할 송전정비 협력회사 총액공사","피뢰기설치(전구간), 애자련보강(No.62,63)","2017-10-21 08:00","2017-10-26 18:00","2017-10-21 08:00","2017-10-26 18:00","연속",null,null,null,201708140026,"-"]
[225,"충북","직할","신제천왕암#1 T/L","변전소 누수개소 보수공사","공사현장 안전거리 확보","2017-10-23 10:00","2017-10-23 18:00","2017-10-23 10:00","2017-10-23 18:00","당일",null,null,null,201708170133,"-"]
[226,"충북","직할","제천영월#2 T/L","2017 직할 154kV GIS 정밀점검 공사","차단기, 상부부스 정밀점검","2017-10-27 09:00","2017-10-28 18:00","2017-10-27 09:00","2017-10-28 18:00","연속",null,null,null,201707120023,"-"]
[227,"충북","직할","점촌단양 T/L","단양S/S 154kV #3Sh.C 설치공사","단양S/S 154kV #3Sh.C 무부하 가압 시험","2017-10-30 14:00","2017-10-30 15:00","2017-10-29 14:00","2017-10-29 15:00","당일",null,null,null,201708170130,"-"]
[228,"충북","청주","서청주사직#2 T/L","17년 청주전력지사 170kV GIS 정밀점검공사","서청주S/S 서청주-사직#2 T/L GIS CB 정밀점검","2017-10-16 09:30","2017-10-17 18:00","2017-10-16 09:30","2017-10-17 18:00","연속",null,null,null,201708140072,"-"]
[229,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","철탑 2기 교체, 전력선 1.1km 교체 / 회선직결","2017-10-19 08:00","2017-11-03 19:00","2017-10-19 08:00","2017-11-03 19:00","연속",null,null,null,201708080219,"-"]
[230,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","철탑 2기 교체, 전력선 1.1km 교체 / 회선직결","2017-10-19 08:00","2017-11-03 19:00","2017-10-19 08:00","2017-11-03 19:00","연속",null,null,null,201708080217,"-"]
[231,"충북","청주","청원죽림#1 T/L","2017년 청주전력 변전협력회사 총액공사","PT 및 LA 대체작업","2017-10-19 09:30","2017-10-19 18:00","2017-10-19 09:30","2017-10-19 18:00","당일",null,null,null,201708140319,"-"]
[232,"충북","청주","청원부강#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","불량애자교체 20호 (1개)","2017-10-20 08:00","2017-10-20 12:00","2017-10-20 08:00","2017-10-20 12:00","당일",null,null,null,201708140311,"○"]
[233,"충북","청주","청원죽림#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","아킹혼 철거 1~22호 (16기)","2017-10-20 08:00","2017-10-21 19:00","2017-10-20 08:00","2017-10-21 19:00","매일",null,null,null,201708140332,"-"]
[234,"충북","청주","청원부강#1 T/L","154kV 부강-신탄진연결T/L 건설사업","구간 : (기설) 154kV 부강T/L No.16 ~ (기설)154kV 청신T/L No.19 지 지 물 : 철탑 설치 11기, 철거 1기 선로길이 : 설치 2C - 4.9km 전 력 선 : HSTACIR/AW 240㎟ × S × 2C 공시선 : ACSR97㎟×1조(OPGW 97㎟×1조, 별도시행)","2017-10-20 13:00","2017-10-29 17:00","2017-10-20 13:00","2017-10-29 17:00","매일",null,null,null,201708110321,"○"]
[235,"충북","청주","청원오송#2 T/L","2017년 청주전력 변전협력회사 총액공사","LA 및 PT 보통점검","2017-10-31 09:30","2017-10-31 18:00","2017-10-31 09:30","2017-10-31 18:00","당일",null,null,null,201708140327,"-"]
[236,"충북","충주","진천덕산#1 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(진천-덕산#1)","전선접속개소해소를 위한 전선교체(154kV 진천-덕산 #1T/L No.7~8, 20~25)","2017-10-11 07:00","2017-10-14 18:00","2017-10-11 07:00","2017-10-14 18:00","연속",null,null,null,201708170115,"○"]
[237,"충북","충주","진천덕산#2 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(진천-덕산#2)","전선접속개소해소를 위한 전선교체(154kV 진천-덕산 #2T/L No.8~9, 20~25)","2017-10-15 07:00","2017-10-18 18:00","2017-10-15 07:00","2017-10-18 18:00","연속",null,null,null,201708170117,"○"]
[238,"충북","충주","신진천S/S 154kV #3 BUS TIE GIS","16-17년 변전정비 협력회사 총액공사","GIS 보통점검","2017-10-18 10:00","2017-10-18 18:00","2017-10-18 10:00","2017-10-18 18:00","당일",null,null,null,201708140296,"-"]
[239,"충북","충주","증평초정#1 T/L","154kV 증평S/S GIS화 공사","증평-초정#1T/L GIS 이설작업 ","2017-10-13 08:00","2017-10-24 18:00","2017-10-13 08:00","2017-10-24 18:00","연속",null,null,null,201708280131,"-"]
[240,"대전충남","대전","신옥천남대전#3 T/L","신옥천, 남대전S/S 신옥천-남대전#3T/L 보호반 교체공사","신옥천, 남대전S/S 신옥천-남대전#3T/L 보호반 교체공사","2017-10-16 09:00","2017-10-18 18:00","2017-10-16T09:00:00","2017-10-18T18:00:00","연속",null,null,null,201708080124,"-"]
[241,"대전충남","대전","신옥천남대전#4 T/L","신옥천, 남대전S/S 신옥천-남대전#4T/L 보호반 교체공사","신옥천, 남대전S/S 신옥천-남대전#4T/L 보호반 교체공사","2017-10-23 09:00","2017-10-25 18:00","2017-10-23T09:00:00","2017-10-25T18:00:00","연속",null,null,null,201708080125,"-"]
[242,"대전충남","서산","서산태안화력 T/L","'17년 변전협력회사 총액공사","서산S/S 154kV 서산-태안화력T/L LA 보통점검","2017-10-11 09:00","2017-10-11 18:00","2017-10-11T09:00:00","2017-10-11T18:00:00","당일",null,null,null,201708140094,"-"]
[243,"대전충남","서산","서산태안 T/L","[송전] 154kV 서산-태안T/L 피뢰기 설치 공사","154kV 서산-태안T/L No.1-14 피뢰기 설치 공사","2017-10-12 07:00","2017-10-13 18:00","2017-10-12T07:00:00","2017-10-13T18:00:00","매일",null,null,null,201708100169,"-"]
[244,"대전충남","서산","대산석문#1 T/L","[송전]154kV 대산-석문#1T/L 정밀점검","154kV 대산-석문#1T/L No.1-48 정밀점검","2017-10-15 07:00","2017-10-17 18:00","2017-10-15T07:00:00","2017-10-17T18:00:00","매일",null,null,null,201708100185,"-"]
[245,"대전충남","서산","석문당진화력#1 T/L","[송전] 154kV 대산-석문#1T/L 정밀점검","154kV 대산-석문#1T/L 정밀점검 4회선 병가구간 안전거리 확보 휴전","2017-10-15 07:00","2017-10-15 18:00","2017-10-15T07:00:00","2017-10-15T18:00:00","당일",null,null,null,201708230057,"-"]
[246,"대전충남","서산","대산석문#2 T/L","[송전]154kV 대산-석문#2T/L 정밀점검","154kV 대산-석문#2T/L No.1-48 정밀점검","2017-10-19 07:00","2017-10-22 18:00","2017-10-19T07:00:00","2017-10-22T18:00:00","매일",null,null,null,201708230044,"-"]
[247,"대전충남","서산","석문당진화력#1 T/L","[송전]154kV 석문-당진화력#1T/L 정밀점검","154kV 석문-당진화력#1T/L No.1-24 정밀점검","2017-10-21 07:00","2017-10-23 18:00","2017-10-21T07:00:00","2017-10-23T18:00:00","매일",null,null,null,201708230047,"-"]
[248,"대전충남","서산","석문당진화력#2 T/L","[송전]154kV 석문-당진화력#2T/L 정밀점검","154kV 석문-당진화력#2T/L No.1-24 정밀점검","2017-10-27 07:00","2017-10-28 18:00","2017-10-27T07:00:00","2017-10-28T18:00:00","매일",null,null,null,201708230048,"-"]
[249,"대전충남","서산","대산석문#1 T/L","[송전]154kV 석문-당진화력#2T/L 정밀점검","154kV 석문-당진화력#2T/L 정밀점검 4회선 병가구간 안전거리 확보 휴전","2017-10-28 07:00","2017-10-28 18:00","2017-10-28T07:00:00","2017-10-28T18:00:00","당일",null,null,null,201708230061,"-"]
[250,"대전충남","세종","덕진송강#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2017-10-30 09:30","2017-10-30 18:00","2017-10-30T09:30:00","2017-10-30T18:00:00","당일",null,null,null,201708140034,"-"]
[251,"대전충남","세종","덕진송강#2 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2017-10-31 09:30","2017-10-31 18:00","2017-10-31T09:30:00","2017-10-31T18:00:00","당일",null,null,null,201708140035,"-"]
[252,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-10-10 09:00","2017-10-13 18:00","2017-10-10T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201705240068,"-"]
[253,"대전충남","아산","풍세장재#1 T/L","풍세S/S 154kV 풍세-장재#1T/L 보호배전반 교체","○ 154kV 풍세-장재#1T/L 보호배전반 교체","2017-10-10 09:00","2017-10-13 18:00","2017-10-10T09:00:00","2017-10-13T18:00:00","연속",null,null,null,201708100276,"-"]
[254,"대전충남","아산","아산온양#2 T/L","[송전]154kV 아산-온양T/L 19,20호 안전이격확보공사","- 19호 신설 - 20호 인클로징 - 기타 부대공사","2017-10-14 07:00","2017-10-15 18:00","2017-10-14T07:00:00","2017-10-15T18:00:00","연속",null,null,null,201708080128,"-"]
[255,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-10-14 10:00","2017-10-20 18:00","2017-10-14T10:00:00","2017-10-20T18:00:00","연속",null,null,null,201705240071,"-"]
[256,"대전충남","아산","풍세장재#2 T/L","풍세S/S 154kV 풍세-장재#2T/L 보호배전반 교체","○ 154kV 풍세-장재#2T/L 보호배전반 교체","2017-10-16 09:00","2017-10-19 18:00","2017-10-16T09:00:00","2017-10-19T18:00:00","연속",null,null,null,201708100278,"-"]
[257,"대전충남","아산","불당서천안#1 T/L","불당S/S 154kV 불당-서천안#1T/L GIS 정밀점검공사","○ 154kV 불당-서천안#1T/L GIS 정밀점검공사","2017-10-21 09:00","2017-10-22 18:00","2017-10-21T09:00:00","2017-10-22T18:00:00","당일",null,null,null,201708100251,"-"]
[258,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-10-21 09:00","2017-10-30 09:00","2017-10-21T09:00:00","2017-10-30T09:00:00","연속",null,null,null,201705240075,"-"]
[259,"대전충남","아산","신온양한샘#2 T/L","154kV 한샘S/S #4M.Tr 증설공사","○ #4M.Tr용 GIS 설치관련 근접선로 안전이격확보","2017-10-25 09:00","2017-10-25 18:00","2017-10-25T09:00:00","2017-10-25T18:00:00","당일",null,null,null,201708110262,"-"]
[260,"대전충남","아산","아산온양#2 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치 3. 온양#2T/L 인출변경 시험가압 (온양#1T/L측으로 이설)","2017-10-28 09:00","2017-10-30 09:00","2017-10-28T09:00:00","2017-10-30T09:00:00","연속",null,null,null,201707260053,"-"]
[261,"대전충남","아산","신온양한샘#2 T/L","154kV 한샘S/S #4M.Tr 증설공사","○ #4M.Tr용 GIS 설치관련 근접선로 안전이격확보","2017-10-30 09:00","2017-10-30 18:00","2017-10-30T09:00:00","2017-10-30T18:00:00","연속",null,null,null,201708110269,"-"]
[262,"대전충남","아산","예산응봉#1 T/L","154kV 예산-음봉T/L 안전거리 확보공사","154kV 예산-음봉T/L 안전거리 확보공사 - No.13 철탑 암 구조변경","2017-10-16 06:00","2017-10-17 18:00","2017-10-16T06:00:00","2017-10-17T18:00:00","연속",null,null,null,201708310063,"-"]
[263,"대전충남","아산","예산응봉#2 T/L","154kV 예산-음봉T/L 안전거리 확보공사","154kV 예산-음봉T/L 안전거리 확보공사 - No.13 철탑 암 구조변경","2017-10-16 06:00","2017-10-17 18:00","2017-10-16T06:00:00","2017-10-17T18:00:00","연속",null,null,null,201708310064,"-"]
[264,"대전충남","아산","인주탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","- 작업내용 : 345kV 북당진-신탕정T/L No.53~59 가선 작업 - 휴전사유 : 345kV 북당진-신탕정T/L No.53~59 가선(연선) 작업시 기설 154kV 인주-탕정#1T/L 근접(4.7m)에 따른 휴전작업을 통한 가선작업시 안전사고 예방","2017-10-30 09:00","2017-11-17 18:00","2017-10-30T09:00:00","2017-11-17T18:00:00","연속",null,null,null,201708090207,"-"]
[265,"대전충남","아산","한샘둔포#2 T/L","한샘S/S 154kV 한샘-둔포#2T/L 보호배전반 교체","○ 154kV 한샘-둔포#2T/L 보호배전반 교체","2017-10-30 09:00","2017-11-02 18:00","2017-10-30T09:00:00","2017-11-02T18:00:00","연속",null,null,null,201708100283,"-"]
[266,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천화력T/L 정밀점검","○ 점검구간 : No.7~91-2 ○ 피뢰기설치공사 병행작업(9.17~21)","2017-10-16 07:00","2017-10-23 18:00","2017-10-16T07:00:00","2017-10-23T18:00:00","매일",null,null,null,201708070307,"-"]
[267,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천화력T/L 정밀점검","점검구간 : No.7~91-2","2017-10-16 07:00","2017-10-23 18:00","2017-10-16T07:00:00","2017-10-23T18:00:00","매일",null,null,null,201708070311,"-"]
[268,"대전충남","청양","대천서천화력#2 T/L","154kV 옥산-서천화력T/L 정밀점검","○ 작업구간 : No.7~91-2","2017-10-24 07:00","2017-10-31 18:00","2017-10-24T07:00:00","2017-10-31T18:00:00","매일",null,null,null,201708100101,"-"]
[269,"대전충남","청양","옥산서천화력#2 T/L","154kV 옥산-서천화력T/L 정밀점검","○ 작업구간 : No.7~91-2","2017-10-24 07:00","2017-10-31 18:00","2017-10-24T07:00:00","2017-10-31T18:00:00","매일",null,null,null,201708100100,"-"]
[270,"전북","군산","군산동군산#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - 군산-동군산#1T/L, 동군산-군산CC#2T/L GIS","2017-10-10 08:00","2017-11-02 18:00","취소","취소","연속",null,null,null,201708090056,"-"]
[271,"전북","군산","동군산군산복합#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - 군산-동군산#1T/L, 동군산-군산CC#2T/L GIS","2017-10-10 08:00","2017-11-02 18:00","취소","취소","연속",null,null,null,201708090057,"-"]
[272,"전북","군산","동군산장항#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - 동군산-장항#2T/L, #2M.Tr 1차 GIS","2017-10-10 08:00","2017-11-02 18:00","2017-10-10 08:00","2017-11-02 18:00","연속",null,null,null,201708220002,"-"]
[273,"전북","군산","팔봉영등#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 2차 공정 - 팔봉-영등#1T/L교체","2017-10-10 09:00","2017-10-22 18:00","2017-10-10 09:00","2017-10-22 18:00","연속",null,null,"신뢰도개선",201708160112,"-"]
[274,"전북","군산","군공군산복합#1 T/L","군공-군산CC#1T/L","차단기 조작시험","2017-10-11 09:00","2017-10-11 15:00","2017-10-11 09:00","2017-10-11 15:00","당일",null,null,null,201708160321,"-"]
[275,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - #2BUS 시험가압","2017-10-11 18:00","2017-10-11 20:00","2017-10-11 18:00","2017-10-11 20:00","당일",null,null,null,201708090063,"-"]
[276,"전북","군산","군공군산복합#2 T/L","군공-군산CC#2T/L","차단기 조작시험","2017-10-12 09:00","2017-10-12 14:00","2017-10-12 09:00","2017-10-12 14:00","당일",null,null,null,201708160336,"-"]
[277,"전북","군산","군산이리#1 T/L","군산-이리#1T/L","차단기 조작시험","2017-10-12 09:00","2017-10-12 11:00","2017-10-12 09:00","2017-10-12 11:00","당일",null,null,null,201708160293,"-"]
[278,"전북","군산","군산복합S/Y S/T T/L GIS","군산복합 S/T T/L","차단기 조작시험","2017-10-12 14:00","2017-10-12 16:00","2017-10-12 14:00","2017-10-12 16:00","당일",null,null,null,201708160346,"-"]
[279,"전북","군산","군산이리#2 T/L","군산-이리#2T/L","차단기 조작시험","2017-10-12 16:00","2017-10-12 18:00","2017-10-12 16:00","2017-10-12 18:00","당일",null,null,null,201708160294,"-"]
[280,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 2차 공정 - 팔봉-영등#1T/L교체 #2BUS 무부하 가압","2017-10-12 16:00","2017-10-12 18:00","2017-10-12 16:00","2017-10-12 18:00","당일",null,null,null,201708160114,"-"]
[281,"전북","군산","군산영등#1 T/L","군산-영등#1T/L","차단기 조작시험","2017-10-13 09:00","2017-10-13 11:00","2017-10-13 09:00","2017-10-13 11:00","당일",null,null,null,201708160351,"-"]
[282,"전북","군산","군산영등#2 T/L","군산-영등#2T/L","차단기 조작시험","2017-10-13 11:00","2017-10-13 16:00","2017-10-13 11:00","2017-10-13 16:00","당일",null,null,null,201708160353,"-"]
[283,"전북","군산","팔봉두마#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 2차 공정 - 팔봉-영등#1교체 #1BUS 무부하 가압","2017-10-16 18:00","2017-10-17 18:00","2017-10-16 18:00","2017-10-17 18:00","연속",null,null,null,201708160116,"-"]
[284,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - #1BUS 시험가압","2017-10-22 08:00","2017-10-23 08:00","2017-10-22 08:00","2017-10-23 08:00","당일",null,null,null,201708090065,"-"]
[285,"전북","군산","팔봉영등#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 2차 공정 - 팔봉-영등#1T/L교체","2017-10-23 09:00","2017-11-04 18:00","2017-10-23 09:00","2017-11-04 18:00","연속",null,null,null,201708170116,"-"]
[286,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 3차 공정 - 팔봉-영등#2T/L교체 #2BUS 무부하 가압","2017-10-25 16:00","2017-10-25 18:00","2017-10-25 16:00","2017-10-25 18:00","당일",null,null,null,201708160120,"-"]
[287,"전북","군산","팔봉두마#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 3차 공정 - 팔봉-영등#2교체 #1BUS 무부하 가압","2017-10-29 18:00","2017-10-30 18:00","2017-10-29 18:00","2017-10-30 18:00","연속",null,null,null,201708160123,"-"]
[288,"전북","김제","신김제S/S 60-61-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-10-03 09:00","2017-10-09 18:00","2017-10-03 09:00","2017-10-09 18:00","연속",null,null,null,201708160326,"-"]
[289,"전북","김제","신김제S/S 65-66-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-10-03 09:00","2017-10-09 18:00","2017-10-03 09:00","2017-10-09 18:00","연속",null,null,null,201708160330,"-"]
[290,"전북","김제","신김제S/S 61-62-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-10-06 09:00","2017-10-09 18:00","2017-10-06 09:00","2017-10-09 18:00","연속",null,null,null,201708160331,"-"]
[291,"전북","김제","신김제S/S 66-67-0 SEC CB","신김제S/S 154kV 모선보호반 교체공사","신김제S/S 154kV 모선보호반 교체공사","2017-10-06 09:00","2017-10-09 18:00","2017-10-06 09:00","2017-10-09 18:00","연속",null,null,null,201708160333,"-"]
[292,"전북","김제","신김제남전주#1 T/L","남전주S/S #3M.Tr 1차 차단기 교체공사","GIS 철거 안전이격 확보","2017-10-10 09:00","2017-10-19 18:00","2017-10-10 09:00","2017-10-19 18:00","연속",null,null,null,201708090228,"-"]
[293,"전북","김제","고창영광 T/L","154kV 영광-고창T/L 정밀점검","154kV 영광-고창T/L 정밀점검(No.46~155)","2017-10-10 09:00","2017-10-14 18:00","2017-10-10 09:00","2017-10-14 18:00","매일",null,null,null,201708160103,"-"]
[294,"전북","김제","정주고창#1 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","154kV 정주-고창T/L No.24~26, 28~33, 34~37호 철탑 3기 및 전력선 교체","2017-10-14 09:00","2017-10-17 18:00","2017-10-14 09:00","2017-10-17 18:00","연속",null,null,null,201708230125,"-"]
[295,"전북","김제","정주고창#2 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","154kV 정주-고창T/L No.24~26, 28~33, 34~37호 철탑 3기 및 전력선 교체","2017-10-18 07:00","2017-10-27 18:00","2017-10-18 07:00","2017-10-27 18:00","연속",null,null,null,201708230127,"-"]
[296,"전북","김제","신김제전주#2 T/L","신김제-전주#2T/L 관형주 정밀점검공사","관형주(No.36,37,38,48호) 정밀점검","2017-10-18 09:00","2017-10-18 18:00","2017-10-18 09:00","2017-10-18 18:00","당일",null,null,null,201708220076,"-"]
[297,"전북","김제","신김제남전주#1 T/L","남전주S/S #3M.Tr 1차 차단기 교체공사","GIS 철거 안전이격 확보","2017-10-24 09:00","2017-10-26 18:00","2017-10-24 09:00","2017-10-26 18:00","매일",null,null,null,201708100016,"-"]
[298,"전북","김제","정주고창#1 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","154kV 정주-고창T/L No.24~26, 28~33, 34~37호 철탑 3기 및 전력선 교체","2017-10-28 07:00","2017-11-06 18:00","2017-10-28 07:00","2017-11-06 18:00","연속",null,null,null,201708230126,"-"]
[299,"전북","직할","무주진안 T/L","무주진안 T/L","1. 무주, 진안S/S 154kV 차단기 점검","2017-10-17 10:00","2017-10-17 18:00","2017-10-17 10:00","2017-10-17 18:00","당일",null,null,null,201708160082,"-"]
[300,"전북","직할","신김제전주#1 T/L","신김제전주#1 T/L","1. 전주S/S 154kV 차단기 점검","2017-10-19 09:00","2017-10-19 18:00","2017-10-19 09:00","2017-10-19 18:00","당일",null,null,null,201708160086,"-"]
[301,"전북","직할","이리전주#1 T/L","이리전주#1 T/L","1. 전주S/S 154kV 차단기 점검","2017-10-20 10:00","2017-10-20 18:00","2017-10-20 10:00","2017-10-20 18:00","당일",null,null,null,201708160087,"-"]
[302,"전북","직할","북전주봉동#2 T/L","관내S/S 154kV 차단기 조작시험","개폐타임 측정","2017-10-21 10:00","2017-10-21 18:00","2017-10-21 10:00","2017-10-21 18:00","당일",null,null,null,201708110477,"-"]
[303,"전북","직할","팔봉봉동#1 T/L","관내S/S 154kV 차단기 조작시험","개폐타임 측정","2017-10-22 10:00","2017-10-22 13:00","2017-10-22 10:00","2017-10-22 13:00","당일",null,null,null,201708110479,"-"]
[304,"전북","직할","팔봉봉동#2 T/L","관내S/S 154kV 차단기 조작시험","개폐타임 측정","2017-10-22 13:00","2017-10-22 18:00","2017-10-22 13:00","2017-10-22 18:00","당일",null,null,null,201708110480,"-"]
[305,"전북","직할","북전주봉동#1 T/L","관내S/S 154kV 차단기 조작시험","개폐타임 측정","2017-10-28 10:00","2017-10-28 13:00","2017-10-28 10:00","2017-10-28 13:00","당일",null,null,null,201708110483,"-"]
[306,"전북","직할","북전주진안 T/L","154kV 북전주-진안T/L 피뢰기 대체공사","장기사용 기타설비 대체공사(154kV 피뢰기 교체공사)","2017-10-18 10:00","2017-10-18 18:00","2017-10-18 10:00","2017-10-18 18:00","당일",null,null,null,201708250103,"-"]
[307,"광주전남","강진","신강진대불#2 T/L","신강진S/S 154kV 신강진-대불#1T/L(취약설비 GIS화 )","공사명 : 신강진S/S 154kV 옥외철구 GIS설치 공사 -신설GIS 부싱설치시 활선근접","2017-10-01 10:00","2017-10-01 12:00","2017-10-01 10:00","2017-10-01 12:00","당일",null,null,null,201708040020,"-"]
[308,"광주전남","강진","강진남창#2 T/L","154kV 강진-남창#2T/L(피뢰기 설치공사)","154kV 강진-남창#2T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사 : 주작업 - 16~17년 송전정비 협력회사 총액공사(S.B댐퍼 설치작업) : 병행작업","2017-10-13 07:00","2017-10-22 18:00","2017-10-13 07:00","2017-10-22 18:00","매일",null,null,null,201708080162,"-"]
[309,"광주전남","강진","해남해남CS#1 T/L","154kV 해남-해남C/S #1T/L(강진 변전협력회사 총액공사)","해남-해남C/S #1T/L LA 보통점검","2017-10-16 09:00","2017-10-16 14:00","2017-10-16 09:00","2017-10-16 14:00","당일",null,null,null,201708140083,"-"]
[310,"광주전남","강진","해남해남CS#2 T/L","154kV 해남-해남CS#2T/L(피뢰기 설치공사)","154kV 해남-해남CS#2T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2017-10-23 07:00","2017-10-28 18:00","2017-10-23 07:00","2017-10-28 18:00","매일",null,null,null,201708080160,"-"]
[311,"광주전남","강진","강진남창#1 T/L","154kV 강진남창#1 T/L(댐퍼설치공사)","154kV 강진남창#1 T/L(댐퍼설치공사) - 송전정비 협력회사 총액공사 (댐퍼설치공사)","2017-10-23 08:00","2017-10-27 18:00","2017-10-23 08:00","2017-10-27 18:00","매일",null,null,null,201708160061,"-"]
[312,"광주전남","강진","남창해남CS#2 T/L","154kV 남창-해남CS#2T/L(피뢰기 설치공사)","154kV 남창-해남CS#2T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2017-10-28 09:00","2017-10-30 18:00","2017-10-28 09:00","2017-10-30 18:00","매일",null,null,null,201708080150,"-"]
[313,"광주전남","강진","남창해남CS#1 T/L","154kV 남창-해남CS#1T/L(피뢰기 설치공사)","154kV 남창-해남CS#1T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2017-10-31 07:00","2017-11-04 18:00","2017-10-31 07:00","2017-11-04 18:00","매일",null,null,null,201708080147,"-"]
[314,"광주전남","광주","신광주곡성#2 T/L","2016~17년 광주전력지사 송전정비협력회사 총액공사","철탑교체 : 신광주-곡성T/L 1기( No.115호 )","2017-10-01 07:00","2017-10-03 18:00","2017-10-01 07:00","2017-10-03 18:00","연속",null,null,null,201708170006,"-"]
[315,"광주전남","광주","곡성남원#2 T/L","곡성S/S 154kV 곡성-남원#2T/L GIS 교체공사","곡성S/S 154kV 곡성-남원#2T/L GIS 교체공사","2017-10-10 09:00","2017-11-04 18:00","2017-10-10 09:00","2017-11-04 18:00","연속",null,null,null,201708040050,"-"]
[316,"광주전남","광주","남광주화순#1 T/L","2017년 변전협력회사 총액공사","남광주화순#1 T/L LA교체","2017-10-11 09:00","2017-10-11 18:00","2017-10-11 09:00","2017-10-11 18:00","당일",null,null,null,201708220212,"-"]
[317,"광주전남","광주","신광주곡성#1 T/L","곡성S/S #1M.Tr 1차 및 곡성-남원#2T/L GIS 교체공사","곡성S/S 154kV #2BUS 무부하가압","2017-10-12 09:00","2017-10-12 10:00","2017-10-12 09:00","2017-10-12 10:00","당일",null,null,null,201708040052,"-"]
[318,"광주전남","광주","북광주계림#1 T/L","2017년 광주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2017-10-16 09:00","2017-10-17 18:00","2017-10-16 09:00","2017-10-17 18:00","당일",null,null,null,201707310015,"-"]
[319,"광주전남","광주","북광주계림#2 T/L","2017년 광주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2017-10-18 09:00","2017-10-19 18:00","2017-10-18 09:00","2017-10-19 18:00","당일",null,null,null,201707310016,"-"]
[320,"광주전남","광주","신광주곡성#1 T/L","곡성S/S #1M.Tr 1차 및 곡성-남원#2T/L GIS 교체공사","곡성S/S 154kV #1BUS 무부하가압","2017-10-20 18:00","2017-10-21 18:00","2017-10-20 18:00","2017-10-21 18:00","연속",null,null,null,201708040055,"-"]
[321,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림승주T/L 안전이격거리확보공사","철탑교체 : 4기 (No.51, 52, 53, 54) 전선교체 : No.50~52, 54~55","2017-10-23 08:00","2017-10-24 18:00","2017-10-23 08:00","2017-10-24 18:00","연속",null,null,null,201708160146,"○"]
[322,"광주전남","광주","북광주일곡#1 T/L","2017년 광주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2017-10-23 09:00","2017-10-24 18:00","2017-10-23 09:00","2017-10-24 18:00","당일",null,null,null,201707310017,"-"]
[323,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","154kV 계림승주T/L 안전이격거리확보공사","철탑교체 : 4기 (No.51, 52, 53, 54) 전선교체 : No.50~52, 54~55","2017-10-25 08:00","2017-11-05 18:00","2017-10-25 08:00","2017-11-05 18:00","연속",null,null,null,201708160149,"○"]
[324,"광주전남","광주","북광주일곡#2 T/L","2017년 광주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2017-10-25 09:00","2017-10-26 18:00","2017-10-25 09:00","2017-10-26 18:00","당일",null,null,null,201707310018,"-"]
[325,"광주전남","광주","신화순매월#2 T/L","2017년 변전협력회사 총액공사","신화순매월#2 T/L LA교체","2017-10-30 09:00","2017-10-30 18:00","2017-10-30 09:00","2017-10-30 18:00","당일",null,null,null,201708220213,"-"]
[326,"광주전남","광주","신화순매월#1 T/L","2017년 변전협력회사 총액공사","신화순매월#1 T/L LA교체","2017-10-31 09:00","2017-10-31 18:00","2017-10-31 09:00","2017-10-31 18:00","당일",null,null,null,201708220214,"-"]
[327,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농T/L(170kV GIS 대체공사)","170kV GIS 대체","2017-10-16 09:00","2017-11-09 18:00","2017-10-16 09:00","2017-11-09 18:00","연속",null,null,null,201708090070,"-"]
[328,"광주전남","순천","여천여수#2 T/L","154kV 여천-여수#2 T/L 보호배전반 대체","17년 순천전력 변전협력 총액공사 - 154kV 여천-여수#2 T/L 보호배전반 대체","2017-10-11 10:00","2017-10-13 18:00","2017-10-11 10:00","2017-10-13 18:00","연속",null,null,null,201708080123,"-"]
[329,"광주전남","순천","여천호남TP#2 T/L","154kV 여천-호남TP#2 T/L","17년 순천전력 변전협력 총액공사 - 여천S/S LA(ABC)대체 및 리드선 교체 -호남화력 LA 보통점검","2017-10-19 10:00","2017-10-20 17:00","2017-10-19 10:00","2017-10-20 17:00","연속",null,null,null,201708140211,"-"]
[330,"광주전남","순천","율촌화치#1 T/L","154kV 율촌-화치#1 T/L 보호배전반 대체","17년 순천전력 변전협력 총액공사 - 154kV 율촌-화치#1 T/L 보호배전반 대체","2017-10-23 10:00","2017-10-25 18:00","2017-10-23 10:00","2017-10-25 18:00","연속",null,null,null,201708080119,"-"]
[331,"광주전남","순천","율촌화치#2 T/L","154kV 율촌-화치#2 T/L 보호배전반 대체","17년 순천전력 변전협력 총액공사 - 154kV 율촌-화치#2 T/L 보호배전반 대체","2017-10-26 10:00","2017-10-28 18:00","2017-10-26 10:00","2017-10-28 18:00","연속",null,null,null,201708080121,"-"]
[332,"광주전남","순천","순천율촌#1 T/L","154kV 순천S/S 변전설비 철거공사","1. 154kV 순천S/S 옥외 변전설비 철거공사 - 순천-율촌#1,2T/L CB 철거","2017-10-30 09:00","2017-10-31 18:00","2017-10-30 09:00","2017-10-31 18:00","당일",null,null,null,201708040016,"○"]
[333,"광주전남","직할","비아하남#2(고려시멘트T분기) T/L","154kV 비아하남#2T/L 전선접속개소 해소공사","154kV 비아하남#2T/L No.53~65 전선접속개소 해소공사","2017-10-10 08:00","2017-10-17 18:00","2017-10-10 08:00","2017-10-17 18:00","연속",null,null,null,201708010106,"-"]
[334,"광주전남","직할","하남장성#2 T/L","154kV 하남장성#2T/L 안전이격거리 확보(비아-하남#2 전선교체)","154kV 비아하남#2T/L No.53~65 전선접속개소 해소공사 관련 하남장성#2T/L 안전 이격거리 확보","2017-10-10 08:00","2017-10-17 18:00","2017-10-11 08:00","2017-10-19 18:00","연속",null,null,null,201708010107,"-"]
[335,"광주전남","직할","하남장성#1 T/L","154kV 하남장성#1T/L 안전이격거리 확보(비아-하남#2 전선교체)","154kV 비아하남#2T/L No.54~55 구간 전선접속개소 해소공사 관련 하남장성#1T/L 안전 이격거리 확보","2017-10-11 08:00","2017-10-12 18:00","2017-10-14 08:00","2017-10-15 18:00","매일",null,null,"신뢰도개선",201708010108,"-"]
[336,"대구","경산","신경산노변 T/L","신경산S/S 170kV 장기사용 GIS 대체관련 #66BUS 테스트 선로","추석연휴(10/3~10/09)기간중, #66BUS 운전시행 관련, #66BUS 사전 건전성 확인관련 테스트 선로","2017-10-02 16:00","2017-10-02 18:00","2017-10-02 16:00","2017-10-02 18:00","당일",null,null,null,201708160100,"-"]
[337,"대구","경산","경산S/S ESS #1 EM.Tr A","경산S/S ESS 주변압기 활용 자동복구시스템 시연회","경산S/S ESS 주변압기 활용 자동복구시스템 구축관련 시연회","2017-10-19 09:00","2017-10-19 18:00","2017-10-19 09:00","2017-10-19 18:00","당일",null,null,null,201708240038,"-"]
[338,"대구","달성","대구염색 T/L","폴리머애관 교체공사","EBA자기애관을 폴리머애관으로 교체","2017-10-05 09:00","2017-10-07 13:00","2017-10-05 09:00","2017-10-07 13:00","연속",null,null,null,201707070119,"-"]
[339,"대구","달성","성서달성#2 T/L","성서-달성T/L 접속개소 전력선 교체공사","- 성서-달성T/L No.16-20 접속개소 전력선 교체공사 - 성서-달성T/L No. 1~20 송전선로 피뢰기 설치","2017-10-07 07:00","2017-10-09 18:00","2017-10-07 07:00","2017-10-09 18:00","연속",null,null,null,201708020175,"-"]
[340,"대구","달성","다사달서#2 T/L","달서S/S 170kV GIS 대체공사","달서S/S 170kV GIS 대체공사","2017-10-12 09:00","2017-10-31 18:00","2017-10-12 09:00","2017-10-31 18:00","연속",null,null,null,201708070236,"-"]
[341,"대구","직할","동인내당#1 T/L","동인S/S 인출 OF선종교체공사","동인내당#1T/L OF케이블 선종교체공사","2017-10-16 08:00","2017-11-15 18:00","2017-10-16 08:00","2017-11-15 18:00","연속",null,null,null,201708170089,"-"]
[342,"대구","직할","노변효목#1 T/L","보호반 교체","보호반 교체","2017-10-23 09:30","2017-10-25 14:00","2017-10-23 09:30","2017-10-25 14:00","연속",null,null,null,201708040188,"-"]
[343,"대구","직할","노변효목#2 T/L","보호반 교체","보호반 교체","2017-10-25 14:00","2017-10-27 18:00","2017-10-25 14:00","2017-10-27 18:00","연속",null,null,null,201708040189,"-"]
[344,"대구","직할","내당두류#1 T/L","차단기 개폐타임 측정","차단기 개폐타임 측정","2017-10-26 09:30","2017-10-26 11:00","2017-10-15 09:30","2017-10-15 11:00","당일",null,null,null,201708170137,"-"]
[345,"대구","직할","내당두류#2 T/L","차단기 개폐타임 측정","차단기 개폐타임 측정","2017-10-26 11:00","2017-10-26 14:00","2017-10-15 11:00","2017-10-15 14:00","당일",null,null,null,201708170138,"-"]
[346,"대구","칠곡","관음구암#1 T/L","2016~17 대구지역본부 직할 가공송전 협력회사 총액공사","154kV 관음-구암#1T/L No.1~45 정밀점검","2017-10-19 08:00","2017-10-23 18:00","2017-10-21 08:00","2017-10-25 18:00","연속",null,null,null,201708070023,"-"]
[347,"대구","칠곡","칠곡인동#1 T/L","154kV 서대구-남인동#1,2T/L 애자교체공사 관련 안전확보 휴전","국산애자교체공사(154kV 서대구-남인동#1,2T/L No.1-1 부하측) 관련 안전확보 휴전","2017-10-22 07:30","2017-10-22 18:00","2017-10-22 07:30","2017-10-22 18:00","당일",null,null,null,201708070088,"-"]
[348,"대구","칠곡","칠곡인동#2 T/L","154kV 서대구-남인동#1,2T/L 애자교체공사 관련 안전확보 휴전","국산애자교체공사(154kV 서대구-남인동#1,2T/L No.1-1 부하측) 관련 안전확보 휴전","2017-10-22 07:30","2017-10-22 18:00","2017-10-22 07:30","2017-10-22 18:00","당일",null,null,null,201708080208,"-"]
[349,"대구","칠곡","관음구암#2 T/L","2016~17 대구지역본부 직할 가공송전 협력회사 총액공사","154kV 관음-구암#2T/L No.1~45 정밀점검","2017-10-23 08:00","2017-10-29 18:00","2017-10-25 08:00","2017-10-31 18:00","연속",null,null,null,201708070024,"-"]
[350,"대구","포항","청하영덕#1 T/L","154kV 청하-영덕T/L 피뢰기설치공사","154kV 청하-영덕T/L 피뢰기설치 No.1~No.136","2017-10-16 09:00","2017-10-29 18:00","2017-10-16 09:00","2017-10-29 18:00","연속",null,null,null,201708080183,"-"]
[351,"대구","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.28-32) 5기 철거, 4기설치(양회선 휴전)","2017-10-18 07:00","2017-10-27 18:00","취소","취소","연속",null,null,null,201708070264,"-"]
[352,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","154kV 아화-건천T/L 안전이격확보 철탑교체공사 (No.28-32) 5기 철거, 4기설치(양회선 휴전)","2017-10-18 07:00","2017-10-27 18:00","취소","취소","연속",null,null,null,201708070269,"-"]
[353,"경북","영주","문경단양 T/L","154kV 단양T/L 노후취약지지물 교체공사","노후취약지지물교체,피뢰기설치","2017-10-20 07:00","2017-10-22 18:00","2017-10-31 07:00","2017-11-02 18:00","연속",null,null,null,201708070134,"-"]
[354,"경북","영주","점촌문경 T/L","2016-17년도 영주 송전정비 협력회사 총액공사","피뢰기 설치","2017-10-23 07:00","2017-10-26 18:00","2017-11-03 07:00","2017-11-05 18:00","연속",null,null,null,201708070137,"-"]
[355,"경북","영주","신영주예천#1 T/L","2017년 예천S/S 170kV 장기사용 GIS 대체(2차 공정)","신영주-예천#1T/L 647, #1M.Tr 1차 6133, BUS TIE 6100, PT GIS 대체(4Bay 동시) 및 BUS SEC DS 설치","2017-10-23 09:00","2017-11-17 18:00","2017-10-23 09:00","2017-11-17 18:00","연속",null,null,null,201708080001,"-"]
[356,"경북","영주","점촌단양 T/L","154kV 단양T/L 노후취약지지물 교체공사","노후취약지지물교체","2017-10-27 07:00","2017-10-29 18:00","취소","취소","연속",null,null,null,201708070135,"-"]
[357,"경북","영주","예천S/S 154kV #1 BUS","2017년 예천S/S 170kV 장기사용 GIS 대체(#1DS철거/설치)","신영주-예천#1T/L 647, #1M.Tr 1차 6133, BUS TIE 6100, PT GIS 대체(4Bay 동시) 관련 #1DS(6131, 641, 6101), #1BUS PT 철거 및 재설치, BUS SEC DS(60-61-1) 설치","2017-10-27 10:00","2017-11-07 10:00","2017-10-27 10:00","2017-11-07 10:00","연속",null,null,null,201708080004,"-"]
[358,"경북","직할","안계의성#1 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-10 08:00","2017-10-12 18:00","2017-10-10 08:00","2017-10-12 18:00","매일",null,null,null,201708160004,"-"]
[359,"경북","직할","안계의성#2 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-10 08:00","2017-10-12 18:00","2017-10-10 08:00","2017-10-12 18:00","매일",null,null,null,201708160005,"-"]
[360,"경북","직할","군위의성#1 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-13 08:00","2017-10-15 18:00","2017-10-13 08:00","2017-10-15 18:00","매일",null,null,null,201708160006,"-"]
[361,"경북","직할","군위의성#2 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-13 08:00","2017-10-15 18:00","2017-10-13 08:00","2017-10-15 18:00","매일",null,null,null,201708160007,"-"]
[362,"경북","직할","안계의성#1 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-23 08:00","2017-10-24 18:00","2017-10-23 08:00","2017-10-24 18:00","매일",null,null,null,201708160008,"-"]
[363,"경북","직할","안계의성#2 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-23 08:00","2017-10-24 18:00","2017-10-23 08:00","2017-10-24 18:00","매일",null,null,null,201708160009,"-"]
[364,"경북","직할","군위의성#1 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-25 08:00","2017-10-26 18:00","2017-10-25 08:00","2017-10-26 18:00","매일",null,null,null,201708160010,"-"]
[365,"경북","직할","군위의성#2 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-10-25 08:00","2017-10-26 18:00","2017-10-25 08:00","2017-10-26 18:00","매일",null,null,null,201708160011,"-"]
[366,"경북","직할","동안동임하HP T/L","경북직할 하반기 154kV 정밀점검 공사 및 T/L 항공장애구설치공사","-동안동-임하HP T/L -송전선로 항공장애구 설치공사(25일~27일)","2017-10-25 09:00","2017-10-27 18:00","2017-10-25 09:00","2017-10-27 18:00","연속",null,null,null,201708080143,"-"]
[367,"부산울산","동부산","수영우동 T/L","154kV 우동 등 3개S/S 지중송전케이블 선종교체공사","154kV 수영-우동T/L 선종교체(우동EBG~J/B#1, OF1200--&gtXLPE1200)","2017-10-23 09:00","2017-11-27 18:00","2017-10-23 09:00","2017-11-27 18:00","연속",null,null,null,201708070309,"-"]
[368,"부산울산","동부산","수영정보#2 T/L","수영,정보S/S 170kV GIS 초기점검","1. 수영 657 GIS 초기점검, 2. 정보 637 GIS 초기점검","2017-10-23 09:30","2017-10-23 17:00","2017-10-23 09:30","2017-10-23 17:00","당일",null,null,null,201708110256,"-"]
[369,"부산울산","동부산","수영정보#1 T/L","수영S/S 170kV GIS 보통점검","수영S/S 170kV 637 GIS 보통점검(수영-정보#1T/L)","2017-10-24 09:30","2017-10-24 17:00","2017-10-24 09:30","2017-10-24 17:00","당일",null,null,null,201708110255,"-"]
[370,"부산울산","북부산","모라엄궁#1 T/L","2017년 북부산 154kV GIS 정밀점검 공사","모라S/S 모라-엄궁#1T/L (667) GIS 정밀점검","2017-10-10 08:00","2017-10-12 16:00","2017-10-10 08:00","2017-10-12 16:00","연속",null,null,null,201708090105,"○"]
[371,"부산울산","북부산","북부산양산 T/L","154kV 양산S/S 현대화 공사(토건공사)","가. GIS, M.Tr 및 제어동 기초 파일시공(안전이격) 나. 송배전 전력구 기초 파일시공(안전이격)","2017-10-10 09:00","2017-10-24 18:00","2017-10-10 09:00","2017-10-24 18:00","연속",null,null,null,201708110194,"-"]
[372,"부산울산","북부산","양산삼랑진PP T/L","154kV 양산S/S 현대화 공사(토건공사)","가. GIS, M.Tr 및 제어동 기초 파일시공(안전이격) 나. 송배전 전력구 기초 파일시공(안전이격)","2017-10-10 09:00","2017-10-24 18:00","2017-10-10 09:00","2017-10-24 18:00","연속",null,null,null,201708110196,"-"]
[373,"부산울산","북부산","모라엄궁#2 T/L","2017년 북부산 154kV GIS 정밀점검 공사","모라S/S 모라-엄궁#2T/L (657) GIS 정밀점검","2017-10-13 08:00","2017-10-15 16:00","2017-10-13 08:00","2017-10-15 16:00","연속",null,null,null,201708210145,"-"]
[374,"부산울산","북부산","호포매리#1 T/L","2017년 북부산 154kV GIS 정밀점검 공사","호포S/S 호포-매리#1T/L (617) GIS 정밀점검","2017-10-16 08:00","2017-10-18 16:00","2017-10-16 08:00","2017-10-18 16:00","연속",null,null,null,201708090104,"-"]
[375,"부산울산","북부산","엄궁학장#1 T/L","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S #2DS 철거 및 고깔설치 후 #2BUS 시험가압 1H (엄궁 617)","2017-10-17 17:00","2017-10-17 18:00","2017-10-17 17:00","2017-10-17 18:00","당일",null,null,null,201708010052,"-"]
[376,"부산울산","북부산","엄궁S/S 154kV #1 BUS","엄궁S/S 170kV 장기사용 GIS 교체공사","PT&ES, 6100, 6333 Bay #1BUS, #1DS, CB 철거 및 설치","2017-10-18 09:00","2017-11-02 18:00","2017-10-18 09:00","2017-11-02 18:00","연속",null,null,null,201708090111,"-"]
[377,"부산울산","북부산","북부산구포#1 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 북부산-구포#1T/L 인출변경 6C7 휴전","2017-10-19 08:00","2017-11-05 18:00","2017-10-19 08:00","2017-11-05 18:00","연속",null,null,null,201708090110,"○"]
[378,"부산울산","북부산","삼계김해 T/L","154kV 어방S/S SW증설공사","※ 송전선로 보호반 설치 이설 1면(김해S/S→어방S/S), 신설 2면(김해S/S, 어방S/S)","2017-10-20 18:00","2017-10-27 18:00","2017-10-20 18:00","2017-10-27 18:00","연속",null,null,null,201708100194,"-"]
[379,"부산울산","북부산","삼계어방 T/L","154kV 어방분기(증)T/L 연계 가공송전선로 건설공사","- 공사목적 : 어방S/S 송전선로 증설로 김해지역 안정적 전력공급 - 공사개요 구간 : 기설 154kV 삼계-김해T/L No.3 ~ 기설 어방C/H 전력선 : 154kV STACIR 240㎟ × S × 2C - 0.029 Km","2017-10-21 07:00","2017-10-22 11:00","2017-10-21 07:00","2017-10-22 11:00","연속",null,null,null,201708070199,"-"]
[380,"부산울산","북부산","김해어방 T/L","154kV 어방분기(증)T/L 연계 가공송전선로 건설공사","- 공사목적 : 어방S/S 송전선로 증설로 김해지역 안정적 전력공급 - 공사개요 구간 : 기설 154kV 삼계-김해T/L No.3 ~ 기설 어방C/H 전력선 : 154kV STACIR 240㎟ × S × 2C - 0.029 Km","2017-10-23 07:00","2017-10-24 18:00","2017-10-23 07:00","2017-10-24 18:00","연속",null,null,null,201708070205,"-"]
[381,"부산울산","북부산","양산산막#1 T/L","2017년 북부산 154kV GIS 정밀점검 공사","산막S/S 6333 GIS 정밀점검 시험가압 1H (산막 617)","2017-10-26 15:00","2017-10-26 16:00","2017-10-26 15:00","2017-10-26 16:00","당일",null,null,null,201708090106,"-"]
[382,"부산울산","북부산","양산산막#1 T/L","2017년 북부산변전협력회사 총액공사","산막S/S 양산-산막#1T/L 617 GIS 하자점검","2017-10-27 10:00","2017-10-27 18:00","2017-10-27 10:00","2017-10-27 18:00","당일",null,null,null,201708100165,"-"]
[383,"부산울산","북부산","삼계어방 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치 공사","154kV 주촌-삼계#2T/L (6회선) 피뢰기 설치에 따른 안전거리 확보","2017-10-28 07:00","2017-10-28 18:00","2017-10-28 07:00","2017-10-28 18:00","당일",null,null,null,201708090186,"-"]
[384,"부산울산","북부산","주촌삼계#2 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치 공사","154kV 주촌-삼계#2T/L No.47-53(7기) 피뢰기 설치","2017-10-28 07:00","2017-10-28 18:00","2017-10-28 07:00","2017-10-28 18:00","당일",null,null,null,201708090184,"-"]
[385,"부산울산","북부산","한림정삼계#2 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치 공사","154kV 주촌-삼계#2T/L (6회선) 피뢰기 설치에 따른 안전거리 확보","2017-10-28 07:00","2017-10-28 18:00","2017-10-28 07:00","2017-10-28 18:00","당일",null,null,null,201708090185,"-"]
[386,"부산울산","북부산","북부산삼랑진PP#2 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치 공사","154kV 호포-물금T/L(4회선) 피뢰기 설치에 따른 안전거리확보","2017-10-29 07:00","2017-10-31 18:00","2017-10-29 07:00","2017-10-31 18:00","연속",null,null,null,201708090154,"-"]
[387,"부산울산","북부산","호포물금 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치 공사","154kV 호포-물금T/L No.25-36,41-46(18기) 피뢰기 설치","2017-10-29 07:00","2017-10-31 18:00","2017-10-29 07:00","2017-10-31 18:00","연속",null,null,null,201708090151,"-"]
[388,"부산울산","북부산","엄궁S/S 154kV #2 BUS","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S PT&ES, 6333 Bay #2DS부 철거 및 고깔설치, #2BUS 및 #2DS 고깔부 진공","2017-10-16 09:00","2017-10-17 18:00","2017-10-16 09:00","2017-10-17 18:00","연속",null,null,null,201708240073,"-"]
[389,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 154kV 용원-녹공#1T/L(617) GIS 정밀점검","녹공S/S 154kV 용원-녹공#1T/L(617) GIS 정밀점검 (모선DS 제외)","2017-10-21 09:00","2017-10-22 18:00","취소","취소","연속",null,null,null,201708140012,"-"]
[390,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 154kV 용원-녹공#2T/L(627) GIS 정밀점검","녹공S/S 154kV 용원-녹공#2T/L(627) GIS 정밀점검 (모선DS 제외)","2017-10-28 09:00","2017-10-29 18:00","취소","취소","연속",null,null,null,201708140015,"-"]
[391,"부산울산","울산","동울산방어진 T/L","동울산S/S 154kV Sh.C 설치공사(파일시공 안전이격거리확보)","-동울산S/S 154kV Sh.C 설치공사(파일시공 안전이격거리확보)","2017-10-11 10:00","2017-10-13 18:00","2017-10-11 10:00","2017-10-13 18:00","연속",null,null,null,201708020033,"-"]
[392,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사","154kV 두왕분기T/L 건설공사 관련 본선로 구성 (구간 : 154kV 신울산-영남TP T/L 37 ~ 38호)","2017-10-14 07:00","2017-10-15 19:00","2017-10-14 07:00","2017-10-15 19:00","연속",null,null,null,201708170128,"-"]
[393,"부산울산","울산","신울산울산#1 T/L","154kV 두왕분기T/L 건설공사","154kV 두왕분기T/L 건설공사 관련 본선로 구성 안전이격 (구간 : 154kV 신울산-울산 T/L 4 ~ 6호)","2017-10-14 07:00","2017-10-15 19:00","2017-10-14 07:00","2017-10-15 19:00","매일",null,null,null,201708210280,"○"]
[394,"부산울산","울산","용연울산TP#3 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","1.용연,울산T/P양단 154kV 용연-울산TP#3T/L 보호반 대체 2.양측 차단기 개폐타임 측정","2017-10-14 08:00","2017-10-15 18:00","2017-10-14 08:00","2017-10-15 18:00","연속",null,null,null,201708110371,"-"]
[395,"부산울산","울산","동울산효문#2 T/L","2017년 가공송전선로 순시점검 위탁공사(울산전력지사)","송전선로 초기점검(22기), 정밀점검(21기)","2017-10-16 09:00","2017-10-19 18:00","2017-10-16 09:00","2017-10-20 18:00","연속",null,null,null,201708080190,"-"]
[396,"부산울산","울산","신온산온산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","온산S/S 170kV 신온산-온산#1T/L GIS 차단기 개폐타임측정","2017-10-16 09:00","2017-10-16 14:00","2017-10-16 09:00","2017-10-16 14:00","당일",null,null,null,201708110372,"-"]
[397,"부산울산","울산","신온산온산#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","온산S/S 170kV 신온산-온산#2T/L GIS 차단기 개폐타임측정","2017-10-16 14:00","2017-10-16 18:00","2017-10-16 14:00","2017-10-16 18:00","당일",null,null,null,201708110373,"-"]
[398,"부산울산","울산","용연처용#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","처용S/S 170kV 용연-처용#1T/L GIS 차단기 개폐타임측정","2017-10-17 09:00","2017-10-17 14:00","2017-10-17 09:00","2017-10-17 14:00","당일",null,null,null,201708110375,"-"]
[399,"부산울산","울산","용연처용#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","처용S/S 170kV 용연-처용#2T/L GIS 차단기 개폐타임측정","2017-10-17 14:00","2017-10-17 18:00","2017-10-17 14:00","2017-10-17 18:00","당일",null,null,null,201708110374,"-"]
[400,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사 (병행)","154kV 두왕분기T/L 건설공사 관련 본선로 구성 (구간 : 154kV 신울산-영남TP T/L 36 ~ 38호) / (병행) 신울산S/S 154kV 신울산-영남TP#1 T/L CVT 대체 (울산전력지사)","2017-10-21 07:00","2017-10-22 19:00","2017-10-21 07:00","2017-10-22 19:00","연속",null,null,null,201708100124,"-"]
[401,"부산울산","울산","신울산울산#1 T/L","154kV 두왕분기T/L 건설공사 (병행)","154kV 두왕분기T/L 건설공사 관련 본선로 구성 안전이격 (구간 : 154kV 신울산-울산 T/L 4 ~ 6호) / (병행) 신울산S/S 154kV 신울산-울산 #1T/L CVT 대체 (울산전력지사)","2017-10-21 07:00","2017-10-22 19:00","2017-10-21 07:00","2017-10-22 19:00","매일",null,null,null,201708100125,"○"]
[402,"부산울산","울산","동울산방어진 T/L","154kV 현대#1T/L 전선교체공사(안전확보)","ㅁ 154kV 현대#1T/L 전선접속개소 전선교체공사 관련 병가구간 안전 확보(실작업 없음)","2017-10-22 06:00","2017-10-22 14:00","취소","취소","당일",null,null,null,201708230069,"-"]
[403,"부산울산","울산","용연울산TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","용연S/S 154V 용연-울산TP#2T/L LA 보통점검","2017-10-24 09:00","2017-10-24 18:00","2017-10-24 09:00","2017-10-24 18:00","당일",null,null,null,201708110385,"-"]
[404,"부산울산","울산","웅촌서창#1 T/L","2017년 170kV 개폐장치 정밀점검공사","웅촌S/S 154kV 6333 GIS 정밀점검관련 시험가압","2017-10-25 17:00","2017-10-25 18:00","2017-10-25 17:00","2017-10-25 18:00","당일",null,null,null,201708110381,"-"]
[405,"부산울산","울산","동울산효문#3 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","효문S/S 170kV 동울산-효문#3T/L GIS 차단기 개폐타임측정","2017-10-27 09:00","2017-10-27 12:00","2017-10-27 09:00","2017-10-27 12:00","당일",null,null,null,201708110376,"-"]
[406,"부산울산","울산","동울산효문#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","효문S/S 170kV 동울산-효문#1T/L GIS 차단기 개폐타임측정","2017-10-27 12:00","2017-10-27 15:00","2017-10-27 12:00","2017-10-27 15:00","당일",null,null,null,201708110377,"-"]
[407,"부산울산","울산","신울산영남TP#2 T/L","154kV 두왕분기T/L 건설공사","154kV 두왕분기T/L 건설공사 관련 본선로 구성 (구간 : 154kV 신울산-영남TP T/L 36 ~ 38호)","2017-10-28 07:00","2017-10-29 18:00","2017-10-28 07:00","2017-10-29 18:00","연속",null,null,null,201708100128,"-"]
[408,"부산울산","울산","신울산울산#2 T/L","154kV 두왕분기T/L 건설공사","154kV 두왕분기T/L 건설공사 관련 본선로 구성 안전이격 (구간 : 154kV 신울산-울산 T/L 4 ~ 6호)","2017-10-28 07:00","2017-10-29 18:00","2017-10-28 07:00","2017-10-29 18:00","매일",null,null,null,201708100130,"-"]
[409,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#1 T/L No.56~64","2017-10-31 07:00","2017-11-02 19:00","취소","취소","연속",null,null,null,201708230065,"-"]
[410,"부산울산","울산","웅촌서창#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","웅촌S/S 170kV 웅촌-서창#2T/L GIS 차단기 개폐타임측정","2017-10-31 09:00","2017-10-31 18:00","2017-10-31 09:00","2017-10-31 18:00","당일",null,null,null,201708110380,"-"]
[411,"부산울산","직할","범일서면#2 T/L","2017년 직할 변전협력회사 총액공사","범일,서면S/S 범일-서면#2T/L 보호배전반 대체","2017-10-11 10:00","2017-10-13 18:00","2017-10-11 10:00","2017-10-13 18:00","연속",null,null,null,201708100285,"-"]
[412,"경남","직할","신김해주촌#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-10-07 07:00","2017-10-09 18:00","2017-10-07 07:00","2017-10-09 18:00","매일",null,null,null,201708020049,"-"]
[413,"경남","직할","신김해진영#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-10-07 07:00","2017-10-09 18:00","2017-10-07 07:00","2017-10-09 18:00","매일",null,null,null,201708020047,"-"]
[414,"경남","직할","신김해진영#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-10-07 07:00","2017-10-09 18:00","2017-10-07 07:00","2017-10-09 18:00","매일",null,null,null,201708020048,"-"]
[415,"경남","직할","신김해진영#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-10-14 07:00","2017-10-15 18:00","2017-10-14 07:00","2017-10-15 18:00","매일",null,null,null,201708020050,"-"]
[416,"경남","직할","신김해진영#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-10-14 07:00","2017-10-15 18:00","2017-10-14 07:00","2017-10-15 18:00","매일",null,null,null,201708020051,"-"]
[417,"경남","직할","신월동읍#2 T/L","2016~17년 경남지역본부 직할 송전협력회사 총액공사","애자교체(C/H, 34호)","2017-10-28 07:00","2017-10-28 18:00","2017-10-28 07:00","2017-10-28 12:00","당일",null,null,null,201708020053,"-"]
[418,"경남","직할","차룡창공#1 T/L","창공S/S 차룡-창공#1T/L CB 초기점검","창공S/S 차룡-창공#1T/L CB 초기점검","2017-10-28 09:30","2017-10-28 17:30","2017-10-28 09:30","2017-10-28 17:30","당일",null,null,null,201708010030,"-"]
[419,"경남","직할","마천진해#2 T/L","마천S/S 마천-진해#2T/L PT, LA 보통점검","마천S/S 마천-진해#2T/L PT, LA 보통점검","2017-10-30 09:30","2017-10-30 13:30","2017-10-30 09:30","2017-10-30 13:30","당일",null,null,null,201708010010,"-"]
[420,"경남","직할","마천진해#1 T/L","마천S/S 마천-진해#1T/L PT, LA 보통점검","마천S/S 마천-진해#1T/L PT, LA 보통점검","2017-10-30 13:30","2017-10-30 17:30","2017-10-30 13:30","2017-10-30 17:30","당일",null,null,null,201708010009,"-"]
[421,"경남","진주","사천개양#1 T/L","154kV 사천-개양T/L 지장송전선로 지중화공사","154kV 사천-개양#1T/L 지장송전선로 지중화공사 (케이블 철거, 포설 및 접속, GIS챔버 철거 및 설치, C/H 설치)","2017-10-11 08:00","2017-10-22 18:00","2017-10-11 08:00","2017-10-22 18:00","연속",null,null,null,201707280037,"-"]
[422,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 항공장애표시구 설치 공사","154kV 의령-함양T/L 112~113호간 항공장애표시구 7개 설치","2017-10-14 07:00","2017-10-14 18:00","2017-10-14 07:00","2017-10-14 18:00","당일",null,null,null,201708020066,"-"]
[423,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L 지장송전선로 지중화공사","154kV 사천-개양#2T/L 지장송전선로 지중화공사 (케이블 철거, 포설 및 접속, GIS챔버 철거 및 설치, C/H 설치)","2017-10-21 08:00","2017-11-02 18:00","2017-10-21 08:00","2017-11-02 18:00","연속",null,null,null,201707280038,"-"]
[424,"경남","진주","의령동진주#1 T/L","의령S/S 의령-동진주#1T/L PT 초기점검","의령-동진주#1T/L PT 초기점검","2017-10-22 09:30","2017-10-22 14:00","2017-10-22 09:30","2017-10-22 14:00","당일",null,null,null,201707310039,"-"]
[425,"경남","진주","의령동진주#2 T/L","의령S/S 의령-동진주#2T/L PT 초기점검","의령-동진주#2T/L PT 초기점검","2017-10-22 14:00","2017-10-22 18:00","2017-10-22 14:00","2017-10-22 18:00","당일",null,null,null,201707310040,"-"]
[426,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천T/L 현수애자 절연성능진단 안전확보","154kV 삼천포-사천#1T/L 61~72호 수평배열 구간 불량애자검출 안전확보차","2017-10-10 09:00","2017-10-10 18:00","2017-10-10 09:00","2017-10-10 18:00","당일",null,null,null,201708010100,"-"]
[427,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 정밀점검","154kV 통영-거제#1T/L 송전선로 정밀점검","2017-10-21 09:00","2017-10-22 18:00","2017-10-21 09:00","2017-10-22 18:00","매일",null,null,null,201708010102,"-"]
[428,"경남","통영","신고성고성 T/L","고성S/S 154kV 신고성-고성T/L 휴전(시험가압)","고성S/S 고성-안정#1T/L GIS 정밀점검관련(시험가압용)","2017-10-21 18:00","2017-10-21 19:00","2017-10-21 18:00","2017-10-21 19:00","당일",null,null,null,201708020021,"-"]
[429,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제T/L 항공장애표시구 설치","154kV 신고성-거제T/L 33~35호구간 항공장애표시구 설치(항공법 상 미설치개소 조치요청사항[항공청])","2017-10-28 07:00","2017-10-28 18:00","2017-10-28 07:00","2017-10-28 18:00","당일",null,null,null,201708010103,"-"]
[430,"경남","통영","신고성고성 T/L","고성S/S 154kV 신고성-고성T/L 휴전(시험가압)","고성S/S 고성-안정#2T/L GIS 정밀점검관련(시험가압용)","2017-10-28 18:00","2017-10-28 19:00","2017-10-27 18:00","2017-10-27 19:00","당일",null,null,null,201708100241,"-"]
[431,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제T/L 항공장애표시구 설치","154kV 신고성-거제T/L 33~35호구간 항공장애표시구 설치(항공법 상 미설치개소 조치요청사항[항공청])","2017-10-29 07:00","2017-10-29 18:00","2017-10-29 07:00","2017-10-29 18:00","당일",null,null,null,201708010105,"-"]
[432,"경남","함안","신마산마산#1 T/L","신마산-마산T/L 정밀점검(6회선 병가구간)","신마산-마산T/L 정밀점검(2~8호)","2017-10-09 09:00","2017-10-09 18:00","2017-10-09 09:00","2017-10-09 18:00","당일",null,null,null,201707280044,"-"]
[433,"경남","함안","신마산마산#2 T/L","신마산-마산T/L 정밀점검(6회선 병가구간)","신마산-마산T/L 정밀점검(2~8호)","2017-10-09 09:00","2017-10-09 18:00","2017-10-09 07:00","2017-10-09 19:00","당일",null,null,null,201707280045,"-"]
[434,"경남","함안","신마산중리#2 T/L","154kV 신마산-중리#1T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 안전거리확보 : 신마산-중리#1T/L 2~8호","2017-10-14 08:00","2017-10-14 18:00","2017-10-14 08:00","2017-10-14 18:00","당일",null,null,null,201708020034,"-"]
[435,"경남","함안","신마산중리#1 T/L","중리S/S 신마산-중리#1T/L 170kV GIS 정밀점검","중리S/S 신마산-중리#1T/L 170kV GIS 정밀점검","2017-10-14 08:30","2017-10-15 17:30","2017-10-14 08:30","2017-10-15 17:30","연속",null,null,null,201708020105,"-"]
[436,"경남","함안","수출월림#1 T/L","수출S/S 수출-월림#1T/L 보호배전반 대체","수출S/S 수출-월림#1T/L 보호배전반 대체 수출S/S 170kV GIS 보통점검 월림S/S 수출-월림#1T/L 보호배전반 대체(병행)","2017-10-14 09:30","2017-10-15 17:30","2017-10-14 09:30","2017-10-15 17:30","연속",null,null,null,201708020102,"-"]
[437,"경남","함안","중리가야#1 T/L","중리S/S 신마산-중리#1T/L 170kV GIS 정밀점검 시험가압","중리S/S 신마산-중리#1T/L 170kV GIS 정밀점검 시험가압","2017-10-15 16:30","2017-10-15 17:30","2017-10-15 16:30","2017-10-15 17:30","당일",null,null,null,201707060258,"-"]
[438,"경남","함안","수출월림#2 T/L","수출S/S 수출-월림#2T/L 보호배전반 대체","수출S/S 수출-월림#2T/L 보호배전반 대체 수출S/S 170kV GIS 보통점검 월림S/S 수출-월림#2T/L 보호배전반 대체(병행)","2017-10-21 09:30","2017-10-22 17:30","2017-10-21 09:30","2017-10-22 17:30","연속",null,null,null,201708020136,"-"]
[439,"경남","함안","청도밀양#2 T/L","154kV 청도-밀양 #2T/L 피뢰기 설치공사","청도-밀양 #2T/L 30~80호 피뢰기 설치공사","2017-10-25 07:30","2017-10-29 18:00","2017-10-25 07:30","2017-10-29 18:00","연속",null,null,null,201708010070,"-"]
[440,"경남","함안","청도밀양#1 T/L","154kV 청도-밀양 #2T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 안전거리 확보 : 청도-밀양 #2T/L 30~80호","2017-10-28 07:30","2017-10-29 18:00","2017-10-28 07:30","2017-10-29 18:00","연속",null,null,null,201708010071,"-"]
[441,"경남","함안","신마산중리#2 T/L","중리S/S 신마산-중리#2T/L 170kV GIS 정밀점검","중리S/S 신마산-중리#2T/L 170kV GIS 정밀점검","2017-10-28 09:30","2017-10-29 17:30","2017-10-28 09:30","2017-10-29 17:30","연속",null,null,null,201708020137,"-"]
[442,"경남","함안","한림정삼계#2 T/L","한림정S/S 한림정-삼계#2T/L 제작사 하자점검","한림정S/S 한림정-삼계#2T/L 제작사 하자점검 (송전병행) 송전선로용 피뢰기 설치 : 한림정-삼계 #2T/L 4~15호","2017-10-28 09:30","2017-10-29 17:30","2017-10-28 09:30","2017-10-29 17:30","연속",null,null,null,201708020141,"-"]
[443,"경남","함안","중리가야#2 T/L","중리S/S 신마산-중리#2T/L 170kV GIS 정밀점검 시험가압","중리S/S 신마산-중리#2T/L 170kV GIS 정밀점검 시험가압","2017-10-29 16:30","2017-10-29 17:30","2017-10-29 16:30","2017-10-29 17:30","당일",null,null,null,201707060261,"-"]

{"sheet":"중부발전","index":3,"n_rows":6,"n_cols":16,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2017년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2017년도 10월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전충남","보령복합","보령복합 GT #3, 4 주변압기 (CB 7300, CB 7372) ","발전기 절연내역시험 및 정기검사 수검","발전기 절연내역시험 및 정기검사 수검","2017-10-18 09:00","2017-10-27 18:00","2017-10-18 09:00","2017-10-27 18:00","연속",{"$nulls":4},"-"]
[2,"대전충남","보령복합","보령복합 ST #2 주변압기 (CB 7300, CB 7372) ","발전기 절연내역시험 및 정기검사 수검","발전기 절연내역시험 및 정기검사 수검","2017-10-18 09:00","2017-10-27 18:00","2017-10-18 09:00","2017-10-27 18:00","연속",{"$nulls":4},"-"]

{"sheet":"한수원","index":4,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 10월 휴전계획표(한국수력원자력)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","월성3발","신월성#2 주변압기","신월성2호기 2차 계획예방정비\n#2 MTR/UAT/EXTR 점검\n* 조작차단기 : CB 7100, 7172","○ MTR/UAT/EXTR 일반점검 등","2017-10-09T09:00:00","2017-10-24T18:00:00","2017-10-09T09:00:00","2017-10-24T18:00:00","연속","Y"]
[2,"월성본부","월성3발","신월성#2 주변압기","신월성 2호기 2차 계획예방정비\n# 소내전원절체시험 \n* 조작차단기 : CB 7100, 7172","○ 소내전원절체시험시 주변압기 \n  모의 보호신호에 의한 PCB개방","2017-10-30T09:00:00","2017-10-31T18:00:00","2017-10-30T09:00:00","2017-10-31T18:00:00","연속","Y"]

{"sheet":"수자원공사","index":5,"n_rows":5,"n_cols":16,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2017년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2017년도 10월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전충남","수자원공사","신탄진대청HPT/L","옥외변전설비 현대화 사업","옥외변전설비 현대화 사업","2017-10-23 09:00","2017-10-23 18:00","2017-10-23 09:00","2017-10-23 18:00","당일",{"$nulls":4},"-"]