{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":6,"n_cols":16,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 1월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경북","영주","신한울S/S #2 M.Tr A-1","신한울S/S 765kV #2M.Tr 하자점검","신한울S/S 765kV #2M.Tr 하자점검","2018-01-15 09:00","2018-01-21 18:00","2018-01-15 09:00","2018-01-21 18:00",null,"연속",null,null,201711140114]
[2,"경북","영주","신한울S/S #1 M.Tr A-1","신한울S/S 765kV #1M.Tr 하자점검","신한울S/S 765kV #1M.Tr 하자점검","2018-01-08 09:00","2018-01-14 18:00","2018-01-08 09:00","2018-01-14 18:00",null,"연속",null,null,201711140104]

{"sheet":"345송부","index":1,"n_rows":36,"n_cols":16,"rows_kept":36,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 1월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","김포","345kV신가좌 - 가정 #1T/L GIS","345kV신가좌 - 가정 #1T/L GIS(7571CB)","Puffercylinder 강도 보강 및 투입저항기 신품 교체","2018-01-22 09:00","2018-01-26 18:00","2018-01-22 09:00","2018-01-26 18:00","연속",null,null,null,201711160067]
[2,"인천","김포","345kV가정 - 인천CC #2T/L GIS","345kV가정 - 인천CC #2T/L GIS(7271CB)","Puffercylinder 강도 보강 및 투입저항기 신품 교체","2018-01-02 09:00","2018-01-06 18:00","2018-01-02 09:00","2018-01-06 18:00","연속",null,null,null,201711160061]
[3,"인천","김포","신가좌 -가정#1 TIE GIS","신가좌 -가정#1 TIE GIS(7500CB)","Puffercylinder 강도 보강 및 투입저항기 신품 교체","2018-01-29 09:00","2018-02-02 18:00","2018-01-29 09:00","2018-02-02 18:00","연속",null,null,null,201711160070]
[4,"인천","김포","345kV가정 - 신부평 #1T/L GIS","345kV가정 - 신부평 #1T/L GIS(7472CB)","Puffercylinder 강도 보강 및 투입저항기 신품 교체","2018-01-15 09:00","2018-01-19 18:00","2018-01-15 09:00","2018-01-19 18:00","연속",null,null,null,201711160063]
[5,"인천","김포","가정인천CC#1 - 가정신부평#1 TIE GIS","가정인천CC#1 - 가정신부평#1 TIE GIS(7400CB)","Puffercylinder 강도 보강 및 투입저항기 신품 교체","2018-01-08 09:00","2018-01-12 18:00","2018-01-08 09:00","2018-01-12 18:00","연속",null,null,null,201711160059]
[6,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2018-01-23 08:00","2018-01-25 18:00","취소","취소","연속",null,null,null,201710310015]
[7,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2018-01-23 08:00","2018-01-23 20:00","취소","취소","당일",null,null,null,201710310016]
[8,"인천","인천","신인천C/C 4MT101 CB (7772)","신인천복합 7772(#4MT 101 GEN) GIS 하자점검","신인천복합 7772(#4MT 101 GEN) GIS 하자점검","2018-01-15 09:00","2018-01-15 18:00","2018-01-15 09:00","2018-01-15 18:00","당일",null,null,null,201711140162]
[9,"인천","인천","인천CC S/Y 70-71-0 SEC CB (70-71-0)","인천CC 70-71-0 GIS 하자점검","인천CC 70-71-0 GIS 하자점검","2018-01-30 09:00","2018-01-30 18:00","2018-01-30 09:00","2018-01-30 18:00","당일",null,null,null,201711140159]
[10,"인천","인천","인천CC S/Y 신경서인천CC#2T/L CB (7471)","인천CC 7471 GIS 하자점검","인천CC 7471 GIS 하자점검","2018-01-16 09:00","2018-01-16 18:00","2018-01-16 09:00","2018-01-16 18:00","당일",null,null,null,201711140163]
[11,"인천","인천","인천CC S/Y 75-76-0 SEC CB (75-76-0)","인천CC 75-76-0 GIS 하자점검","인천CC 75-76-0 GIS 하자점검","2018-01-31 09:00","2018-01-31 18:00","2018-01-31 09:00","2018-01-31 18:00","당일",null,null,null,201711140160]
[12,"인천","인천","인천CC S/Y #2 TIE Tr 1차 CB (7C72)","인천CC 7C72 GIS 하자점검","인천CC 7C72 GIS 하자점검","2018-01-25 09:00","2018-01-25 18:00","2018-01-25 09:00","2018-01-25 18:00","당일",null,null,null,201711140158]
[13,"인천","인천","인천CC S/Y 가정인천#2 - #2TIE Tr 1차 CB (7C00)","인천CC 7C00 GIS 하자점검","인천CC 7C00 GIS 하자점검","2018-01-24 09:00","2018-01-24 18:00","2018-01-24 09:00","2018-01-24 18:00","당일",null,null,null,201711140157]
[14,"인천","인천","인천CC S/Y 가정인천#2T/L CB (7C71)","인천CC 7C71 GIS 하자점검","인천CC 7C71 GIS 하자점검","2018-01-23 09:00","2018-01-23 18:00","2018-01-23 09:00","2018-01-23 18:00","당일",null,null,null,201711140156]
[15,"강원","강릉","동해신양양 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치 (No.114~115, 180~181, 207~208)","2018-01-15 07:00","2018-01-15 18:00","2018-01-15 07:00","2018-01-15 18:00","당일",null,null,null,201711160131]
[16,"강원","강릉","동해양양PP T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치 (No.114~115, 180~181, 207`208)","2018-01-16 07:00","2018-01-16 18:00","2018-01-16 07:00","2018-01-16 18:00","당일",null,null,null,201711160133]
[17,"강원","동해","신제천동해#2 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","345kV 신제천-동해T/L 항공장애구 설치","2018-01-11 09:00","2018-01-17 18:00","2018-01-11 09:00","2018-01-17 18:00","매일",null,null,null,201711160096]
[18,"강원","태백","신태백한울NP2#2 T/L","○ 신태백S/S 362kV GIS 정밀점검 공사","○ 신태백-한울NP2#2T/L GIS 정밀점검 공사","2018-01-15 09:00","2018-01-19 18:00","2018-01-15 09:00","2018-01-19 18:00","연속",null,null,null,201711160244]
[19,"전북","군산","군산새만금#2 T/L","와이피피제 345kV 송전선로 보호반 성능개선","○ 전류차동계전기 통신 Fail 발생현상 개선 : CPU 교체 (64MHz → 400MHz) ○ 재폐로 관련 로직개선 (43RC 투입순서에 따른 재폐로 동작저지 발생 개선 등)","2018-01-10 10:00","2018-01-10 18:00","2018-01-10 10:00","2018-01-10 18:00","당일",null,null,null,201711060177]
[20,"전북","군산","군산새만금#1 T/L","와이피피제 345kV 송전선로 보호반 성능개선","○ 전류차동계전기 통신 Fail 발생현상 개선 : CPU 교체 (64MHz → 400MHz) ○ 재폐로 관련 로직개선 (43RC 투입순서에 따른 재폐로 동작저지 발생 개선 등)","2018-01-09 10:00","2018-01-09 18:00","2018-01-09 10:00","2018-01-09 18:00","당일",null,null,null,201711060176]
[21,"전북","군산","군산S/S #3 M.Tr A","2018년 군산P/O 345kV 주변압기 정밀점검공사","군산S/S 345kV #3M.Tr 정밀점검","2018-01-15 08:00","2018-01-21 18:00","2018-01-15 08:00","2018-01-21 18:00","연속",null,null,null,201711290032]
[22,"광주전남","군산","신김제한빛NP#1 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","345kV 신김제-한빛NP T/L 10 - 13호 전력선 교체 345kV 신남원-한빛NP T/L 12호 철탑이설 및 11-16호 전력선 교체 345kV 신광주-한빛NP T/L 12,13,14호 철탑이설 및 11-16호 전력선 교체 154kV 홍농분기 T/L 51,52호 철탑이설 및 46-52호 전력선 교체","2018-01-22 09:00","2018-01-26 18:00","2018-01-22 09:00","2018-01-26 18:00","연속",null,null,null,201710160139]
[23,"광주전남","군산","신김제한빛NP#2 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","345kV 신김제-한빛NP T/L 10 - 13호 전력선 교체 345kV 신남원-한빛NP T/L 12호 철탑이설 및 11-16호 전력선 교체 345kV 신광주-한빛NP T/L 12,13,14호 철탑이설 및 11-16호 전력선 교체 154kV 홍농분기 T/L 51,52호 철탑이설 및 46-52호 전력선 교체","2018-01-29 09:00","2018-02-02 18:00","2018-01-29 09:00","2018-02-02 18:00","연속",null,null,null,201710160143]
[24,"경북","영주","신한울한울#2T/L","신한울S/S 362kV GIS puffercylinder 교체","신한울S/S 362kV GIS puffercylinder 교체","2018-01-15 09:00","2018-01-21 18:00","2018-01-15 09:00","2018-01-21 18:00","연속",null,null,null,201711140115]
[25,"경북","영주","신한울한울#1T/L","신한울S/S 362kV GIS puffercylinder 교체","신한울S/S 362kV GIS puffercylinder 교체","2018-01-08 09:00","2018-01-14 18:00","2018-01-08 09:00","2018-01-14 18:00","연속",null,null,null,201711140116]
[26,"경북","영주","신영주한울NP2#2 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","한울2발S/Y 7971, 7900, 7972 CB 하자점검","2018-01-31 09:00","2018-02-01 18:00","취소","취소","연속",null,null,null,201711060224,"○"]
[27,"부산울산","직할","신대연S/S 345kV #2 BUS","신대연S/S 345kV #2 Sh.R 증설공사","345kV #2Sh.R 최초가압","2018-01-10 15:00","2018-01-11 15:00","2018-01-22 09:30","2018-01-28 14:00","연속",null,null,null,201711100032]
[28,"부산울산","직할","신대연S/S #1M.Tr A","신대연S/S 345kV #2 Sh.R 증설공사","345kV #2Sh.R 최초가압","2018-01-10 15:00","2018-01-11 15:00","2018-01-27 14:00","2018-01-28 14:00","연속",null,null,null,201711100181]
[29,"부산울산","직할","신양산신대연#1 T/L","신대연S/S 345kV #2 Sh.R 증설공사","345kV #2Sh.R 최초가압 시험선로","2018-01-10 15:00","2018-01-11 15:00","2018-01-27 14:00","2018-01-28 14:00","연속",null,null,null,201711100180]
[30,"경남","함안","신마산S/S 345kV #2 BUS","345kV 신마산S/S 용량부족차단기 대체공사","#2BUS 하단 전력구 가시설 철거","2018-01-05 09:00","2018-01-07 18:00","2018-01-05 09:00","2018-01-07 18:00","당일",null,null,null,201711070001]
[31,"경남","함안","신마산S/S #5 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#3M.Tr 1측 전력구 가시설 시공","2018-01-15 09:00","2018-01-27 18:00","2018-01-15 09:00","2018-01-27 18:00","당일",null,null,null,201711070003]
[32,"경남","함안","신마산S/S 345kV #1 BUS","345kV 신마산S/S 용량부족차단기 대체공사","#1BUS 하단 전력구 가시설 철거","2018-01-12 09:00","2018-01-14 18:00","2018-01-12 09:00","2018-01-14 18:00","당일",null,null,null,201711070002]

{"sheet":"154송부","index":2,"n_rows":30,"n_cols":16,"rows_kept":30,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 1월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","시흥","도림오봉 T/L","도림S/S 도림오봉 T/L GIS 보통점검","도림S/S 도림오봉 T/L GIS 보통점검","2018-01-30 09:00","2018-01-30 15:00","취소","취소","당일",null,null,null,201711150117]
[2,"인천","시흥","도림S/S 154kV #1 BUS TIE GIS","도림S/S 154kV #1 BUS TIE GIS 하자점검","도림S/S 154kV #1 BUS TIE GIS 하자점검","2018-01-23 09:00","2018-01-23 15:00","취소","취소","당일",null,null,null,201711150114]
[3,"인천","시흥","시화동시화#2 T/L","동시화S/S 시화동시화#2 T/L GIS 보통점검","동시화S/S 시화동시화#2 T/L GIS 보통점검","2018-01-29 14:00","2018-01-29 18:00","취소","취소","당일",null,null,null,201711150116]
[4,"인천","시흥","시화동시화#1 T/L","동시화S/S 시화동시화#1 T/L GIS 보통점검","동시화S/S 시화동시화#1 T/L GIS 보통점검","2018-01-29 09:00","2018-01-29 14:00","2018-01-28 09:00","2018-01-28 14:00","당일",null,null,null,201711150115]
[5,"인천","시흥","소래S/S 154kV #1 BUS TIE GIS","소래S/S 154kV #1 BUS TIE GIS CB 특성시험","소래S/S 154kV #1 BUS TIE GIS CB 특성시험","2018-01-08 10:00","2018-01-08 12:00","취소","취소","당일",null,null,null,201711150108]
[6,"강원","강릉","속초간성#2 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치 (No.11~12)","2018-01-20 07:00","2018-01-20 18:00","2018-01-20 07:00","2018-01-20 18:00","당일",null,null,null,201711160138]
[7,"강원","강릉","속초간성#1 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치 (No.11~12)","2018-01-19 07:00","2018-01-19 18:00","2018-01-19 07:00","2018-01-19 18:00","당일",null,null,null,201711160137]
[8,"강원","강릉","신양양_양양#2 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치 (No.47~49)","2018-01-17 07:00","2018-01-17 18:00","2018-01-17 07:00","2018-01-17 18:00","당일",null,null,null,201711160134]
[9,"강원","강릉","신양양_양양#1 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치 (No.47~49)","2018-01-18 07:00","2018-01-18 18:00","2018-01-18 07:00","2018-01-18 18:00","당일",null,null,null,201711160136]
[10,"강원","동해","동해동영월 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","154kV 영월화력T/L 항공장애표지구 설치","2018-01-22 09:00","2018-01-29 18:00","2018-01-22 09:00","2018-01-29 18:00","매일",null,null,null,201711160098]
[11,"강원","동해","이원태백 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","154kV 태원T/L 항공장애표지구 설치","2018-01-18 09:00","2018-01-21 18:00","2018-01-18 09:00","2018-01-21 18:00","매일",null,null,null,201711160097]
[12,"강원","동해","동해이원#2 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","154kV 이원T/L 항공장애표지구 설치","2018-01-30 14:00","2018-01-30 18:00","2018-01-30 14:00","2018-01-30 18:00","매일",null,null,null,201711160101]
[13,"강원","동해","동해이원#1 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","154kV 이원T/L 항공장애표지구 설치","2018-01-30 09:00","2018-01-30 14:00","2018-01-30 09:00","2018-01-30 14:00","매일",null,null,null,201711160100]
[14,"강원","원주","홍천소양강HP T/L","강원직할 송전정비 협력회사 총액공사","○ 항공장애표시구 설치 : 6개","2018-01-08 08:00","2018-01-08 18:00","2018-01-08 08:00","2018-01-08 18:00","당일",null,null,null,201711160099]
[15,"강원","직할","남춘천춘천 T/L","강원직할 송전정비 협력회사 총액공사","○ 항공장애표시구 설치 : 5개","2018-01-09 08:00","2018-01-09 18:00","2018-01-09 08:00","2018-01-09 18:00","당일",null,null,null,201711160102]
[16,"강원","태백","태백고한 T/L","○ 항공장애주간표시구 설치공사","○ 태백-고한T/L 항공장애주간표시구 설치공사","2018-01-01 09:00","2018-01-03 18:00","2018-01-01 09:00","2018-01-03 18:00","매일",null,null,null,201711160240]
[17,"강원","태백","태백영월 T/L","○ 항공장애주간표시구 설치공사","○ 항공장애주간표시구 설치공사","2018-01-04 09:00","2018-01-05 18:00","2018-01-04 09:00","2018-01-05 18:00","매일",null,null,null,201711160242]
[18,"강원","태백","태백삼척GP#1 T/L","○ 항공장애주간표시구 설치공사","○ 항공장애주간표시구 설치공사","2018-01-08 09:00","2018-01-12 18:00","2018-01-08 09:00","2018-01-12 18:00","매일",null,null,null,201711160243]
[19,"광주전남","강진","강진남창#1 T/L","남창S/S 154kV 강진-남창 #1T/L (PG클램프 교체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 송전선 PG클램프 노후화로 인한 교체","2018-01-08 09:00","2018-01-08 14:00","취소","취소","당일",null,null,null,201711060196]
[20,"광주전남","강진","강진남창#2 T/L","남창S/S 154kV 강진-남창 #2T/L (PG클램프 교체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 송전선 PG클램프 노후화로 인한 교체","2018-01-08 14:00","2018-01-08 18:00","취소","취소","당일",null,null,null,201711060198]
[21,"광주전남","직할","나주엄다#1 T/L","154kV 나주S/S 옥내화 토건공사","송전전력구 : 115.0m 관로 : 48m","2018-01-23 13:00","2018-01-23 18:00","2018-01-27 08:00","2018-01-27 13:00","당일",null,null,null,201711100023]
[22,"광주전남","직할","나주엄다#2 T/L","154kV 나주S/S 옥내화 토건공사","송전전력구 : 115.0m 관로 : 48m","2018-01-24 08:00","2018-01-24 13:00","2018-01-27 13:00","2018-01-27 18:00","당일",null,null,null,201711100024]
[23,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 현대미포조선T/L GIS 1CCT 증설","154kV 방어진S/S 현대미포조선T/L GIS 1CCT 증설- 최초시험가압 선로","2018-01-19 14:00","2018-01-20 14:00","2018-01-19 14:00","2018-01-20 14:00","연속",null,null,null,201711140004]
[24,"경남","진주","하동개양#1 T/L","154kV 사천-개양 등 2개T/L 지장송전선로 지중화공사","154kV 하동-개양#1,2T/L 지장송전선로 지중화공사(기설 케이블 철거, 포설, 접속 및 가공지중 연결작업)","2018-01-29 08:00","2018-02-09 18:00","취소","취소","연속",null,null,null,201711070090]
[25,"경남","진주","하동개양#2 T/L","154kV 사천-개양 등 2개T/L 지장송전선로 지중화공사","154kV 하동-개양#1,2T/L 지장송전선로 지중화공사(기설 케이블 철거, 포설, 접속 및 가공지중 연결작업)","2018-01-15 08:00","2018-01-26 18:00","취소","취소","연속",null,null,null,201711070091]
[26,"경남","진주","가야사봉 T/L","154kV 사봉분기(증)T/L 건설공사","ACSR330㎟×S×2C-1.76km (2회선 철탑 1기 신설 및 기설 4회선 철탑 하단 2회선 가선)","2018-01-20 08:00","2018-01-21 13:00","취소","취소","연속",null,null,null,201711060173]

{"sheet":"한수원","index":3,"n_rows":15,"n_cols":20,"rows_kept":15,"cut":false,"hidden":false,"merged":[[0,0,0,6],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,19,4,19],[9,0,10,0],[9,1,10,1],[9,2,10,2],[9,3,10,3],[9,4,10,4],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,14,4,14],[9,12,10,12],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[9,5,10,5],[9,6,9,7],[9,8,9,9],[9,10,10,10],[9,11,10,11],[9,19,10,19],[9,13,10,13],[9,14,10,14],[9,15,10,15],[9,16,10,16],[9,17,10,17],[9,18,10,18]]}
["2018년도 01월 휴전계획표(한국수력원자력)"]
[]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"새울본부","1발전소","신고리#3 주변압기(8200,8272 CB)","신고리3호기 1차 O/H 중 주변압기\n점검\n- 조작기기 : CB8200, 8272","○ 주변압기 및 GIB 정밀점검 수행","2018-01-18T09:00:00","2018-02-28T18:00:00","2018-01-18T09:00:00","2018-02-28T18:00:00","연속","Y"]
[2,"새울본부","1발전소","신고리#1 주변압기(8400,8472 CB)","신고리1호기 4차 계획예방정비관련 \n주변압기 휴전\n* 조작차단기 : CB 8400, 8472","○ 소내전원절체(UAT→SAT)시험 후\n    차단기 재투입","2018-01-02 10:00","2018-01-05 18:00","2018-01-02 10:00","2018-01-05 18:00","연속","Y"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","월성2발","#4 주변압기 ","월성4호기 15차 계획예방정비 \n주변압기/소내용변압기 점검\n* 조작차단기 : CB 7700, 7772","○ 주변압기 및 소내용변압기 점검","2018-01-16T09:00:00","2018-01-27T19:00:00","2018-01-16T09:00:00","2018-01-27T19:00:00","연속","Y"]
[2,"월성본부","월성2발","#4 주변압기 ","월성4호기 15차 계획예방정비 \n주변압기 역가압\n* 조작차단기 : CB 7700, 7772","○ 주변압기 및 소내용변압기 역가압","2018-01-27T19:00:00","2018-02-25T20:00:00","2018-01-27T19:00:00","2018-02-25T20:00:00","연속","Y"]
[3,"월성본부","월성2발","#4 기동용변압기 ","월성4호기 15차 계획예방정비 \n기동용변압기 점검\n* 조작차단기 : CB 7800, 7872","○ 기동용변압기 점검","2018-01-29T20:00:00","2018-02-07T17:00:00","2018-01-29T20:00:00","2018-02-07T17:00:00","연속","Y"]
[4,"한울본부","한울2발","#3 주변압기","한울3호기 14차 O/H 중 \n주변압기 교체\n* 조작차단기 : CB 7900, 7972","○ 주변압기 A,B,C상 교체\n○ 소내보조 변압기 01M/N 정밀점검","2018-01-03T10:00:00","2018-02-22T18:00:00","2018-01-03T10:00:00","2018-02-22T18:00:00","연속","Y"]