{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":5,"n_cols":11,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 2월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr","신가평S/S 765kV M.Tr 복구공사 (이설)","이설 후 #2M.Tr 분리운전 환원, 이설 후 각종 시험","2023-02-06 09:00","2023-02-17 18:00","2023-02-06 09:00","2023-02-17 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":57,"n_cols":11,"rows_kept":57,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 2월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #1 M.Tr","22-23년 중부P/O 총액공사","메커니즘 Air Ring V/V 교체","2023-02-01 09:00","2023-02-01 18:00","2023-02-01 09:00","2023-02-01 18:00","연속"]
[2,"서울","중부","중부S/S #3 M.Tr","22-23년 중부P/O 총액공사","메커니즘 Air Ring V/V 교체","2023-02-02 09:00","2023-02-02 18:00","2023-02-02 09:00","2023-02-02 18:00","연속"]
[3,"남서울","강남","신양재S/S #3 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","-345kV #74BAY B/F PNL 대체","2023-02-20 09:00","2023-02-24 18:00","2023-02-20 09:00","2023-02-24 18:00","연속"]
[4,"남서울","강남","신양재S/S #4 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","-345kV #74BAY B/F PNL 대체","2023-02-20 09:00","2023-02-24 18:00","2023-02-20 09:00","2023-02-24 18:00","연속"]
[5,"경기북부","구리","신포천S/S CB 7171","신포천S/S 345kV 7171 CB SF6가스 압력계 교체","신포천S/S 345kV 7171 CB SF6가스 압력계 불량(접지발생)에 따른 신품 교체작업","2023-02-22 09:00","2023-02-22 18:00","2023-02-22 09:00","2023-02-22 18:00","연속"]
[6,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사","345kV 신용인-동서울T/L No.53 본선로 설치 - 가선공사 : No.48~54","2023-02-20 07:00","2023-02-28 18:00","2023-02-20 07:00","2023-02-28 18:00","연속"]
[7,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사","345kV 신용인-동서울T/L No.53 본선로 설치 - 가선공사 : No.48~54","2023-02-10 07:00","2023-02-19 18:00","2023-02-10 07:00","2023-02-19 18:00","연속"]
[8,"경기","성남","신성남신양재#2 T/L","신성남S/S 345kV 7700CB 무부하 가압용","신성남S/S 345kV 7700CB 무부하 가압용","2023-02-20 09:00","2023-02-24 18:00","취소","취소","연속"]
[9,"강원","동해","동해S/S STATCOM CB","동해S/S STATCOM 정기점검","1. STATCOM 정기점검 2. STATCOM 냉각설비 개선공사 3. STATCOM YARD 포장공사 4. STATCOM Valve room 크레인 점검","2023-02-20 09:00","2023-03-17 18:00","2023-02-20 09:00","2023-03-17 18:00","연속"]
[10,"대전세종충남","대전","신옥천신계룡 T/L","[송전] 345kV 신옥천-청양 등 2개T/L 추락방지장치 설치공사","345kV 신옥천-신계룡T/L 추락방지장치 설치공사","2023-02-27 08:00","2023-02-27 18:00","2023-02-27 08:00","2023-02-27 18:00","연속"]
[11,"대전세종충남","대전","신계룡청양 T/L","[송전] 345kV 신옥천-청양 등 2개T/L 추락방지장치 설치공사","345kV 신계룡-청양T/L 추락방지장치 설치공사","2023-02-28 08:00","2023-02-28 18:00","2023-02-28 08:00","2023-02-28 18:00","연속"]
[12,"대전세종충남","세종","세종남청주#2 T/L","345kV 세종S/S #1M.Tr 증설공사","362kV 1CB설치관련 B/F PNL개조 LCP-GP1,2,0간 결선 및 인터록확인 B/F반 연동시험등","2023-02-06 09:00","2023-02-13 09:00","2023-02-13 09:00","2023-02-18 18:00","연속"]
[13,"대전세종충남","천안","신온양S/S CB 7900","신온양S/S 345kV 7971, 7900CB 개폐타임 측정","신온양S/S 345kV 7971, 7900CB 개폐타임 측정","2023-02-27 14:00","2023-02-27 18:00","2023-02-27 14:00","2023-02-27 18:00","연속"]
[14,"대전세종충남","천안","신온양S/S CB 7571","신온양S/S 345kV 7571, 7500CB 개폐타임 측정","신온양S/S 345kV 7571, 7500CB 개폐타임 측정","2023-02-23 09:00","2023-02-23 14:00","2023-02-23 09:00","2023-02-23 14:00","연속"]
[15,"대전세종충남","천안","신온양S/S CB 7871","신온양S/S 345kV 7871, 7800CB 개폐타임 측정","신온양S/S 345kV 7871, 7800CB 개폐타임 측정","2023-02-24 09:00","2023-02-24 14:00","2023-02-24 09:00","2023-02-24 14:00","연속"]
[16,"대전세종충남","천안","신온양S/S CB 7400","신온양S/S 345kV 7400, 7472CB 개폐타임 측정","신온양S/S 345kV 7400, 7472CB 개폐타임 측정","2023-02-22 09:00","2023-02-22 14:00","2023-02-22 09:00","2023-02-22 14:00","연속"]
[17,"대전세종충남","천안","신온양S/S CB 7500","신온양S/S 345kV 7571, 7500CB 개폐타임 측정","신온양S/S 345kV 7571, 7500CB 개폐타임 측정","2023-02-23 14:00","2023-02-23 18:00","2023-02-23 14:00","2023-02-23 18:00","연속"]
[18,"대전세종충남","천안","신온양S/S CB 7472","신온양S/S 345kV 7400, 7472CB 개폐타임 측정","신온양S/S 345kV 7400, 7472CB 개폐타임 측정","2023-02-22 14:00","2023-02-22 18:00","2023-02-22 14:00","2023-02-22 18:00","연속"]
[19,"대전세종충남","천안","신온양S/S CB 7971","신온양S/S 345kV 7971, 7900CB 개폐타임 측정","신온양S/S 345kV 7971, 7900CB 개폐타임 측정","2023-02-27 09:00","2023-02-27 14:00","2023-02-27 09:00","2023-02-27 14:00","연속"]
[20,"대전세종충남","천안","신온양S/S CB 7800","신온양S/S 345kV 7871, 7800CB 개폐타임 측정","신온양S/S 345kV 7871, 7800CB 개폐타임 측정","2023-02-24 14:00","2023-02-24 18:00","2023-02-24 14:00","2023-02-24 18:00","연속"]
[21,"대전세종충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양 등 2개T/L 추락방지장치 설치공사","345kV 신옥천-청양T/L 추락방지장치 설치공사","2023-02-20 08:00","2023-02-24 18:00","2023-02-20 08:00","2023-02-24 18:00","매일"]
[22,"전북","군산","군산새만금#1 T/L","군산변전소345kV GIS 대체공사(무부하가압)","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-02-09 09:00","2023-02-10 18:00","취소","취소","연속"]
[23,"전북","김제","신김제한빛NP#1 T/L","345kV 신김제-한빛T/L 추락방지시설 설치공사","○ 수평#1T/L 추락방지시설 설치 : No.26~221(196기)","2023-02-15 07:00","2023-02-28 18:00","취소","취소","연속"]
[24,"광주전남","순천","광양CC여수TP#2 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-13 09:00","2023-02-16 18:00","취소","취소","매일"]
[25,"광주전남","순천","광양CC여수TP#1 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-06 09:00","2023-02-10 18:00","2023-02-06 09:00","2023-02-10 18:00","매일"]
[26,"광주전남","순천","광양여수TP T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-17 09:00","2023-02-17 18:00","2023-02-17 09:00","2023-02-17 18:00","연속"]
[27,"광주전남","순천","율촌CC여수TP T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-20 09:00","2023-02-20 18:00","2023-02-20 09:00","2023-02-20 18:00","연속"]
[28,"대구","칠곡","북대구S/S 예비 M.Tr","북대구S/S 345kV 예비M.Tr 보통점검","북대구S/S 345kV 예비M.Tr 보통점검","2023-02-20 09:30","2023-02-20 18:00","취소","취소","연속"]
[29,"대구","칠곡","북대구S/S #1 Sh.R CB","북대구S/S 345kV #1Sh.R 보통점검","북대구S/S 345kV #1Sh.R 보통점검","2023-02-23 09:30","2023-02-23 18:00","2023-02-23 09:30","2023-02-23 18:00","연속"]
[30,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 변전설비 기초 철거 관련 안전이격 확보","2023-02-06 09:00","2023-02-10 18:00","2023-02-06 09:00","2023-02-10 18:00","연속"]
[31,"대구","포항","월성N/P CB 7800","월성S/Y 7800, 7872 GIS 보통점검","월성S/Y 7800, 7872 GIS 보통점검","2023-02-02 09:00","2023-02-07 18:00","2023-02-05 09:00","2023-02-09 18:00","연속"]
[32,"대구","포항","월성NP신월성NP#2 T/L","월성S/Y 7800,7872 GIS 정밀점검관련 무부하가압","월성S/Y 7800,7872 GIS 정밀점검관련 무부하가압","2023-02-07 09:00","2023-02-07 18:00","2023-02-09 16:00","2023-02-09 18:00","연속"]
[33,"대구","포항","월성N/P CB 7872","월성S/Y 7800, 7872 GIS 보통점검","월성S/Y 7800, 7872 GIS 보통점검","2023-02-02 09:00","2023-02-07 18:00","2023-02-05 09:00","2023-02-09 18:00","연속"]
[34,"경북","구미","선산S/S #2 M.Tr","2022-23년 구미전력지사 변전협력업체 총액공사","- 2차 A상 부싱 절연유 추적분석","2023-02-01 09:00","2023-02-01 14:00","2023-02-01 09:00","2023-02-01 14:00","연속"]
[35,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","74bay #3M.Tr Bay(7400, 7472) GIS 교체 - #75BUS 교체","2023-02-20 09:00","2023-03-09 09:00","2023-02-20 09:00","2023-03-09 09:00","연속"]
[36,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","74bay #3M.Tr Bay(7400, 7472) GIS 교체","2023-02-20 08:30","2023-04-28 18:00","2023-02-20 08:30","2023-04-28 18:00","연속"]
[37,"경북","구미","선산S/S #4 M.Tr","2022-23년 구미전력지사 변전협력업체 총액공사","- 2차 A상 부싱 절연유 추적분석","2023-02-01 14:00","2023-02-01 18:00","2023-02-01 14:00","2023-02-01 18:00","연속"]
[38,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 시험가압용도","2023-02-22 09:00","2023-02-22 18:00","2023-02-22 09:00","2023-02-22 18:00","연속"]
[39,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 시험가압용도","2023-02-23 09:00","2023-02-23 18:00","2023-02-23 09:00","2023-02-23 18:00","연속"]
[40,"부산울산","울산","신온산S/S #4 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","76BAY GIS(7600, 7672) 교체","2023-02-15 09:00","2023-03-31 18:00","2023-02-08 09:00","2023-03-31 18:00","연속"]
[41,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","76BAY GIS(7600, 7672) 교체","2023-02-15 09:00","2023-03-03 18:00","2023-02-08 09:00","2023-03-03 18:00","연속"]
[42,"부산울산","울산","신울산S/S #70G BUS","신울산S/S 345kV 용량대체공사","- 2차분 GIS 모선 연결","2023-02-20 09:00","2023-02-24 18:00","2023-02-20 09:00","2023-02-24 18:00","연속"]
[43,"부산울산","울산","북부산신울산#1 T/L","신울산S/S 345kV 용량대체공사","- 2차분 GIS 모선 연결 후 시험가압 선로","2023-02-23 09:00","2023-02-24 18:00","2023-02-23 09:00","2023-02-24 18:00","연속"]
[44,"부산울산","울산","신울산S/S #75G BUS","신울산S/S 345kV 용량대체공사","- 2차분 GIS 모선 연결","2023-02-13 09:00","2023-02-17 18:00","2023-02-13 09:00","2023-02-17 18:00","연속"]
[45,"부산울산","울산","북부산신울산#1 T/L","신울산S/S 345kV 용량대체공사","- 2차분 GIS 모선 연결 후 시험가압 선로","2023-02-16 09:00","2023-02-17 18:00","2023-02-16 09:00","2023-02-17 18:00","연속"]
[46,"부산울산","직할","신대연S/S #2 M.Tr","22~23년 직할변전협력회사 총액공사","#2M.Tr 정밀점검, 7272 GIS,4289 GIS,#2S.Tr 보통점검","2023-02-27 09:00","2023-03-17 18:00","취소","취소","매일"]
[47,"대구",null,"월성N/P #4 기동용변압기 (CB 7800, 7872)","월성4호기 19차 O/H 중 소내모선 정전작업 및 전원절체시험 * 조작차단기 : CB 7800, 7872","○ 소내모선 정전작업, ○ 소내전원절체시험","2023-02-21 09:00","2023-02-24 18:00","2023-02-21 09:00","2023-02-24 18:00","연속"]
[48,"대구",null,"월성N/P #4호기 주변압기 (CB 7700, 7772)","월성4호기 19차 O/H 중 전원절체시험 및 동기병입 회로시험 등\n * 조작차단기 : CB 7700,7772","○ 소내전원절체시험, ○ 동기병입 회로시험, ○ 계통연결 전 발전기 링크 조립 및 대기","2023-02-22 18:00","2023-03-03 07:00","2023-02-22 18:00","2023-03-03 07:00","연속"]
[49,"광주전남",null,"한빛N/P #5호기 주변압기 (CB 7D00, 7D71)","한빛5호기 14차 계획예방정비 주변압기 점검 및 갑종보호계전기 점검 ※ 조작차단기:7D00, 7D71","주변압기, 소내 전원 차단기, GIB, 갑종보호계전기 등 점검","2023-02-15 10:00","2023-03-08 18:00","2023-02-15 10:00","2023-03-08 18:00","연속"]
[50,"경북",null,"한울N/P #2호기 주변압기 (CB 7400, 7472)","2호기 24차 계획예방정비 * 조작차단기 : CB 7400, 7472","○ 주/소내보조/여자변압기 일반점검 ○ 소내전원 절체(UAT→SAT)시험","2023-02-24 16:00","2023-05-01 18:00","2023-02-24 16:00","2023-05-01 18:00","연속"]
[51,"경북",null,"한울N/P #4호기 주변압기 (CB 7A00, 7A72)","한울4호기 16차 계획예방정비 *조작 차단기 : CB 7A00, 7A72","○ 한울4호기 계획예방정비 수행 ○ 주변압기 점검","2023-02-22 10:00","2023-03-24 18:00","2023-02-22 10:00","2023-03-24 18:00","연속"]
[52,"대전세종충남",null,"보령T/P #77 BUS","#78Bay 및 #77BUS 정밀점검","#78Bay 및 #77BUS 정밀점검","2023-02-27 09:00","2023-03-17 17:00","2023-02-27 09:00","2023-03-17 17:00","연속"]
[53,"대전세종충남",null,"보령TP보령CC#2 T/L","보령연락#2T/L 정밀점검","보령연락#2T/L 정밀점검","2023-02-27 09:00","2023-03-17 17:00","2023-02-27 09:00","2023-03-17 17:00","연속"]

{"sheet":"154설비","index":2,"n_rows":55,"n_cols":11,"rows_kept":55,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 2월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울강동#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사","2023-02-27 08:00","2023-03-09 18:00","2023-02-27 08:00","2023-03-09 18:00","연속"]
[2,"경기북부","구리","서홍천청평PP T/L","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-02-27 09:00","2023-03-10 18:00","2023-02-27 09:00","2023-03-10 18:00","연속"]
[3,"경기북부","구리","서종청평PP#2 T/L","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-02-27 09:00","2023-03-10 18:00","2023-02-27 09:00","2023-03-10 18:00","연속"]
[4,"경기","직할","율전의왕#2 T/L","서서울,의왕S/S 154kV SW 증설공사","남군포-의왕#2T/L #2DS,CB,상부 무부하가압","2023-02-27 18:00","2023-02-28 18:00","2023-02-27 18:00","2023-02-28 18:00","연속"]
[5,"경기","직할","율전의왕#2 T/L","서서울,의왕S/S 154kV SW 증설공사","남군포-의왕#2T/L 1DS부 무부하가압","2023-02-16 18:00","2023-02-17 18:00","2023-02-16 18:00","2023-02-17 18:00","연속"]
[6,"경기","직할","율전의왕#2 T/L","서서울,의왕S/S 154kV SW 증설공사","남군포-의왕#2T/L #2DS부(엔드커버) 무부하가압","2023-02-07 18:00","2023-02-08 09:00","2023-02-07 18:00","2023-02-08 09:00","연속"]
[7,"경기","평택","원정평택TP#2 T/L","원정S/S 원정-평택T/P#2T/L GIS 누기개소 보수","원정S/S 원정-평택T/P#2T/L GIS 누기개소 보수","2023-02-11 09:00","2023-02-11 18:00","2023-02-11 09:00","2023-02-11 18:00","연속"]
[8,"경기","평택","평택오성CC#2 T/L","평택S/S 평택-오성복합#2T/L 에어링밸브 교체","평택S/S 평택-오성복합#2T/L 에어링밸브 누기관련 교체","2023-02-04 09:00","2023-02-04 18:00","2023-02-04 09:00","2023-02-04 18:00","연속"]
[9,"강원","강릉","신제천주진#1 T/L","2022년 가공송전선로 순시점검 위탁공사","154kV 신제천-주진T/L No.96-97 지장수목벌채","2023-02-13 08:00","2023-02-14 18:00","2023-02-13 08:00","2023-02-14 18:00","매일"]
[10,"강원","원주","홍천상남#2 T/L","345kV 동해 등 5개T/L 추락방지장치 설치공사","□ 와이어형 추락방지장치 설치 : 502기 ○ 345kV 동해T/L : No.174∼297(124기, 수직수평) ○ 154kV 둔내-횡성T/L : No.2∼52(51기, 수평) ○ 154kV 신제천-주진T/L : No.1∼100, 108～121(115기, 수평) ○ 154kV 주진-둔내T/L : No.1∼66(65기, 수평)","2023-02-27 08:00","2023-03-10 18:00","2023-02-27 08:00","2023-03-10 18:00","매일"]
[11,"강원","원주","홍천상남#1 T/L","345kV 동해 등 5개T/L 추락방지장치 설치공사","□ 와이어형 추락방지장치 설치 : 502기 ○ 345kV 동해T/L : No.174∼297(124기, 수직수평) ○ 154kV 둔내-횡성T/L : No.2∼52(51기, 수평) ○ 154kV 신제천-주진T/L : No.1∼100, 108～121(115기, 수평) ○ 154kV 주진-둔내T/L : No.1∼66(65기, 수평)","2023-02-13 08:00","2023-02-26 18:00","2023-02-13 08:00","2023-02-26 18:00","매일"]
[12,"대전세종충남","대전","남대전신흥#3 T/L","남대전S/S 154kV 노후 GIS 교체공사(4차분)","677, 6433Bay 교체","2023-02-06 08:00","2023-03-02 18:00","2023-02-06 08:00","2023-03-02 18:00","연속"]
[13,"대전세종충남","대전","신옥천남대전#1 T/L","남대전S/S 154kV 노후 GIS 교체공사(4차분)","677, 6433Bay 교체 (무부하 가압용)","2023-02-16 09:00","2023-02-17 09:00","2023-02-16 09:00","2023-02-17 09:00","연속"]
[14,"대전세종충남","대전","신옥천남대전#1 T/L","남대전S/S 154kV 노후 GIS 교체공사(4차분)","677, 6433Bay 교체 (무부하 가압용)","2023-02-24 09:00","2023-02-27 09:00","2023-02-24 09:00","2023-02-27 09:00","연속"]
[15,"대전세종충남","대전","가수원서대전#1 T/L","서대전S/S 154kV 장기사용 GIS 교체공사(4차분)","617,6133,6100 교체","2023-02-01 09:00","2023-03-08 18:00","2023-02-01 09:00","2023-03-08 18:00","연속"]
[16,"대전세종충남","대전","서대전S/S CB 6100","서대전S/S 154kV 장기사용 GIS 교체공사(4차분)","617,6133,6100 교체","2023-02-01 09:00","2023-03-08 18:00","2023-02-01 09:00","2023-03-08 18:00","연속"]
[17,"대전세종충남","세종","세종S/S #60 BUS","345kV 세종S/S #1M.Tr 증설공사","#1M.Tr 무부하 가압 - #60BUS 사용전검사 및 실부하가압","2023-02-10 15:00","2023-02-13 09:00","2023-02-17 15:00","2023-02-18 18:00","연속"]
[18,"대전세종충남","세종","세종S/S #65 BUS","345kV 세종S/S #1M.Tr 증설공사","#1M.Tr 무부하 가압 - #65BUS","2023-02-10 10:00","2023-02-10 15:00","2023-02-17 10:00","2023-02-17 15:00","연속"]
[19,"전북","김제","담양김제 T/L","154kV 담양-김제 62,63,64호 안전이격거리 확보공사","○ 본철탑 교체(3기) 및 가철탑(2기) 설치 - 본철탑 : 관형지지물 2기(No.62, 64), 인클로징 1기(No.63) - 가철탑 : No.62, 64","2023-02-21 07:00","2023-02-24 18:00","2023-02-21 07:00","2023-02-24 18:00","연속"]
[20,"전북","김제","김제칠보HP T/L","154kV 담양-김제 62,63,64호 안전이격거리 확보공사","○ 본철탑 교체(3기) 및 가철탑(2기) 설치 - 본철탑 : 관형지지물 2기(No.62, 64), 인클로징 1기(No.63) - 가철탑 : No.62, 64","2023-02-14 07:00","2023-02-20 18:00","2023-02-14 07:00","2023-02-20 18:00","연속"]
[21,"전북","김제","담양김제 T/L","154kV 담양-김제 62,63,64호 안전이격거리 확보공사","○ 본철탑 교체(3기) 및 가철탑(2기) 설치 - 본철탑 : 관형지지물 2기(No.62, 64), 인클로징 1기(No.63) - 가철탑 : No.62, 64","2023-02-13 07:00","2023-02-13 18:00","2023-02-13 07:00","2023-02-13 18:00","연속"]
[22,"전북","김제","신김제남전주#2 T/L","신김제S/S 170kV 차단기 보통점검","신김제S/S 170kV 차단기 보통점검","2023-02-08 09:00","2023-02-08 18:00","2023-02-08 09:00","2023-02-08 18:00","연속"]
[23,"전북","김제","정공정주#1 T/L","정공S/S 154kV 정공-정주#1T/L CVT 교체","정공S/S 154kV 정공-정주#1T/L CVT 교체","2023-02-09 09:00","2023-02-09 18:00","2023-02-09 09:00","2023-02-09 18:00","연속"]
[24,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","가. 철탑교체 : 설치 9기, 철거 9기, 가철탑 설치철거 6기 나. 전력선 교체 ○ 신김제-동전주T/L : 1.711C-km[ACSR 410㎟×2B] (33~39호) ○ 남전주-임실T/L : 1.235C-km[ACSR 410㎟×S] (23~28호) 다. 금구류 교체 및 기타 부대공사","2023-02-01 08:00","2023-02-07 17:00","취소","취소","연속"]
[25,"전북","직할","동전주북전주#2 T/L","동전주-북전주#2T/L 초기점검","GIS 초기점검","2023-02-21 15:00","2023-02-21 18:00","2023-02-21 15:00","2023-02-21 18:00","연속"]
[26,"전북","직할","북전주S/S #1 BUS","북전주S/S 170kV GIS 대체공사","154kV #1Sh.C GIS 대체","2023-02-28 15:00","2023-03-08 15:00","2023-02-14 15:00","2023-02-23 15:00","연속"]
[27,"전북","직할","동전주북전주#1 T/L","효성제 GIS 조작기구부 교체작업","효성제 GIS 조작기구부 교체작업","2023-02-20 09:00","2023-02-20 18:00","2023-02-20 09:00","2023-02-20 18:00","연속"]
[28,"전북","직할","북전주용담수력 T/L","북전주-용담수력T/L 전자변 러버히터 설치(즉시가압가능)","북전주-용담수력T/L 전자변 러버히터 설치 (즉시가압가능)","2023-02-16 15:00","2023-02-16 18:00","2023-02-16 15:00","2023-02-16 18:00","연속"]
[29,"전북","직할","북전주S/S #2 BUS","북전주S/S 170kV GIS 대체공사","154kV #1Sh.C GIS 대체","2023-02-27 10:00","2023-02-28 15:00","2023-02-13 10:00","2023-02-14 15:00","연속"]
[30,"광주전남","강진","해남진도#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","작업명 : 추락방지장치 설치 작업구간 : 해남해남CS 2~3호(병가구간)","2023-02-27 09:00","2023-02-27 18:00","2023-02-27 09:00","2023-02-27 18:00","연속"]
[31,"광주전남","강진","해남진도#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","작업명 : 추락방지장치 설치 작업구간 : 해남해남CS 2~3호(병가구간)","2023-02-13 09:00","2023-02-13 18:00","2023-02-13 09:00","2023-02-13 18:00","연속"]
[32,"광주전남","강진","해남해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","작업명 : 추락방지장치 설치 작업구간 : 해남해남CS 1호~81호","2023-02-13 09:00","2023-02-24 18:00","2023-02-13 09:00","2023-02-24 18:00","매일"]
[33,"광주전남","강진","남창해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","작업명 : 추락방지장치 설치 작업구간 : 해남해남CS 68-80호(병가구간)","2023-02-27 09:00","2023-03-02 18:00","2023-02-27 09:00","2023-03-02 18:00","매일"]
[34,"광주전남","강진","해남해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","작업명 : 추락방지장치 설치 작업구간 : 해남해남CS 1~81호","2023-02-27 09:00","2023-03-08 18:00","2023-02-27 09:00","2023-03-08 18:00","매일"]
[35,"광주전남","강진","남창해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","작업명 : 추락방지장치 설치 작업구간 : 해남해남CS 68-80호(병가구간)","2023-02-21 09:00","2023-02-24 18:00","2023-02-21 09:00","2023-02-24 18:00","매일"]
[36,"광주전남","광주","신광주일곡#2 T/L","2022년 광주전력 철탑추락방지장치 설치공사","수평추락방지장치 설치","2023-02-20 07:00","2023-02-20 18:00","취소","취소","매일"]
[37,"광주전남","광주","신광주장성#2 T/L","2022년 광주전력 철탑추락방지장치 설치공사","수평추락방지장치 설치","2023-02-20 07:00","2023-02-24 18:00","취소","취소","매일"]
[38,"광주전남","광주","신광주일곡#1 T/L","2022년 광주전력 철탑추락방지장치 설치공사","수평추락방지장치 설치","2023-02-13 07:00","2023-02-13 18:00","취소","취소","매일"]
[39,"광주전남","광주","신광주장성#1 T/L","2022년 광주전력 철탑추락방지장치 설치공사","수평 추락방지장치 설치","2023-02-13 07:00","2023-02-17 18:00","취소","취소","매일"]
[40,"광주전남","광주","장성영광#2 T/L","2022~23년 송전협력회사 총액공사","안전이격확보공사관련 보조암 설치","2023-02-27 07:00","2023-02-28 18:00","2023-02-27 07:00","2023-02-28 18:00","연속"]
[41,"광주전남","순천","벌교고흥#2 T/L","154kV 벌교-고흥T/L 선종교체공사","154kV 벌교-고흥T/L No.1~고흥S/S (37.2km) ACSR/AW 410sq를 ASCC/TW 520sq로 교체","2023-02-20 07:00","2023-04-07 18:00","2023-02-20 07:00","2023-04-07 18:00","연속"]
[42,"광주전남","순천","여수TP화치#2 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-20 09:00","2023-02-20 18:00","취소","취소","연속"]
[43,"광주전남","순천","여수TP화치#1 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-17 09:00","2023-02-17 18:00","취소","취소","연속"]
[44,"광주전남","순천","호남TP여수TP#2 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-17 09:00","2023-02-17 18:00","취소","취소","연속"]
[45,"광주전남","순천","호남TP여수TP#1 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-20 09:00","2023-02-20 18:00","취소","취소","연속"]
[46,"광주전남","순천","여천호남TP#1 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-07 09:00","2023-02-07 18:00","취소","취소","연속"]
[47,"광주전남","순천","여천호남TP#2 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","345kV 광양CC-여수TP T/L 추락방지시설 설치","2023-02-14 09:00","2023-02-14 18:00","취소","취소","연속"]
[48,"대구","달성","구지서구지#2 T/L","#61-#66 모선보호반 대체작업 관련 시험","#61-#66 모선보호반 대체작업 관련 시험","2023-02-22 14:30","2023-02-22 15:00","2023-02-22 14:30","2023-02-22 15:00","연속"]
[49,"경남","직할","창공월림#2 T/L","154kV 창공-월림T/L 4-5호 인근 공사현장 안전확보","154kV 창공-월림T/L 4-5호 송전선로 직하 공장신축 공사현장 안전확보(민원)","2023-02-01 09:00","2023-02-28 18:00","2023-02-01 09:00","2023-02-28 18:00","연속"]
[50,"경남","직할","창공월림#1 T/L","154kV 창공-월림T/L 4-5호 인근 공사현장 안전확보","154kV 창공-월림T/L 4-5호 송전선로 직하 공장신축 공사현장 안전확보(민원)","2023-02-01 09:00","2023-02-28 18:00","2023-02-01 09:00","2023-02-28 18:00","연속"]
[51,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제T/L OPGW 불량사항 조치","154kV 신고성-거제T/L OPGW 불량사항 조치","2023-02-18 09:00","2023-02-18 18:00","2023-02-19 09:00","2023-02-19 18:00","연속"]