{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":14,"n_cols":11,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 3월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백신가평#2 T/L","신태백S/S 삼척블루파워 발전기 차단 고장파급방지시스템(SPS) 설치공사","신태백S/S 삼척블루파워 발전기 차단 고장파급방지시스템(SPS) 설치공사","2023-03-23 10:00","2023-03-24 18:00","취소","취소","연속"]
[2,"강원","태백","신태백S/S #1 BUS","2023년 태백전력지사 변전정비회사 총액공사","신태백S/S 765kV #1BUS 보호반 대체","2023-03-23 10:00","2023-03-30 18:00","2023-03-23 10:00","2023-03-30 18:00","연속"]
[3,"강원","태백","신태백S/S #2 BUS","2023년 태백전력지사 변전정비회사 총액공사","신태백S/S 765kV #2BUS 보호반 대체","2023-03-31 09:00","2023-04-07 18:00","2023-03-31 09:00","2023-04-07 18:00","연속"]
[4,"강원","태백","신태백신가평#1 T/L","신태백S/S 삼척블루파워 발전기 차단 고장파급방지시스템(SPS) 설치공사","신태백S/S 삼척블루파워 발전기 차단 고장파급방지시스템(SPS) 설치공사","2023-03-23 10:00","2023-03-24 18:00","취소","취소","연속"]
[5,"경기북부","구리","신가평S/S #2 M.Tr","신가평S/S 765kV M.Tr 이설공사","신가평S/S 765kV M.Tr 이설공사 - #2M.Tr 이동 완료 후 분리운전 환원작업 (R Tank 분리운전 → R Tank 접속)","2023-03-13 09:00","2023-03-22 18:00","취소","취소","연속"]
[6,"대전세종충남","서산","신서산S/S #4 M.Tr","23년 서산P/O 변전협력회사 총액공사","신서산S/S 765kV #4M.Tr 3차측 광명제 PT 교체 (병행) 신서산S/S 765kV #4M.Tr 2차 CB 보통점검 (병행) 신서산S/S 765kV #4M.Tr 2차측 불량 부싱압력계 교체","2023-03-29 09:00","2023-03-31 18:00","2023-03-29 09:00","2023-03-31 18:00","연속"]
[7,"대전세종충남","서산","신서산S/S #2 BUS","23년 서산P/O 배전반 대체공사","신서산S/S 765kV #2BUS 보호반 대체 (병행) 신서산S/S 765kV #2BUS 가스누기 보수공사","2023-03-13 09:00","2023-03-17 18:00","취소","취소","연속"]
[8,"대전세종충남","서산","신서산S/S #1 BUS","23년 서산P/O 배전반 대체공사","신서산S/S 765kV #1BUS 보호반 대체","2023-03-06 09:00","2023-03-10 18:00","취소","취소","연속"]
[9,"충북","직할","신중부신안성#1 T/L","2022~2023년 충북본부 직할 가공송전 협력회사 총액공사","24~26,28~30,31~32호 5경간 가공지선 항공장애표시구 교체(풍소음방지용)","2023-03-06 07:30","2023-03-10 18:00","2023-03-06 07:30","2023-03-10 18:00","연속"]
[10,"충북","직할","신중부신안성#2 T/L","765kV 신중부-신안성T/L OPGW 항공구 풍소음 민원관련 교체공사","24~26,28~30,31~32호 5경간 OPGW 항공장애표시구 26개 교체(풍소음방지용)","2023-03-18 08:00","2023-03-19 18:00","2023-03-18 08:00","2023-03-19 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":328,"n_cols":11,"rows_kept":328,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 3월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부서울CC#2 T/L","23 중부P/O 총액공사","GIS 보통점검 보조계전기 교체 인출PT 보통점검","2023-03-10 10:00","2023-03-10 18:00","취소","취소","연속"]
[2,"서울","중부","중부서울CC#1 T/L","23 중부P/O 총액공사","GIS 보통점검 인출PT 보통점검","2023-03-07 10:00","2023-03-07 18:00","2023-03-07 10:00","2023-03-07 18:00","연속"]
[3,"서울","중부","중부S/S CB 7300","23 중부P/O 총액공사","GIS 보통점검 보조계전기 교체","2023-03-07 10:00","2023-03-07 18:00","2023-03-07 10:00","2023-03-07 18:00","연속"]
[4,"서울","중부","중부S/S CB 7400","23 중부P/O 총액공사","차단기조작시험 공기압력계 교체","2023-03-10 10:00","2023-03-10 18:00","2023-03-10 10:00","2023-03-10 18:00","연속"]
[5,"남서울","강남","신양재S/S #2 M.Tr","22-23년도 강남전력지사 변전협력회사 총액공사","-M.Tr 보통 -3차 VCB, DS 보통","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[6,"남서울","강남","신양재S/S #1 M.Tr","22-23년도 강남전력지사 변전협력회사 총액공사","-M.Tr 보통 -3차 VCB, DS 보통","2023-03-02 09:00","2023-03-02 18:00","2023-03-02 09:00","2023-03-02 18:00","연속"]
[7,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","옥외철구 설비 철거 관련 안전이격거리 확보, 보호배전반 이설","2023-03-24 09:00","2023-04-06 18:00","2023-03-27 09:00","2023-04-07 18:00","연속"]
[8,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","옥외철구 설비 GIS 운전전환, 옥외철구 설비 철거","2023-03-10 09:00","2023-03-23 18:00","2023-03-13 09:00","2023-03-24 18:00","연속"]
[9,"남서울","동서울","동서울미금#2 T/L","동서울S/S 동서울-미금#2T/L GIS 정밀점검","2023년도 362kV GIS 정밀점검","2023-03-13 09:00","2023-03-17 18:00","2023-03-13 09:00","2023-03-18 18:00","연속"]
[10,"남서울","동서울","신성남동서울#2 T/L","동서울S/S 신성남-동서울#2T/L GIS 정밀점검","2023년도 362kV GIS 정밀점검","2023-03-17 07:00","2023-03-23 17:00","2023-03-20 09:00","2023-03-25 18:00","연속"]
[11,"남서울","영등포","신광명S/S CB 신7572","2022~23년 영등포전력지사 변전협력회사 총액공사","신7572 GIS 초기점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[12,"남서울","영등포","신광명S/S CB 신7500","2022~23년 영등포전력지사 변전협력회사 총액공사","신7500 GIS 초기점검","2023-03-21 09:00","2023-03-21 18:00","2023-03-21 09:00","2023-03-21 18:00","연속"]
[13,"남서울","영등포","신광명S/S CB 신7400","2022~23년 영등포전력지사 변전협력회사 총액공사","신7400 GIS 초기점검","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[14,"남서울","영등포","신광명S/S CB 신7472","2022~23년 영등포전력지사 변전협력회사 총액공사","신7472 GIS 초기점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[15,"남서울","영등포","신광명S/S CB 신7471","2022~23년 영등포전력지사 변전협력회사 총액공사","신7471 GIS 초기점검","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[16,"남서울","영등포","신광명S/S CB 7100","2022~23년 영등포전력지사 변전협력회사 총액공사","345kV GCB 7100 보통점검","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[17,"남서울","영등포","신광명S/S CB 신7371","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-03-13 09:00","2023-04-25 18:00","2023-03-20 09:00","2023-05-02 18:00","연속"]
[18,"남서울","영등포","신광명S/S #2 M.Tr","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-03-13 09:00","2023-04-25 18:00","2023-03-20 09:00","2023-05-02 18:00","연속"]
[19,"남서울","영등포","신광명S/S CB 7172","2022~23년 영등포전력지사 변전협력회사 총액공사","345kV GCB 7172 보통점검","2023-03-10 09:00","2023-03-10 18:00","취소","취소","연속"]
[20,"남서울","영등포","신광명S/S CB 신7100","2022~23년 영등포전력지사 변전협력회사 총액공사","신7100 GIS 하자점검","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[21,"남서울","영등포","신광명S/S CB 신7172","2022~23년 영등포전력지사 변전협력회사 총액공사","신7172 GIS 하자점검","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[22,"남서울","영등포","신광명S/S CB 신7171","2022~23년 영등포전력지사 변전협력회사 총액공사","신7171 GIS 하자점검","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[23,"남서울","영등포","서서울신광명#2 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-03-02 09:00","2023-03-12 18:00","취소","취소","연속"]
[24,"남서울","영등포","신광명S/S CB 7472","2022~23년 영등포전력지사 변전협력회사 총액공사","345kV GCB 7472 보통점검","2023-03-31 09:00","2023-03-31 18:00","2023-03-31 09:00","2023-03-31 18:00","연속"]
[25,"남서울","영등포","신광명S/S CB 신7571","2022~23년 영등포전력지사 변전협력회사 총액공사","신7571 GIS 초기점검","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[26,"인천","김포","신김포S/S CB 7600","신김포S/S #3M.Tr용 362kV GIS 증설공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차)","2023-03-20 09:00","2023-04-01 18:00","2023-03-20 09:00","2023-04-01 18:00","연속"]
[27,"인천","김포","신김포S/S #76 BUS","신김포S/S #3M.Tr용 362kV GIS 증설공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차)","2023-03-20 09:00","2023-04-01 18:00","2023-03-20 09:00","2023-04-01 18:00","연속"]
[28,"인천","부평","신인천C/C CB 7671","신인천S/Y 76BAY B/F 보호반 대체 공사","신인천S/Y 76BAY B/F 보호반 대체 공사","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[29,"인천","부평","신인천C/C CB 7600","신인천S/Y 76BAY B/F 보호반 대체 공사","신인천S/Y 76BAY B/F 보호반 대체 공사","2023-03-27 09:00","2023-03-27 18:00","2023-03-27 09:00","2023-03-27 18:00","연속"]
[30,"인천","부평","신인천C/C CB 7672","신인천S/Y 76BAY B/F 보호반 대체 공사","신인천S/Y 76BAY B/F 보호반 대체 공사","2023-03-29 09:00","2023-03-29 18:00","2023-03-29 09:00","2023-03-29 18:00","연속"]
[31,"인천","시흥","신시흥신광명#1 T/L","신시흥S/S 345kV 신시흥신광명#1 T/L GIS 보통점검(7971)","신시흥S/S 345kV 신시흥신광명#1 T/L GIS 보통점검(7971) -LA 보통점검","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[32,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S #1 M.Tr 2차 GIS 보통점검 및 #1S.Tr 보통점검","신시흥#S/S #1 M.Tr 2차 GIS(6144) 보통점검 및 #1S.Tr 보통점검 3차 Main(4179), #1S.Tr(4189), #1-1,2 Sh.R VCB 조작시험 1M.Tr 2차 부싱 절연유 채유","2023-03-17 09:00","2023-03-17 18:00","2023-03-17 09:00","2023-03-17 18:00","연속"]
[33,"인천","시흥","신시흥#1S/S CB 7900","신시흥S/S 345kV 신시흥신광명#1 T/L GIS 보통점검(7900)","신시흥S/S 345kV 신시흥신광명#1 T/L GIS 보통점검(7900)","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[34,"인천","시흥","신시흥#1S/S CB 7A00","신시흥S/S 345kV 신시흥신광명#2 T/L GIS 보통점검(7A00)","신시흥S/S 345kV 신시흥신광명#2 T/L GIS 보통점검(7A00)","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[35,"인천","시흥","신시흥#1S/S CB 7B00","신시흥S/S 345kV 신가좌신시흥#1T/L GIS 보통점검(7B00)","신시흥S/S 345kV 신가좌신시흥#1 T/L GIS 보통점검(7B00)","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[36,"인천","시흥","신가좌신시흥#1 T/L","신시흥S/S 345kV 신가좌신시흥#1 T/L GIS 보통점검","신시흥S/S 345kV 신가좌신시흥#1 T/L GIS 보통점검(7B71) -LA 보통점검","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[37,"인천","시흥","신가좌신시흥#2 T/L","신시흥S/S 345kV 신가좌신시흥#2 T/L 결상회로 보완","신시흥S/S 345kV 신가좌신시흥#2 T/L GIS 보통점검(7C71, 7C00) 및 결상회로 보완 - LA 보통점검","2023-03-06 09:00","2023-03-07 18:00","2023-03-06 09:00","2023-03-07 18:00","연속"]
[38,"인천","시흥","신시흥#1S/S CB 7A71","신시흥S/S 345kV 신시흥신광명#2 T/L GIS 보통점검(7A71)","신시흥S/S 345kV 신시흥신광명#2 T/L GIS 보통점검(7A71)","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[39,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S 345kV #6 M.Tr 보통점검 및 보호반 대체","신시흥S/S 345kV #6 M.Tr 보통점검 및 변압기 보호반 대체 - OLTC 보통점검 - 1,2,3차 LA 보통점검 - 1차 GIS 보통점검, 2차 GIS 보통점검 - #4S.Tr 보통점검 및 #4S.Tr VCB(4689), DS(4685) 보통점검 - 3차 PT 보통점검","2023-03-20 09:00","2023-03-24 18:00","2023-03-20 09:00","2023-03-24 18:00","연속"]
[40,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥S/S 345kV #4M.Tr 보통점검 76Bay B/F반 대체","신시흥S/S 345kV #4M.Tr 보통점검 및76Bay B/F 보호반 대체 - OLTC 보통점검 - 1차 LA 대체, 2,3차 LA 보통점검 - #4M.Tr 1차 GIS(7672) 보통점검, 2차 GIS 조작시험 - 3차 PT 보통점검 - 절연커버 시공","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[41,"인천","시흥","서서울#2신시흥#2 T/L","신시흥S/S 7671,7600 GIS 보통점검, 76Bay B/F 대체","신시흥S/S 7671, 7600 GIS 보통점검 및 76Bay B/F 보호반 대체 - 서서울2신시흥#2T/L LA 대체","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[42,"인천","직할","갈산S/S #2 Sh.R CB","갈산S/S #2Sh.R GIS 하자점검","갈산S/S #2Sh.R GIS 하자점검","2023-03-03 09:30","2023-03-03 18:00","2023-03-03 09:30","2023-03-03 18:00","연속"]
[43,"인천","직할","갈산S/S #1 Sh.R CB","갈산S/S #1Sh.R GIS 하자점검","갈산S/S #1Sh.R GIS 하자점검","2023-03-02 09:30","2023-03-02 18:00","2023-03-02 09:30","2023-03-02 18:00","연속"]
[44,"인천","직할","신부평S/S #1 M.Tr","신부평S/S 362kV #1M,Tr 1차,2차 GIS 보통점검","신부평S/S 362kV #1M,Tr 1차,2차 GIS 보통점검","2023-03-07 09:30","2023-03-07 18:00","2023-03-07 09:30","2023-03-07 18:00","연속"]
[45,"인천","직할","신부평S/S #2 M.Tr","신부평S/S 362kV #2M,Tr 1차,2차 GIS 보통점검","신부평S/S 362kV #2M,Tr 1차,2차 GIS 보통점검/ 7200조작시험","2023-03-08 09:30","2023-03-08 18:00","2023-03-08 09:30","2023-03-08 18:00","연속"]
[46,"인천","직할","신부평S/S #3 M.Tr","신부평S/S 362kV #3M,Tr 1차,2차 GIS 보통점검","신부평S/S 362kV #3M,Tr 1차,2차 GIS 보통점검/ 7300조작시험","2023-03-09 09:30","2023-03-09 18:00","2023-03-09 09:30","2023-03-09 18:00","연속"]
[47,"인천","직할","신부평S/S #4 M.Tr","신부평S/S 362kV #4M,Tr 1차GIS 조작시험","신부평S/S 362kV #4M,Tr 1차GIS 조작시험/ 7400GIS 조작시험","2023-03-10 09:30","2023-03-10 18:00","2023-03-10 09:30","2023-03-10 18:00","연속"]
[48,"인천","직할","신부평S/S #4 Sh.R CB","신부평S/S #4Sh.R GIS 보통점검","신부평S/S #4Sh.R GIS 보통점검","2023-03-14 09:30","2023-03-14 18:00","2023-03-14 09:30","2023-03-14 18:00","연속"]
[49,"경기북부","고양","신덕은S/S #3 M.Tr","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[50,"경기북부","고양","신덕은S/S #1 M.Tr","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[51,"경기북부","고양","신덕은파주문산CC#2 T/L","22-23년 고양전력지사 변전협력회사 총액공사","신덕은S/S 신덕은-파주문산#1T/L 362kV GIS 보통점검(7372)","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[52,"경기북부","고양","신덕은파주문산CC#1 T/L","22-23년 고양전력지사 변전협력회사 총액공사","신덕은S/S 신덕은-파주문산#1T/L 362kV GIS 보통점검(7572)","2023-03-21 09:00","2023-03-21 18:00","2023-03-21 09:00","2023-03-21 18:00","연속"]
[53,"경기북부","고양","신덕은S/S #2 M.Tr","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-21 09:00","2023-03-21 18:00","2023-03-21 09:00","2023-03-21 18:00","연속"]
[54,"경기북부","고양","파주문산C/C CB 7100","22-23년 고양전력지사 변전협력회사 총액공사","파주문산C/C 7100 BUSTIE 362kV GIS 보통점검","2023-03-06 10:00","2023-03-06 18:00","2023-03-06 10:00","2023-03-06 18:00","연속"]
[55,"경기북부","고양","파주문산C/C CB 7400","22-23년 고양전력지사 변전협력회사 총액공사","파주문산C/C 7400 BUSTIE 362kV GIS 보통점검","2023-03-09 10:00","2023-03-09 18:00","2023-03-09 10:00","2023-03-09 18:00","연속"]
[56,"경기북부","고양","파주문산C/C CB 7300","22-23년 고양전력지사 변전협력회사 총액공사","파주문산C/C 7300 BUSTIE 362kV GIS 보통점검","2023-03-08 10:00","2023-03-08 18:00","2023-03-08 10:00","2023-03-08 18:00","연속"]
[57,"경기북부","고양","파주문산C/C CB 7200","22-23년 고양전력지사 변전협력회사 총액공사","파주문산C/C 7200 BUSTIE 362kV GIS 보통점검","2023-03-07 10:00","2023-03-07 18:00","2023-03-07 10:00","2023-03-07 18:00","연속"]
[58,"경기북부","구리","미금S/S CB 7271","미금S/S 345kV 가변형 리액터(VSR) 설치공사","- OLTC Tap 표시관련 MDU 전류 측정을 위한 OLTC Tap 조정","2023-03-07 10:00","2023-03-10 16:00","취소","취소","매일"]
[59,"경기북부","구리","미금S/S #2 M.Tr","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사(4차분) - 362kV 50kA GIS → 63kA GIS 용량대체","2023-03-27 09:00","2023-06-23 18:00","2023-03-27 09:00","2023-06-23 18:00","연속"]
[60,"경기북부","구리","동서울미금#1 T/L","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사(4차분) - 362kV 50kA GIS → 63kA GIS 용량대체","2023-03-27 09:00","2023-06-23 18:00","2023-03-27 09:00","2023-06-23 18:00","연속"]
[61,"경기북부","구리","동서울미금#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치(수평)","2023-03-17 07:30","2023-03-17 18:00","취소","취소","연속"]
[62,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 종합예방진단시스템 설치","□ 미금S/S 종합예방진단시스템 설치 - 345kV #3M.Tr OLTC PD센서 및 구동모터센서 설치 - M.Tr 상부 배관 설치 및 기타 작업 - MLU ↔ #3M.Tr 간 연동시험","2023-03-16 09:00","2023-03-17 18:00","2023-03-16 09:00","2023-03-17 18:00","연속"]
[63,"경기북부","구리","미금성동#1 T/L","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사 - #71Bay 회로 보완작업","2023-03-20 09:00","2023-03-24 18:00","2023-03-20 09:00","2023-03-24 18:00","연속"]
[64,"경기북부","구리","미금S/S #1 M.Tr","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사 - #71Bay 회로 보완작업","2023-03-20 09:00","2023-03-24 18:00","2023-03-20 09:00","2023-03-24 18:00","연속"]
[65,"경기북부","구리","신가평신의정부#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치(수평)","2023-03-23 07:30","2023-03-24 18:00","2023-03-23 07:30","2023-03-24 18:00","연속"]
[66,"경기북부","구리","신포천S/S CB 7172","2022~23 구리전력 변전협력 총액공사","신포천S/S #1M.Tr 1차 7172 GIS 조작시험","2023-03-09 16:00","2023-03-09 18:00","2023-03-09 16:00","2023-03-09 18:00","연속"]
[67,"경기북부","구리","신포천S/S CB 7100","2022~23 구리전력 변전협력 총액공사","신포천S/S 포천LNG#1 - #1M.Tr TIE 7100 GIS 조작시험","2023-03-09 13:00","2023-03-09 16:00","2023-03-09 13:00","2023-03-09 16:00","연속"]
[68,"경기북부","구리","신포천S/S CB 7472","2022~23 구리전력 변전협력 총액공사","신포천S/S #3M.Tr 1차 7472 GIS 조작시험","2023-03-13 15:30","2023-03-13 18:00","2023-03-13 15:30","2023-03-13 18:00","연속"]
[69,"경기북부","구리","신포천S/S CB 7271","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천LNGCC#2T/L 7271 GIS 조작시험","2023-03-09 09:00","2023-03-09 13:00","2023-03-09 09:00","2023-03-09 13:00","연속"]
[70,"경기북부","구리","신포천S/S CB 7400","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천CC#2T/L - #3M.Tr 1차 TIE 7400 GIS 조작시험","2023-03-13 09:00","2023-03-13 12:00","2023-03-13 09:00","2023-03-13 12:00","연속"]
[71,"경기북부","구리","신포천S/S CB 7471","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천CC#2T/L 7471 GIS 조작시험","2023-03-13 13:00","2023-03-13 15:30","2023-03-13 13:00","2023-03-13 15:30","연속"]
[72,"경기북부","구리","포천LNGC/C CB 7272","2022~23 구리전력 변전협력 총액공사","포천LNGCC #2G/T TR 2차 7272 GIS 보통점검","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[73,"경기북부","구리","포천LNGC/C CB 7200","2022~23 구리전력 변전협력 총액공사","포천LNGCC 신포천#2T/L - #2G/T TR TIE 7200 GIS 보통점검","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[74,"경기북부","구리","포천LNGC/C CB 7271","2022~23 구리전력 변전협력 총액공사","포천LNGCC 신포천-포천LNGCC#2T/L 7271 GIS 보통점검","2023-03-29 09:00","2023-03-29 18:00","2023-03-29 09:00","2023-03-29 18:00","연속"]
[75,"경기북부","직할","신의정부S/S CB 7772","22-23년도 직할 변전협력회사 총액공사","신의정부S/S #2Sh.R 보통점검","2023-03-23 07:30","2023-03-24 18:00","2023-03-23 07:30","2023-03-24 18:00","연속"]
[76,"경기북부","직할","신의정부S/S #3 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","신의정부S/S #3Sh.R 보통점검","2023-03-06 09:00","2023-03-08 18:00","2023-03-06 09:00","2023-03-08 18:00","연속"]
[77,"경기북부","직할","신의정부S/S CB 7800","22-23년도 직할 변전협력회사 총액공사","신의정부S/S #3Sh.R 보통점검","2023-03-06 09:00","2023-03-08 18:00","2023-03-06 09:00","2023-03-08 18:00","연속"]
[78,"경기북부","직할","신의정부S/S CB 7872","22-23년도 직할 변전협력회사 총액공사","신의정부S/S #3Sh.R 보통점검","2023-03-06 09:00","2023-03-08 18:00","2023-03-06 09:00","2023-03-08 18:00","연속"]
[79,"경기북부","직할","신가평신의정부#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV 7871, 7800 GIS 보통점검","2023-03-06 09:00","2023-03-08 18:00","2023-03-06 09:00","2023-03-09 18:00","연속"]
[80,"경기북부","직할","신의정부S/S #2 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","신의정부S/S #2Sh.R 보통점검","2023-03-23 07:30","2023-03-24 18:00","2023-03-23 07:30","2023-03-24 18:00","연속"]
[81,"경기북부","직할","신의정부미금#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV 7571 GIS 보통점검, 7500 조작시험","2023-03-16 09:00","2023-03-17 18:00","2023-03-16 09:00","2023-03-17 18:00","연속"]
[82,"경기북부","직할","신의정부S/S #3 M.Tr","22-23년도 직할 변전협력회사 총액공사","신의정부S/S #3M.Tr 보통점검","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[83,"경기북부","직할","양주S/S #4 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","양주S/S #4Sh.R 보통점검","2023-03-13 09:00","2023-03-14 13:00","2023-03-13 09:00","2023-03-14 13:00","연속"]
[84,"경기북부","직할","신의정부양주#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV 7271, 7200 GIS 보통점검 신의정부S/S 362kV 7471 GIS 조작시험","2023-03-20 09:00","2023-03-22 18:00","2023-03-20 09:00","2023-03-22 18:00","연속"]
[85,"경기북부","직할","양주S/S #2 M.Tr","22-23년도 직할 변전협력회사 총액공사","양주S/S 345kV #2M.Tr 보통점검","2023-03-20 09:00","2023-03-23 18:00","취소","취소","연속"]
[86,"경기북부","직할","양주S/S #1 M.Tr","2022-2023년 경기북부 직할 변전협력회사 총액공사","362kV 7172 GIS 보통점검","2023-03-09 09:00","2023-03-10 18:00","2023-03-29 09:00","2023-03-31 18:00","연속"]
[87,"경기북부","직할","양주S/S #67 BUS","양주 HVDC용 170kV GIS 설치공사","170kV GIS 2CCT","2023-03-29 14:00","2023-03-31 18:00","취소","취소","연속"]
[88,"경기북부","직할","양주S/S #62 BUS","양주 HVDC 용 170kV GIS 설치공사","170kV GIS 2CCT","2023-03-27 09:00","2023-03-29 14:00","취소","취소","연속"]
[89,"경기북부","직할","양주S/S #66 BUS","양주 HVDC용 170kV GIS 설치공사","170kv GIS 2CCT","2023-03-22 14:00","2023-03-24 18:00","취소","취소","연속"]
[90,"경기북부","직할","양주S/S #61 BUS","양주 HVDC 용 170kV GIS 설치공사","170kV GIS 2CCT 설치","2023-03-20 09:00","2023-03-22 14:00","취소","취소","연속"]
[91,"경기북부","직할","양주중부#1 T/L","22-23년도 직할 변전협력회사 총액공사","양주S/S #5Sh.R 보통점검","2023-03-14 13:00","2023-03-15 18:00","취소","취소","연속"]
[92,"경기북부","직할","양주S/S #5 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","양주S/S #5Sh.R 보통점검","2023-03-14 13:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-17 18:00","연속"]
[93,"경기북부","직할","양주S/S CB 7600","22-23년도 직할 변전협력회사 총액공사","양주S/S #4Sh.R 보통점검","2023-03-13 09:00","2023-03-14 13:00","2023-03-13 09:00","2023-03-14 13:00","연속"]
[94,"경기북부","직할","양주S/S CB 7672","22-23년도 직할 변전협력회사 총액공사","양주S/S #4Sh.R 보통점검","2023-03-13 09:00","2023-03-14 13:00","2023-03-13 09:00","2023-03-14 13:00","연속"]
[95,"경기","군포","서서울#2신성남#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-11 14:00","2023-03-11 18:00","취소","취소","연속"]
[96,"경기","군포","서서울#2S/S #1 BUS","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-03-08 09:00","2023-03-11 18:00","2023-03-08 09:00","2023-03-11 18:00","연속"]
[97,"경기","군포","서서울#2신시흥#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-23 14:00","2023-03-23 18:00","2023-03-23 14:00","2023-03-23 18:00","연속"]
[98,"경기","군포","서서울#2S/S #2 BUS","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-03-20 09:00","2023-03-23 18:00","2023-03-20 09:00","2023-03-23 18:00","연속"]
[99,"경기","군포","서서울#2신성남#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-03-15 09:00","2023-03-16 18:00","2023-03-15 09:00","2023-03-16 18:00","연속"]
[100,"경기","군포","서서울#2S/S CB 7D71, 7D00","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-03-02 09:00","2023-03-03 18:00","2023-03-02 09:00","2023-03-03 18:00","연속"]
[101,"경기","군포","서서울#2신성남#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-07 14:00","2023-03-07 18:00","취소","취소","연속"]
[102,"경기","군포","서서울#2S/S #1 BUS","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-07 14:00","2023-03-07 18:00","취소","취소","연속"]
[103,"경기","군포","서서울#2S/S CB 7C71, 7C00","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-03-06 09:00","2023-03-07 18:00","2023-03-06 09:00","2023-03-07 18:00","연속"]
[104,"경기","군포","서서울#2신성남#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-03 14:00","2023-03-03 18:00","취소","취소","연속"]
[105,"경기","군포","서서울#2S/S #1 BUS","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-03 14:00","2023-03-03 18:00","취소","취소","연속"]
[106,"경기","군포","서서울#2신성남#2 T/L","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-03-13 09:00","2023-03-14 18:00","2023-03-13 09:00","2023-03-14 18:00","연속"]
[107,"경기","동부","곤지암S/S CB 7571","곤지암S/S 345kV 차단기 설치공사","7571GIS 무부하가압(전력케이블 포함)","2023-03-25 08:00","2023-03-26 17:00","2023-03-25 08:00","2023-03-26 17:00","연속"]
[108,"경기","동부","곤지암S/S CB 7600","곤지암S/S 345kV 차단기 설치공사","7671GIS 준공시험 및 전력케이블 내전압 7671GIS 무부하가압(전력케이블 포함)","2023-03-13 09:00","2023-03-26 17:00","2023-03-13 09:00","2023-03-26 17:00","연속"]
[109,"경기","동부","곤지암S/S CB 7500","곤지암S/S 345kV 차단기 설치공사","7571GIS 무부하가압(전력케이블 포함)","2023-03-25 08:00","2023-03-26 17:00","2023-03-25 08:00","2023-03-26 17:00","연속"]
[110,"경기","동부","곤지암S/S #1 BUS","곤지암S/S 345kV 차단기 설치공사","7571,7671GIS 무부하가압(전력케이블 포함)","2023-03-25 08:00","2023-03-26 17:00","2023-03-25 08:00","2023-03-26 17:00","연속"]
[111,"경기","동부","곤지암S/S CB 7571","곤지암S/S 345kV 차단기 설치공사","7571GIS 사용전검사","2023-03-30 09:00","2023-03-30 15:00","2023-03-30 09:00","2023-03-30 15:00","연속"]
[112,"경기","동부","곤지암S/S CB 7500","곤지암S/S 345kV 차단기 설치공사","7571GIS 사용전검사","2023-03-30 09:00","2023-03-30 15:00","2023-03-30 09:00","2023-03-30 15:00","연속"]
[113,"경기","동부","곤지암S/S CB 7600","곤지암S/S 345kV 차단기 설치공사","7671GIS 사용전검사","2023-03-30 15:00","2023-03-31 11:00","2023-03-30 15:00","2023-03-31 11:00","연속"]
[114,"경기","동부","곤지암S/S CB 7671","곤지암S/S 345kV 차단기 설치공사","7671GIS 사용전검사","2023-03-30 15:00","2023-03-31 11:00","2023-03-30 15:00","2023-03-31 11:00","연속"]
[115,"경기","동부","곤지암S/S CB 7671","곤지암S/S 345kV 차단기 설치공사","7671GIS 준공시험 및 전력케이블 내전압 7671GIS 무부하가압(전력케이블 포함)","2023-03-13 09:00","2023-03-26 17:00","2023-03-13 09:00","2023-03-26 17:00","연속"]
[116,"경기","동부","곤지암S/S #4 M.Tr","곤지암S/S 345kV 차단기 설치공사","7671GIS 준공시험 B/F PNL 조정(2CB → 3CB)","2023-03-13 09:00","2023-03-23 11:00","2023-03-13 09:00","2023-03-23 11:00","연속"]
[117,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 345kV 차단기 설치공사","7571,7671GIS 무부하가압(전력케이블 포함)","2023-03-25 08:00","2023-03-26 17:00","2023-03-25 08:00","2023-03-26 17:00","연속"]
[118,"경기","동부","곤지암S/S CB 7500","곤지암S/S 345kV 차단기 설치공사","7571GIS 준공시험 및 전력케이블 내전압","2023-03-02 09:00","2023-03-10 18:00","2023-03-02 09:00","2023-03-10 18:00","연속"]
[119,"경기","동부","곤지암S/S CB 7571","곤지암S/S 345kV 차단기 설치공사","7571GIS 준공시험 및 전력케이블 내전압","2023-03-02 09:00","2023-03-10 18:00","2023-03-02 09:00","2023-03-10 18:00","연속"]
[120,"경기","동부","곤지암S/S #3 M.Tr","곤지암S/S 345kV 차단기 설치공사","7571GIS 준공시험 B/F PNL 조정(2CB → 3CB)","2023-03-02 09:00","2023-03-10 18:00","2023-03-02 09:00","2023-03-10 18:00","연속"]
[121,"경기","동부","곤지암여주복합#2 T/L","여주복합발전소 연계 송전선로 건설공사","96-1호 C5 보조암 설치","2023-03-04 07:00","2023-03-05 18:00","취소","취소","연속"]
[122,"경기","성남","신수원S/S #1 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 1차 CVT 하자점검 - 1차 LA 초기점검 - 2차 GIS 조작시험 - 예방진단시스템설치","2023-03-20 09:00","2023-03-21 18:00","2023-03-20 09:00","2023-03-21 18:00","연속"]
[123,"경기","성남","신수원S/S #2 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 1차 CVT 하자점검 - 1차 LA 초기점검 - 2차 GIS 조작시험 - 예방진단시스템설치","2023-03-23 09:00","2023-03-24 18:00","2023-03-23 09:00","2023-03-24 18:00","연속"]
[124,"경기","성남","신용인S/S #1 BUS","23년 성남전력지사 변전협력회사 총액공사","- PT케이블 포설 및 결선","2023-03-10 09:00","2023-03-10 14:00","2023-03-10 09:00","2023-03-10 14:00","연속"]
[125,"경기","성남","신용인S/S #2 BUS","23년 성남전력지사 변전협력회사 총액공사","- PT케이블 포설 및 결선","2023-03-10 14:00","2023-03-10 18:00","2023-03-10 14:00","2023-03-10 18:00","연속"]
[126,"경기","성남","신성남동서울#2 T/L","23년 성남전력지사 변전협력회사 총액공사","CVT 대체 및 기초 재시공","2023-03-14 09:00","2023-03-21 18:00","취소","취소","연속"]
[127,"경기","직할","화성S/S #1 M.Tr","345kV 화성S/S GIS 용량대체공사","73Bay (3CB) GIS 용량대체","2023-03-09 09:00","2023-06-20 18:00","2023-03-09 09:00","2023-06-20 18:00","연속"]
[128,"경기","직할","화성S/S 예비 M.Tr CB","345kV 화성S/S GIS 용량대체공사","GIS 철거관련 예비모선 철거","2023-03-02 09:00","2023-11-30 18:00","취소","취소","연속"]
[129,"경기","직할","화성S/S #2 M.Tr","345kV 화성S/S GIS 용량대체공사","예비모선 철거 관련 안전이격거리 확보","2023-03-12 11:00","2023-03-12 14:00","2023-03-12 11:00","2023-03-12 14:00","연속"]
[130,"경기","직할","화성신안산#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 하자점검","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[131,"경기","직할","화성서서울#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 초기점검","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[132,"경기","평택","고덕#2S/S #1 M.Tr","345kV 고덕2S/S 건설사업","154kV 고덕-동평택 #1T/L 인출변경 무부하가압","2023-03-29 09:00","2023-03-30 18:00","2023-03-29 09:00","2023-03-30 18:00","연속"]
[133,"경기","평택","북당진고덕#2 HVDC CB","북당진-고덕 2단계 HVDC 건설사업","Bi-POLE 구성, 제어기 설치, 부하시험","2023-03-01 09:00","2023-06-30 18:00","취소","취소","연속"]
[134,"경기","평택","북당진고덕#1 HVDC CB","북당진-고덕 2단계 HVDC 건설사업","Bi-POLE 구성, 제어기 설치, 부하시험","2023-03-01 09:00","2023-06-30 18:00","취소","취소","연속"]
[135,"경기","평택","고덕S/S #4 M.Tr","23년 평택전력지사 변전협력회사 총액공사","고덕S/S 345kV #4M.Tr 변압기 보통점검 7672,7600GIS 보통점검, 6444GIS 보통점검, 4489 SIS 보통점검, STATCOM용 #2S.Tr 보통점검","2023-03-30 09:00","2023-03-31 18:00","2023-03-30 09:00","2023-03-31 18:00","연속"]
[136,"경기","평택","고덕S/S #1 M.Tr","23년 평택전력지사 변전협력회사 총액공사","고덕S/S 345kV #1M.Tr 변압기 보통점검, C상 펌프 누유보수, 7371,7300GIS 보통점검, 6144GIS 보통점검, 4189, 4189-1,4189-2SIS 보통점검, #1S.Tr 보통점검","2023-03-07 09:00","2023-03-10 18:00","2023-03-07 09:00","2023-03-10 18:00","연속"]
[137,"경기","평택","고덕S/S #3 M.Tr","23년 평택전력지사 변전협력회사 총액공사","고덕S/S 345kV #3M.Tr 변압기 보통점검 7571,7500GIS 보통점검, 6344GIS 보통점검, 4389 SIS 보통점검, STATCOM용 #1S.Tr 보통점검","2023-03-28 09:00","2023-03-29 18:00","2023-03-28 09:00","2023-03-29 18:00","연속"]
[138,"경기","평택","평택T/P #3 TIE Tr","23년 평택전력지사 변전협력회사 총액공사","평택T/P 345kV #3Tie-Tr 2차 GIB, 6341DS 누기개소 보수","2023-03-04 09:00","2023-03-06 18:00","2023-03-04 09:00","2023-03-06 18:00","연속"]
[139,"경기","평택","화성평택TP#1 T/L","23년 평택전력지사 변전협력회사 총액공사","평택T/P 화성-평택T/P #1T/L 7621 인출 DS 인디케이터 보수","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[140,"강원","강릉","안인개폐소양양PP T/L","2022~2023년 강릉전력지사 가공송전헙력회사 총액공사","○ 수직, 수평 추락방지장치 설치(345kV 양양양수T/L No.4~137)","2023-03-16 07:00","2023-04-05 18:00","2023-03-16 07:00","2023-04-05 18:00","매일"]
[141,"강원","강릉","안인개폐소신양양 T/L","2022~2023년 강릉전력지사 가공송전헙력회사 총액공사","○ 수직, 수평 추락방지장치 설치(345kV 양양양수T/L No.4~55, 116~124)","2023-03-02 07:00","2023-03-15 18:00","취소","취소","매일"]
[142,"강원","동해","동해삼척GP#1 T/L","동해S/S 345kV 용량부족차단기 대체공사","345kV 75Bay 용량부족차단기 3CB 대체","2023-03-20 09:00","2023-05-31 18:00","2023-03-20 09:00","2023-05-31 18:00","연속"]
[143,"강원","동해","신제천동해#1 T/L","345kV 동해 등 5개T/L 추락방지장치 설치공사","○ 추락방지장치 설치(수직, 수평) 124기 (No.174~297)","2023-03-16 07:00","2023-03-25 18:00","취소","취소","연속"]
[144,"강원","동해","동해S/S #2 M.Tr","23년 동해전력지사 변전정비팀 총액공사","보통점검","2023-03-13 09:00","2023-03-15 18:00","2023-03-13 09:00","2023-03-15 18:00","연속"]
[145,"강원","동해","동해안인개폐소#2 T/L","2023년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(345kV 동해-안인개폐소#2T/L No. 1~64)","2023-03-09 08:00","2023-03-15 18:00","2023-03-09 08:00","2023-03-15 18:00","연속"]
[146,"강원","동해","동해안인개폐소#1 T/L","2023년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(345kV 동해-안인개폐소#1T/L No.1~64)","2023-03-02 08:00","2023-03-08 18:00","2023-03-02 08:00","2023-03-08 18:00","연속"]
[147,"강원","동해","동해북평TP#3 T/L","동해S/S 345kV 용량부족차단기 대체공사","345kV 75Bay 용량부족차단기 3CB 대체","2023-03-20 09:00","2023-05-31 18:00","2023-03-20 09:00","2023-05-31 18:00","연속"]
[148,"강원","동해","신제천동해#2 T/L","345kV 동해 등 5개T/L 추락방지장치 설치공사","○ 추락방지장치 설치(수직, 수평) 124기","2023-03-26 07:00","2023-04-04 18:00","취소","취소","연속"]
[149,"강원","동해","동해S/S #3 M.Tr","동해S/S 345kV M.Tr 정밀점검","M.Tr 정밀점검","2023-03-06 09:00","2023-03-11 18:00","2023-03-06 09:00","2023-03-11 18:00","연속"]
[150,"강원","동해","삼척G/P #1 Tie-Tr","23년 동해전력지사 변전정비팀 총액공사","1. 보통점검 2. LA 2차 A,B,C상","2023-03-07 09:00","2023-03-09 18:00","2023-03-07 09:00","2023-03-09 18:00","연속"]
[151,"강원","태백","신태백S/S #1 BUS","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #1BUS B/P PNL 교체","2023-03-06 10:00","2023-03-10 18:00","2023-03-06 10:00","2023-03-10 18:00","연속"]
[152,"강원","태백","신태백한울NP#1 T/L","345kV 울태T/L 고정형 폴리머점퍼지지애자 설치공사","- 345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사 - 345kV 신태백-한울NP2#1T/L 정밀점검(병행)","2023-03-20 09:00","2023-03-31 18:00","취소","취소","연속"]
[153,"강원","태백","신태백S/S #2 BUS","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #1BUS B/P PNL 교체","2023-03-13 10:00","2023-03-17 18:00","2023-03-13 10:00","2023-03-17 18:00","연속"]
[154,"충북","직할","신진천S/S #4 M.Tr","22-23년 충북직할 변전협력회사 총액공사","#4M.Tr 1차 PT 하자점검 및 154kV #2Sh.C 정밀점검 후 무부하가압","2023-03-14 09:00","2023-03-15 18:00","취소","취소","연속"]
[155,"충북","직할","신진천S/S #3 M.Tr","23년 상반기 충북본부 직할 gis 정밀점검 공사","154kV #3M.Tr 2차 GIS 정밀점검","2023-03-20 09:00","2023-03-24 18:00","취소","취소","연속"]
[156,"충북","직할","신진천S/S #2 M.Tr","22-23년 충북직할 변전협력회사 총액공사","345kv #2M.Tr 1차 PT 점검","2023-03-09 09:00","2023-03-10 18:00","취소","취소","연속"]
[157,"충북","직할","신진천S/S #1 M.Tr","22-23년 충북직할 변전협력회사 총액공사","345kv #1M.Tr 1,2차 LA 및 1차 PT 점검","2023-03-07 09:00","2023-03-08 18:00","취소","취소","연속"]
[158,"충북","청주","세종남청주#1 T/L","남청주S/S 345kV 송전선로 인출변경","74 BAY → 76 BAY 인출변경","2023-03-01 08:00","2023-03-04 18:00","2023-03-06 08:00","2023-03-09 18:00","연속"]
[159,"충북","청주","남청주S/S #4 M.Tr","345kV 남청주S/S #5 M.Tr 증설공사","#5 M.Tr 1차 7871 CB 증설 관련 78 BAY B/F반 대체 (2CB → 3CB)","2023-03-31 14:00","2023-04-03 18:00","취소","취소","연속"]
[160,"충북","청주","남청주S/S CB 7271","남청주S/S 345kV 송전선로 인출변경","72 BAY → 73 BAY 인출변경 71 BAY → 72 BAY 인출변경","2023-03-26 18:00","2023-03-31 14:00","2023-03-27 18:00","2023-03-31 14:00","연속"]
[161,"충북","청주","남청주S/S CB 7200","남청주S/S 345kV 송전선로 인출변경","72 BAY → 73 BAY 인출변경 71 BAY → 72 BAY 인출변경","2023-03-26 18:00","2023-03-31 14:00","2023-03-27 18:00","2023-03-31 14:00","연속"]
[162,"충북","청주","신중부남청주#1 T/L","남청주S/S 345kV 송전선로 인출변경","71 BAY → 72 BAY 인출변경","2023-03-26 08:00","2023-03-31 14:00","2023-03-27 08:00","2023-03-31 14:00","연속"]
[163,"충북","청주","남청주S/S CB 7300","남청주S/S 345kV 송전선로 인출변경","72 BAY → 73 BAY 인출변경","2023-03-21 08:00","2023-03-24 18:00","2023-03-21 08:00","2023-03-24 18:00","연속"]
[164,"충북","청주","남청주S/S CB 7371","남청주S/S 345kV 송전선로 인출변경","72 BAY → 73 BAY 인출변경","2023-03-21 08:00","2023-03-24 18:00","2023-03-21 08:00","2023-03-24 18:00","연속"]
[165,"충북","청주","신중부남청주#2 T/L","남청주S/S 345kV 송전선로 인출변경","72 BAY → 73 BAY 인출변경","2023-03-21 08:00","2023-03-24 18:00","2023-03-21 08:00","2023-03-24 18:00","연속"]
[166,"충북","청주","남청주S/S CB 7600","남청주S/S 345kV 송전선로 인출변경","74 BAY → 76 BAY 인출변경","2023-03-01 15:00","2023-03-04 18:00","2023-03-06 15:00","2023-03-09 18:00","연속"]
[167,"충북","청주","남청주S/S CB 7671","남청주S/S 345kV 송전선로 인출변경","74 BAY → 76 BAY 인출변경","2023-03-01 15:00","2023-03-04 18:00","2023-03-06 15:00","2023-03-09 18:00","연속"]
[168,"충북","청주","남청주S/S CB 7471","남청주S/S 345kV 송전선로 인출변경","73 BAY → 74 BAY 인출변경","2023-03-12 08:00","2023-03-17 18:00","2023-03-13 08:00","2023-03-17 18:00","연속"]
[169,"충북","청주","세종남청주#2 T/L","남청주S/S 345kV 송전선로 인출변경","73 BAY → 74 BAY 인출변경","2023-03-12 08:00","2023-03-17 18:00","2023-03-13 08:00","2023-03-17 18:00","연속"]
[170,"충북","청주","남청주S/S CB 7400","남청주S/S 345kV 송전선로 인출변경","73 BAY → 74 BAY 인출변경","2023-03-12 08:00","2023-03-17 18:00","2023-03-13 08:00","2023-03-17 18:00","연속"]
[171,"충북","청주","신옥천신남원#1 T/L","2022~2023년 청주전력지사 송전협력회사 총액공사(추락방지시설 설치)","345kV 신옥천-신남원#1T/L 수평 추락방지시설 설치(No.179~247, 61기)","2023-03-29 07:00","2023-04-05 18:00","2023-03-29 07:00","2023-04-05 18:00","매일"]
[172,"충북","청주","신옥천S/S #2 M.Tr","22~23년 청주전력 변전협력회사 총액공사","신옥천S/S #345kV #2M.Tr 1차 GIS 보통점검","2023-03-28 08:00","2023-03-30 18:00","2023-03-28 08:00","2023-03-30 18:00","연속"]
[173,"충북","충주","신제천신영주#2 T/L","345kV 신제천-신영주T/L 낙뢰소손 관련 OPGW 교체공사","○ #2T/L 5~12호 OPGW 3.075km 교체 ○ 항공장애표시구 31개 설치","2023-03-24 07:00","2023-03-26 18:00","2023-03-24 07:00","2023-03-26 18:00","연속"]
[174,"충북","충주","신충주S/S #2 M.Tr","22-23년 충주전력지사 변전정비 총액공사","신충주S/S 345kV #2M.Tr PNL 대체(장기사용 보호배전반 대체)","2023-03-20 09:00","2023-03-24 18:00","2023-03-20 09:00","2023-03-24 18:00","연속"]
[175,"충북","충주","신충주S/S #1 M.Tr","22-23년 충주전력지사 변전정비 총액공사","신충주S/S 345kV #1M.Tr PNL 대체(장기사용 보호배전반 대체)","2023-03-14 09:00","2023-03-17 18:00","2023-03-14 09:00","2023-03-17 18:00","연속"]
[176,"충북","충주","신충주S/S #3 M.Tr","345kV 신충주S/S 종합예방진단시스템 구축공사","○ 신충주S/S 종합예방진단시스템 구축 - 부싱진단장비 설치, OLTC 진단장비 설치 등","2023-03-27 09:00","2023-03-29 18:00","2023-03-27 09:00","2023-03-29 18:00","연속"]
[177,"대전세종충남","대전","신계룡청양 T/L","(2월 취소시)[송전] 345kV신옥천-청양등 2개TL추락방지 설치공사","345kV 신계룡-청양T/L 추락방지장치 설치공사","2023-03-14 08:00","2023-03-14 18:00","2023-03-15 08:00","2023-03-17 18:00","연속"]
[178,"대전세종충남","대전","신옥천신계룡 T/L","(2월 취소시)[송전] 345kV신옥천-청양등 2개TL추락방지 설치공사","345kV 신옥천-신계룡T/L 추락방지장치 설치공사","2023-03-13 08:00","2023-03-13 18:00","2023-03-13 08:00","2023-03-14 18:00","연속"]
[179,"대전세종충남","서산","당진T/P #71 Tie-Tr","23년 서산P/O 변전협력회사 총액공사","당진화력S/S 345kV #71TIE-Tr 1차 CVT, 1,2차 LA 교체 (병행) 당진화력S/S 345kV 1호기 LA 교체 (1호기 오버홀 중 및 안전이격거리 확보) (병행) 당진화력S/S 345kV #71TIE-Tr, 2차 6144, 3차 4189 CB 보통점검","2023-03-20 09:00","2023-03-22 18:00","2023-03-20 09:00","2023-03-22 18:00","연속"]
[180,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 신당진-서산#2T/L 피뢰기 설치공사(2기) (No.34,47 병가)","2023-03-16 08:00","2023-03-16 18:00","취소","취소","연속"]
[181,"대전세종충남","서산","신당진S/S SEC CB 75760","23년도 345kV 차단기 조작시험","신당진S/S 75-76-0 CB","2023-03-30 10:00","2023-03-30 14:00","2023-03-30 10:00","2023-03-30 14:00","연속"]
[182,"대전세종충남","서산","신당진S/S CB 7400","23년도 345kV 차단기 조작시험","신당진S/S 7400 CB","2023-03-29 10:00","2023-03-29 14:00","2023-03-29 10:00","2023-03-29 14:00","연속"]
[183,"대전세종충남","서산","신서산신당진#2 T/L","23년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV 신서산-신당진#2T/L GIS 결상회로 개선","2023-03-09 10:00","2023-03-09 14:00","2023-03-09 10:00","2023-03-09 14:00","연속"]
[184,"대전세종충남","서산","신당진S/S #1 M.Tr","23년 서산P/O 345kV 이하 M.Tr 보통점검공사","신당진S/S 345kV #1M.Tr 보통점검 (병행) 1차 7472, 2차 6144 CB 보통점검 (병행) 신당진S/S 345kV #1M.Tr 3차 노후 PT 및 PT 분전함 교체","2023-03-06 09:00","2023-03-08 18:00","2023-03-06 09:00","2023-03-08 18:00","연속"]
[185,"대전세종충남","서산","신당진S/S CB 7172","23년도 345kV 차단기 조작시험","신당진S/S 7172 CB","2023-03-28 14:00","2023-03-28 18:00","2023-03-28 14:00","2023-03-28 18:00","연속"]
[186,"대전세종충남","서산","신당진S/S SEC CB 70710","23년도 345kV 차단기 조작시험","신당진S/S 70-71-0 SEC CB","2023-03-28 10:00","2023-03-28 14:00","2023-03-28 10:00","2023-03-28 14:00","연속"]
[187,"대전세종충남","서산","신당진S/S CB 7771","23년도 345kV 차단기 조작시험","신당진S/S 7772 CB","2023-03-30 14:00","2023-03-30 18:00","2023-03-30 14:00","2023-03-30 18:00","연속"]
[188,"대전세종충남","서산","태안T/P CB 7172","태안화력S/Y 7100,7172CB 스페이서 가스누기관련 해체점검","태안화력S/Y 7100,7172CB 스페이서 가스누기관련 해체점검","2023-03-13 09:00","2023-03-24 18:00","2023-03-13 09:00","2023-03-24 18:00","연속"]
[189,"대전세종충남","서산","태안T/P CB 7100","태안화력S/Y 7100,7172CB 스페이서 가스누기관련 해체점검","태안화력S/Y 7100,7172CB 스페이서 가스누기관련 해체점검","2023-03-13 09:00","2023-03-24 18:00","2023-03-13 09:00","2023-03-24 18:00","연속"]
[190,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","23년 서산P/O 변전협력회사 총액공사","태안화력S/Y, 신당진개폐소 345kV 개폐소-태안화력#2T/L 보호반 대체 (병행) 태안화력S/Y,신당진개폐소 345kV 개폐소-태안화력#2T/L CB 보통점검","2023-03-20 09:00","2023-03-24 18:00","취소","취소","연속"]
[191,"대전세종충남","서산","태안T/P #1 Tie-Tr","23년 서산P/O 변전협력회사 총액공사","태안화력S/Y 345kV #1M.Tr 1차 PT측 스페이서 교체 (병행) 태안화력S/Y 345kV #1M.Tr 1차 GIS 가스누기 보수공사 (병행) 태안화력S/Y 345kV #1M.Tr, 1,2,3차 CB 보통점검","2023-03-13 09:00","2023-03-17 18:00","2023-03-13 09:00","2023-03-17 18:00","연속"]
[192,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 신온양서서울#1T/L 단상재폐로 회로개선","신온양S/S 345kV 신온양서서울#1T/L 단상재폐로 회로개선","2023-03-23 09:00","2023-03-23 18:00","취소","취소","연속"]
[193,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 신온양서서울#2T/L 단상재폐로 회로개선","신온양S/S 345kV 신온양서서울#2T/L 단상재폐로 회로개선","2023-03-24 09:00","2023-03-24 18:00","취소","취소","연속"]
[194,"대전세종충남","천안","신탕정S/S #4 M.Tr","신탕정S/S 345kV #4 M.Tr 제작사 하자보수 및 하자점검","신탕정S/S 345kV #4 M.Tr 제작사 하자보수 및 하자점검","2023-03-20 09:00","2023-03-24 18:00","2023-03-20 09:00","2023-03-24 18:00","연속"]
[195,"대전세종충남","천안","청양신탕정#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 345kV 청양-신탕정T/L 91기(주말작업 없음)","2023-03-02 07:00","2023-03-10 18:00","취소","취소","매일"]
[196,"대전세종충남","천안","청양신탕정#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 345kV 청양-신탕정T/L 91기(주말작업 없음)","2023-03-02 07:00","2023-03-10 18:00","취소","취소","매일"]
[197,"대전세종충남","천안","아산화성#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 345kV 아산-화성T/L 12기","2023-03-27 07:00","2023-03-31 18:00","취소","취소","매일"]
[198,"대전세종충남","천안","아산S/S #4 M.Tr","아산S/S 345kV #4 M.Tr 보통점검","아산S/S 345kV #4 M.Tr 보통점검","2023-03-06 09:00","2023-03-07 18:00","2023-03-06 09:00","2023-03-07 18:00","연속"]
[199,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 345kV #1 M.Tr 2차 부싱절연유 채유","아산S/S 345kV #1 M.Tr 2차 부싱절연유 채유","2023-03-02 09:00","2023-03-02 18:00","2023-03-02 09:00","2023-03-02 18:00","연속"]
[200,"대전세종충남","천안","아산화성#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 345kV 아산-화성T/L 12기","2023-03-27 07:00","2023-03-31 18:00","취소","취소","매일"]
[201,"대전세종충남","청양","신옥천청양 T/L","(2월 취소시)[송전] 345kV신옥천-청양등 2개TL추락방지 설치공사","345kV 신옥천-청양T/L 추락방지장치 설치공사","2023-03-06 08:00","2023-03-10 18:00","취소","취소","매일"]
[202,"전북","군산","군산S/S #3 M.Tr","군산P/O 부싱유 채유 공사","군산P/O 부싱유 채유 공사","2023-03-21 09:00","2023-03-21 18:00","2023-03-21 09:00","2023-03-21 18:00","연속"]
[203,"전북","군산","군산S/S #1 M.Tr","군산P/O 부싱유 채유 공사","군산P/O 부싱유 채유 공사","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[204,"전북","군산","군산S/S #1 Sh.R CB","군산P/O 조상설비 점검공사","군산P/O 조상설비 점검공사","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[205,"전북","군산","군산S/S #2 M.Tr","군산P/O 부싱유 채유 공사","군산P/O 부싱유 채유 공사","2023-03-13 09:00","2023-03-14 18:00","취소","취소","연속"]
[206,"전북","군산","청양군산#2 T/L","군산S/S 345kV 장기사용 GIS 대체공사","○ 송전선로 보호반 이설(청양-군산#2T/L) ○ 인출송전선로 이설(74Bay →75Bay) ○ LA, CVT 이설(74Bay →75Bay)","2023-03-22 09:00","2023-03-30 18:00","2023-03-22 09:00","2023-03-30 18:00","연속"]
[207,"전북","군산","새만금S/S #2 M.Tr","새만금S/S 주변압기 점검공사","군산P/O 주변압기 점검공사","2023-03-07 09:00","2023-03-08 18:00","취소","취소","연속"]
[208,"전북","군산","새만금S/S #3 M.Tr","새만금S/S 주변압기 점검공사","군산P/O 주변압기 점검공사","2023-03-09 09:00","2023-03-10 18:00","취소","취소","연속"]
[209,"전북","김제","군산신김제#2 T/L","관내S/S 345kV GIS 보통점검","관내S/S 345kV GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[210,"전북","김제","군산신김제#1 T/L","관내S/S 345kV GIS 보통점검","관내S/S 345kV GIS 보통점검","2023-03-17 09:00","2023-03-17 18:00","2023-03-17 09:00","2023-03-17 18:00","연속"]
[211,"광주전남","강진","신강진S/S #1 BUS","신강진S/S 신강진-광양#2T/L 7551DS부 가스누기 복구 공사","신강진S/S 신강진-광양#2T/L 7551DS부 가스누기 개소 점검 및 보수","2023-03-20 09:00","2023-03-29 18:00","취소","취소","연속"]
[212,"광주전남","강진","신강진광양#2 T/L","신강진S/S 신강진-광양#2T/L 7551DS부 가스누기 복구 공사","신강진S/S 신강진-광양#2T/L 7551DS부 가스누기 개소 점검 및 보수","2023-03-20 09:00","2023-03-29 18:00","취소","취소","연속"]
[213,"광주전남","목포","한빛2NP한빛3NP#4 T/L","2023년도 목포전력지사 변전협력회사 총액공사","2023년도 목포전력지사 변전협력회사 총액공사","2023-03-13 09:00","2023-03-15 18:00","취소","취소","연속"]
[214,"광주전남","목포","신김제한빛NP#1 T/L","2023년도 목포전력지사 변전협력회사 총액공사","2023년도 목포전력지사 변전협력회사 총액공사","2023-03-01 09:00","2023-03-01 18:00","취소","취소","연속"]
[215,"광주전남","순천","신강진광양#2 T/L","345kV 신강진-광양 등 29개 T/L 추락방지시설 설치공사","345kV 신강진-광양#2T/L 수평 추락방지시설 설치 구간 : 140~280호, 141기","2023-03-22 07:00","2023-03-31 18:00","2023-03-22 07:00","2023-03-31 18:00","매일"]
[216,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양 등 29개 T/L 추락방지시설 설치공사","345kV 신강진-광양#1T/L 수직, 수평 추락방지시설 설치 구간 : 140~280호, 141기","2023-03-06 07:00","2023-03-17 18:00","2023-03-06 07:00","2023-03-17 18:00","매일"]
[217,"광주전남","순천","광양광양CC#2 T/L","광양S/S 362kV 용량부족 GIS 교체공사(7A BAY)","광양-광양CC, 광양제철 #2T/L GIS(7A71, 7A00, 7A72CB 교체)","2023-03-02 10:00","2023-05-30 16:00","2023-03-02 10:00","2023-05-30 16:00","연속"]
[218,"광주전남","순천","광양S/S CB 7A00","광양S/S 362kV 용량부족 GIS 교체공사(7A BAY)","광양-광양CC, 광양제철 #2T/L GIS(7A71, 7A00, 7A72CB 교체)","2023-03-02 10:00","2023-05-30 16:00","2023-03-02 10:00","2023-05-30 16:00","연속"]
[219,"광주전남","순천","광양광양제철#2 T/L","광양S/S 362kV 용량부족 GIS 교체공사(7A BAY)","광양-광양CC, 광양제철 #2T/L GIS(7A71, 7A00, 7A72CB 교체)","2023-03-02 10:00","2023-05-30 16:00","2023-03-02 10:00","2023-05-30 16:00","연속"]
[220,"광주전남","순천","여수T/P #3 Tie-Tr","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력 #3M.Tr 러버백, 96G 교체 및 점검창 설치","2023-03-27 09:00","2023-03-31 18:00","취소","취소","연속"]
[221,"대구","달성","고령의령#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 고령-의령T/L 수평 추락방지장치 설치공사","2023-03-13 07:00","2023-03-16 18:00","2023-03-13 07:00","2023-03-16 18:00","연속"]
[222,"대구","달성","고령의령#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 고령-의령T/L 수평 추락방지장치 설치공사","2023-03-20 07:00","2023-03-23 18:00","2023-03-20 07:00","2023-03-23 18:00","연속"]
[223,"대구","칠곡","북대구서대구#1 T/L","북대구S/S #74Bay B/F 보호반 교체공사","북대구S/S #74Bay B/F 보호반 교체공사","2023-03-06 09:30","2023-03-10 18:00","2023-03-06 09:30","2023-03-10 18:00","연속"]
[224,"대구","칠곡","북대구서대구#2 T/L","북대구S/S #73Bay B/F 보호반 교체공사","북대구S/S #73Bay B/F 보호반 교체공사","2023-03-13 09:30","2023-03-17 18:00","2023-03-13 09:30","2023-03-17 18:00","연속"]
[225,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S #73Bay B/F 보호반 교체공사","북대구S/S #73Bay B/F 보호반 교체공사","2023-03-13 09:30","2023-03-17 18:00","2023-03-13 09:30","2023-03-17 18:00","연속"]
[226,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S #74Bay B/F 보호반 교체공사","북대구S/S #74Bay B/F 보호반 교체공사","2023-03-06 09:30","2023-03-10 18:00","2023-03-06 09:30","2023-03-10 18:00","연속"]
[227,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","변전기초 철거 등 안전이격 확보","2023-03-06 08:30","2023-03-09 18:00","2023-03-06 08:30","2023-03-09 18:00","연속"]
[228,"대구","포항","신영일안동CC T/L","기설철탑 추락방지장치 설치공사","345kV 영포T/L 수평 추락방지장치 설치 : No.211~355","2023-03-06 08:00","2023-03-09 18:00","2023-03-06 08:00","2023-03-09 18:00","연속"]
[229,"대구","포항","신포항신영일 T/L","기설철탑 추락방지장치 설치공사","345kV 영포T/L 수평 추락방지장치 설치 : No.211~355","2023-03-10 08:00","2023-03-15 18:00","2023-03-10 08:00","2023-03-15 18:00","연속"]
[230,"대구","포항","신포항S/S #3 M.Tr","신포항S/S #3M.Tr OLTC절연유 보충","신포항S/S #3M.Tr A상 OLTC절연유 보충 및 부싱절연유 채유","2023-03-02 09:00","2023-03-02 18:00","2023-03-02 09:00","2023-03-02 18:00","연속"]
[231,"대구","포항","신포항청송PP T/L","기설철탑 추락방지장치 설치공사","345kV 영포T/L 수평 추락방지장치 설치 : No.211~355","2023-03-16 08:00","2023-03-23 18:00","2023-03-16 08:00","2023-03-23 18:00","연속"]
[232,"대구","포항","신포항북대구 T/L","기설철탑 추락방지장치 설치공사","345kV 신포항-북대구T/L 수평 추락방지장치 설치 : No.149~276","2023-03-27 08:00","2023-04-04 18:00","2023-03-27 08:00","2023-04-04 18:00","연속"]
[233,"대구","포항","월성N/P CB 7372","월성S/Y 7300, 7372 GIS 보통점검","월성S/Y 7300, 7372 GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[234,"대구","포항","동울산월성NP T/L","월성S/Y 7371 GIS 보통점검","월성S/Y 7371 GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[235,"대구","포항","월성N/P CB 7300","월성S/Y 7300, 7372 GIS 보통점검","월성S/Y 7300, 7372 GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[236,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","74bay #3M.Tr Bay(7400, 7472) GIS 교체 - #70BUS 교체분 무부하가압","2023-03-27 09:00","2023-03-28 09:00","2023-03-24 09:00","2023-03-27 09:00","연속"]
[237,"경북","구미","선산신포항 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- 7471 GIS 보통점검 - LA 보통점검 - PT 보통점검","2023-03-21 09:00","2023-03-21 18:00","취소","취소","연속"]
[238,"경북","구미","선산신포항 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","74bay #3M.Tr Bay(7400, 7472) GIS 교체 - 74bay측 #70BUS 교체관련 안전거리 확보 등","2023-03-18 09:00","2023-04-28 18:00","2023-03-09 09:00","2023-04-28 18:00","연속"]
[239,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","74bay #3M.Tr Bay(7400, 7472) GIS 교체 - #75BUS 교체분 무부하가압 및 73bay측 #70BUS 설치관련 안전거리 확보 등","2023-03-08 09:00","2023-03-17 18:00","2023-03-08 09:00","2023-03-17 18:00","연속"]
[240,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","74bay #3M.Tr Bay(7400, 7472) GIS 교체 - 73bay측 #70BUS 교체관련 안전거리 확보","2023-03-09 09:00","2023-03-28 09:00","2023-03-09 09:00","2023-03-27 18:00","연속"]
[241,"경북","구미","북대구선산 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- 7371,7300 GIS 보통점검[정밀] - LA 보통점검 - PT 보통점검","2023-03-10 09:00","2023-03-10 18:00","취소","취소","연속"]
[242,"경북","영주","신영주한울NP#1 T/L","345kV신영주-한울NP2 수평 추락방지시설 설치공사","2022년 울진 산불발생 선하지 통과구간 정밀점검을 위한 수평 추락방지시설 설치","2023-03-03 09:00","2023-03-16 18:00","취소","취소","연속"]
[243,"경북","영주","신영주한울NP#2 T/L","345kV신영주-한울NP2 수평 추락방지시설 설치공사","2022년 울진 산불발생 선하지 통과구간 정밀점검을 위한 수평 추락방지시설 설치","2023-03-17 09:00","2023-03-30 18:00","취소","취소","연속"]
[244,"경북","영주","신영주청송PP T/L","345kV영포T/L 폴리머지지애자 설치공사","345kV영포T/L 폴리머지지애자 설치공사","2023-03-06 12:00","2023-03-07 18:00","2023-03-02 09:00","2023-03-03 18:00","연속"]
[245,"경북","영주","신영주안동CC T/L","345kV영포T/L 폴리머지지애자 설치공사","345kV영포T/L 폴리머지지애자 설치공사","2023-03-06 09:00","2023-03-06 12:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[246,"경북","영주","신영주S/S #1 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","보호배전반 대체","2023-03-20 10:00","2023-03-24 18:00","2023-03-20 10:00","2023-03-24 18:00","연속"]
[247,"경북","영주","신영주한울NP#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","71BAY B/F 대체","2023-03-20 10:00","2023-03-24 18:00","취소","취소","연속"]
[248,"경북","영주","삼척GP한울NP#2 T/L","2022-23년도 영주전력지사 변전정비회사 총액공사","초고압 애자 절연 코팅공사","2023-03-08 09:00","2023-03-09 09:00","2023-03-08 09:00","2023-03-09 09:00","연속"]
[249,"경북","영주","한울1NP한울2NP#1 T/L","2022-23년도 영주전력지사 변전정비회사 총액공사","초고압 애자 절연 코팅공사","2023-03-29 09:00","2023-03-30 09:00","취소","취소","연속"]
[250,"경북","영주","삼척GP한울NP#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","초고압 애자 절연 코팅공사","2023-03-07 09:00","2023-03-08 09:00","2023-03-07 09:00","2023-03-08 09:00","연속"]
[251,"경북","영주","신태백한울NP#2 T/L","2022-23년도 영주전력지사 변전정비회사 총액공사","초고압 애자 절연 코팅공사","2023-03-14 09:00","2023-03-15 09:00","2023-03-14 09:00","2023-03-15 09:00","연속"]
[252,"경북","영주","신태백한울NP#1 T/L","2022-23년도 영주전력지사 변전정비회사 총액공사","초고압 애자 절연 코팅공사","2023-03-15 09:00","2023-03-16 09:00","2023-03-15 09:00","2023-03-16 09:00","연속"]
[253,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 시험용도","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[254,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 시험용도","2023-03-23 09:00","2023-03-23 18:00","2023-03-23 09:00","2023-03-23 18:00","연속"]
[255,"부산울산","동부산","신양산고리NP#2 T/L","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 인출 위치 변경(75bay -> 72bay)에 따른 부싱 설치 및 모선이설","2023-03-27 09:00","2023-04-01 18:00","2023-03-27 09:00","2023-04-01 18:00","연속"]
[256,"부산울산","북부산","북부산S/S #4 M.Tr","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #4M.Tr 1차측 CVT 설치","2023-03-14 09:00","2023-03-15 18:00","2023-03-14 09:00","2023-03-15 18:00","연속"]
[257,"부산울산","북부산","북부산S/S CB 7371","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV 7371 차단기 보통점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[258,"부산울산","북부산","북부산S/S #2 M.Tr","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #2M.Tr 보통점검","2023-03-07 09:00","2023-03-09 18:00","2023-03-07 09:00","2023-03-09 18:00","연속"]
[259,"부산울산","서부산","서부산S/S #2 M.Tr","서부산S/S 345kV #2M.Tr 고장복구 대체공사","서부산S/S 345kV #2M.Tr 고장복구 대체공사","2023-03-08 09:00","2023-07-28 18:00","2023-03-08 09:00","2023-07-28 18:00","연속"]
[260,"부산울산","서부산","신김해신녹산#2 T/L","345kV 신김해-신녹산T/L No.31~39간 교체공사","OPGW 교채 : 2.5km","2023-03-11 08:00","2023-03-12 18:00","2023-03-11 08:00","2023-03-12 18:00","연속"]
[261,"부산울산","울산","남울산울산TP#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-21 07:00","2023-03-22 18:00","2023-03-21 07:00","2023-03-22 18:00","연속"]
[262,"부산울산","울산","남울산울산TP#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-04 07:00","2023-03-05 18:00","취소","취소","연속"]
[263,"부산울산","울산","동울산S/S CB 7171","22~23년 변전협력회사 총액공사","GIS(7171)차단기 동작시험","2023-03-20 09:00","2023-03-20 12:00","2023-03-20 09:00","2023-03-20 12:00","연속"]
[264,"부산울산","울산","동울산S/S CB 7100","22~23년 변전협력회사 총액공사","GIS(7100)차단기 동작시험","2023-03-20 12:00","2023-03-20 15:00","2023-03-20 12:00","2023-03-20 15:00","연속"]
[265,"부산울산","울산","동울산S/S CB 7172","22~23년 변전협력회사 총액공사","GIS(7172)차단기 동작시험","2023-03-20 15:00","2023-03-20 18:00","2023-03-20 15:00","2023-03-20 18:00","연속"]
[266,"부산울산","울산","동울산S/S CB 7271","22~23년 변전협력회사 총액공사","GIS(7271)차단기 동작시험","2023-03-21 09:00","2023-03-21 12:00","2023-03-21 09:00","2023-03-21 12:00","연속"]
[267,"부산울산","울산","동울산S/S CB 7200","22~23년 변전협력회사 총액공사","GIS(7200)차단기 동작시험","2023-03-21 12:00","2023-03-21 15:00","2023-03-21 12:00","2023-03-21 15:00","연속"]
[268,"부산울산","울산","동울산S/S CB 7272","22~23년 변전협력회사 총액공사","GIS(7272)차단기 동작시험","2023-03-21 15:00","2023-03-21 18:00","2023-03-21 15:00","2023-03-21 18:00","연속"]
[269,"부산울산","울산","신온산남울산#2 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","76Bay #1,2BUS, 7600, 7672GIS 교체 관련 시험가압 선로 휴전","2023-03-02 15:00","2023-03-03 15:00","2023-03-02 15:00","2023-03-03 15:00","연속"]
[270,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","76Bay #1,2BUS, 7600, 7672GIS 교체","2023-03-30 13:00","2023-03-30 13:30","2023-03-30 13:00","2023-03-30 13:30","연속"]
[271,"부산울산","울산","신온산남울산#2 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","76Bay #1,2BUS, 7600, 7672GIS 교체 관련 시험가압 선로 휴전","2023-03-16 15:00","2023-03-17 15:00","2023-03-16 15:00","2023-03-17 15:00","연속"]
[272,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","76Bay #1,2BUS, 7600, 7672GIS 교체","2023-03-06 09:00","2023-03-17 15:00","2023-03-06 09:00","2023-03-17 15:00","연속"]
[273,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","76Bay #1,2BUS, 7600, 7672GIS 교체","2023-03-30 14:00","2023-03-30 14:30","2023-03-30 14:00","2023-03-30 14:30","연속"]
[274,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S 345kV 용량대체공사","- #3M.Tr 신설 GIS 가압(구75BAY -> 신79BAY) - #3-1, #3-2Sh.R 이설 - 관련 보호반 이설 및 신설","2023-03-27 09:00","2023-04-14 18:00","2023-03-27 09:00","2023-04-14 18:00","연속"]
[275,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV 용량대체공사","- #4M.Tr 1차측 가선을 위한 #75BUS 모선 절단","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[276,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S 345kV 용량대체공사","- #4M.Tr 1차 인출 변경(구76BAY -> 신77BAY)","2023-03-02 09:00","2023-03-24 18:00","2023-03-02 09:00","2023-03-24 18:00","연속"]
[277,"부산울산","울산","신울산S/S #70 BUS","신울산S/S 345kV 용량대체공사","- #4M.Tr 1차측 가선을 위한 #70BUS 모선 절단","2023-03-02 09:00","2023-03-02 18:00","2023-03-02 09:00","2023-03-02 18:00","연속"]
[278,"부산울산","울산","북부산울산TP#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-20 07:00","2023-03-31 18:00","2023-03-20 07:00","2023-03-31 18:00","연속"]
[279,"부산울산","울산","울산C/C CB 7200","22년 울산복합S/Y 345kV GIS 보통점검공사","GIS(7200) 보통점검","2023-03-27 09:00","2023-03-27 18:00","2023-03-27 09:00","2023-03-27 18:00","연속"]
[280,"부산울산","울산","북부산울산TP#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-04 07:00","2023-03-16 18:00","취소","취소","연속"]
[281,"부산울산","울산","울주S/S CB 7671","22~23년 변전협력회사 총액공사","- GIS(7671)보통점검","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[282,"부산울산","울산","울주S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 1차 GIS(7600) 보통점검 - 1차 GIS(7672) 차단기 동작시험 - 3차 PT 보통점검","2023-03-08 09:00","2023-03-09 18:00","2023-03-08 09:00","2023-03-09 18:00","연속"]
[283,"부산울산","울산","울주S/S CB 7800","22~23년 변전협력회사 총액공사","GIS(7800)차단기 동작시험","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[284,"부산울산","울산","울주S/S CB 7871","22~23년 변전협력회사 총액공사","- GIS(7871)보통점검","2023-03-17 09:00","2023-03-17 18:00","2023-03-17 09:00","2023-03-17 18:00","연속"]
[285,"부산울산","울산","울주S/S CB 7600","22~23년 변전협력회사 총액공사","- GIS(7600)보통점검","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[286,"부산울산","울산","울주S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 1차 GIS(7472,7400) 보통점검 - 2차 GIS(6244) 보통점검 - 1,2,3차 LA 보통점검","2023-03-06 09:00","2023-03-07 18:00","2023-03-06 09:00","2023-03-07 18:00","연속"]
[287,"부산울산","울산","울주신경산#2 T/L","22~23년 변전협력회사 총액공사","- GIS(7771) 보통점검 - GIS(7700) 차단기 동작시험 - 피뢰기, CVT 보통점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[288,"부산울산","울산","울주고리NP#2 T/L","22~23년 변전협력회사 총액공사","- GIS(7571) 보통점검 - GIS(7500) 차단기 동작시험 - 피뢰기, CVT 보통점검","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[289,"부산울산","울산","울주S/S CB 7871","22~23년 변전협력회사 총액공사","- GIS(7871)보통점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[290,"부산울산","직할","신대연S/S #2 M.Tr","신대연S/S #2M.Tr 정밀점검공사","신대연S/S #2M.Tr 정밀점검공사","2023-03-27 09:00","2023-04-14 18:00","2023-03-27 09:00","2023-04-14 18:00","연속"]
[291,"부산울산","직할","신대연S/S #1 M.Tr","신대연S/S #1M.Tr 정밀점검공사","신대연S/S #1M.Tr 정밀점검공사","2023-03-06 09:00","2023-03-24 18:00","2023-03-06 09:00","2023-03-24 18:00","매일"]
[292,"경남","직할","신김해S/S #1 M.Tr","신김해S/S 베어링 발청 보수 공사","신김해S/S 베어링 발청 보수 공사 대상설비 : #1M.Tr 2차 GIS","2023-03-27 09:30","2023-03-27 18:00","2023-03-27 09:30","2023-03-27 18:00","연속"]
[293,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-신고성T/L 추락방지장치 설치","345kV 창원-신고성T/L 추락방지장치 설치","2023-03-13 08:00","2023-03-19 18:00","2023-03-13 08:00","2023-03-19 18:00","매일"]
[294,"경남","직할","창원삼천포TP#1 T/L","345kV 창원-신고성T/L 추락방지장치 설치","345kV 창원-신고성T/L 추락방지장치 설치","2023-03-06 08:00","2023-03-12 18:00","2023-03-06 08:00","2023-03-12 18:00","매일"]
[295,"경남","진주","하동T/P CB 7800","하동T/P 345kV TIE GIS(7800) 조작시험","하동T/P 345kV TIE GIS(7800) 조작시험","2023-03-08 09:00","2023-03-08 14:00","2023-03-08 09:00","2023-03-08 14:00","연속"]
[296,"경남","진주","하동T/P CB 7872","하동T/P 345kV GIS(7872) 조작시험","하동T/P 345kV GIS(7872) 조작시험","2023-03-08 14:00","2023-03-08 17:00","2023-03-08 14:00","2023-03-08 17:00","연속"]
[297,"경남","진주","하동T/P CB 7700","하동T/P 345kV TIE GIS(7700) 보통점검","하동T/P 345kV TIE GIS(7700) 보통점검","2023-03-15 10:00","2023-03-15 14:00","2023-03-17 10:00","2023-03-17 18:00","연속"]
[298,"경남","진주","하동T/P CB 7772","하동T/P 345kV GIS(7772) 보통점검","하동T/P 345kV GIS(7772) 보통점검","2023-03-15 14:00","2023-03-15 18:00","2023-03-16 10:00","2023-03-16 18:00","연속"]
[299,"경남","통영","삼천포T/P CB 7272","신고성S/S 345kV 신고성-신마산#2T/L 7272 GIS 보통점검","신고성S/S 345kV 신고성-신마산#2T/L 7272 GIS 보통점검","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[300,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 보통점검","1. 신고성S/S #3M.Tr 보통점검 2. 신고성S/S #3M.Tr 1차 GIS 보통점검(7572, 7500) 3. 신고성S/S #3M.Tr 2차 GIS 조작시험 4 신고성S/S #3M.Tr 3차 PT, 모선 보통점검 5. 신고성S/S #3M.Tr 1,2,3차 LA 보통점검","2023-03-20 09:00","2023-03-23 18:00","2023-03-20 09:00","2023-03-23 18:00","연속"]
[301,"경남","통영","신고성S/S #2 M.Tr","신고성S/S #2M.Tr 보통점검","1. 신고성S/S #2M.Tr 보통점검 2. 신고성S/S #2M.Tr 1차 GIS 보통점검(7372, 7300) 3. 신고성S/S #2M.Tr 2차 GIS 조작시험 4 신고성S/S #2M.Tr 3차 PT, 모선 보통점검 5. 신고성S/S #2M.Tr 1,2,3차 LA 보통점검","2023-03-13 09:00","2023-03-16 18:00","2023-03-13 09:00","2023-03-16 18:00","연속"]
[302,"경남","통영","삼천포T/P CB 7371","신고성S/S 345kV #G3호기 1차 7371 GIS 보통점검","신고성S/S 345kV #G3호기 1차 7371 GIS 보통점검","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[303,"경남","통영","삼천포T/P CB 7200","신고성S/S 345kV G2호기 TIE 7200 GIS 보통점검","신고성S/S 345kV 신마산#2T/L-#G2호기 1차 7200 GIS 보통점검","2023-03-29 09:00","2023-03-29 18:00","2023-03-29 09:00","2023-03-29 18:00","연속"]
[304,"경남","통영","삼천포T/P CB 7271","신고성S/S 345kV #G2호기 1차 7271 GIS 보통점검","신고성S/S 345kV #G2호기 1차 7271 GIS 보통점검","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[305,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345kV #5 M.Tr 변압기 보호반 대체","신마산S/S 345kV #5 M.Tr 변압기 보호반 대체","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[306,"경기","군포","서서울#2신시흥#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-03 14:00","2023-03-03 18:00","2023-03-03 14:00","2023-03-03 18:00","연속"]
[307,"경기","군포","서서울#2신시흥#2 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-07 14:00","2023-03-07 18:00","2023-03-07 14:00","2023-03-07 18:00","연속"]
[308,"경기","군포","서서울#2신시흥#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-11 14:00","2023-03-11 18:00","2023-03-11 14:00","2023-03-11 18:00","연속"]
[309,"경기","군포","서서울#2S/S CB 7D71","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","서서울#2S/S 362kV GIS PD발생개소 보수(무부하가압용)","2023-03-11 14:00","2023-03-11 18:00","2023-03-11 14:00","2023-03-11 18:00","연속"]
[310,"대전세종충남",null,"보령C/C #3-4GT 주변압기 (CB 7300, 7372)","발전기 계획예방정비 공사","발전기 계획예방정비 공사","2023-03-20 09:00","2023-06-14 18:00","2023-03-20 09:00","2023-06-14 18:00","연속"]
[311,"대전세종충남",null,"보령C/C #2ST 주변압기 (CB 7400, 7472)","발전기 계획예방정비 공사","발전기 계획예방정비 공사","2023-03-20 09:00","2023-06-14 18:00","2023-03-20 09:00","2023-06-14 18:00","연속"]
[312,"광주전남",null,"한빛#3N/P 대기보조변압기 (CB 7B00, 7B71)","한빛5호기 14차 계획예방정비 대기보조변압기 및 갑종보호계전기 점검 ※ 조작차단기:7B00, 7B71","대기보조변압기, 소내 전원 차단기, OF CABLE, 갑종보호계전기 등 점검","2023-03-09 10:00","2023-03-22 18:00","2023-03-09 10:00","2023-03-22 18:00","연속"]
[313,"광주전남",null,"한빛#3N/P #5호기 주변압기 (CB 7D00, 7D71)","한빛5호기 14차 계획예방정비 소내전원 절체시험 ※ 조작차단기:7D00, 7D71","소내전원 절체시험(주변압기→대기보조변압기)","2023-03-23 09:00","2023-03-23 18:00","2023-03-23 09:00","2023-03-23 18:00","연속"]
[314,"부산울산",null,"고리N/P #4호기 #2기동변압기 (CB 7600, 7672)","고리 4호기 계획예방정비관련 기동변압기 #2 점검 * 조작차단기 : 7600, 7672","- 기동변압기 #2 점검 ","2023-03-27 10:00","2023-04-05 17:00","2023-03-27 10:00","2023-04-05 17:00","연속"]
[315,"부산울산",null,"고리N/P #4호기 주변압기 (CB 7B00, 7B72)","고리 4호기 제27차 계획예방정비 * 조작차단기 : 7B00,7B72","- 주/보조변압기 및 발전기 점검","2023-03-05 10:00","2023-05-07 17:00","2023-03-05 10:00","2023-05-07 17:00","연속"]
[316,"부산울산",null,"고리N/P #4호기 #1기동변압기 (CB 7C00, 7C72)","고리 4호기 계획예방정비관련 기동변압기 #1 점검 * 조작차단기 : 7C00, 7C72","- 기동변압기 #1 점검 ","2023-03-14 10:00","2023-03-23 17:00","2023-03-14 10:00","2023-03-23 17:00","연속"]
[317,"부산울산",null,"고리N/P #3호기 주변압기 (CB 7900, 7972)","고리 3호기 제 27차 계획예방정비 * 조작차단기: 7900, 7972","- 주/보조변압기 및 발전기 점검","2023-03-28 10:00","2023-06-02 17:00","2023-03-28 10:00","2023-06-02 17:00","연속"]
[318,"대구",null,"월성N/P #2호기 주변압기 (CB 7300, 7372)","345KV 월성N/P 주변압기#2 계획예방정비 *조작차단기 7300, 7372","○ 주변압기 점검","2023-03-09 09:00","2023-04-08 18:00","2023-03-09 09:00","2023-04-08 18:00","연속"]
[319,"경북",null,"한울#1N/P #2호기 비상보조변압기 (CB 7200, 7272)","2호기 24차 계획예방정비 * 조작차단기 : CB 7200, 7272","○ 비상보조변압기 일반점검","2023-03-26 15:00","2023-04-01 15:00","2023-03-26 15:00","2023-04-01 15:00","연속"]
[320,"경북",null,"한울#2N/P #4호기 대기보조변압기 (CB 7700, 7772)","한울4호기 제16차 계획예방정비 관련 SAT02M/N 일반점검 * 조작차단기(02M) : 7700, 7772","한울4호기 제16차 계획예방정비 관련 SAT02M 일반점검","2023-03-22 10:00","2023-04-04 18:00","2023-03-22 10:00","2023-04-04 18:00","연속"]
[321,"경북",null,"한울#2N/P #4호기 대기보조변압기 (CB 7800, 7872)","한울4호기 제16차 계획예방정비 관련 SAT02M/N 일반점검 * 조작차단기(02N) : 7800, 7872","한울4호기 제16차 계획예방정비 관련 SAT02N 일반점검","2023-03-22 10:00","2023-04-04 18:00","2023-03-22 10:00","2023-04-04 18:00","연속"]
[322,"경기북부",null,"미금성동#2 T/L","미금 VSR 관련 시험가압 선로","미금 VSR 관련 시험가압 선로","2023-03-07 09:00","2023-03-10 18:00","2023-03-07 09:00","2023-03-10 18:00","매일"]
[323,"경기북부",null,"미금S/S #3 VSR CB","미금 VSR 200Mvar OLTC 운전 시험","미금 VSR 200Mvar OLTC 운전 시험","2023-03-07 09:00","2023-03-10 18:00","2023-03-07 09:00","2023-03-10 18:00","연속"]
[324,"전북","군산","군산S/S #75 BUS","신설 75 BAY 무부하가압 활용 ","대상범위 CB 7500, 7571","2023-03-13 08:00","2023-03-14 08:00","2023-03-13 08:00","2023-03-14 08:00","연속"]

{"sheet":"154설비","index":2,"n_rows":653,"n_cols":11,"rows_kept":653,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 3월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#1 T/L","세니온제 154kV 송전선로보호반 성능개선","○ F/W업데이트 및 연동시험","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[2,"서울","성동","화양성수 T/L","세니온제 154kV 송전선로보호반 성능개선","○ F/W업데이트 및 연동시험","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[3,"서울","중부","녹번세종로 T/L","23 중부P/O 총액공사","GIS 하자점검","2023-03-21 10:00","2023-03-21 18:00","2023-03-21 10:00","2023-03-21 18:00","연속"]
[4,"서울","중부","수색S/S #1 BUS","23 중부P/O 총액공사","PT, 피뢰기 보통점검","2023-03-27 10:00","2023-03-27 14:00","취소","취소","연속"]
[5,"서울","중부","수색S/S #2 BUS","23 중부P/O 총액공사","PT, 피뢰기 보통점검","2023-03-29 14:00","2023-03-29 18:00","취소","취소","연속"]
[6,"서울","중부","수색S/S #1 BUS","23 중부P/O 총액공사","PT, 피뢰기 보통점검","2023-03-29 10:00","2023-03-29 14:00","취소","취소","연속"]
[7,"서울","중부","수색S/S CB 6100","23 중부P/O 총액공사","차단기 조작시험","2023-03-29 10:00","2023-03-29 18:00","취소","취소","연속"]
[8,"서울","중부","수색S/S #2 BUS","23 중부P/O 총액공사","PT, 피뢰기 보통점검","2023-03-27 14:00","2023-03-27 18:00","취소","취소","연속"]
[9,"서울","중부","원흥수색#1 T/L","23 중부P/O 총액공사","LS ,PT,LA 보통점검","2023-03-27 10:00","2023-03-27 18:00","취소","취소","연속"]
[10,"서울","중부","수색상암 T/L","23 중부P/O 총액공사","GCB 보통점검","2023-03-09 10:00","2023-03-09 18:00","취소","취소","연속"]
[11,"서울","중부","수색S/S CB 6100","23 중부P/O 총액공사","차단기 조작시험","2023-03-27 10:00","2023-03-27 18:00","취소","취소","연속"]
[12,"서울","중부","옥인운니#1 T/L","OF케이블 절연유 채유","옥인운니#1T/L OF케이블 절연유분석 시료 채취","2023-03-29 10:00","2023-03-29 14:00","2023-03-29 10:00","2023-03-29 14:00","연속"]
[13,"서울","중부","은평녹번#2 T/L","23 중부P/O 총액공사","GIS 하자점검(녹번) 조작시험(은평)","2023-03-09 10:00","2023-03-09 18:00","2023-03-09 10:00","2023-03-09 18:00","연속"]
[14,"서울","직할","현저서대문#2 T/L","23년 직할 변전협력 총액공사","-170kV GIS 보통점검","2023-03-13 10:00","2023-03-13 18:00","2023-03-13 10:00","2023-03-13 18:00","연속"]
[15,"서울","직할","현저서대문#1 T/L","23년 직할 변전협력 총액공사","-170kV GIS 보통점검","2023-03-14 10:00","2023-03-14 18:00","2023-03-14 10:00","2023-03-14 18:00","연속"]
[16,"서울","직할","운니원남#2 T/L","23년 직할변전 총액공사","-170kV GIS 조작시험","2023-03-02 10:00","2023-03-02 18:00","2023-03-02 10:00","2023-03-02 18:00","연속"]
[17,"남서울","강남","논현선릉#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 보통점검","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[18,"남서울","강남","대치논현#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 보통점검","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[19,"남서울","동서울","강동S/S #2 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화 관련 선로별 상체크","2023-03-21 14:00","2023-03-21 14:10","2023-03-21 14:00","2023-03-21 14:10","연속"]
[20,"남서울","동서울","강동S/S #1 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화 관련 선로별 상체크","2023-03-08 14:00","2023-03-08 14:10","2023-03-08 14:00","2023-03-08 14:10","연속"]
[21,"남서울","동서울","동서울위례#1 T/L","동서울,위례S/S 동서울-위례#1T/L 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-03-06 09:00","2023-03-06 13:00","2023-03-06 09:00","2023-03-06 13:00","연속"]
[22,"남서울","동서울","동서울#2S/S #69 BUS","동서울S/S 154kV 옥외철구 GIS화 공사","#2M.Tr GIS 전환관련 무부하 가압 모선","2023-03-22 14:00","2023-03-23 14:00","2023-03-22 14:00","2023-03-23 14:00","연속"]
[23,"남서울","동서울","동서울위례#2 T/L","동서울,위례S/S 동서울-위례#2T/L 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-03-06 13:00","2023-03-06 18:00","2023-03-06 13:00","2023-03-06 18:00","연속"]
[24,"남서울","동서울","동서울강동#2 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사","2023-03-10 08:00","2023-03-21 18:00","2023-03-13 08:00","2023-03-24 18:00","연속"]
[25,"남서울","동서울","동서울S/S #65 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사 관련 무부하가압 선로","2023-03-08 14:00","2023-03-09 14:00","2023-03-08 14:00","2023-03-09 14:00","연속"]
[26,"남서울","동서울","동서울S/S #67 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사 관련 무부하가압 선로","2023-03-20 14:00","2023-03-21 14:00","2023-03-20 14:00","2023-03-21 14:00","연속"]
[27,"남서울","동서울","산성수서#2 T/L","22~23년도 동서울전력지사 가공송전 협력회사 총액공사","피뢰기, 추락방지장치 설치공사","2023-03-08 07:00","2023-03-10 17:00","2023-03-08 07:00","2023-03-10 17:00","연속"]
[28,"남서울","동서울","산성수서#1 T/L","22~23년도 동서울전력지사 가공송전 협력회사 총액공사","추락방지장치 설치공사","2023-03-15 07:00","2023-03-16 17:00","2023-03-15 07:00","2023-03-16 17:00","연속"]
[29,"남서울","동서울","동서울신장#2 T/L","154kV 동서울-신장 지중T/L 선종교체공사","(신설)XLPE 2500SQ 2C-0.3km (철거)XLPE 1200SQ 2C(D)-0.3km","2023-03-23 09:00","2023-04-08 18:00","취소","취소","연속"]
[30,"남서울","동서울","동서울신장#1 T/L","154kV 동서울-신장 지중T/L 선종교체공사","(신설)XLPE 2500SQ 2C-0.3km (철거)XLPE 12000SQ 2C(D)-0.3km","2023-03-06 09:00","2023-03-22 18:00","취소","취소","연속"]
[31,"남서울","동서울","풍납석촌#2 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - SA혼용시스템 현장정보처리반 수용 x 1식 - 기타 부대 공사 x 1식","2023-03-22 09:00","2023-03-23 18:00","2023-03-22 09:00","2023-03-23 18:00","연속"]
[32,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - SA혼용시스템 현장정보처리반 수용 x 1식 - 기타 부대 공사 x 1식","2023-03-20 09:00","2023-03-21 18:00","2023-03-20 09:00","2023-03-21 18:00","연속"]
[33,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","3차분(#3M.Tr 1차 GIS) 철거 및 설치 - #2BUS, #3M.Tr 무부하 가압","2023-03-31 18:00","2023-04-01 18:00","취소","취소","연속"]
[34,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","3차분(#3M.Tr 1차 GIS) 철거 및 설치 - #1BUS 무부하 가압","2023-03-23 18:00","2023-03-24 18:00","취소","취소","연속"]
[35,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","3차분(#3M.Tr 1차 GIS) 철거 및 설치 - #2BUS 무부하 가압","2023-03-16 18:00","2023-03-17 18:00","취소","취소","연속"]
[36,"남서울","영등포","구공S/S SEC CB 60610","2022~23년 영등포전력지사 변전협력회사 총액공사","- 154kV GIS 메커니즘 점검 - 베어링 발청 및 조작점검","2023-03-14 09:00","2023-03-14 11:00","2023-03-14 09:00","2023-03-14 11:00","연속"]
[37,"남서울","영등포","구공S/S CB 6200","2022~23년 영등포전력지사 변전협력회사 총액공사","- 154kV GIS 메커니즘 점검 - 베어링 발청 및 조작점검","2023-03-14 15:00","2023-03-14 18:00","2023-03-14 15:00","2023-03-14 18:00","연속"]
[38,"남서울","영등포","구공S/S SEC CB 65660","2022~23년 영등포전력지사 변전협력회사 총액공사","- 154kV GIS 메커니즘 점검 - 베어링 발청 및 조작점검","2023-03-14 11:00","2023-03-14 15:00","2023-03-14 11:00","2023-03-14 15:00","연속"]
[39,"남서울","영등포","대방신길#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","대방-신길#1T/L 조작시험","2023-03-20 09:00","2023-03-20 14:00","2023-03-20 09:00","2023-03-20 14:00","연속"]
[40,"남서울","영등포","대방신길#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","대방-신길#2T/L 조작시험","2023-03-21 09:00","2023-03-21 14:00","2023-03-21 09:00","2023-03-21 14:00","연속"]
[41,"남서울","영등포","마곡S/S #1 BUS","154kV GIS IED 성능개선(세니온)","- 로직변경 및 경보수정","2023-03-25 09:00","2023-03-25 14:00","2023-03-25 09:00","2023-03-25 14:00","연속"]
[42,"남서울","영등포","마곡가양#2 T/L","154kV GIS IED 성능개선(세니온)","- 로직변경 및 경보수정","2023-03-22 14:00","2023-03-22 18:00","2023-03-22 14:00","2023-03-22 18:00","연속"]
[43,"남서울","영등포","마곡S/S CB 6100","154kV GIS IED 성능개선(세니온)","- 로직변경 및 경보수정","2023-03-25 09:00","2023-03-25 18:00","2023-03-25 09:00","2023-03-25 18:00","연속"]
[44,"남서울","영등포","마곡가양#1 T/L","154kV GIS IED 성능개선(세니온)","- 로직변경 및 경보수정","2023-03-22 09:00","2023-03-22 14:00","2023-03-22 09:00","2023-03-22 14:00","연속"]
[45,"남서울","영등포","마곡S/S #2 BUS","154kV GIS IED 성능개선(세니온)","- 로직변경 및 경보수정","2023-03-25 14:00","2023-03-25 18:00","2023-03-25 14:00","2023-03-25 18:00","연속"]
[46,"남서울","영등포","신문래목동#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","-신문래-목동#2T/L 조작시험 -세니온 154kV 송전선로 보호계전기 성능개선","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[47,"남서울","영등포","신정목동#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","신정-목동#1T/L 조작시험","2023-03-08 09:00","2023-03-08 14:00","2023-03-08 09:00","2023-03-08 14:00","연속"]
[48,"남서울","영등포","신정목동#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","신정-목동#2T/L 조작시험","2023-03-08 14:00","2023-03-08 18:00","2023-03-08 14:00","2023-03-08 18:00","연속"]
[49,"남서울","영등포","신문래목동#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","-신문래-목동#1T/L 조작시험 -세니온 154kV 송전선로 보호계전기 성능개선","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[50,"남서울","영등포","시흥독산#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","시흥-독산#1T/L 보통점검","2023-03-31 09:00","2023-03-31 14:00","2023-03-31 09:00","2023-03-31 14:00","연속"]
[51,"남서울","영등포","시흥독산#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","시흥-독산#2T/L 조작시험","2023-03-31 14:00","2023-03-31 18:00","2023-03-31 14:00","2023-03-31 18:00","연속"]
[52,"남서울","영등포","신광명소래 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","신광명-소래T/L 보통점검","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[53,"남서울","영등포","오류목동 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","오류-목동T/L 보통점검","2023-03-24 09:00","2023-03-24 18:00","2023-03-24 09:00","2023-03-24 18:00","연속"]
[54,"남서울","영등포","천왕구로#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","천왕-구로#1T/L 보통점검","2023-03-29 09:00","2023-03-29 18:00","2023-03-29 09:00","2023-03-29 18:00","연속"]
[55,"남서울","영등포","천왕S/S #2 BUS","천왕SS 154kV PT집합반 교체공사","천왕S/S 154kV PT집합반 교체공사","2023-03-06 14:00","2023-03-07 14:00","2023-03-06 14:00","2023-03-07 14:00","연속"]
[56,"남서울","영등포","천왕S/S #1 BUS","천왕SS 154kV PT집합반 교체공사","천왕S/S 154kV PT집합반 교체공사","2023-03-07 14:00","2023-03-07 18:00","2023-03-07 14:00","2023-03-07 18:00","연속"]
[57,"남서울","영등포","천왕S/S #1 BUS","천왕SS 154kV PT집합반 교체공사","천왕S/S 154kV PT집합반 교체공사","2023-03-06 09:00","2023-03-06 14:00","2023-03-06 09:00","2023-03-06 14:00","연속"]
[58,"남서울","영등포","화곡S/S #1 BUS","화곡SS 154kV PT집합반 교체공사","화곡S/S 154kV PT집합반 교체공사","2023-03-03 14:00","2023-03-03 18:00","2023-03-03 14:00","2023-03-03 18:00","연속"]
[59,"남서울","영등포","고강화곡#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","고강-화곡#1T/L 조작시험","2023-03-27 09:00","2023-03-27 14:00","2023-03-27 09:00","2023-03-27 14:00","연속"]
[60,"남서울","영등포","고강화곡#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","고강-화곡#2T/L 조작시험","2023-03-27 14:00","2023-03-27 18:00","2023-03-27 14:00","2023-03-27 18:00","연속"]
[61,"남서울","영등포","화곡S/S CB 6100","2022~23년 영등포전력지사 변전협력회사 총액공사","6100 GIS 차단기 조작시험","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[62,"남서울","영등포","고강화곡#3 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","고강-화곡#3T/L 조작시험","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[63,"남서울","영등포","화곡S/S #1 BUS","화곡SS 154kV PT집합반 교체공사","화곡S/S 154kV PT집합반 교체공사","2023-03-02 09:00","2023-03-02 14:00","2023-03-02 09:00","2023-03-02 14:00","연속"]
[64,"남서울","영등포","화곡S/S #2 BUS","화곡SS 154kV PT집합반 교체공사","화곡S/S 154kV PT집합반 교체공사","2023-03-02 14:00","2023-03-03 14:00","2023-03-02 14:00","2023-03-03 14:00","연속"]
[65,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검 무부하가압(#2BUS)","170kV GIS 정밀점검 무부하가압(#2BUS) - 노들S/S 154kV #60-#65 BUS-TIE GIS 무부하가압","2023-03-18 12:00","2023-03-18 18:00","2023-03-18 12:00","2023-03-18 18:00","연속"]
[66,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS) - 노들S/S 154kV #60-#65 BUS-TIE GIS 무부하가압","2023-03-17 12:00","2023-03-17 14:00","2023-03-17 12:00","2023-03-17 14:00","연속"]
[67,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검 무부하가압(#2BUS)","170kV GIS 정밀점검 무부하가압(#2BUS) - 노들S/S 154kV #2M.Tr 1차 GIS 무부하가압","2023-03-15 12:00","2023-03-15 18:00","2023-03-15 12:00","2023-03-15 18:00","연속"]
[68,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS) - 노들S/S 154kV #2M.Tr 1차 GIS 무부하가압","2023-03-14 12:00","2023-03-14 14:00","2023-03-14 12:00","2023-03-14 14:00","연속"]
[69,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검 무부하가압(#2BUS)","170kV GIS 정밀점검 무부하가압(#2BUS) - 노들S/S 154kV #1M.Tr 1차 GIS 무부하가압","2023-03-08 14:00","2023-03-08 18:00","2023-03-08 14:00","2023-03-08 18:00","연속"]
[70,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS) - 노들S/S 154kV #1M.Tr 1차 GIS 무부하가압","2023-03-07 14:00","2023-03-07 18:00","2023-03-07 14:00","2023-03-07 18:00","연속"]
[71,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 노들S/S 154kV 노들-노량진T/L GIS","2023-03-20 09:00","2023-03-22 18:00","2023-03-20 09:00","2023-03-22 18:00","연속"]
[72,"남서울","직할","신문래노들 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 노들S/S 154kV 신문래-노들T/L GIS","2023-03-23 09:00","2023-03-25 18:00","2023-03-23 09:00","2023-03-25 18:00","연속"]
[73,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS) - 신문래S/S 154kV 신문래-노들T/L GIS","2023-03-29 10:00","2023-03-29 14:00","2023-03-29 10:00","2023-03-29 14:00","연속"]
[74,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검 무부하가압(#2BUS)","170kV GIS 정밀점검 무부하가압(#2BUS) - 신문래S/S 154kV 신문래-노들T/L GIS","2023-03-30 14:00","2023-03-30 18:00","2023-03-30 14:00","2023-03-30 18:00","연속"]
[75,"남서울","직할","신문래노들 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 신문래S/S 154kV 신문래-노들T/L GIS","2023-03-28 09:00","2023-03-30 18:00","2023-03-28 09:00","2023-03-30 18:00","연속"]
[76,"인천","김포","경서북인천#2 T/L","경서S/S 170kV 경서-북인천#2T/L GIS 조작시험","경서S/S 170kV 경서-북인천#2T/L GIS 조작시험","2023-03-13 14:00","2023-03-13 18:00","2023-03-13 14:00","2023-03-13 18:00","연속"]
[77,"인천","김포","신경서경서#3 T/L","경서S/S 170kV 신경서-경서#3T/L GIS 보통점검","경서S/S 170kV 신경서-경서#3T/L GIS 보통점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[78,"인천","김포","경서양촌#2 T/L","경서S/S 170kV 경서-양촌#2T/L GIS 조작시험","경서S/S 170kV 경서-양촌#2T/L GIS 조작시험","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[79,"인천","김포","경서북인천#1 T/L","경서S/S 170kV 경서-북인천#1T/L GIS 조작시험","경서S/S 170kV 경서-북인천#1T/L GIS 조작시험","2023-03-13 09:00","2023-03-13 14:00","2023-03-13 09:00","2023-03-13 14:00","연속"]
[80,"인천","김포","영종경서 T/L","경서S/S 170kV 영종-경서T/L GIS 보통점검","경서S/S 170kV 영종-경서T/L GIS 보통점검","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[81,"인천","김포","양촌양곡#1 T/L","양곡S/S 170kV 양촌-양곡#1T/L GIS 조작시험","양곡S/S 170kV 양촌-양곡#1T/L GIS 조작시험","2023-03-01 09:00","2023-03-01 14:00","2023-03-01 09:00","2023-03-01 14:00","연속"]
[82,"인천","김포","양촌양곡#2 T/L","양곡S/S 170kV 양촌-양곡#2T/L GIS 조작시험","양곡S/S 170kV 양촌-양곡#2T/L GIS 조작시험","2023-03-01 14:00","2023-03-01 18:00","2023-03-01 14:00","2023-03-01 18:00","연속"]
[83,"인천","김포","신김포양곡#2 T/L","양곡S/S 170kV 신김포-양곡#2T/L GIS 조작시험","양곡S/S 170kV 신김포-양곡#2T/L GIS 조작시험","2023-03-04 14:00","2023-03-04 18:00","2023-03-04 14:00","2023-03-04 18:00","연속"]
[84,"인천","김포","신김포양곡#1 T/L","양곡S/S 170kV 신김포-양곡#1T/L GIS 조작시험","양곡S/S 170kV 신김포-양곡#1T/L GIS 조작시험","2023-03-04 09:00","2023-03-04 14:00","2023-03-04 09:00","2023-03-04 14:00","연속"]
[85,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV 경서-양촌#1T/L GIS 보통점검","양촌S/S 170kV 경서-양촌#1T/L GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[86,"인천","김포","신김포장기#2 T/L","장기S/S 170kV 신김포-장기#2T/L GIS 보통점검","장기S/S 170kV 신김포-장기#2T/L GIS 보통점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[87,"인천","김포","신김포장기#1 T/L","장기S/S 170kV 신김포-장기#1T/L GIS 보통점검","장기S/S 170kV 신김포-장기#1T/L GIS 보통점검","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[88,"인천","부평","부흥부개#2 T/L","부개S/S 154kV 부흥-부개#2T/L 조작시험","부개S/S 154kV 부흥-부개#2T/L 조작시험","2023-03-18 09:00","2023-03-18 18:00","2023-03-18 09:00","2023-03-18 18:00","연속"]
[89,"인천","부평","부개원미#1 T/L","부개S/S 154kV 부개-원미#1T/L 조작시험","부개S/S 154kV 부개-원미#1T/L 조작시험","2023-03-11 09:00","2023-03-11 18:00","2023-03-11 09:00","2023-03-11 18:00","연속"]
[90,"인천","부평","신가좌부개#1 T/L","부개S/S 154kV 신가좌-부개#1T/L 조작시험","부개S/S 154kV 신가좌-부개#1T/L 조작시험 * 신가좌S/S 154kV 신가좌-부개#1T/L 조작시험 병행","2023-03-17 09:00","2023-03-17 18:00","2023-03-17 09:00","2023-03-17 18:00","연속"]
[91,"인천","부평","송현포스코CC#2 T/L","지중송전설비 위탁정비공사 종단접속함(EBA) 절연유 채유","EBA 절연유 채취를 통한 접속함 열화상태 진단","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[92,"인천","부평","신가좌신현#2 T/L","신가좌S/S 154kV 신가좌-신현#2T/L 보호반대체","신가좌S/S 154kV 신가좌-신현#2T/L 보호반대체 및 보통점검 * 신현S/S 154kV 신가좌-신현#2T/L 보통점검 병행","2023-03-20 09:00","2023-03-23 18:00","2023-03-20 09:00","2023-03-23 18:00","연속"]
[93,"인천","부평","신가좌신현#1 T/L","신가좌S/S 154kV 신가좌-신현#1T/L 보호반대체","신가좌S/S 154kV 신가좌-신현#1T/L 보호반대체 및 보통점검 * 신현S/S 154kV 신가좌-신현#1T/L 보통점검 병행","2023-03-14 09:00","2023-03-16 18:00","2023-03-14 09:00","2023-03-16 18:00","연속"]
[94,"인천","부평","원창포스코CC#2 T/L","원창S/S 154kV 원창-포스코CC#2T/L 보통점검","원창S/S 154kV 원창-포스코CC#2T/L 보통점검","2023-03-24 13:00","2023-03-24 18:00","2023-03-24 13:00","2023-03-24 18:00","연속"]
[95,"인천","부평","원창포스코CC#1 T/L","원창S/S 154kV 원창-포스코CC#1T/L 보통점검","원창S/S 154kV 원창-포스코CC#1T/L 보통점검","2023-03-24 09:00","2023-03-24 12:00","2023-03-24 09:00","2023-03-24 12:00","연속"]
[96,"인천","부평","인천CC북인천#2 T/L","인천CC S/Y 154kV 인천CC-북인천#2T/L 보통점검","인천CC S/Y 154kV 인천CC-북인천#2T/L 보통점검","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[97,"인천","부평","인천CC포스코CC#2 T/L","인천CC S/Y 154kV 인천CC-포스코CC#2T/L 보통점검","인천CC S/Y 154kV 인천CC-포스코CC#2T/L 보통점검","2023-03-21 09:00","2023-03-21 18:00","2023-03-21 09:00","2023-03-21 18:00","연속"]
[98,"인천","부평","인천CC포스코CC#1 T/L","인천CC S/Y 154kV 인천CC-포스코CC#1T/L 보통점검","인천CC S/Y 154kV 인천CC-포스코CC#1T/L 보통점검","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[99,"인천","부평","영종공항열병합#1 T/L","GIS 보통점검","영종S/S 공항열병합#1T/L GIS 보통점검","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[100,"인천","부평","영종공항열병합#2 T/L","GIS 보통점검","영종S/S 공항열병합#2T/L GIS 보통점검","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[101,"인천","부평","인천CC북인천#1 T/L","인천CC S/Y 154kV 인천CC-북인천#1T/L 보통점검","인천CC S/Y 154kV 인천CC-북인천#1T/L 보통점검","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[102,"인천","부평","신가좌인천#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[103,"인천","부평","신가좌인천#3 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2023-03-13 09:00","2023-03-14 18:00","2023-03-13 09:00","2023-03-14 18:00","연속"]
[104,"인천","부평","신가좌인천#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[105,"인천","부평","인천남인천#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2023-03-24 09:00","2023-03-24 18:00","2023-03-24 09:00","2023-03-24 18:00","연속"]
[106,"인천","부평","학익연수#2 T/L","학익S/S 154kV 학익-연수#2T/L 조작시험","학익S/S 154kV 학익-연수#2T/L 조작시험","2023-03-16 13:00","2023-03-16 18:00","2023-03-16 13:00","2023-03-16 18:00","연속"]
[107,"인천","부평","학익연수#1 T/L","학익S/S 154kV 학익-연수#1T/L 조작시험","학익S/S 154kV 학익-연수#1T/L 조작시험","2023-03-16 09:00","2023-03-16 12:00","2023-03-16 09:00","2023-03-16 12:00","연속"]
[108,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동T/L 용량증대 선종교체공사","선종교체공사(OF→XLPE)를 통한 선로 용량증대","2023-03-27 09:00","2023-05-26 18:00","2023-03-27 09:00","2023-05-26 18:00","연속"]
[109,"인천","시흥","신시흥S/S CB 6100","신시흥#1S/S 154kV #60-#65 BUS TIE GIS 보통점검","신시흥#1S/S 154kV #60-#65 BUS TIE GIS 보통점검","2023-03-15 09:00","2023-03-15 14:00","2023-03-15 09:00","2023-03-15 14:00","연속"]
[110,"인천","시흥","신시흥도림#2 T/L","신시흥S/S 154kV 신시흥도림#2T/L GIS 보통점검 및 LA 대체","신시흥S/S 154kV 신시흥도림#2T/L GIS 보통점검 및 LA 대체","2023-03-11 09:00","2023-03-11 18:00","2023-03-11 09:00","2023-03-11 18:00","연속"]
[111,"인천","시흥","신시흥S/S SEC CB 60610","신시흥#1S/S 154kV #60-#61 SEC GIS 보통점검","신시흥#1S/S 154kV #60-#61 SEC GIS 보통점검","2023-03-09 09:00","2023-03-09 14:00","2023-03-09 09:00","2023-03-09 14:00","연속"]
[112,"인천","시흥","신시흥S/S SEC CB 61620","신시흥#1S/S 154kV #61-#62 SEC GIS 조작시험","신시흥#1S/S 154kV #61-#62 SEC GIS 조작시험","2023-03-10 16:00","2023-03-10 18:00","2023-03-10 16:00","2023-03-10 18:00","연속"]
[113,"인천","시흥","신시흥S/S SEC CB 66670","신시흥#1S/S 154kV #66-#67 SEC GIS 조작시험","신시흥#1S/S 154kV #66-#67 SEC GIS 조작시험","2023-03-10 14:00","2023-03-10 16:00","2023-03-10 14:00","2023-03-10 16:00","연속"]
[114,"인천","시흥","신시흥S/S SEC CB 65660","신시흥#1S/S 154kV #65-#66 SEC GIS 보통점검","신시흥#1S/S 154kV #65-#66 SEC GIS 보통점검","2023-03-10 09:00","2023-03-10 14:00","2023-03-10 09:00","2023-03-10 14:00","연속"]
[115,"인천","시흥","신시흥S/S CB 6200","신시흥#1S/S 154kV #61-#66 BUS TIE GIS 보통점검","신시흥#1S/S 154kV #61-#66 BUS TIE GIS 보통점검(6200)","2023-03-15 14:00","2023-03-15 18:00","2023-03-15 14:00","2023-03-15 18:00","연속"]
[116,"인천","시흥","신시흥도림#1 T/L","신시흥S/S 154kV 신시흥도림#1T/L GIS 보통점검 및 LA 대체","신시흥S/S 154kV 신시흥도림#1T/L GIS 보통점검 및 LA 대체","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[117,"인천","직할","신부평도당#2 T/L","신부평S/S 신부평도당#2T/L GIS 보통점검","신부평S/S 신부평도당#2T/L GIS 보통점검","2023-03-15 09:30","2023-03-15 18:00","2023-03-15 09:30","2023-03-15 18:00","연속"]
[118,"인천","직할","신부평중동#1 T/L","신부평S/S 신부평중동#1T/L GIS 보통점검","신부평,중동S/S 신부평중동#1T/L GIS 보통점검(양단)","2023-03-06 09:30","2023-03-06 18:00","2023-03-06 09:30","2023-03-06 18:00","연속"]
[119,"인천","직할","신부평고강#1 T/L","신부평S/S 신부평고강#1T/L 보호반대체","신부평S/S 신부평고강#1T/L 보호반대체","2023-03-18 09:00","2023-03-19 19:00","2023-03-18 09:00","2023-03-19 19:00","연속"]
[120,"인천","직할","부천원미#1 T/L","원미S/S 154kV 부천-원미#1T/L GIS 정밀점검","원미S/S 154kV 부천-원미#1T/L GIS 정밀점검","2023-03-20 09:30","2023-03-22 14:00","2023-03-20 09:30","2023-03-22 14:00","연속"]
[121,"인천","직할","부천원미#2 T/L","원미S/S 154kV 부천-원미#2T/L GIS GIS 정밀점검","원미S/S 154kV 부천-원미#2T/L GIS GIS 정밀점검","2023-03-22 14:00","2023-03-24 18:00","2023-03-22 14:00","2023-03-24 18:00","연속"]
[122,"인천","직할","신부평중동#3 T/L","중동S/S 신부평-중동#3T/L GIS 보통점검","중동S/S 신부평-중동#3T/L GIS 보통점검","2023-03-22 09:30","2023-03-22 18:00","2023-03-22 09:30","2023-03-22 18:00","연속"]
[123,"인천","직할","신부평중동#2 T/L","중동S/S 신부평-중동#2T/L GIS 보통점검","중동S/S 신부평-중동#2T/L GIS 보통점검","2023-03-21 09:30","2023-03-21 18:00","2023-03-21 09:30","2023-03-21 18:00","연속"]
[124,"인천","직할","중동화곡#1 T/L","중동S/S 중동-화곡#1T/L GIS 보통점검","중동S/S 중동-화곡#1T/L GIS 보통점검","2023-03-04 09:30","2023-03-04 18:00","2023-03-04 09:30","2023-03-04 18:00","연속"]
[125,"경기북부","고양","양주고양#2 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치, 지지애자 교체","2023-03-27 07:00","2023-03-31 18:00","2023-03-27 07:00","2023-03-31 18:00","연속"]
[126,"경기북부","고양","신덕은금촌#2 T/L","22~23년 가공송전협력회사 총액공사","피뢰기 설치 및 추락방지장치 설치공사","2023-03-07 07:00","2023-03-07 12:00","2023-03-07 07:00","2023-03-07 12:00","연속"]
[127,"경기북부","고양","양주금촌#2 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치, 지지애자 교체, 압축인류크램프 교체","2023-03-28 07:00","2023-04-07 18:00","2023-03-28 07:00","2023-04-07 18:00","연속"]
[128,"경기북부","고양","양주금촌#1 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치, 지지애자 교체, 불량애자 교체, 압축인류크램프 교체","2023-03-07 07:00","2023-03-10 18:00","2023-03-07 07:00","2023-03-10 18:00","연속"]
[129,"경기북부","고양","능곡상암#1 T/L","22-23년 고양전력지사 변전협력회사 총액공사","능곡S/S 능곡-상암#1T/L 차단기 조작시험","2023-03-23 09:30","2023-03-23 12:00","2023-03-23 09:30","2023-03-23 12:00","연속"]
[130,"경기북부","고양","능곡상암#2 T/L","22-23년 고양전력지사 변전협력회사 총액공사","능곡S/S 능곡-상암#2T/L 차단기 조작시험","2023-03-23 13:00","2023-03-23 15:00","2023-03-23 13:00","2023-03-23 15:00","연속"]
[131,"경기북부","고양","신덕은S/S CB 6200","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[132,"경기북부","고양","신덕은S/S SEC CB 60610","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-29 09:00","2023-03-29 18:00","2023-03-29 09:00","2023-03-29 18:00","연속"]
[133,"경기북부","고양","신덕은S/S SEC CB 65660","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[134,"경기북부","고양","신덕은S/S CB 6100","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-03-27 09:00","2023-03-27 18:00","2023-03-27 09:00","2023-03-27 18:00","연속"]
[135,"경기북부","고양","일산호수#1 T/L","22-23년 고양전력지사 변전협력회사 총액공사","일산S/S 일산-호수#1T/L 차단기 조작시험","2023-03-29 09:30","2023-03-29 12:00","2023-03-29 09:30","2023-03-29 12:00","연속"]
[136,"경기북부","고양","일산호수#2 T/L","22-23년 고양전력지사 변전협력회사 총액공사","일산S/S 일산-호수#2T/L 차단기 조작시험","2023-03-29 13:00","2023-03-29 15:00","2023-03-29 13:00","2023-03-29 15:00","연속"]
[137,"경기북부","구리","구리신내#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 초기점검","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[138,"경기북부","구리","덕소팔당HP T/L","23-24년 직할 지중송전설비 위탁정비공사 (피뢰기 교체 등)","1. 154kV 덕소-팔당T/L 덕팔C/T 피뢰기 교체 (3상) 2. EBA PD집합반 센서 연결 (3상)","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[139,"경기북부","구리","덕소진건#1 T/L","154kV 덕소-진건T/L 수평추락방지시설 및 피뢰기설치","154kV 덕소-진건T/L 수평추락방지시설 및 피뢰기설치","2023-03-27 08:00","2023-03-30 18:00","2023-03-27 08:00","2023-03-30 18:00","연속"]
[140,"경기북부","구리","덕소진건#2 T/L","154kV 덕소-진건T/L 수평추락방지시설 설치","154kV 덕소-진건T/L 수평추락방지시설 설치","2023-03-31 08:00","2023-03-31 18:00","2023-03-31 08:00","2023-03-31 18:00","연속"]
[141,"경기북부","구리","마석청평HP#2 T/L","'22~23년 구리전력지사 변전협력회사 총액공사","□ 22~23년 구리전력지사 변전협력회사 총액공사 - 154kV 마석-청평HP#2T/L 보호반 교체공사(마석, 청평수력 양단)","2023-03-06 09:00","2023-03-10 18:00","2023-03-06 09:00","2023-03-10 18:00","연속"]
[142,"경기북부","구리","미금S/S SEC CB 65660","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-31 09:00","2023-03-31 18:00","2023-03-31 09:00","2023-03-31 18:00","연속"]
[143,"경기북부","구리","미금구리#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-20 09:00","2023-03-20 18:00","2023-03-20 09:00","2023-03-20 18:00","연속"]
[144,"경기북부","구리","미금구리#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-17 09:00","2023-03-17 18:00","2023-03-17 09:00","2023-03-17 18:00","연속"]
[145,"경기북부","구리","미금덕소#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[146,"경기북부","구리","미금S/S SEC CB 60610","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[147,"경기북부","구리","신포천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치(수평)","2023-03-27 07:30","2023-03-31 18:00","2023-03-27 07:30","2023-03-31 18:00","연속"]
[148,"경기북부","구리","신포천덕계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치(수평)","2023-03-27 07:30","2023-03-27 18:00","2023-03-27 07:30","2023-03-27 18:00","연속"]
[149,"경기북부","구리","운천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","철탑추락방지시설 설치(수평)","2023-03-30 07:30","2023-04-12 18:00","2023-03-30 07:30","2023-04-12 18:00","연속"]
[150,"경기북부","구리","문막지제#2 T/L","154kV 문막-지제T/L 수평추락방지시설 설치","154kV 문막-지제T/L 수평추락방지시설 설치","2023-03-10 08:00","2023-03-17 18:00","취소","취소","연속"]
[151,"경기북부","구리","문막지제#1 T/L","154kV 문막-지제T/L 수평추락방지시설 설치","154kV 문막-지제T/L 수평추락방지시설 설치","2023-03-02 08:00","2023-03-09 18:00","취소","취소","연속"]
[152,"경기북부","구리","지제용문#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-28 14:00","2023-03-28 18:00","2023-03-28 14:00","2023-03-28 18:00","연속"]
[153,"경기북부","구리","지제용문#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-03-28 09:00","2023-03-28 14:00","2023-03-28 09:00","2023-03-28 14:00","연속"]
[154,"경기북부","구리","진건별내#2 T/L","154kV 진건-별내T/L 수평추락방지시설 설치","154kV 진건-별내T/L 수평추락방지시설 설치","2023-03-24 08:00","2023-03-24 18:00","2023-03-24 08:00","2023-03-24 18:00","연속"]
[155,"경기북부","구리","진건별내#1 T/L","154kV 진건-별내T/L 수평추락방지시설 및 피뢰기설치","154kV 진건-별내T/L 수평추락방지시설 및 피뢰기설치","2023-03-22 08:00","2023-03-23 18:00","2023-03-22 08:00","2023-03-23 18:00","연속"]
[156,"경기북부","구리","덕소팔당HP청평HP T/L","22-23년 구리전력지사 변전협력회사 총액공사","청평H/P 154kV 덕소-팔당HP-청평HPT/L CB 보통점검","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[157,"경기북부","구리","서종청평PP#2 T/L","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-03-27 09:00","2023-04-07 18:00","2023-03-27 09:00","2023-04-07 18:00","연속"]
[158,"경기북부","구리","서홍천청평PP T/L","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-03-27 09:00","2023-04-07 18:00","2023-03-27 09:00","2023-04-07 18:00","연속"]
[159,"경기북부","직할","금오상계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치(수평)","2023-03-22 07:30","2023-03-22 18:00","취소","취소","연속"]
[160,"경기북부","직할","녹양백석#1 T/L","22-23 변전협력 총액공사","170kV GIS 조작시험","2023-03-20 09:00","2023-03-20 18:00","취소","취소","연속"]
[161,"경기북부","직할","신포천동두천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신포천-동두천T/L No.24,28,31~35","2023-03-08 07:00","2023-03-10 18:00","2023-03-08 07:00","2023-03-10 18:00","연속"]
[162,"경기북부","직할","신포천동두천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신포천-동두천T/L No.24,28,31~35","2023-03-15 07:00","2023-03-17 18:00","2023-03-15 07:00","2023-03-17 18:00","연속"]
[163,"경기북부","직할","남면백석#2 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[164,"경기북부","직할","백석덕계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","항공장애표시구 설치","2023-03-27 07:30","2023-03-27 18:00","2023-03-27 07:30","2023-03-27 18:00","연속"]
[165,"경기북부","직할","신의정부내촌#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치(수평)","2023-03-23 07:30","2023-03-24 18:00","2023-03-23 07:30","2023-03-24 18:00","연속"]
[166,"경기북부","직할","양주지축#1 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치, 지지애자 교체","2023-03-13 07:00","2023-03-14 18:00","2023-03-13 07:00","2023-03-14 18:00","연속"]
[167,"경기북부","직할","양주지축#2 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치, 지지애자 교체","2023-03-15 07:00","2023-03-16 18:00","2023-03-09 07:00","2023-03-10 18:00","연속"]
[168,"경기북부","직할","양주은평#2 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치, 지지애자 교체","2023-03-13 07:00","2023-03-14 18:00","2023-03-13 07:00","2023-03-14 18:00","연속"]
[169,"경기북부","직할","양주은평#1 T/L","22~23년 가공송전협력회사 총액공사","추락방지장치 설치","2023-03-15 07:00","2023-03-16 18:00","2023-03-09 07:00","2023-03-10 18:00","연속"]
[170,"경기북부","직할","옥정송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.2~8,12","2023-03-13 07:00","2023-03-14 18:00","2023-03-13 07:00","2023-03-14 18:00","연속"]
[171,"경기북부","직할","옥정송우#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.2~8,12","2023-03-06 07:00","2023-03-07 18:00","2023-03-06 07:00","2023-03-07 18:00","연속"]
[172,"경기북부","직할","옥정동두천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2~11,17~24,28,31~36","2023-03-13 07:00","2023-03-17 18:00","2023-03-13 07:00","2023-03-17 18:00","연속"]
[173,"경기북부","직할","옥정동두천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2~11,17~24,28,31~36","2023-03-06 07:00","2023-03-10 18:00","2023-03-06 07:00","2023-03-10 18:00","연속"]
[174,"경기","군포","사강남양#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 14기","2023-03-20 07:00","2023-03-21 18:00","취소","취소","연속"]
[175,"경기","군포","사강남양#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 14기","2023-03-22 07:00","2023-03-23 18:00","취소","취소","연속"]
[176,"경기","군포","마도사강#2 T/L","마도-사강#2T/L GIS, PT 보통점검 등","마도SS : GIS 보통, 세니온IED 성능개선 사강SS : GIS 조작, PT 보통, 에어링밸브 교체","2023-03-03 09:00","2023-03-03 18:00","취소","취소","연속"]
[177,"경기","군포","서서울산본#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기","2023-03-27 07:00","2023-03-28 18:00","취소","취소","연속"]
[178,"경기","군포","서서울산본#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기","2023-03-29 07:00","2023-03-30 18:00","취소","취소","연속"]
[179,"경기","군포","서안양소래 T/L","서안양S/S 154kV 신규수용공사(LG유플러스)","서안양S/S 154kV 신규수용공사 무부하가압 -서안양-LG유플러스#1, 2T/L GIS 증설","2023-03-21 09:00","2023-03-22 18:00","2023-03-21 09:00","2023-03-22 18:00","연속"]
[180,"경기","군포","서안양소래 T/L","서안양S/S 154kV 신규수용공사(LG유플러스)","서안양S/S 154kV 신규수용공사 무부하가압 -서안양-LG유플러스#1, 2T/L GIS 증설","2023-03-13 09:00","2023-03-14 14:00","2023-03-13 09:00","2023-03-14 14:00","연속"]
[181,"경기","군포","시화성곡 T/L","시화S/S 154kV 시화-성곡T/L 조작시험","시화S/S 154kV 시화-성곡T/L 조작시험","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[182,"경기","군포","산본안양#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 10기","2023-03-25 07:00","2023-03-25 18:00","취소","취소","연속"]
[183,"경기","군포","산본안양#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 10기","2023-03-24 07:00","2023-03-24 18:00","취소","취소","연속"]
[184,"경기","군포","서서울#2일동#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-03-06 07:00","2023-03-08 18:00","취소","취소","연속"]
[185,"경기","군포","서서울#2일동#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-03-02 07:00","2023-03-04 18:00","2023-03-02 07:00","2023-03-04 18:00","연속"]
[186,"경기","동부","가남S/S CB 6100","23년 동부 변전협력총액공사","가남:6100 (보통),4344(조작) 순간압력상승계 설치","2023-03-23 09:30","2023-03-23 14:00","2023-03-23 09:30","2023-03-23 14:00","연속"]
[187,"경기","동부","곤지암초월#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 불량애자 교체공사, 1~58호","2023-03-02 07:30","2023-03-15 18:00","2023-03-02 07:30","2023-03-15 18:00","연속"]
[188,"경기","동부","곤지암초월#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 불량애자 교체공사, 1~58호","2023-03-16 07:30","2023-03-23 18:00","2023-03-16 07:30","2023-03-22 18:00","연속"]
[189,"경기","동부","분당S/S SEC CB 65660","23년 동부 변전협력총액공사","분당:65-66(보통,전자변교체-H)","2023-03-23 09:30","2023-03-23 18:00","취소","취소","연속"]
[190,"경기","동부","분당S/S SEC CB 60610","23년 동부 변전협력총액공사","분당:60-61(보통,전자변교체-H)","2023-03-22 09:30","2023-03-22 18:00","취소","취소","연속"]
[191,"경기","동부","분당S/S CB 6100","23년 동부 변전협력총액공사","분당:G/T#1(조작)[3.7~30] 6111 DS 누기 확인 6100(보통,전자변교체-H)","2023-03-16 14:00","2023-03-16 18:00","취소","취소","연속"]
[192,"경기","동부","성현S/S CB 6100","23년 동부 변전협력총액공사","성현:6100(보통)","2023-03-10 09:30","2023-03-10 18:00","2023-03-10 09:30","2023-03-10 18:00","연속"]
[193,"경기","동부","중원야탑 T/L","23년 동부 변전협력총액공사","야탑:중원-야탑T/L(조작),6100(조작)","2023-03-31 09:00","2023-03-31 14:00","2023-03-31 09:00","2023-03-31 14:00","연속"]
[194,"경기","동부","동판교야탑 T/L","23년 동부 변전협력총액공사","동판교: 동판교-야탑T/L(보통) 순간압력상승계 설치 야탑 : 동판교-야탑T/L(조작)","2023-03-30 09:30","2023-03-30 18:00","2023-03-30 09:30","2023-03-30 18:00","연속"]
[195,"경기","동부","왕암여주#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 성능저하 지지애자 교체공사, 158~203호","2023-03-24 07:30","2023-04-04 18:00","2023-03-24 07:30","2023-04-04 18:00","연속"]
[196,"경기","동부","오포모현#2 T/L","오포S/S #4M.Tr 증설공사","오포S/S #4M.Tr 증설공사","2023-03-24 09:30","2023-03-25 18:00","2023-03-23 11:00","2023-03-24 18:00","연속"]
[197,"경기","동부","이천S/S CB 6200","23년 동부 변전협력총액공사","이천:6200(보통)","2023-03-20 09:30","2023-03-20 18:00","2023-03-20 09:30","2023-03-20 18:00","연속"]
[198,"경기","동부","이천가남#1 T/L","23년 동부 변전협력총액공사","이천:이천-가남#1T/L(보통) 가남:이천-가남#1T/L(보통) (상부누기)","2023-03-18 09:30","2023-03-18 18:00","2023-03-18 09:30","2023-03-18 18:00","연속"]
[199,"경기","동부","이천율현#2 T/L","23년 동부 변전협력총액공사","이천:이천-율현#2T/L(보통) 순간압력상승계 설치 율현:이천-율현#2T/L(보통) 순간압력상승계 설치","2023-03-31 09:30","2023-03-31 18:00","취소","취소","연속"]
[200,"경기","동부","이천율현#1 T/L","23년 동부 변전협력총액공사","이천:이천-율현#1T/L(보통) LA 대체(A,B,C) 율현:이천-율현#1T/L(보통) 순간압력상승계 설치","2023-03-24 09:30","2023-03-24 18:00","취소","취소","연속"]
[201,"경기","동부","초월S/S CB 6100","23년 동부 변전협력총액공사","초월:6100(조작)","2023-03-29 09:30","2023-03-29 18:00","2023-03-29 09:30","2023-03-29 18:00","연속"]
[202,"경기","성남","서안성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(휴전)","2023-03-03 08:00","2023-03-03 18:00","취소","취소","매일"]
[203,"경기","성남","서안성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(휴전)","2023-03-02 08:00","2023-03-02 18:00","취소","취소","매일"]
[204,"경기","성남","덕성남사#2 T/L","23년 성남전력 변전협력회사 총액공사","GIS 하자점검","2023-03-29 14:00","2023-03-29 18:00","2023-03-29 14:00","2023-03-29 18:00","연속"]
[205,"경기","성남","덕성남사#1 T/L","23년 성남전력 변전협력회사 총액공사","GIS 하자점검","2023-03-29 09:00","2023-03-29 14:00","2023-03-29 09:00","2023-03-29 14:00","연속"]
[206,"경기","성남","용인덕성#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 하자점검","2023-03-10 14:00","2023-03-10 18:00","2023-03-10 14:00","2023-03-10 18:00","연속"]
[207,"경기","성남","용인덕성#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 하자점검","2023-03-10 09:00","2023-03-10 14:00","2023-03-10 09:00","2023-03-10 14:00","연속"]
[208,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-03-24 07:00","2023-03-27 18:00","취소","취소","연속"]
[209,"경기","성남","신봉이의#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-03-22 07:00","2023-03-23 18:00","취소","취소","연속"]
[210,"경기","성남","신성남S/S SEC CB 61620","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-24 09:00","2023-03-24 14:00","2023-03-24 09:00","2023-03-24 14:00","연속"]
[211,"경기","성남","신성남S/S SEC CB 66670","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-24 14:00","2023-03-24 18:00","2023-03-24 14:00","2023-03-24 18:00","연속"]
[212,"경기","성남","신성남S/S CB 6100","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-03-22 09:00","2023-03-22 14:00","2023-03-22 09:00","2023-03-22 14:00","연속"]
[213,"경기","성남","신성남S/S SEC CB 65660","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-03-21 14:00","2023-03-21 18:00","2023-03-21 14:00","2023-03-21 18:00","연속"]
[214,"경기","성남","신성남S/S SEC CB 60610","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-03-21 09:00","2023-03-21 14:00","2023-03-21 09:00","2023-03-21 14:00","연속"]
[215,"경기","성남","신성남과천#1 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-03-21 07:00","2023-03-23 18:00","취소","취소","연속"]
[216,"경기","성남","신성남사당#1 T/L","추락방지시설 설치공사","추락방지시설 설치(4회선 구간)","2023-03-21 07:00","2023-03-23 18:00","취소","취소","연속"]
[217,"경기","성남","신성남사당#2 T/L","추락방지시설 설치공사","추락방지시설 설치(4회선 구간)","2023-03-24 07:00","2023-03-25 18:00","취소","취소","연속"]
[218,"경기","성남","신성남과천#2 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-03-24 07:00","2023-03-25 18:00","취소","취소","연속"]
[219,"경기","성남","신성남S/S CB 6200","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-22 14:00","2023-03-22 18:00","2023-03-22 14:00","2023-03-22 18:00","연속"]
[220,"경기","성남","신수원S/S SEC CB 60610","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-17 09:00","2023-03-17 11:00","2023-03-17 09:00","2023-03-17 11:00","연속"]
[221,"경기","성남","신수원S/S CB 6100","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-17 15:00","2023-03-17 18:00","2023-03-17 15:00","2023-03-17 18:00","연속"]
[222,"경기","성남","신수원S/S CB 6200","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-13 09:00","2023-03-13 14:00","2023-03-13 09:00","2023-03-13 14:00","연속"]
[223,"경기","성남","신수원S/S CB 6300","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-03-13 14:00","2023-03-13 18:00","2023-03-13 14:00","2023-03-13 18:00","연속"]
[224,"경기","성남","신수원S/S SEC CB 61620","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-03-15 09:00","2023-03-15 14:00","2023-03-15 09:00","2023-03-15 14:00","연속"]
[225,"경기","성남","신수원S/S SEC CB 66670","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-03-15 14:00","2023-03-15 18:00","2023-03-15 14:00","2023-03-15 18:00","연속"]
[226,"경기","성남","신수원S/S SEC CB 65660","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-17 11:00","2023-03-17 15:00","2023-03-17 11:00","2023-03-17 15:00","연속"]
[227,"경기","성남","신용인S/S SEC CB 66670","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-31 14:00","2023-03-31 18:00","2023-03-31 14:00","2023-03-31 18:00","연속"]
[228,"경기","성남","신용인S/S SEC CB 61620","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-03-31 09:00","2023-03-31 14:00","2023-03-31 09:00","2023-03-31 14:00","연속"]
[229,"경기","직할","조암구문천#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-03-06 00:07","2023-03-07 18:00","취소","취소","연속"]
[230,"경기","직할","조암구문천#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-03-08 07:00","2023-03-08 18:00","취소","취소","연속"]
[231,"경기","직할","발안구문천#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-03-08 07:00","2023-03-08 18:00","취소","취소","연속"]
[232,"경기","직할","발안구문천#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-03-07 07:00","2023-03-07 18:00","취소","취소","연속"]
[233,"경기","직할","의왕동안양#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동안양S/S 의왕-동안양#2T/L GCB 보통점검","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[234,"경기","직할","과천동안양#2 T/L","철탑추락방지시설(수평) 설치공사","철탑추락방지시설(수평) 설치 : 4기","2023-03-31 12:00","2023-03-31 18:00","취소","취소","연속"]
[235,"경기","직할","동안양안양CC#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","메커니즘 점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[236,"경기","직할","의왕동안양#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","CB 보통점검","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[237,"경기","직할","관양동안양#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","메커니즘 점검","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[238,"경기","직할","동안양안양CC#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","메커니즘 점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[239,"경기","직할","서수원율전#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-17 09:00","2023-03-17 14:00","2023-03-17 09:00","2023-03-17 14:00","연속"]
[240,"경기","직할","서서울서수원#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-31 09:00","2023-03-31 14:00","2023-03-31 09:00","2023-03-31 14:00","연속"]
[241,"경기","직할","서서울서수원#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-31 14:00","2023-03-31 18:00","2023-03-31 14:00","2023-03-31 18:00","연속"]
[242,"경기","직할","서수원율전#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-17 14:00","2023-03-17 18:00","2023-03-17 14:00","2023-03-17 18:00","연속"]
[243,"경기","직할","서서울율전#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-21 14:00","2023-03-21 18:00","2023-03-21 14:00","2023-03-21 18:00","연속"]
[244,"경기","직할","율전의왕#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-23 09:00","2023-03-23 14:00","2023-03-23 09:00","2023-03-23 14:00","연속"]
[245,"경기","직할","율전의왕#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-23 14:00","2023-03-23 18:00","2023-03-23 14:00","2023-03-23 18:00","연속"]
[246,"경기","직할","서서울율전#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","조작시험","2023-03-21 09:00","2023-03-21 14:00","2023-03-21 09:00","2023-03-21 14:00","연속"]
[247,"경기","직할","화성발안#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","관형지지물 수직/수평 추락방지장치 설치","2023-03-03 07:00","2023-03-03 18:00","2023-03-03 07:00","2023-03-03 18:00","연속"]
[248,"경기","직할","화성S/S CB 6200","2022-23 경기본부 직할변전협력회사 총액공사","GIS 하자점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[249,"경기","직할","화성S/S CB 6100","2022-23 경기본부 직할변전협력회사 총액공사","GIS 초기점검","2023-03-09 09:00","2023-03-09 14:00","2023-03-09 09:00","2023-03-09 14:00","연속"]
[250,"경기","직할","화성S/S CB 6300","2022-23 경기본부 직할변전협력회사 총액공사","GIS 조작시험","2023-03-09 14:00","2023-03-09 18:00","2023-03-09 14:00","2023-03-09 18:00","연속"]
[251,"경기","직할","화성발안#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","관형지지물 수직/수평 추락방지장치 설치","2023-03-02 07:00","2023-03-02 18:00","2023-03-02 07:00","2023-03-02 18:00","연속"]
[252,"경기","평택","고덕#2고덕 T/L","345kV 고덕2S/S 건설사업","154kV 고덕-동평택 #1T/L 인출변경 및 154kV 고덕-고덕2 임시T/L 철거","2023-03-06 09:00","2023-03-30 18:00","2023-03-06 09:00","2023-03-30 18:00","연속"]
[253,"경기","평택","고덕동평택#1 T/L","345kV 고덕2S/S 건설사업","154kV 고덕-동평택 #1T/L 인출변경 및 154kV 고덕-고덕2 임시T/L 철거","2023-03-06 09:00","2023-03-30 18:00","2023-03-06 09:00","2023-03-30 18:00","연속"]
[254,"경기","평택","고덕진위#1 T/L","345kV 고덕-서안성T/L 건설공사","(1) 선로길이 : 345kV ( 2회선 ) - 10.237km / 154kV ( 2회선 ) - 0.516 km (2) 지지물 ○ 345kV –154kV ( 4회선 ) : 설치 2기 ○ 345kV ( 2회선 ) : 설치 33기 ○ 154kV ( 1회선 ) : 설치 및 철거 1기 (가철탑) ○ 발받침 철탑 : 설치 및 철거 1기","2023-03-06 07:00","2023-03-25 18:00","2023-03-06 07:00","2023-03-25 18:00","연속"]
[255,"경기","평택","고덕진위#2 T/L","345kV 고덕-서안성T/L 건설공사","(1) 선로길이 : 345kV ( 2회선 ) - 10.237km / 154kV ( 2회선 ) - 0.516 km (2) 지지물 ○ 345kV –154kV ( 4회선 ) : 설치 2기 ○ 345kV ( 2회선 ) : 설치 33기 ○ 154kV ( 1회선 ) : 설치 및 철거 1기 (가철탑) ○ 발받침 철탑 : 설치 및 철거 1기","2023-03-02 07:00","2023-03-04 18:00","2023-03-02 07:00","2023-03-04 18:00","연속"]
[256,"경기","평택","고덕진위#2 T/L","345kV 고덕-서안성T/L 건설공사","(1) 선로길이 : 345kV ( 2회선 ) - 10.237km / 154kV ( 2회선 ) - 0.516 km (2) 지지물 ○ 345kV –154kV ( 4회선 ) : 설치 2기 ○ 345kV ( 2회선 ) : 설치 33기 ○ 154kV ( 1회선 ) : 설치 및 철거 1기 (가철탑) ○ 발받침 철탑 : 설치 및 철거 1기","2023-03-27 07:00","2023-03-30 18:00","2023-03-27 07:00","2023-03-30 18:00","연속"]
[257,"경기","평택","원정만호#1 T/L","23년 평택전력지사 변전협력회사 총액공사","원정S/S 원정만호#1 T/L GIS 보통점검 및 LA 하자점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[258,"경기","평택","원정평택TP#2 T/L","23년 평택전력지사 변전협력회사 총액공사","평택T/P 6341DS 누기개소 보수","2023-03-03 09:00","2023-03-06 18:00","2023-03-03 09:00","2023-03-06 18:00","연속"]
[259,"경기","평택","평택T/P #61 BUS","23년 평택전력지사 변전협력회사 총액공사","평택T/P 6341DS 누기개소 보수","2023-03-03 09:00","2023-03-06 18:00","2023-03-03 09:00","2023-03-06 18:00","연속"]
[260,"경기","평택","포승만호 T/L","23년 평택전력지사 변전협력회사 총액공사","만호-포승T/L 세니온 보호배전반 성능개선 및 인출 DS 인터록개선","2023-03-24 09:00","2023-03-24 18:00","2023-03-24 09:00","2023-03-24 18:00","연속"]
[261,"경기","평택","포승평택TP#2 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-03-22 07:00","2023-03-23 17:00","2023-03-22 07:00","2023-03-23 17:00","연속"]
[262,"경기","평택","포승평택TP#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-03-20 07:00","2023-03-21 17:00","2023-03-20 07:00","2023-03-21 17:00","연속"]
[263,"강원","강릉","동해강릉 T/L","2023년 강릉전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-03-28 10:00","2023-03-28 18:00","2023-03-28 10:00","2023-03-28 18:00","연속"]
[264,"강원","강릉","강릉횡계#1 T/L","2023년 강릉전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-03-16 10:00","2023-03-16 18:00","2023-03-16 10:00","2023-03-16 18:00","연속"]
[265,"강원","강릉","영동T/P #2 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 154kV 6333, (운휴) 북평-영동TP #2T/L GIS 상부 Bus #2DS철거 - #2Bus GIS 고깔 설치 - 3/21~22 #2Bus 시험가압","2023-03-15 08:00","2023-03-22 08:00","2023-03-15 08:00","2023-03-22 08:00","연속"]
[266,"강원","강릉","영동T/P #1 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 154kV 6333, (운휴) 북평-영동TP #2T/L GIS #1DS, 본체 철거 - #1DS, 본체 GIS 설치 - 3/30~31 #1Bus 시험가압","2023-03-22 08:00","2023-03-31 08:00","2023-03-22 08:00","2023-03-31 08:00","연속"]
[267,"강원","강릉","영동T/P #2 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 154kV 6333 GIS GIB 철거 - #2DS, 상부 Bus 설치 - 4/12~13 #2Bus 시험가압","2023-03-31 08:00","2023-04-13 08:00","2023-03-31 08:00","2023-04-13 08:00","연속"]
[268,"강원","원주","원주서원주#1 T/L","2023년 원주전력지사 변전협력회사 총액공사","GIS보통점검","2023-03-13 10:00","2023-03-13 18:00","취소","취소","연속"]
[269,"강원","원주","남원주원주#2 T/L","2023년 원주전력지사 변전협력회사 총액공사","GIS 차단기 동작시험","2023-03-17 14:00","2023-03-17 18:00","취소","취소","연속"]
[270,"강원","원주","남원주원주#1 T/L","2023년 원주전력지사 변전협력회사 총액공사","GIS 차단가 동작시험","2023-03-17 10:00","2023-03-17 14:00","취소","취소","연속"]
[271,"강원","원주","원주서원주#2 T/L","2023년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2023-03-14 10:00","2023-03-14 18:00","취소","취소","연속"]
[272,"강원","원주","서원주문막#1 T/L","154kV 문막-지제T/L 수평추락방지시설 설치(병가구간)","154kV 문막-지제T/L 수평추락방지시설 설치(병가구간)","2023-03-10 08:00","2023-03-10 18:00","취소","취소","연속"]
[273,"강원","원주","서원주문막#2 T/L","154kV 문막-지제T/L 수평추락방지시설 설치(병가구간)","154kV 문막-지제T/L 수평추락방지시설 설치(병가구간)","2023-03-02 08:00","2023-03-02 18:00","취소","취소","연속"]
[274,"강원","직할","남춘천춘천열병합#2 T/L","2022~23년 직할 변전정비 총액공사","남춘천S/S SA혼용 디지털화공사 - 대상 : 154kV 남춘천-춘천열병합 #2T/L","2023-03-20 09:00","2023-03-21 18:00","2023-03-20 09:00","2023-03-22 18:00","연속"]
[275,"강원","직할","홍천남춘천 T/L","2022~23년 직할 변전정비 총액공사","남춘천S/S SA혼용 디지털화공사 - 대상 : 154kV 홍천-남춘천T/L","2023-03-13 09:00","2023-03-14 18:00","2023-03-13 09:00","2023-03-14 18:00","연속"]
[276,"강원","직할","남춘천춘천열병합#1 T/L","2022~23년 직할 변전정비 총액공사","남춘천S/S SA혼용 디지털화공사 - 대상 : 154kV 남춘천-춘천열병합 #1T/L","2023-03-15 09:00","2023-03-16 18:00","2023-03-15 09:00","2023-03-17 18:00","연속"]
[277,"강원","직할","서홍천춘천열병합 T/L","2022~2023 가공송전협력회사 총액공사","154kV 서홍천분기, 청평양수 T/L 추락방지장치 설치공사","2023-03-27 08:00","2023-04-02 18:00","2023-03-27 08:00","2023-04-02 18:00","매일"]
[278,"강원","직할","인제양구#2 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 철탑 추락방지장치 설치","2023-03-20 08:00","2023-04-05 18:00","2023-03-20 08:00","2023-04-05 18:00","매일"]
[279,"강원","직할","상남인제#2 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구, 상제 T/L 철탑 추락방지장치 설치","2023-03-20 08:00","2023-03-22 18:00","2023-03-20 08:00","2023-03-22 18:00","매일"]
[280,"강원","직할","철원화천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","병가선로 휴전_추락방지시설 설치(수평)","2023-03-20 07:30","2023-03-21 18:00","2023-03-20 07:30","2023-03-21 18:00","연속"]
[281,"강원","직할","남춘천춘천 T/L","2023년 가공송전 순시점검 위탁공사","154kV 소양 T/L No.23 과열개소 점검 및 조치","2023-03-06 09:00","2023-03-06 12:00","2023-03-06 09:00","2023-03-06 12:00","연속"]
[282,"강원","태백","신제천영월CC#2 T/L","2023년 태백전력지사 변전협력회사 총액공사","영월C/C S/Y 154kV 신제천-영월C/C#2T/L GIS 보통점검","2023-03-24 10:00","2023-03-24 18:00","2023-03-24 10:00","2023-03-24 18:00","연속"]
[283,"강원","태백","신제천영월CC#1 T/L","2023년 태백전력지사 변전협력회사 총액공사","영월C/C S/Y 154kV 신제천-영월C/C#1T/L GIS 보통점검","2023-03-23 10:00","2023-03-23 18:00","2023-03-23 10:00","2023-03-23 18:00","연속"]
[284,"강원","태백","영월영월에코윈드#1 T/L","154kV 태백T/L 선종 교체공사","전력선 교체 및 철탑 교체(2기) - 전력선 교체 : 영월S/S ~ No.77[37.22C-kM, ACMR/TW 240SQ*S) - 철탑교체 : 2기(No.32,33/인클로징 공법)","2023-03-27 09:00","2023-06-27 18:00","2023-03-27 09:00","2023-06-27 18:00","연속"]
[285,"강원","태백","태백고한 T/L","2023년 태백전력지사 변전협력회사 총액공사","154kV 태백-고한T/L 보호반 교체","2023-03-20 10:00","2023-03-22 18:00","2023-03-20 10:00","2023-03-22 18:00","연속"]
[286,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 대소-광혜원#1T/L 증설","2023-03-27 10:00","2023-04-01 18:00","2023-03-27 10:00","2023-04-01 18:00","연속"]
[287,"충북","직할","신진천S/S SEC CB 60610","23년 상반기 충북본부 직할 gis 정밀점검 공사(6100 무부하)","154kV 6100Bustie 정밀점검 후 무부하가압을위한 60-61 SEC 휴전","2023-03-27 17:00","2023-03-27 18:00","2023-03-27 17:00","2023-03-27 18:00","연속"]
[288,"충북","직할","신진천S/S SEC CB 61620","23년 상반기 충북본부 직할 gis 정밀점검 공사(무부하가압)","154kV 6300,#2Sh.C 정밀점검 후 무부하가압을위한 61-62SEC휴전","2023-03-24 17:00","2023-03-24 18:00","2023-03-24 17:00","2023-03-24 18:00","연속"]
[289,"충북","직할","신진천S/S CB 6100","23년 상반기 충북본부 직할 gis 정밀점검 공사","신진천변전소 154kV 6100Bustie 정밀점검","2023-03-25 09:00","2023-03-27 18:00","2023-03-25 09:00","2023-03-27 18:00","연속"]
[290,"충북","직할","신진천S/S CB 6200","23년 상반기 충북본부 직할 gis 정밀점검 공사","신진천변전소 154kV 6200Bustie 정밀점검","2023-03-28 09:00","2023-03-30 18:00","취소","취소","연속"]
[291,"충북","직할","신진천진천#1 T/L","154kV신진천-오창T/L OPGW 증설공사","154kV 신진천-진천#1T/L 29~30호 OPGW 교체","2023-03-06 07:00","2023-03-06 18:00","취소","취소","연속"]
[292,"충북","직할","신진천진천#2 T/L","154kV신진천-오창T/L OPGW 증설공사","154kV신진천-오창#2T/L 2~3호 OPGW 시설","2023-03-07 07:00","2023-03-07 18:00","취소","취소","연속"]
[293,"충북","직할","신진천진천#1 T/L","23년 상반기 충북본부 직할 gis 정밀점검 공사","154kV 신진천-진천#1 T/L GIS 정밀점검","2023-03-10 09:00","2023-03-12 18:00","취소","취소","연속"]
[294,"충북","직할","신진천S/S CB 6300","23년 상반기 충북본부 직할 gis 정밀점검 공사","신진천변전소 154kV 6300Bustie 정밀점검","2023-03-18 09:00","2023-03-20 18:00","2023-03-18 09:00","2023-03-20 18:00","연속"]
[295,"충북","청주","남청주오송#2 T/L","남청주S/S 345kV 송전선로 인출변경","74 BAY → 76 BAY 인출변경 관련 병가선로 안전이격 (즉시가압 가능)","2023-03-01 08:00","2023-03-04 18:00","2023-03-01 08:00","2023-03-04 18:00","연속"]
[296,"충북","청주","남청주오송#2 T/L","남청주S/S 345kV 송전선로 인출변경","73 BAY → 74 BAY 인출변경 관련 병가선로 안전이격 (즉시가압 가능)","2023-03-12 08:00","2023-03-17 18:00","2023-03-12 08:00","2023-03-17 18:00","연속"]
[297,"충북","청주","북청주봉명#2 T/L","22~23년 청주전력 변전협력회사 총액공사","북청주-봉명#2T/L 보호배전반 대체공사","2023-03-20 09:00","2023-03-22 18:00","2023-03-20 09:00","2023-03-22 18:00","연속"]
[298,"충북","청주","신진천오창#2 T/L","154kV 문백-오창 송전선로 건설공사","신진천-오창T/L No.22호 인근 가선로 구성","2023-03-06 07:00","2023-03-08 18:00","취소","취소","연속"]
[299,"충북","청주","신진천오창#1 T/L","154kV 문백-오창 송전선로 건설공사","신진천-오창T/L No.22호 인근 가선로 구성","2023-03-09 07:00","2023-03-11 18:00","취소","취소","연속"]
[300,"충북","충주","신충주감곡#1 T/L","2023년 가공송전 순시점검 위탁공사 초기점검 및 정밀점검","2023년 가공송전 순시점검 위탁공사 초기점검 및 정밀점검 1. 초기점검 : 신충주감곡#1 No.77~85 (왕암여주#1 No.141~133 병가) 2. 정밀점검 : 신충주감곡#1 No.86~88(감곡가남#2 No.1~3 병가) 3. 애자 절연저항 측정 : 11기, No.1,3,5,7,8,14,16,19,21,23,36(신충주-음성#2T/L 병가)","2023-03-27 07:30","2023-04-04 18:00","2023-03-27 07:30","2023-04-04 18:00","매일"]
[301,"충북","충주","감곡가남#2 T/L","2023년 가공송전 순시점검 위탁공사 초기점검 및 정밀점검","2023년 가공송전 순시점검 위탁공사 정밀점검 : 감곡가남#2 No.1~3 (신충주감곡#1 No.86~88 병가) 및 감곡가남#2TL No.4","2023-03-27 07:30","2023-03-28 18:00","취소","취소","매일"]
[302,"충북","충주","감곡가남#1 T/L","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사 항공장애표지도장 하도 및 상도 154kV 감곡가남#1T/L No.2 (신충주감곡#2T/L No.87 병가)","2023-03-22 08:00","2023-03-24 18:00","취소","취소","매일"]
[303,"충북","충주","신충주감곡#2 T/L","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사 항공장애표지도장 하도 및 상도 154kV 신충주감곡#2T/L No.87 (감곡가남#1T/L No.2)","2023-03-22 08:00","2023-03-24 18:00","2023-03-22 08:00","2023-03-24 18:00","매일"]
[304,"충북","충주","금왕남음성#1 T/L","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사 항공장애표지도장 하도 및 상도 154kV 금왕남음성#1T/L No.14 (음성금왕#2T/L No.52 병가)","2023-03-07 08:00","2023-03-10 18:00","취소","취소","매일"]
[305,"충북","충주","금왕남음성#2 T/L","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사 항공장애표지도장 하도 및 상도 154kV 금왕남음성#2T/L No.14 (음성금왕#1T/L No.52 병가) ※ 주말작업 제외","2023-03-02 08:00","2023-03-06 18:00","취소","취소","매일"]
[306,"충북","충주","문경단양 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 문경-단양 T/L 인출변경 및 보호반 대체","2023-03-04 08:00","2023-03-04 18:00","2023-03-04 08:00","2023-03-04 18:00","연속"]
[307,"충북","충주","점촌단양 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 점촌-단양 T/L 인출변경 및 보호반 대체","2023-03-01 08:00","2023-03-01 18:00","2023-03-01 08:00","2023-03-01 18:00","연속"]
[308,"충북","충주","신제천영월CC#2 T/L","2022~23년 충주전력지사 변전협력회사 총액공사","154kV GIS 및 LA 보통점검","2023-03-24 09:00","2023-03-24 18:00","취소","취소","연속"]
[309,"충북","충주","신제천제천#2 T/L","2022~23년 충주전력지사 변전협력회사 총액공사","154kV GIS 및 LA 보통점검(양단)","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[310,"충북","충주","신제천영월CC#1 T/L","2022~23년 충주전력지사 변전협력회사 총액공사","154kV GIS 및 LA 보통점검","2023-03-23 09:00","2023-03-23 18:00","취소","취소","연속"]
[311,"충북","충주","신충주음성#2 T/L","2023년 가공송전 순시점검 위탁공사","2023년 가공송전 순시점검 위탁공사 애자 절연저항 측정 : 11기, No.1,3,5,7,8,14,16,19,21,23,36(신충주-감곡#1T/L 병가)","2023-03-29 07:30","2023-03-31 18:00","취소","취소","매일"]
[312,"충북","충주","신충주북충주#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신충주-북충주#1 T/L No.1~87 송전피뢰기 설치공사","2023-03-02 07:00","2023-03-11 18:00","2023-03-02 07:00","2023-03-11 18:00","매일"]
[313,"충북","충주","신충주북충주#2 T/L","154kV 왕암-충주 등 5개T/L 불량 압축인류클램프 교체공사","불량 압축인류클램프 교체 및 수평 추락방지장치 설치","2023-03-21 09:00","2023-03-22 18:00","2023-03-21 09:00","2023-03-22 18:00","매일"]
[314,"충북","충주","신충주음성#1 T/L","2022~23년 충주전력지사 변전협력회사 총액공사","154kV GIS 보통점검(양단) 음성S/S CVT 보통점검","2023-03-07 09:00","2023-03-07 18:00","취소","취소","연속"]
[315,"충북","충주","왕암여주#2 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 왕암-여주#2 T/L No.55~98 송전피뢰기 설치","2023-03-07 07:00","2023-03-13 18:00","2023-03-07 07:00","2023-03-13 18:00","매일"]
[316,"충북","충주","음성금왕#2 T/L","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사 항공장애표지도장 하도 및 상도 154kV 음성금왕 #2T/L No.52 (금왕남음성#1T/L No.14 병가)","2023-03-07 08:00","2023-03-10 18:00","취소","취소","매일"]
[317,"충북","충주","음성사리 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 및 지지애자 교체 (주말제외) 음성사리 T/L No.1 ~ 39 (병가구간 휴전)","2023-03-13 07:30","2023-03-26 18:00","2023-03-13 07:30","2023-03-26 18:00","매일"]
[318,"충북","충주","음성금왕#1 T/L","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사","765kV 신중부-신안성 등 5개T/L 항공시설물 설치공사 항공장애표지도장 하도 및 상도 154kV 음성금왕#1T/L No.52 (금왕남음성#2T/L No.14 병가) ※ 주말작업 제외","2023-03-02 08:00","2023-03-06 18:00","취소","취소","매일"]
[319,"충북","충주","북충주충주 T/L","154kV 왕암-충주등 5개T/L 불량 압축인류클램프 교체공사","불량 압축인류클램프 교체 및 수평 추락방지장치 설치","2023-03-27 09:00","2023-04-01 18:00","2023-03-27 09:00","2023-04-01 18:00","매일"]
[320,"충북","충주","충주충주HP#2 T/L","154kV 왕암-충주등 5개T/L 불량 압축인류클램프 교체공사","불량 압축인류클램프 교체 및 수평 추락방지장치 설치","2023-03-27 09:00","2023-04-01 18:00","2023-03-27 09:00","2023-04-01 18:00","매일"]
[321,"충북","충주","충주충주HP#1 T/L","154kV 왕암-충주 등 5개T/L 불량 압축인류클램프 교체공사","불량 압축인류클램프 교체 및 수평 추락방지장치 설치","2023-03-13 09:00","2023-03-20 18:00","2023-03-13 09:00","2023-03-20 18:00","매일"]
[322,"충북","충주","풍동음성#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 및 지지애자 교체 (주말제외) 풍동음성#2 T/L No.13 ~ 92","2023-03-06 07:30","2023-03-26 18:00","2023-03-06 07:30","2023-03-26 18:00","매일"]
[323,"대전세종충남","대전","남대전신흥#1 T/L","남대전S/S 154kV 노후 GIS교체공사(5차분)","6233, 637 교체공사","2023-03-16 09:00","2023-03-17 09:00","2023-03-16 09:00","2023-03-17 09:00","연속"]
[324,"대전세종충남","대전","신옥천남대전#3 T/L","남대전S/S 154kV 노후 GIS교체공사(5차분)","6233, 637 교체공사","2023-03-06 08:00","2023-03-29 18:00","2023-03-06 08:00","2023-03-29 18:00","연속"]
[325,"대전세종충남","대전","남대전신흥#1 T/L","남대전S/S 154kV 노후 GIS교체공사(5차분)","6233, 637 교체공사","2023-03-24 09:00","2023-03-27 09:00","2023-03-24 09:00","2023-03-27 09:00","연속"]
[326,"대전세종충남","대전","추부금산#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산T/L 추락방지시설 설치공사","2023-03-27 08:00","2023-04-21 18:00","취소","취소","매일"]
[327,"대전세종충남","대전","신옥천추부#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-추부T/L 추락방지시설 설치공사","2023-03-20 08:00","2023-03-31 18:00","취소","취소","매일"]
[328,"대전세종충남","서산","서산대산 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 대산-석문#2T/L 피뢰기 설치공사(2기) (No.5,6 병가)","2023-03-13 08:00","2023-03-13 18:00","취소","취소","연속"]
[329,"대전세종충남","서산","대산석문#1 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 대산-석문#1T/L 피뢰기 설치공사(3기) (No.5,6,48)","2023-03-23 08:00","2023-03-23 18:00","취소","취소","연속"]
[330,"대전세종충남","서산","대산성연 T/L","154kV 대산-성연T/L 애자교체 등","애자교체 : No.37,61 상간스페이서 설치 : No.74~75","2023-03-23 08:00","2023-03-24 18:00","취소","취소","매일"]
[331,"대전세종충남","서산","서산대산#4 T/L","23년 서산P/O 변전협력회사 총액공사","대산S/S 154kV 서산-대산#3T/L 6G7 CB 보통점검","2023-03-28 09:00","2023-03-28 18:00","취소","취소","연속"]
[332,"대전세종충남","서산","대산석문#2 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 대산-석문#2T/L 피뢰기 설치공사(39기) (No.1~20,23~29,32~36,39~41,45~48)","2023-03-13 08:00","2023-03-16 18:00","2023-03-08 08:00","2023-03-10 18:00","매일"]
[333,"대전세종충남","서산","서산대산#3 T/L","23년 서산P/O 변전협력회사 총액공사","대산S/S 154kV 서산-대산#3T/L 627 CB 보통점검 (병행) 서산S/S 154kV 서산-대산#3T/L LA 보통점검 (병행) 서산S/S 154kV 서산-대산#3T/L 667 CB 보통점검","2023-03-27 09:00","2023-03-27 18:00","취소","취소","연속"]
[334,"대전세종충남","서산","서산홍성 T/L","[송전] 154kV 서산-홍성T/L 송전선로 정밀점검","154kV 서산-홍성T/L No.1~138 송전선로 정밀점검","2023-03-16 08:00","2023-03-27 18:00","2023-03-16 08:00","2023-03-27 18:00","매일"]
[335,"대전세종충남","서산","서산해미 T/L","[송전] 154kV 서산-해미T/L 송전선로 정밀점검","154kV 서산-해미T/L No.66~138 송전선로 정밀점검","2023-03-10 08:00","2023-03-15 18:00","2023-03-06 08:00","2023-03-10 18:00","매일"]
[336,"대전세종충남","서산","석문당진화력#2 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 대산-석문#1T/L 피뢰기 설치공사(1기) (No.48 병가)","2023-03-23 08:00","2023-03-23 18:00","취소","취소","연속"]
[337,"대전세종충남","서산","석문당진화력#1 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 대산-석문#2T/L 피뢰기 설치공사(1기) (No.48 병가)","2023-03-16 08:00","2023-03-16 18:00","취소","취소","연속"]
[338,"대전세종충남","서산","서산성연 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 서산-성연T/L 피뢰기 설치공사(1기) (No.24)","2023-03-21 08:00","2023-03-21 18:00","취소","취소","연속"]
[339,"대전세종충남","서산","신당진서산#1 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 신당진-서산#1T/L 피뢰기 설치공사(55기) (No.1~55)","2023-03-17 08:00","2023-03-23 18:00","2023-03-02 08:00","2023-03-07 18:00","매일"]
[340,"대전세종충남","서산","신당진서산#2 T/L","154kV 신당진-서산 T/L 애자교체 등","애자련보강 : No.10,11 애자교체 : No.22 상간스페이서 설치 : No.57~58","2023-03-14 08:00","2023-03-16 18:00","2023-03-08 08:00","2023-03-10 18:00","연속"]
[341,"대전세종충남","서산","태안태안화력 T/L","154kV 태안분기T/L 건설공사","154kV 태안분기T/L 건설공사 휴전작업 개요(No.59~태안S/T) ○ No.59 ~ No.64 : 전력선 공중이동 작업(임시선로 상단) ○ No.64 ~ 태안S/T : 전력선 연,긴선(하단암) ○ No.79 ~ 태안S/T : 가공지전 연,긴선 ○ No.64 ~ No.79 : (수평)추락방지장치 설치 및 이동통로용 안전발판(하단암) 설치. 끝.","2023-03-13 07:00","2023-04-08 18:00","2023-03-13 07:00","2023-04-08 18:00","연속"]
[342,"대전세종충남","서산","해미홍성 T/L","[송전] 154kV 해미-홍성T/L 송전선로 정밀점검","154kV 해미-홍성T/L No.1~65 송전선로 정밀점검","2023-03-06 08:00","2023-03-09 18:00","취소","취소","매일"]
[343,"대전세종충남","세종","부강신탄진 T/L","[송전]154kV 부강-신탄진T/L 추락방지시설 설치공사","[송전]154kV 부강-신탄진T/L 추락방지시설 설치공사 - No.41~57, 62 (18기)","2023-03-06 07:00","2023-03-13 18:00","취소","취소","매일"]
[344,"대전세종충남","세종","월산S/S #2 BUS","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV GIS x 2대 증설(637,647)","2023-03-20 08:00","2023-03-31 18:00","2023-03-20 08:00","2023-03-30 08:00","연속"]
[345,"대전세종충남","세종","월산S/S #1 BUS","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV GIS x 2대 증설(637,647)","2023-03-30 08:00","2023-03-31 18:00","2023-03-30 08:00","2023-03-31 18:00","연속"]
[346,"대전세종충남","세종","세종월산#1 T/L","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV 남부열병합#1,2T/L 증설 - 세종월산#1T/L 활용 무부하 가압","2023-03-30 08:00","2023-03-31 18:00","2023-03-30 16:00","2023-03-31 18:00","연속"]
[347,"대전세종충남","세종","세종월산#1 T/L","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV 남부열병합#1,2T/L 증설 - 세종월산#1T/L 활용 무부하 가압","2023-03-17 08:00","2023-03-20 18:00","2023-03-17 08:00","2023-03-20 08:00","연속"]
[348,"대전세종충남","세종","세종월산#1 T/L","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV 남부열병합#1,2T/L 증설 - 세종월산#1T/L 활용 무부하 가압","2023-03-27 08:00","2023-03-28 18:00","2023-03-28 16:00","2023-03-29 18:00","연속"]
[349,"대전세종충남","세종","월산S/S #1 BUS","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV GIS x 2대 증설(637,647)","2023-03-13 08:00","2023-03-20 18:00","2023-03-13 08:00","2023-03-20 08:00","연속"]
[350,"대전세종충남","세종","조치원전의#2 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 보통점검(전의S/S) ○154kV GIS 차단기 조작시험(조치원S/S)","2023-03-06 10:00","2023-03-06 18:00","2023-03-06 10:00","2023-03-06 18:00","연속"]
[351,"대전세종충남","세종","천안전의#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV LA 보통점검","2023-03-08 10:00","2023-03-08 18:00","2023-03-08 10:00","2023-03-08 18:00","연속"]
[352,"대전세종충남","세종","서세종조치원 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험(조치원)","2023-03-09 10:00","2023-03-09 18:00","2023-03-09 10:00","2023-03-09 18:00","연속"]
[353,"대전세종충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 추락방지시설 설치공사","[송전]154kV 조치원-월산T/L 추락방지시설 설치공사 - No.1~56 (56기)","2023-03-14 07:00","2023-04-07 18:00","취소","취소","매일"]
[354,"대전세종충남","세종","조치원전의#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험(조치원S/S)","2023-03-07 10:00","2023-03-07 18:00","2023-03-07 10:00","2023-03-07 18:00","연속"]
[355,"대전세종충남","직할","대덕덕진#1 T/L","대덕-덕진T/L 수목이격거리 미달개소 전지작업","대덕변전소 구내 수목이격거리 미달개소 상순전지 시행 (대덕-덕진T/L S/T)","2023-03-02 13:30","2023-03-02 16:30","취소","취소","연속"]
[356,"대전세종충남","직할","송강신일#1 T/L","[송전] 154kV 송강-신일T/L OF케이블 선종교체공사","○ 공사구간 : 154kV 송강-신일T/L J/B#4~신일S/S ○ 선종교체 : 154kV OF 2000㎟ → 154kV XLPE 2000㎟ (2.32km)","2023-03-20 09:00","2023-06-09 18:00","취소","취소","연속"]
[357,"대전세종충남","천안","불당서천안#1 T/L","불당S/S 154kV 불당서천안#1T/L 전자변 교체","불당S/S 154kV 불당서천안#1T/L 전자변 교체","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[358,"대전세종충남","천안","불당서천안#2 T/L","불당S/S 154kV 불당서천안#2T/L 전자변 교체","불당S/S 154kV 불당서천안#2T/L 전자변 교체","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[359,"대전세종충남","천안","둔포석곡#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 154kV 둔포-석곡T/L 9기","2023-03-20 07:00","2023-03-20 18:00","취소","취소","연속"]
[360,"대전세종충남","천안","신온양석곡#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 154kV 신온양-석곡T/L 12기","2023-03-23 07:00","2023-03-24 18:00","취소","취소","연속"]
[361,"대전세종충남","천안","신온양석곡#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 154kV 신온양-석곡T/L 12기","2023-03-21 07:00","2023-03-22 18:00","취소","취소","매일"]
[362,"대전세종충남","천안","둔포석곡#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 154kV 둔포-석곡T/L 9기","2023-03-20 07:00","2023-03-20 18:00","2023-03-20 07:00","2023-03-20 18:00","연속"]
[363,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 아산합덕#1TL GIS 초기점검","아산S/S 154kV 아산합덕#1TL GIS 초기점검","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[364,"대전세종충남","천안","아산인주#1 T/L","아산·인주SS 154kV 아산인주#1T/L 보호배전반 교체","아산·인주SS 154kV 아산인주#1T/L 보호배전반 교체","2023-03-13 09:00","2023-03-17 18:00","취소","취소","연속"]
[365,"대전세종충남","천안","아산온양#1 T/L","아산S/S 154kV 아산온양#1TL GIS 보통점검","아산S/S 154kV 아산온양#1TL GIS 보통점검","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[366,"대전세종충남","천안","아산인주#2 T/L","아산·인주SS 154kV 아산인주#2T/L 보호배전반 교체","아산·인주SS 154kV 아산인주#2T/L 보호배전반 교체","2023-03-27 09:00","2023-03-31 18:00","취소","취소","연속"]
[367,"대전세종충남","천안","아산온양#2 T/L","아산S/S 154kV 아산온양#2TL GIS 보통점검","아산S/S 154kV 아산온양#2TL GIS 보통점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[368,"대전세종충남","천안","예산응봉#2 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 - 154kV 예산-응봉T/L No.2~47 ※ 주말작업 없음","2023-03-20 08:00","2023-03-29 18:00","2023-03-27 08:00","2023-03-31 18:00","매일"]
[369,"대전세종충남","천안","예산응봉#2 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 - 154kV 예산-응봉T/L No.47","2023-03-30 12:00","2023-03-30 18:00","취소","취소","연속"]
[370,"대전세종충남","천안","예산응봉#1 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 - 154kV 예산-응봉T/L No.2~47 ※ 주말작업 없음","2023-03-20 08:00","2023-03-30 12:00","2023-03-20 08:00","2023-03-24 18:00","매일"]
[371,"대전세종충남","천안","둔포직산#1 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 및 초기점검 - 154kV 직산-둔포T/L No.1~12(초기). 13~27(정밀)","2023-03-06 08:00","2023-03-09 18:00","2023-03-06 08:00","2023-03-09 18:00","매일"]
[372,"대전세종충남","천안","둔포직산#2 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 및 초기점검 - 154kV 직산-둔포T/L No.1~12(초기). 13~27(정밀)","2023-03-13 08:00","2023-03-16 18:00","2023-03-13 08:00","2023-03-16 18:00","매일"]
[373,"대전세종충남","천안","한샘직산#2 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 및 초기점검 - 154kV 한샘-직산T/L No.1~8(정밀). 9~20(초기)","2023-03-13 08:00","2023-03-16 18:00","2023-03-13 08:00","2023-03-16 18:00","매일"]
[374,"대전세종충남","천안","한샘직산#1 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 및 초기점검 - 154kV 한샘-직산T/L No.1~8(정밀). 9~20(초기)","2023-03-06 08:00","2023-03-09 18:00","2023-03-06 08:00","2023-03-09 18:00","매일"]
[375,"대전세종충남","천안","신온양한샘#2 T/L","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사[안전이격]","2023-03-15 14:00","2023-03-17 18:00","2023-03-15 14:00","2023-03-17 18:00","연속"]
[376,"대전세종충남","천안","한샘S/S #1 BUS","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사","2023-03-13 09:00","2023-03-24 15:00","2023-03-13 09:00","2023-03-24 15:00","연속"]
[377,"대전세종충남","천안","신온양한샘#1 T/L","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사[안전이격 휴전]","2023-03-13 09:00","2023-03-15 14:00","2023-03-13 09:00","2023-03-15 14:00","연속"]
[378,"대전세종충남","천안","신온양한샘#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 154kV 신온양-한샘T/L 6기","2023-03-21 07:00","2023-03-22 18:00","취소","취소","매일"]
[379,"대전세종충남","천안","신온양한샘#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","수평 추락방지장치 설치 154kV 신온양-한샘T/L 6기","2023-03-23 07:00","2023-03-24 18:00","취소","취소","연속"]
[380,"대전세종충남","천안","한샘S/S #2 BUS","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사","2023-03-27 09:00","2023-04-07 18:00","2023-03-27 09:00","2023-04-07 18:00","연속"]
[381,"대전세종충남","천안","한샘직산#2 T/L","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사[안전이격]","2023-03-27 09:00","2023-03-29 18:00","2023-03-27 09:00","2023-03-29 18:00","연속"]
[382,"대전세종충남","천안","신온양한샘#2 T/L","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사[안전이격]","2023-03-29 14:00","2023-03-31 18:00","2023-03-29 14:00","2023-03-31 18:00","연속"]
[383,"대전세종충남","청양","관창보령CC T/L","154kV 차단기 부동작 예방 조작시험","154kV 차단기 부동작 예방 조작시험","2023-03-10 09:00","2023-03-10 18:00","취소","취소","연속"]
[384,"대전세종충남","청양","관창대천#2 T/L","[송전] 154kV 대천S/S 인출T/L 지중화공사","- 선종 및 길이 : XLPE 2,500㎟ × 4C, 0.136km - 휴전작업내용 : 가공-지중 연결 및 GIS 가압","2023-03-20 09:00","2023-03-24 18:00","취소","취소","연속"]
[385,"대전세종충남","청양","신서천대천#2 T/L","[송전] 154kV 대천S/S 인출T/L 지중화공사","- 선종 및 길이 : XLPE 2,500㎟ × 4C, 0.136km - 휴전작업내용 : 가공-지중 연결 및 GIS 가압","2023-03-20 09:00","2023-03-24 18:00","취소","취소","연속"]
[386,"대전세종충남","청양","보령TP보령CC T/L","154kV 차단기 부동작 예방 조작시험","154kV 차단기 부동작 예방 조작시험","2023-03-16 09:00","2023-03-16 18:00","취소","취소","연속"]
[387,"대전세종충남","청양","옥산부여#1 T/L","154kV 옥산-부여#1T/L 관련기기 점검","부여S/S 170kV GIS 보통점검 옥산S/S 154kV 차단기 부동작 예방 조작시험","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[388,"대전세종충남","청양","옥산부여#2 T/L","154kV 옥산-부여#2T/L 관련기기 점검","부여S/S 170kV GIS 보통점검 및 LA 초기점검 옥산S/S 154kV 차단기 부동작 예방 조작시험","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[389,"대전세종충남","청양","부여논산#2 T/L","170kV GIS 보통점검 및 LA 초기점검","170kV GIS 보통점검 및 LA 초기점검","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[390,"대전세종충남","청양","부여논산#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[391,"대전세종충남","청양","신서천옥산#1 T/L","170kV GIS 보통점검 및 LA 보통점검","170kV GIS 보통점검 및 LA 보통점검","2023-03-07 09:00","2023-03-07 18:00","취소","취소","연속"]
[392,"대전세종충남","청양","응봉홍성#2 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 - 154kV 예산-응봉T/L No.47(4회선 병가철탑 안전확보)","2023-03-30 08:00","2023-03-30 12:00","2023-03-29 08:00","2023-03-31 18:00","연속"]
[393,"대전세종충남","청양","응봉홍성#1 T/L","2023년 가공송전 순시점검 위탁공사","정밀점검 - 154kV 예산-응봉T/L No.47(4회선 병가철탑 안전확보)","2023-03-30 12:00","2023-03-30 18:00","2023-03-22 08:00","2023-03-24 18:00","연속"]
[394,"대전세종충남","청양","동군산장항#2 T/L","[송전] 154kV 옥산-장항#1T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-03-08 08:00","2023-03-10 18:00","취소","취소","매일"]
[395,"대전세종충남","청양","청양신풍#2 T/L","[송전] 154kV 청양-신풍#2T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-03-20 08:00","2023-03-24 18:00","취소","취소","매일"]
[396,"대전세종충남","청양","청양신풍#1 T/L","[송전] 154kV 청양-신풍#1T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-03-13 08:00","2023-03-17 18:00","취소","취소","매일"]
[397,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-03-13 07:00","2023-03-20 18:00","취소","취소","매일"]
[398,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-03-02 07:00","2023-03-09 18:00","취소","취소","매일"]
[399,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-03-02 07:00","2023-03-07 18:00","취소","취소","매일"]
[400,"전북","군산","군산이리#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-03-18 07:00","2023-03-20 18:00","취소","취소","매일"]
[401,"전북","군산","영등낭산#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[402,"전북","군산","영등낭산#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[403,"전북","군산","새만금소룡#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[404,"전북","군산","새만금소룡#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[405,"전북","군산","새만금비응#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[406,"전북","군산","새만금비응#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[407,"전북","군산","영등낭산#1 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-03-07 07:00","2023-03-15 18:00","취소","취소","연속"]
[408,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-03-16 07:00","2023-03-24 18:00","취소","취소","연속"]
[409,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-03-06 07:00","2023-03-06 18:00","취소","취소","연속"]
[410,"전북","김제","정주고창#2 T/L","김제P/O 효성제 170kV 차단기 투입불량 관련 조치","김제P/O 효성제 170kV 차단기 투입불량 관련 조치","2023-03-09 09:00","2023-03-09 18:00","취소","취소","연속"]
[411,"전북","김제","정주고창#1 T/L","김제P/O 효성제 170kV 차단기 투입불량 관련 조치","김제P/O 효성제 170kV 차단기 투입불량 관련 조치","2023-03-08 09:00","2023-03-08 18:00","취소","취소","연속"]
[412,"전북","김제","신김제전주#2 T/L","신김제S/S 154kV LA, CVT 보통점검","154kV 신김제-전주#2T/L LA,CVT 보통점검","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[413,"전북","김제","신김제정공#1 T/L","신김제,정공S/S 154kV LA, CVT 보통점검","154kV 신김제-정공#1T/L LA,CVT 보통점검","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[414,"전북","김제","신김제전주#1 T/L","신김제S/S 154kV LA 보통점검","154kV 신김제-전주#1T/L LA 보통점검","2023-03-16 09:00","2023-03-16 14:00","2023-03-16 09:00","2023-03-16 14:00","연속"]
[415,"전북","김제","신김제동전주#2 T/L","김제P/O 효성제 170kV 차단기 투입불량 관련 조치","김제P/O 효성제 170kV 차단기 투입불량 관련 조치","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[416,"전북","김제","신김제동전주#1 T/L","관내S/S 170kV GIS 보통점검","관내S/S 170kV GIS 보통점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[417,"전북","김제","신김제남전주#1 T/L","관내S/S 170kV GIS 보통점검","관내S/S 170kV GIS 보통점검","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[418,"전북","김제","신김제정공#2 T/L","정공S/S 154kV LA 보통점검","154kV 신김제-정공#2T/L LA 보통점검","2023-03-06 09:00","2023-03-06 14:00","2023-03-06 09:00","2023-03-06 14:00","연속"]
[419,"전북","김제","정공정주#2 T/L","정공S/S 154kV LA 보통점검","154kV 정공-정주#2T/L LA 보통점검","2023-03-07 09:00","2023-03-07 14:00","취소","취소","연속"]
[420,"전북","김제","정공칠보HP T/L","관내S/S 170kV GIS 보통점검","관내S/S 170kV GIS 보통점검","2023-03-02 09:00","2023-03-02 18:00","2023-03-02 09:00","2023-03-02 18:00","연속"]
[421,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","가. 철탑교체 : 설치 9기, 철거 9기, 가철탑 설치철거 6기 나. 전력선 교체 ○ 신김제-동전주T/L : 1.711C-km[ACSR 410㎟×2B] (33~39호) ○ 남전주-임실T/L : 1.235C-km[ACSR 410㎟×S] (23~28호) 다. 금구류 교체 및 기타 부대공사","2023-03-27 08:00","2023-04-02 17:00","취소","취소","연속"]
[422,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","가. 철탑교체 : 설치 9기, 철거 9기, 가철탑 설치·철거 6기 나. 전력선 교체 ○ 신김제-동전주T/L : 1.711C-km[ACSR 410㎟×2B] (33~39호) ○ 남전주-임실T/L : 1.235C-km[ACSR 410㎟×S] (23~28호) 다. 금구류 교체 및 기타 부대공사","2023-03-20 08:00","2023-03-26 17:00","취소","취소","연속"]
[423,"전북","직할","동전주북전주#2 T/L","'23년 전북직할 변전협력 총액공사","170kV GIS 보통점검","2023-03-21 15:00","2023-03-21 20:00","2023-03-21 15:00","2023-03-21 20:00","연속"]
[424,"전북","직할","동전주태평#1 T/L","'23년 전북직할 변전협력 총액공사","170kV GIS 조작시험","2023-03-31 09:00","2023-03-31 14:00","2023-03-31 09:00","2023-03-31 14:00","연속"]
[425,"전북","직할","동전주태평#2 T/L","'23년 전북직할 변전협력 총액공사","170kV GIS 조작시험","2023-03-31 14:00","2023-03-31 18:00","2023-03-31 14:00","2023-03-31 18:00","연속"]
[426,"광주전남","광주","계림S/S SEC CB 65660","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #2DS 철거","2023-03-06 09:00","2023-03-08 14:00","취소","취소","연속"]
[427,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-03-06 09:00","2023-04-07 18:00","취소","취소","연속"]
[428,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L 교체","2023-03-06 09:00","2023-04-07 18:00","취소","취소","연속"]
[429,"광주전남","광주","계림S/S CB 6200","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - #60BUS → #65BUS 절체를 위한 6200 BUS TIE 투입(6100BUS 설치중)","2023-03-18 18:00","2023-03-18 19:00","취소","취소","연속"]
[430,"광주전남","광주","계림S/S SEC CB 65660","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #2DS 철거 후 #2DS 및 상부BUS 설치, 준공시험 등","2023-03-18 18:00","2023-04-07 15:00","취소","취소","연속"]
[431,"광주전남","광주","계림S/S #65 BUS","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #2DS 철거 후 #2DS 및 상부BUS 설치, 준공시험 등","2023-03-18 18:00","2023-04-07 15:00","취소","취소","연속"]
[432,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-03-06 09:00","2023-04-07 18:00","취소","취소","연속"]
[433,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #60BUS 신설분 무부하 가압","2023-03-17 15:00","2023-03-18 18:00","취소","취소","연속"]
[434,"광주전남","광주","계림S/S SEC CB 60610","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #1DS, CB 철거 후 신설분 설치","2023-03-08 14:00","2023-03-18 18:00","취소","취소","연속"]
[435,"광주전남","광주","계림S/S #60 BUS","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #1DS, CB 철거 후 신설분 설치","2023-03-08 14:00","2023-03-18 18:00","취소","취소","연속"]
[436,"광주전남","광주","계림S/S CB 6200","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - #65BUS → #60BUS 절체를 위한 6200 BUS TIE 투입(6100BUS 철거중)","2023-03-08 14:00","2023-03-08 15:00","취소","취소","연속"]
[437,"광주전남","광주","계림S/S #65 BUS","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #2DS 철거","2023-03-06 09:00","2023-03-08 14:00","취소","취소","연속"]
[438,"광주전남","광주","정공담양 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2023-03-30 08:00","2023-04-19 18:00","2023-03-30 08:00","2023-04-19 18:00","연속"]
[439,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L 케이블타워 이설공사","ㅇ 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 ㅇ 전선교체 : ACSR 410㎟ X 2B(2회선), 0.360km - 임시선로 구성 : 임시철탑 1기, ACSR 410㎟ X 2B(2회선) 0.547km","2023-03-06 09:00","2023-03-28 18:00","취소","취소","연속"]
[440,"광주전남","광주","신광주계림#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","PT보통점검, LA보통점검 (비상시 즉시가압 불가)","2023-03-30 09:00","2023-03-30 18:00","취소","취소","연속"]
[441,"광주전남","광주","신광주계림#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","170kV GIS 보통점검, PT보통점검, LA보통점검 (비상시 즉시가압 불가)","2023-03-29 09:00","2023-03-29 18:00","취소","취소","연속"]
[442,"광주전남","광주","일곡비아#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","일곡S/S 일곡-비아#2T/L GIS 보통점검","2023-03-28 09:00","2023-03-28 18:00","취소","취소","연속"]
[443,"광주전남","광주","담양일곡#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","일곡S/S 담양-일곡#2T/L GIS 보통점검","2023-03-27 09:00","2023-03-27 18:00","2023-03-27 09:00","2023-03-27 18:00","연속"]
[444,"광주전남","광주","신광주일곡#2 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-일곡T/L 철탑추락방지장치(수평) 설치 공사구간 : No.16~21호(6기)","2023-03-24 07:00","2023-03-24 18:00","취소","취소","연속"]
[445,"광주전남","광주","신광주일곡#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","일곡S/S 신광주-일곡#2T/L GIS 보통점검","2023-03-21 09:00","2023-03-21 18:00","취소","취소","연속"]
[446,"광주전남","광주","신광주일곡#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","일곡S/S 신광주-일곡#1T/L GIS 보통점검","2023-03-20 09:00","2023-03-20 18:00","취소","취소","연속"]
[447,"광주전남","광주","신광주일곡#1 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-일곡T/L 철탑추락방지장치(수평) 설치 공사구간 : No.16~21호(6기)","2023-03-17 07:00","2023-03-17 18:00","취소","취소","연속"]
[448,"광주전남","광주","신광주일곡#2 T/L","154kV 일곡-비아T/L 가공송전선로 철거공사","154kV 일곡-비아T/L 4회선(No.2,3)구간 상단 철거관련 하단(신광주-일곡T/L)작업자 안전확보 차 휴전","2023-03-15 07:00","2023-03-20 18:00","취소","취소","매일"]
[449,"광주전남","광주","신광주일곡#1 T/L","154kV 일곡-비아T/L 가공송전선로 철거공사","154kV 일곡-비아T/L 4회선(No.2,3)구간 상단 철거관련 하단(신광주-일곡T/L)작업자 안전확보 차 휴전","2023-03-11 07:00","2023-03-13 18:00","취소","취소","매일"]
[450,"광주전남","광주","신광주장성#2 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-장성T/L 철탑추락방지장치(수평) 설치 공사구간 : No.7~72호(65기)","2023-03-20 07:00","2023-03-24 18:00","2023-03-20 07:00","2023-03-24 18:00","매일"]
[451,"광주전남","광주","장성영광#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (하남-장성 1~36호, 장성-영광T/L 병가)","2023-03-17 09:00","2023-03-21 18:00","취소","취소","매일"]
[452,"광주전남","광주","하남장성#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 하남-장성#2T/L GIS 보통점검","2023-03-14 09:00","2023-03-14 18:00","2023-03-14 09:00","2023-03-14 18:00","연속"]
[453,"광주전남","광주","하남장성#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 하남-장성#1T/L GIS 보통점검","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[454,"광주전남","광주","신광주장성#1 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-장성T/L 철탑추락방지장치(수평) 설치 공사구간 : No.7~72호(65기)","2023-03-13 07:00","2023-03-17 18:00","2023-03-13 07:00","2023-03-17 18:00","매일"]
[455,"광주전남","광주","신광주장성#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 신광주-장성#1T/L GIS 보통점검","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[456,"광주전남","광주","장성영광#1 T/L","154kV 장성-영광T/L 선종교체공사(No.1~126)","○ 공사구간 : 154kV 장성-영광 #1T/L No.1 ~ 126(약 35.9㎞) ○ 공사내용 - 전력선 교체(ACSR 330㎟ → ASCC/TW 430㎟) - 애자 부족분 증결, 불량애자 교체 및 금구류 교체 ○ 시공사 : 청보전설(주)","2023-03-03 09:00","2023-04-17 18:00","취소","취소","연속"]
[457,"광주전남","광주","장성영광#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 장성-영광#1T/L GIS 보통점검","2023-03-03 09:00","2023-03-03 18:00","2023-03-03 09:00","2023-03-03 18:00","연속"]
[458,"광주전남","광주","하남장성#2 T/L","154kV 장성-영광T/L 선종교체공사(No.1~126)","※공사구간 병가선로로서, 작업자 안전을 위한 선로 휴전 시행 ○ 공사구간 : 154kV 장성-영광 #1T/L No.1 ~ 126(약 35.9㎞) ○ 공사내용 - 전력선 교체(ACSR 330㎟ → ASCC/TW 430㎟) - 애자 부족분 증결, 불량애자 교체 및 금구류 교체 ○ 시공사 : 청보전설(주)","2023-03-03 09:00","2023-03-18 18:00","취소","취소","매일"]
[459,"광주전남","광주","장성영광#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (하남-장성 1~36호, 장성-영광T/L 병가)","2023-03-02 09:00","2023-03-06 18:00","취소","취소","매일"]
[460,"광주전남","광주","계림충장#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#1T/L GIS 보통점검","2023-03-09 09:00","2023-03-09 18:00","취소","취소","연속"]
[461,"광주전남","광주","계림충장#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#2T/L GIS 보통점검","2023-03-10 09:00","2023-03-10 18:00","취소","취소","연속"]
[462,"광주전남","광주","충장농성#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 충장-농성#1T/L GIS 보통점검","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[463,"광주전남","광주","충장농성#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 충장-농성#2T/L GIS 보통점검","2023-03-17 09:00","2023-03-17 18:00","2023-03-17 09:00","2023-03-17 18:00","연속"]
[464,"광주전남","광주","계림충장#3 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#3T/L GIS 보통점검","2023-03-24 09:00","2023-03-24 18:00","취소","취소","연속"]
[465,"광주전남","목포","나주엄다#2 T/L","154kV 나주-엄다 등 2개T/L 추락방지장치 설치공사","154kV 나주-엄다T/L No.8~118호","2023-03-02 09:00","2023-03-15 18:00","2023-03-01 07:00","2023-03-10 18:00","매일"]
[466,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","○ 공사구간 : 154kV 영광-홍농 T/L No. 1 ~ 41(약 12..232㎞) ○ 공사내용 - 추락방지장치 설치 (목포) - 장성-영광#1(4회선구간) 선종교체공사 안전휴전 (직할) ○ 시공사 : 목포전력지사 협력업체 (시공사 : (주)대호전기 / 감리 (주)중앙씨아씨)","2023-03-19 08:00","2023-04-17 18:00","취소","취소","매일"]
[467,"광주전남","순천","광양순천#1 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비] 광양S/S 광양-순천#1T/L GIS 보통점검 및 상시여자 보조계전기 교체","2023-03-06 09:00","2023-03-06 18:00","2023-03-06 09:00","2023-03-06 18:00","연속"]
[468,"광주전남","순천","광양순천#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비] 광양S/S 광양-순천#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[469,"광주전남","순천","보성벌교 T/L","154kV 벌교-고흥T/L 선종교체공사(1공구)","휴전목적 : 154kV 벌교-고흥T/L 4회선구간 선종교체작업 안전거리 확보 대상공사 - 구 간 : 154kV 벌교-고흥T/L 16.89km(벌교변전소 ∼ No.49) - 내 용 : 전력선 교체 ACSR/AW 410㎟ × S → ASCC/TW 520㎟ × S","2023-03-01 07:00","2023-03-06 18:00","2023-03-01 07:00","2023-03-06 18:00","연속"]
[470,"광주전남","순천","승주서순천 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","승주S/S 승주-서순천T/L GIS 보통점검 및 상시여자 보조계전기 교체 서순천S/S 승주-서순천T/L GIS CB 타임측정","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","연속"]
[471,"광주전남","순천","순천승주#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비]승주S/S 순천-승주#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2023-03-13 09:00","2023-03-13 18:00","2023-03-13 09:00","2023-03-13 18:00","연속"]
[472,"광주전남","순천","순천승주#1 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비]승주S/S 순천-승주#1T/L GIS 보통점검 및 상시여자 보조계전기 교체","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[473,"광주전남","순천","여수소라#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-14 09:00","2023-03-15 18:00","2023-03-14 09:00","2023-03-15 18:00","연속"]
[474,"광주전남","순천","여수소라#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-16 09:00","2023-03-17 18:00","2023-03-16 09:00","2023-03-17 18:00","연속"]
[475,"광주전남","순천","여천여수#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","여수S/S 여천-여수#1,2T/L GIS CB 타임측정 및 #1,2T/L LA(보통점검) 여천S/S 여천-여수#1,2T/L GIS CB 타임측정","2023-03-15 14:00","2023-03-15 18:00","2023-03-15 14:00","2023-03-15 18:00","연속"]
[476,"광주전남","순천","여천여수산단#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비]여수산단개폐소 여천-여수산단 #2T/L GIS 보통점검","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[477,"광주전남","순천","율촌여수산단#2 T/L","'22년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2023-03-20 09:00","2023-03-21 18:00","취소","취소","연속"]
[478,"광주전남","순천","여수TP용성#1 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력 여수TP-용성#1T/L GIS 보통점검 및 상시여자 보조계전기 교체 용성S/S 여수TP-용성#1T/L GIS 보통점검, LA(A, B, C) 보통점검 및 상시여자 보조계전기 교체","2023-03-03 09:00","2023-03-03 18:00","취소","취소","연속"]
[479,"광주전남","순천","호남TP여수TP#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-09 09:00","2023-03-10 18:00","취소","취소","연속"]
[480,"광주전남","순천","여수TP용성#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수TP-용성#2T/L GIS 보통점검 및 상시여자 보조계전기 교체 용성S/S 여수TP-용성#2T/L GIS 보통점검, LA(A, B, C) 보통점검 및 상시여자 보조계전기 교체","2023-03-02 09:00","2023-03-02 18:00","취소","취소","연속"]
[481,"광주전남","순천","호남TP여수TP#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-07 09:00","2023-03-08 18:00","취소","취소","연속"]
[482,"광주전남","순천","여천호남TP#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비]여천S/S 여천-호남TP #1T/L GIS CB 타임측정 [정비]여천S/S 여천-호남TP #2T/L GIS CB 타임측정 및 LA (A,B,C)보통점검","2023-03-14 09:00","2023-03-14 14:00","취소","취소","연속"]
[483,"광주전남","순천","여천호남TP#1 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","[정비]여천S/S 여천-호남TP #1T/L GIS CB 타임측정 [정비]여천S/S 여천-호남TP #2T/L GIS CB 타임측정 및 LA (A,B,C)보통점검","2023-03-14 14:00","2023-03-14 18:00","취소","취소","연속"]
[484,"광주전남","순천","용성여수산단#1 T/L","345kV 신강진-광양 등 29개 T/L 추락방지시설 설치공사","154kV 용성-여수산단#1T/L 수평 추락방지시설 설치 구간 : 1~15호, 16기","2023-03-02 07:00","2023-03-02 18:00","2023-03-02 07:00","2023-03-02 18:00","연속"]
[485,"광주전남","순천","용성여수산단#2 T/L","345kV 신강진-광양 등 29개 T/L 추락방지시설 설치공사","154kV 용성-여수산단#2T/L 수평 추락방지시설 설치 구간 : 1~15호, 16기","2023-03-03 07:00","2023-03-03 18:00","2023-03-03 07:00","2023-03-03 18:00","연속"]
[486,"광주전남","순천","순천율촌#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-23 09:00","2023-03-24 18:00","2023-03-23 09:00","2023-03-24 18:00","연속"]
[487,"광주전남","순천","순천율촌#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-21 09:00","2023-03-22 18:00","2023-03-21 09:00","2023-03-22 18:00","연속"]
[488,"광주전남","순천","율촌화치#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-03-27 09:00","2023-03-30 18:00","2023-03-27 09:00","2023-03-30 18:00","연속"]
[489,"광주전남","직할","나주금천#1 T/L","22~23년 철탑 추락방지장치 설치공사","작업명 : 22~23년 철탑 추락방지장치 설치공사 공사구간 : 나주금천#1 T/L No.2,3,9,10","2023-03-09 07:00","2023-03-10 18:00","2023-03-09 07:00","2023-03-10 18:00","연속"]
[490,"광주전남","직할","왕곡나주#2 T/L","154kV 나주-엄다 등 2개T/L 추락방지장치 설치공사","154kV 나주-엄다T/L No.8~19호","2023-03-07 09:00","2023-03-07 18:00","2023-03-07 09:00","2023-03-07 18:00","매일"]
[491,"광주전남","직할","하남장성#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (하남-장성 1~36호, 장성-영광T/L 병가)","2023-03-02 09:00","2023-03-06 18:00","취소","취소","매일"]
[492,"광주전남","직할","하남장성#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 병가)","2023-03-07 09:00","2023-03-16 18:00","2023-03-07 09:00","2023-03-16 18:00","매일"]
[493,"광주전남","직할","비아하남#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 병가)","2023-03-07 09:00","2023-03-17 18:00","2023-03-08 08:00","2023-03-17 18:00","매일"]
[494,"광주전남","직할","하남장성#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (하남-장성 1~36호, 장성-영광T/L 병가)","2023-03-03 09:00","2023-03-07 18:00","취소","취소","매일"]
[495,"광주전남","직할","비아하남#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 병가)","2023-03-22 09:00","2023-04-03 18:00","2023-03-20 08:00","2023-03-30 18:00","매일"]
[496,"광주전남","직할","하남장성#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 병가)","2023-03-22 09:00","2023-04-03 18:00","취소","취소","매일"]
[497,"광주전남","직할","매월화정#1 T/L","2022~23년 직할 변전협력회사 총액공사","170kV GIS 보통점검","2023-03-13 14:00","2023-03-13 18:00","2023-03-13 14:00","2023-03-13 18:00","연속"]
[498,"광주전남","직할","농성화정#1 T/L","2022~23년 직할 변전협력회사 총액공사","170kV GIS 보통점검","2023-03-13 09:00","2023-03-13 14:00","2023-03-13 09:00","2023-03-13 14:00","연속"]
[499,"대구","경산","진량노변 T/L","22-23년 경산P/O 변전협력회사 총액공사","- 무부하가압용(주작업: 진량S/S #1Sh.C GIS(6179) 주접점 교체)","2023-03-09 16:00","2023-03-09 18:00","2023-03-09 16:00","2023-03-09 18:00","연속"]
[500,"대구","달성","논공달성#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사","2023-03-08 07:00","2023-03-10 18:00","2023-03-08 07:00","2023-03-10 18:00","연속"]
[501,"대구","달성","논공달성#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사","2023-03-02 07:00","2023-03-07 18:00","2023-03-02 07:00","2023-03-07 18:00","연속"]
[502,"대구","달성","다사달서 T/L","2023~2024년 달성전력지사 지중송전설비 위탁정비공사","154kV 다사-달서T/L 기중종단접속함 절연유 추적조사(4차)","2023-03-28 08:00","2023-03-28 18:00","2023-03-28 08:00","2023-03-28 18:00","연속"]
[503,"대구","달성","성서달성#1 T/L","154kV 모선보호반 대체","154kV 모선보호반 대체","2023-03-22 10:00","2023-03-22 10:30","2023-03-22 10:00","2023-03-22 10:30","연속"]
[504,"대구","달성","성서달성#2 T/L","154kV 모선보호반 대체","154kV 모선보호반 대체","2023-03-22 10:30","2023-03-22 11:00","2023-03-22 10:30","2023-03-22 11:00","연속"]
[505,"대구","달성","강창성서#1 T/L","154kV 모선보호반 대체","154kV 모선보호반 대체","2023-03-22 11:00","2023-03-22 11:30","2023-03-22 11:00","2023-03-22 11:30","연속"]
[506,"대구","달성","강창성서#2 T/L","154kV 모선보호반 대체","154kV 모선보호반 대체","2023-03-22 11:30","2023-03-22 12:30","2023-03-22 11:30","2023-03-22 12:30","연속"]
[507,"대구","직할","남대구동인#1 T/L","23-24년 대구본부 직할 지중송전 위탁정비공사","OF케이블 절연유채유","2023-03-08 09:00","2023-03-08 18:00","2023-03-08 09:00","2023-03-08 18:00","연속"]
[508,"대구","직할","범물남대구#1 T/L","23-24년 대구본부 직할 지중송전 위탁정비공사","EBA절연유 채유","2023-03-04 09:00","2023-03-04 18:00","2023-03-04 09:00","2023-03-04 18:00","연속"]
[509,"대구","직할","시지효목#1 T/L","효목S/S 시지-효목#1,2,T/L 차단기동작시간 측정","효목S/S 시지-효목#1,2,T/L 차단기동작시간 측정","2023-03-16 09:30","2023-03-16 14:00","2023-03-16 09:30","2023-03-16 14:00","연속"]
[510,"대구","직할","시지효목#2 T/L","효목S/S 시지-효목#1,2,T/L 차단기동작시간 측정","효목S/S 시지-효목#1,2,T/L 차단기동작시간 측정","2023-03-16 14:00","2023-03-16 18:00","2023-03-16 14:00","2023-03-16 18:00","연속"]
[511,"대구","칠곡","광평S/S CB 6100","광평S/S 154kV 6100 GIS 유압 누유 보수","광평S/S 154kV 6100 GIS 유압 누유 보수","2023-03-07 09:30","2023-03-07 14:00","2023-03-07 09:30","2023-03-07 14:00","연속"]
[512,"대구","포항","건천천북#1 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-03-17 08:00","2023-03-21 18:00","2023-03-17 08:00","2023-03-21 18:00","연속"]
[513,"대구","포항","건천천북#2 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-03-22 08:00","2023-03-26 18:00","2023-03-22 08:00","2023-03-26 18:00","연속"]
[514,"대구","포항","천북경주 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","154kV 건천-천북T/L 병가 구간 안전확보","2023-03-19 15:00","2023-03-19 18:00","취소","취소","연속"]
[515,"대구","포항","포항경주 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","154kV 건천-천북T/L 병가 구간 안전확보","2023-03-19 08:00","2023-03-19 15:00","취소","취소","연속"]
[516,"대구","포항","포항천북 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","154kV 건천-천북T/L 병가 구간 안전확보","2023-03-26 08:00","2023-03-26 18:00","취소","취소","연속"]
[517,"대구","포항","포항경주 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","154kV 건천-천북T/L 병가 구간 안전확보","2023-03-26 08:00","2023-03-26 12:00","취소","취소","연속"]
[518,"대구","포항","포항천북 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","154kV 건천-천북T/L 병가 구간 안전확보","2023-03-19 09:00","2023-03-19 12:00","취소","취소","연속"]
[519,"대구","달성","논공S/S #1 EM.Tr CB","#2M.Tr 대체관련 부하공급","#2M.Tr 대체관련 부하공급","2023-03-20 09:00","2023-04-03 18:00","2023-03-20 09:00","2023-04-03 18:00","연속"]
[520,"경북","구미","선산청리#1 T/L","154kV 청리S/S #4M.Tr 증설공사","- #4M.Tr 설치 관련 무부하가압","2023-03-06 09:00","2023-03-07 18:00","2023-03-06 09:00","2023-03-07 18:00","연속"]
[521,"경북","구미","청리상주#1 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 청리-상주T/L 추락방지시설 설치(No.1, 41~57, 59)","2023-03-29 08:00","2023-03-31 17:00","취소","취소","매일"]
[522,"경북","구미","청리상주#2 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 청리-상주T/L 추락방지시설 설치(No.1, 41~57, 59)","2023-03-31 08:00","2023-04-04 17:00","취소","취소","매일"]
[523,"경북","영주","신영주영주#2 T/L","154kV신영주-영주T/L 추락방지시설 설치공사","154kV신영주-영주T/L 추락방지시설 설치공사","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[524,"경북","영주","신영주영주#1 T/L","154kV신영주-영주T/L 추락방지시설 설치공사","154kV신영주-영주T/L 추락방지시설 설치공사","2023-03-14 09:00","2023-03-20 18:00","2023-03-14 09:00","2023-03-20 18:00","연속"]
[525,"경북","영주","신영주영주#2 T/L","신영주-영주#2T/L IED 보드 교체","인출DS 조작 불량 관련 IED 보드 교체","2023-03-06 10:00","2023-03-06 18:00","2023-03-06 10:00","2023-03-06 18:00","연속"]
[526,"경북","영주","동상주점촌#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT 대체","2023-03-10 10:00","2023-03-10 18:00","2023-03-10 10:00","2023-03-10 18:00","연속"]
[527,"경북","영주","예천점촌#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT,LA 대체 CB 조작시험, 공기조작부 점검","2023-03-16 10:00","2023-03-17 18:00","2023-03-16 10:00","2023-03-17 18:00","연속"]
[528,"경북","영주","점촌단양 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT 대체 CB 조작시험","2023-03-20 10:00","2023-03-20 18:00","2023-03-20 10:00","2023-03-20 18:00","연속"]
[529,"경북","영주","점촌문경 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","LA 초기점검 CB 조작시험","2023-03-21 10:00","2023-03-21 18:00","2023-03-21 10:00","2023-03-21 18:00","연속"]
[530,"경북","영주","예천점촌#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT,LA 대체 CB 조작시험, 공기조작부 점검","2023-03-27 10:00","2023-03-28 18:00","2023-03-27 10:00","2023-03-28 18:00","연속"]
[531,"경북","영주","동상주점촌#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT 대체","2023-03-13 10:00","2023-03-13 18:00","2023-03-13 10:00","2023-03-13 18:00","연속"]
[532,"경북","직할","울진삼척GP#1 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사 GIS 교체 1,2 차분)","2023-03-20 09:00","2023-04-06 18:00","취소","취소","연속"]
[533,"경북","직할","울진삼척GP#2 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사 GIS 교체 1,2 차분)","2023-03-20 09:00","2023-04-06 18:00","취소","취소","연속"]
[534,"부산울산","동부산","구서노포#2 T/L","154kV 언양-산막 등 2개T/L 자기애관 교체공사(비표준)","154kV 구서-노포T/L 비표준 자기애관 교체공사 자기애관1,200㎟을 폴리머애관 1,200㎟으로 변경","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[535,"부산울산","동부산","구서노포#1 T/L","154kV 언양-산막 등 2개T/L 자기애관 교체공사(비표준)","154kV 구서-노포T/L 비표준 자기애관 교체공사 자기애관1,200㎟을 폴리머애관 1,200㎟으로 변경","2023-03-20 09:00","2023-03-24 18:00","2023-03-20 09:00","2023-03-24 18:00","연속"]
[536,"부산울산","동부산","노포정관#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-03-21 07:00","2023-03-24 18:00","2023-03-21 07:00","2023-03-24 18:00","연속"]
[537,"부산울산","동부산","노포정관#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치, 피뢰기 설치","2023-03-28 07:00","2023-03-31 18:00","2023-03-28 07:00","2023-03-31 18:00","연속"]
[538,"부산울산","동부산","명례고리NP T/L","명례S/S 637GIS 보통점검","명례S/S 637GIS 보통점검 병행)명례-고리T/L 파일럿밸브 교체 및 오일 보충","2023-03-09 09:30","2023-03-09 17:00","2023-03-09 09:30","2023-03-09 17:00","연속"]
[539,"부산울산","동부산","명례장안 T/L","154kV 명례-장안T/L OPGW 증설공사","OPGW 교체 : 4km","2023-03-06 00:08","2023-03-09 18:00","2023-03-06 00:08","2023-03-09 18:00","연속"]
[540,"부산울산","동부산","신양산구서#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치, 피뢰기 설치","2023-03-10 07:00","2023-03-10 18:00","2023-03-10 07:00","2023-03-10 18:00","연속"]
[541,"부산울산","동부산","신양산구서#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-03-09 07:00","2023-03-09 18:00","2023-03-09 07:00","2023-03-09 18:00","연속"]
[542,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-23 18:00","2023-03-23 20:00","취소","취소","연속"]
[543,"부산울산","북부산","북부산구포#3 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-13 16:00","2023-03-14 16:00","2023-03-28 16:00","2023-03-29 16:00","연속"]
[544,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-10 09:00","2023-03-14 18:00","2023-03-24 09:00","2023-03-29 18:00","연속"]
[545,"부산울산","북부산","북부산구포#3 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-09 10:00","2023-03-09 14:00","2023-03-23 10:00","2023-03-23 14:00","연속"]
[546,"부산울산","북부산","구포대저#1 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-06 09:00","2023-03-23 20:00","2023-03-20 09:00","2023-04-06 20:00","연속"]
[547,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-06 09:00","2023-03-09 18:00","2023-03-20 09:00","2023-03-23 18:00","연속"]
[548,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-15 09:00","2023-03-23 18:00","2023-03-29 09:00","2023-04-06 20:00","연속"]
[549,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-31 09:00","2023-04-05 18:00","취소","취소","연속"]
[550,"부산울산","북부산","구포대저#2 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-30 18:00","2023-03-30 20:00","취소","취소","연속"]
[551,"부산울산","북부산","북부산구포#2 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-27 09:00","2023-04-15 20:00","취소","취소","연속"]
[552,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-03-27 09:00","2023-03-30 20:00","취소","취소","연속"]
[553,"부산울산","북부산","모라S/S CB 6100","22-23년 북부산전력지사 변전총액공사","모라S/S 154kV 6100 BUS TIE GIS 보통점검","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[554,"부산울산","북부산","미남S/S #60 BUS","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2023-03-27 13:00","2023-03-27 18:00","2023-03-27 13:00","2023-03-27 18:00","연속"]
[555,"부산울산","북부산","미남S/S CB 6100","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2023-03-27 13:00","2023-03-27 18:00","2023-03-27 13:00","2023-03-27 18:00","연속"]
[556,"부산울산","북부산","미남S/S SEC CB 65660","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2023-03-27 13:00","2023-03-27 18:00","2023-03-27 13:00","2023-03-27 18:00","연속"]
[557,"부산울산","북부산","미남S/S SEC CB 60610","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2023-03-27 13:00","2023-03-27 18:00","2023-03-27 13:00","2023-03-27 18:00","연속"]
[558,"부산울산","북부산","북부산호포 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#2T/L No.132호 수평추락방지장치 설치관련 안전확보","2023-03-05 08:00","2023-03-05 18:00","2023-03-05 08:00","2023-03-05 18:00","연속"]
[559,"부산울산","북부산","서창산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 서창-산막T/L 수평 추락방지장치 설치공사 병가구간 안전확보(25호 등 32기)","2023-03-11 09:00","2023-03-12 18:00","2023-03-11 09:00","2023-03-12 18:00","매일"]
[560,"부산울산","북부산","서창산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 서창-산막T/L 수평 추락방지장치 설치공사(25호 등 32기)","2023-03-11 09:00","2023-03-12 18:00","2023-03-11 09:00","2023-03-12 18:00","매일"]
[561,"부산울산","북부산","양산산막#1 T/L","도시철도 양산선(노포~북정) 4공구 건설공사","도시철도 양산선(노포~북정) 4공구 건설공사 ○ 발주처 및 휴전요청자 : 부산교통공사 ○ 공사구간 : 154kV 양산-산막T/L 2호 인근 4공구 건설공사 교각(P429) ○ 휴전목적 : 안전이격 거리 확보 휴전 ○ 기타사항 : 1월 휴전및 작업시행 예정이였으나, 지장선로이설 감리발주 관련 사항으로 휴전일정 변경","2023-03-29 07:00","2023-04-14 18:00","2023-03-29 07:00","2023-04-14 18:00","연속"]
[562,"부산울산","북부산","양산삼랑진PP T/L","154kV 양산-삼랑진T/L 송전선로 정밀점검","송전선로 정밀점검(양산분기T/L 1~18호)","2023-03-21 09:00","2023-03-22 18:00","2023-03-21 09:00","2023-03-22 18:00","연속"]
[563,"부산울산","북부산","북부산양산 T/L","154kV 북부산-양산T/L 송전선로 정밀점검","송전선로 정밀점검(양산분기T/L 1~18호)","2023-03-23 09:00","2023-03-24 18:00","2023-03-23 09:00","2023-03-24 18:00","연속"]
[564,"부산울산","북부산","양산산막#2 T/L","154kV 양산-산막T/L 2호 지장철탑 이설공사","154kV 양산-산막T/L 지장철탑 이설공사 임시선로 구성 ○ 공사구간 : 154kV 양산-산막T/L 1호~3호 ○ 작업내용 : #2T/L 전력선 공중이동 및 긴선, OPGW 이설","2023-03-27 07:00","2023-03-28 18:00","2023-03-27 07:00","2023-03-28 18:00","연속"]
[565,"부산울산","북부산","엄궁학장#2 T/L","22-23년 북부산전력지사 변전총액공사","엄궁S/S 154kV 엄궁-학장#2T/L GIS 보통점검","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[566,"부산울산","북부산","엄궁학장#1 T/L","22-23년 북부산전력지사 변전총액공사","엄궁S/S 154kV 엄궁-학장#1T/L GIS 보통점검","2023-03-09 09:00","2023-03-09 18:00","2023-03-09 09:00","2023-03-09 18:00","연속"]
[567,"부산울산","울산","남울산신온산#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-10 07:00","2023-03-16 18:00","취소","취소","연속"]
[568,"부산울산","울산","남울산처용#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-08 07:00","2023-03-09 18:00","취소","취소","연속"]
[569,"부산울산","울산","남울산신온산#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-27 07:00","2023-03-30 18:00","2023-03-27 07:00","2023-03-30 18:00","연속"]
[570,"부산울산","울산","남울산처용#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-23 07:00","2023-03-24 18:00","2023-03-23 07:00","2023-03-24 18:00","연속"]
[571,"부산울산","울산","두왕울산#2 T/L","154kV 추락방지장치 설치공사","ㅇ두왕-울산#2 추락방지 설치 - 수직수평 11기(신울산-두왕#1 7호 병가포함)","2023-03-15 07:30","2023-03-17 18:00","2023-03-15 07:30","2023-03-17 18:00","연속"]
[572,"부산울산","울산","반천언양#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치, 피뢰기 설치","2023-03-03 07:00","2023-03-03 18:00","2023-03-03 07:00","2023-03-03 18:00","연속"]
[573,"부산울산","울산","반천언양#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치, 피뢰기 설치","2023-03-02 07:00","2023-03-02 18:00","2023-03-02 07:00","2023-03-02 18:00","연속"]
[574,"부산울산","울산","성암울산TP#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-21 07:00","2023-03-22 18:00","2023-03-21 07:00","2023-03-22 18:00","연속"]
[575,"부산울산","울산","성암울산TP#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-07 07:00","2023-03-08 18:00","취소","취소","연속"]
[576,"부산울산","울산","신온산온산#3 T/L","22~23년 변전협력회사 총액공사","- 신온산S/S측 GIS(697) 차단기 동작시험 - 온산S/S측 GIS(637) 에어링밸브 교체","2023-03-10 09:00","2023-03-10 18:00","2023-03-10 09:00","2023-03-10 18:00","연속"]
[577,"부산울산","울산","신울산울산#1 T/L","154kV 추락방지장치 설치공사","ㅇ 신울산-울산#1 수직 수평 추락방지 설치 - 17기(관형2, 4회선5기포함)","2023-03-07 07:30","2023-03-14 18:00","2023-03-07 07:30","2023-03-14 18:00","연속"]
[578,"부산울산","울산","신울산언양#1 T/L","2023년 가공송전 순시점검 위탁공사","-공사내용: 154kV 신울산-언양#1T/L 정밀점검 -작업구간: S/T~S/T(총 69기)","2023-03-27 09:00","2023-03-31 18:00","2023-03-27 09:00","2023-03-31 18:00","연속"]
[579,"부산울산","울산","신울산두왕#1 T/L","154kV 추락방지장치 설치공사","ㅇ 신울산-두왕#1 추락방지 설치 - 수직수평 7기(신울산-울산2~5호, 두왕-울산1호 병가포함)","2023-03-13 07:30","2023-03-15 18:00","2023-03-13 07:30","2023-03-15 18:00","연속"]
[580,"부산울산","울산","옥동외동#1 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","ㅁ 성능저하 국산애자 교체 - 대상철탑 : No.1,7 ㅁ 휴전작업 : 3/6 14:00 ~3/7 18:00","2023-03-06 14:00","2023-03-07 18:00","2023-03-04 14:00","2023-03-05 18:00","연속"]
[581,"부산울산","울산","옥동외동#2 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","ㅁ 성능저하 국산애자 교체 - 대상철탑 : No.6,7 ㅁ 휴전작업 : 3/8 07:00 ~ 14:00","2023-03-08 07:00","2023-03-08 14:00","2023-03-06 07:00","2023-03-06 14:00","연속"]
[582,"부산울산","울산","온산처용#2 T/L","154kV 추락방지장치 설치공사","ㅇ 온산-처용#2 수평 추락방지장치 설치 - 10기(11~20호)","2023-03-30 08:00","2023-03-31 18:00","2023-03-30 08:00","2023-03-31 18:00","연속"]
[583,"부산울산","울산","남울산용연#2 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검 - 피뢰기 보통점검","2023-03-30 09:00","2023-03-30 18:00","2023-03-30 09:00","2023-03-30 18:00","연속"]
[584,"부산울산","울산","용연울산TP#3 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-03-02 07:00","2023-03-06 18:00","취소","취소","연속"]
[585,"부산울산","울산","용연울산TP#1 T/L","154kV 추락방지장치 설치공사","ㅇ 용연-울산#1 추락방지 설치 - 수직수평 11기(4회선 2기 포함)","2023-03-27 07:30","2023-03-29 18:00","2023-03-27 07:30","2023-03-29 18:00","연속"]
[586,"부산울산","울산","남울산용연#1 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검 - 피뢰기 보통점검","2023-03-29 09:00","2023-03-29 18:00","2023-03-29 09:00","2023-03-29 18:00","연속"]
[587,"부산울산","울산","용연울산TP#2 T/L","154kV 추락방지장치 설치공사","ㅇ 용연-울산#2 추락방지 설치 - 용연-울산#1 9 9.1 병가구간 공사","2023-03-27 07:30","2023-03-27 18:00","2023-03-27 07:30","2023-03-27 18:00","연속"]
[588,"부산울산","울산","울산영남TP#2 T/L","22~23년 변전협력회사 총액공사","- GIS보통점검","2023-03-28 09:00","2023-03-28 18:00","2023-03-28 09:00","2023-03-28 18:00","연속"]
[589,"부산울산","울산","두왕울산#1 T/L","22~23년 변전협력회사 총액공사","- GIS보통점검","2023-03-23 09:00","2023-03-23 18:00","2023-03-23 09:00","2023-03-23 18:00","연속"]
[590,"부산울산","울산","울주직동#1 T/L","22~23년 변전협력회사 총액공사","- 울주S/S측 GIS(687) 보통점검 - 울주S/S측 CVT 보통점검 - 직동S/S측 GIS(617) 차단기 동작시험","2023-03-16 09:00","2023-03-16 18:00","2023-03-16 09:00","2023-03-16 18:00","연속"]
[591,"부산울산","울산","울주직동#2 T/L","22~23년 변전협력회사 총액공사","- 울주S/S측 GIS(677) 보통점검 - 울주S/S측 CVT 보통점검 - 직동S/S측 GIS(627) 차단기 동작시험","2023-03-15 09:00","2023-03-15 18:00","2023-03-15 09:00","2023-03-15 18:00","연속"]
[592,"부산울산","울산","울주외동#2 T/L","22~23년 변전협력회사 총액공사","GIS 보통점검","2023-03-21 09:00","2023-03-21 18:00","2023-03-21 09:00","2023-03-21 18:00","연속"]
[593,"부산울산","울산","울주외동#1 T/L","22~23년 변전협력회사 총액공사","GIS 보통점검","2023-03-22 09:00","2023-03-22 18:00","2023-03-22 09:00","2023-03-22 18:00","연속"]
[594,"부산울산","울산","웅촌서창#2 T/L","웅촌곡천지구 154kV 웅촌-서창 등 2개T/L 지중화공사","154kV 웅촌-서창T/L(신울산-웅촌 병가) 지중화공사 관련 가선로 구성","2023-03-13 07:00","2023-03-17 18:00","2023-03-13 07:00","2023-03-17 18:00","연속"]
[595,"부산울산","울산","신울산웅촌#1 T/L","웅촌곡천지구 154kV 웅촌-서창 등 2개T/L 지중화공사","154kV 웅촌-서창T/L(신울산-웅촌 병가) 지중화공사 관련 가선로 구성","2023-03-13 07:00","2023-03-17 18:00","2023-03-13 07:00","2023-03-17 18:00","연속"]
[596,"부산울산","울산","신울산웅촌#2 T/L","웅촌곡천지구 154kV 웅촌-서창 등 2개T/L 지중화공사","154kV 웅촌-서창T/L(신울산-웅촌 병가) 지중화공사 관련 가선로 구성","2023-03-20 07:00","2023-03-24 18:00","2023-03-20 07:00","2023-03-24 18:00","연속"]
[597,"부산울산","울산","웅촌서창#1 T/L","웅촌곡천지구 154kV 웅촌-서창 등 2개T/L 지중화공사","154kV 웅촌-서창T/L(신울산-웅촌 병가) 지중화공사 관련 가선로 구성","2023-03-20 07:00","2023-03-24 18:00","2023-03-20 07:00","2023-03-24 18:00","연속"]
[598,"부산울산","울산","온산처용#1 T/L","22~23년 변전협력회사 총액공사","- GIS(687) 차단기 동작시험","2023-03-27 09:00","2023-03-27 18:00","2023-03-27 09:00","2023-03-27 18:00","연속"]
[599,"부산울산","울산","신울산태화#1 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사(안전이격)","ㅁ 외동-옥동#1,2T/L 국산애자 교체 관련 안전이격 확보 휴전","2023-03-06 14:00","2023-03-08 14:00","2023-03-04 14:00","2023-03-06 14:00","매일"]
[600,"부산울산","울산","신울산태화#2 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사(안전이격)","ㅁ 외동-옥동#1,2T/L 국산애자 교체 관련 안전이격 확보 휴전","2023-03-06 14:00","2023-03-08 14:00","2023-03-04 14:00","2023-03-06 14:00","매일"]
[601,"부산울산","울산","신울산태화#2 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","ㅁ 성능저하 국산애자 교체 - 대상철탑 : No.16,17,18,19,27,28 ㅁ 휴전작업 : 3/8 14:00 ~3/17 18:00 ㅁ 안전이격 휴전 : 3/6 14:00 ~ 3/8 14:00","2023-03-08 14:00","2023-03-17 18:00","취소","취소","연속"]
[602,"부산울산","울산","신울산태화#1 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","ㅁ 성능저하 국산애자 교체 - 대상철탑 : No.10 ㅁ 휴전작업 : 3/6 07:00 ~14:00 ㅁ 안전이격 휴전 : 3/6 14:00 ~ 3/8 14:00","2023-03-06 07:00","2023-03-06 14:00","취소","취소","연속"]
[603,"부산울산","직할","범일서면#2 T/L","22~23년 직할변전협력회사 총액공사","서면S/S 범일-서면#2T/L GIS 조작시험","2023-03-04 14:00","2023-03-04 18:00","2023-03-04 14:00","2023-03-04 18:00","연속"]
[604,"부산울산","직할","범일서면#1 T/L","22~23년 직할변전협력회사 총액공사","서면S/S 범일-서면#1T/L GIS 조작시험","2023-03-04 09:00","2023-03-04 14:00","2023-03-04 09:00","2023-03-04 14:00","연속"]
[605,"부산울산","직할","부산수정#1 T/L","22~23년 직할변전협력회사 총액공사","수정S/S 부산-수정#1T/L GIS 조작시험","2023-03-11 09:30","2023-03-11 14:00","2023-03-11 09:30","2023-03-11 14:00","연속"]
[606,"부산울산","직할","부산수정#2 T/L","22~23년 직할변전협력회사 총액공사","수정S/S 부산-수정#2 T/L GIS 조작시험","2023-03-11 14:00","2023-03-11 18:00","2023-03-11 14:00","2023-03-11 18:00","연속"]
[607,"부산울산","직할","수정범일#1 T/L","22~23년 직할변전협력회사 총액공사","수정S/S 수정-범일#1 T/L GIS 조작시험","2023-03-08 09:30","2023-03-08 18:00","2023-03-08 09:30","2023-03-08 18:00","연속"]
[608,"부산울산","직할","수정범일#2 T/L","22~23년 직할변전협력회사 총액공사","수정S/S 수정-범일#2 T/L GIS 조작시험","2023-03-09 09:30","2023-03-09 18:00","2023-03-09 09:30","2023-03-09 18:00","연속"]
[609,"경남","직할","녹공마천#1 T/L","마천S/S LID 이설공사","마천S/S LID 이설공사 대상설비 : 녹공-마천#1T/L GIS","2023-03-30 09:30","2023-03-31 18:00","2023-03-30 09:30","2023-03-31 18:00","연속"]
[610,"경남","직할","신김해삼정#1 T/L","신김해S/S 베어링 발청 보수 공사","신김해S/S 베어링 발청 보수 공사 대상설비 : 154kV 신김해-삼정#1T/L (병행)삼정S/S 신김해-삼정#1T/L GIS 하자점검","2023-03-10 09:30","2023-03-10 18:00","2023-03-10 09:30","2023-03-10 18:00","연속"]
[611,"경남","직할","신김해삼정#2 T/L","신김해S/S 베어링 발청 보수 공사","신김해S/S 베어링 발청 보수 공사 대상설비 : 신김해-삼정#2T/L GIS (병행)삼정S/S 신김해-삼정#2T/L GIS 하자점검","2023-03-15 09:30","2023-03-15 18:00","2023-03-15 09:30","2023-03-15 18:00","연속"]
[612,"경남","직할","신월동읍#1 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 신월-동읍T/L 1~45호 구간 수평 추락방지장치 설치","2023-03-27 07:00","2023-04-07 18:00","2023-03-27 07:00","2023-04-07 18:00","매일"]
[613,"경남","직할","안민천선#1 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 안민-천선T/L 20호~S/T 구간 애자련 보강","2023-03-23 07:00","2023-03-23 18:00","2023-03-25 07:00","2023-03-25 18:00","연속"]
[614,"경남","직할","안민천선#2 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 안민-천선T/L 20호~S/T 구간 애자련 보강 및 2호 불량애자교체","2023-03-24 07:00","2023-03-24 18:00","2023-03-26 07:00","2023-03-26 18:00","연속"]
[615,"경남","직할","안민천선#2 T/L","천선S/S 안민-천선#2T/L GIS 보통점검","천선S/S 안민-천선#2T/L GIS 보통점검 (병행)안민S/S 안민-천선#2T/L GIS 조작시험","취소","취소","취소","취소","연속"]
[616,"경남","직할","안민천선#1 T/L","천선S/S 안민-천선#1T/L 보통점검","천선S/S 안민-천선#1T/L 보통점검 (병행)안민S/S 안민-천선#1T/L GIS 보통점검","취소","취소","취소","취소","연속"]
[617,"경남","진주","의령구룡#1 T/L","구룡S/S 154kV 장기사용 GIS 대체공사","구룡S/S 154kV 장기사용 GIS 대체공사","취소","취소","취소","취소","연속"]
[618,"경남","진주","의령구룡#2 T/L","구룡S/S 154kV 장기사용 GIS 대체공사","구룡S/S 154kV 장기사용 GIS 대체공사","취소","취소","취소","취소","연속"]
[619,"경남","진주","동진주진주#1 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사","○ 송전선로 GIS화 이설관련 사전작업","2023-03-18 08:00","2023-03-18 14:00","2023-03-18 08:00","2023-03-18 14:00","연속"]
[620,"경남","진주","진주개양#1 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사","○ 송전선로 GIS화 이설관련 사전작업","2023-03-18 14:00","2023-03-18 18:00","2023-03-18 14:00","2023-03-18 18:00","연속"]
[621,"경남","진주","동진주진주#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사","○ 송전선로 GIS화 이설관련 사전작업","2023-03-19 08:00","2023-03-19 14:00","2023-03-19 08:00","2023-03-19 14:00","연속"]
[622,"경남","진주","진주개양#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사","○ 송전선로 GIS화 이설관련 사전작업","2023-03-19 14:00","2023-03-19 18:00","2023-03-19 14:00","2023-03-19 18:00","연속"]
[623,"경남","진주","태금하동#1 T/L","'23년 가공송전 순시점검 위탁공사","154kV 태금분기T/L No.1~17 초기점검","2023-03-22 09:00","2023-03-24 18:00","2023-03-22 09:00","2023-03-24 18:00","매일"]
[624,"경남","진주","태금하동화력 T/L","'23년 가공송전 순시점검 위탁공사","154kV 태금분기T/L No1~17 초기점검","2023-03-20 09:00","2023-03-21 18:00","2023-03-20 09:00","2023-03-21 18:00","매일"]
[625,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","2023-03-04 07:00","2023-03-05 18:00","취소","취소","매일"]
[626,"경남","통영","신고성거제#2 T/L","거제S/S 신고성-거제#2T/L 조작시험 등 3건","거제S/S 신고성-거제#2T/L 조작시험 등 3건 - 거제S/S 신고성-거제#2T/L 조작시험 - 신고성, 거제S/S 세니온제 보호반 성능개선","2023-03-25 09:30","2023-03-25 18:00","2023-03-25 09:30","2023-03-25 18:00","연속"]
[627,"경남","통영","신고성거제#1 T/L","거제S/S 신고성-거제#1T/L 조작시험 등 3건","거제S/S 신고성-거제#1T/L 조작시험 등 3건 - 거제S/S 신고성-거제#1T/L 조작시험 - 신고성, 거제S/S 세니온제 보호반 성능개선","2023-03-18 09:30","2023-03-18 18:00","2023-03-18 09:30","2023-03-18 18:00","연속"]
[628,"경남","함안","마산S/S CB 6100","마산S/S 154kV #60-#65 BUS TIE GIS 보통점검","마산S/S 154kV #60-#65 BUS TIE GIS 보통점검","취소","취소","취소","취소","연속"]
[629,"경남","함안","매리김해#1 T/L","매리S/S 154kV 매리김해#1 T/L (정밀점검 시험가압)","매리S/S 154kV 매리김해#1 T/L (정밀점검 시험가압)","2023-03-30 16:00","2023-03-30 18:00","2023-03-30 16:00","2023-03-30 18:00","연속"]
[630,"경남","함안","매리S/S CB 6100","매리S/S 154kV #1-#2 BUS TIE GIS 정밀점검","매리S/S 154kV #1-#2 BUS TIE GIS 정밀점검","2023-03-28 09:00","2023-03-30 18:00","2023-03-28 09:00","2023-03-30 18:00","연속"]
[631,"경남","함안","매리김해#1 T/L","매리S/S 154kV 매리김해#1 T/L (정밀점검 시험가압)","매리S/S 154kV 매리김해#1 T/L (정밀점검 시험가압)","2023-03-29 11:00","2023-03-29 13:00","2023-03-29 11:00","2023-03-29 13:00","연속"]
[632,"경남","함안","청도밀양#1 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-03-04 07:00","2023-03-06 18:00","2023-03-04 07:00","2023-03-06 18:00","연속"]
[633,"경남","함안","청도밀양#2 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-03-04 07:00","2023-03-06 18:00","2023-03-04 07:00","2023-03-06 18:00","연속"]
[634,"경남","함안","초동밀양#2 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-03-01 07:00","2023-03-03 18:00","2023-03-01 07:00","2023-03-03 18:00","연속"]
[635,"경남","함안","초동밀양#1 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-03-01 07:00","2023-03-03 18:00","2023-03-01 07:00","2023-03-03 18:00","연속"]
[636,"경남","함안","한림정삼계#2 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9호 철탑 보강 공사","2023-03-18 07:00","2023-03-19 18:00","2023-03-18 07:00","2023-03-19 18:00","연속"]
[637,"경남","함안","삼계어방#2 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9호 철탑 보강 공사","2023-03-25 07:00","2023-03-26 18:00","2023-03-25 07:00","2023-03-26 18:00","연속"]
[638,"경남","함안","한림정삼계#1 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9호 철탑 보강 공사","2023-03-25 07:00","2023-03-26 18:00","2023-03-25 07:00","2023-03-26 18:00","연속"]
[639,"경남","함안","삼계어방#1 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9호 철탑 보강 공사","2023-03-18 07:00","2023-03-19 18:00","2023-03-18 07:00","2023-03-19 18:00","연속"]
[640,"경남","함안","신마산칠서#2 T/L","신마산S/S 신마산칠서#2 T/L GIS 조작시험","신마산S/S 신마산칠서#2 T/L GIS 조작시험","2023-03-24 09:30","2023-03-24 17:30","2023-03-24 09:30","2023-03-24 17:30","연속"]
[641,"경남","함안","신마산칠서#1 T/L","신마산S/S 신마산칠서#1 T/L GIS 조작시험","신마산S/S 신마산칠서#1 T/L GIS 조작시험","2023-03-22 09:30","2023-03-22 17:30","2023-03-22 09:30","2023-03-22 17:30","연속"]
[642,"경남","함안","어방S/S CB 6100","어방S/S 154kV #1-#2 BUS TIE GIS 보통점검","어방S/S 154kV #1-#2 BUS TIE GIS 보통점검","2023-03-14 09:30","2023-03-14 17:30","2023-03-14 09:30","2023-03-14 17:30","연속"]
[643,"경남","함안","진영수산#1 T/L","진영S/S 진영수산#1 T/L GIS 보통점검","진영S/S 진영수산#1 T/L GIS 보통점검","취소","취소","취소","취소","연속"]
[644,"경남","함안","진영수산#2 T/L","진영S/S 진영수산#2 T/L GIS 보통점검","진영S/S 진영수산#2 T/L GIS 보통점검","2023-03-15 09:30","2023-03-15 17:30","2023-03-15 09:30","2023-03-15 17:30","연속"]
[645,"경남","함안","창녕초동#1 T/L","154kV 창녕-초동#1T/L 송전선로용 피뢰기 설치공사","154kV 창녕-초동#1T/L 송전선로용 피뢰기 설치공사 - 대상 : 154kV 창녕-초동#1T/L 8~56호 * 1~7호는 창녕-구지#2T/L 휴전시 별도 시행","2023-03-27 07:00","2023-03-31 18:00","2023-03-27 07:00","2023-03-31 18:00","연속"]
[646,"경기북부","직할","양주S/S #67 BUS","양주 HVDC용 170kV GIS 설치공사","170kV GIS 2CCT","2023-03-29 14:00","2023-03-31 18:00","2023-03-29 14:00","2023-03-31 18:00","연속"]
[647,"경기북부","직할","양주S/S #62 BUS","양주 HVDC 용 170kV GIS 설치공사","170kV GIS 2CCT","2023-03-27 09:00","2023-03-29 14:00","2023-03-27 09:00","2023-03-29 14:00","연속"]
[648,"경기북부","직할","양주S/S #66 BUS","양주 HVDC용 170kV GIS 설치공사","170kv GIS 2CCT","2023-03-22 14:00","2023-03-24 18:00","2023-03-22 14:00","2023-03-24 18:00","연속"]
[649,"경기북부","직할","양주S/S #61 BUS","양주 HVDC 용 170kV GIS 설치공사","170kV GIS 2CCT 설치","2023-03-20 09:00","2023-03-22 14:00","2023-03-20 09:00","2023-03-22 14:00","연속"]