{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["양식"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"양식","index":0,"n_rows":17,"n_cols":22,"rows_kept":17,"cut":false,"hidden":false,"merged":[[2,21,4,21],[3,7,3,10],[3,3,3,6],[2,3,2,11],[3,12,4,12],[3,13,4,13],[3,15,3,20],[3,11,4,11],[5,9,17,9],[2,12,2,20],[3,14,4,14],[5,7,17,7],[5,3,17,3],[5,8,17,8],[5,11,17,11],[5,10,17,10],[5,4,17,4],[5,5,17,5],[5,6,17,6],[5,0,17,0],[5,1,17,1],[5,2,17,2],[2,0,4,0],[2,1,4,1],[2,2,4,2]],"flags":["formulas_cached_only"]}
["□ 하도급 공사 계약현황"]
[]
["공사명","계약일자","낙찰률\n(%)","원도급 계약정보",{"$nulls":8},"하도급 계약정보",{"$nulls":8},"비고사항"]
[null,null,null,"계약상대자",null,null,null,"계약금액(총차)",null,null,null,"계약기간(장기계속계약)","공종","계약체결일","하도급 부분 도급액","계약상대자"]
[null,null,null,"회사명","지분율(%)","대표자","소재지","최초계약금액","변경계약금액(1차)","변경계약금액(2차)","변경계약금액(n차)",{"$nulls":4},"회사명","하도급율(%)","대표자","소재지","계약기간","계약금액"]
["육지 후비 전력관제센터 건립 건축공사","2023.10.20.",80.776,"신화종합건설㈜\n유선종합건설㈜\n㈜지인종합건설","60\n30\n10","박철진\n김관교\n전영순","충남\n경기\n경기",14148948990,null,null,null,"2023.10.30. ~ 2025.10.28.","가설울타리 공사","2023.11.30.",134125712,"㈜삼영개발",0.9946,"채만기","전남","2023.11.30. ~ 2025.10.28.",133408000]
[{"$nulls":12},"가설사무실 공사","2024.1.5.",66462000,"㈜상경건설",1.0576,"김상돈","대전","2023.12.14. ~ 2025.10.28.",70290000]
[{"$nulls":12},"철근콘크리트 공사","2024.2.21.",2827699320,"제이피건설㈜",0.9705,"임순열","충남","2024.02.23. ~ 2025.06.30.",2744350000]
[{"$nulls":12},"철근콘크리트 공사(변경)","2024.8.5.",2920678185,"제이피건설㈜",1.0103,"임순열","충남","2024.02.23. ~ 2025.06.30.",2950860000]
[{"$nulls":12},"기계설비공사","2024.2.28.",2597191960,"㈜부석이엔씨",0.8259,"남인호","인천","2024.03.04. ~ 2025.10.28.",2145000000]
[{"$nulls":12},"습식공사","2024.5.28.",868438150,"㈜정인건설",0.8866,"정일식","경기","2024.05.30. ~ 2025.10.28.",770000000]
[{"$nulls":12},"철골공사","2024.7.17.",858852104,"세진에스앤티㈜",0.8282,"조동진","충북","2024.08.01. ~ 2024.11.30.",711260000]
[{"$nulls":12},"Post-Tension공사","2024.7.17.",33535668,"㈜피티솔루션",0.8587,"박광옥","서울","2024.07.29. ~ 2024.11.10.",28798000]
[{"$nulls":12},"금속창호공사","2024.8.30.",519694769,"대림건설산업㈜",0.8202,"안은경","대전","2024.09.10. ~ 2025.08.30.",422950000]
[{"$nulls":12},"실내건축공사","2024.9.30.",1341066618,"다산산업개발㈜",0.8219,"박광운","충북","2024.10.07. ~ 2025.10.28.",1102200000]
[{"$nulls":12},"유리공사","2024.10.25.",200231347,"동일유리㈜",0.8213,"김정환","충북","2024.11.25. ~ 2025.08.31.",164450000]
[{"$nulls":12},"석공사","2024.10.29.",941956123,"대림석재산업㈜",0.8226,"김동주,\n이옥선","경기","2024.12.02. ~ 2025.08.31.",774840000]